## A
[11 empty] | Completed | Completed
Construction details: |  | Building No. = 2B + G + P + 2nd to 8th P/R + 1st to 40th Floor | [8 empty] | Excavation, Plinth
Basement | 2 | Ground | 1 | Podium | 1 | Floors | 47 |  |  |  |  | , RCC upto 9 Slab
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 9 Slab Completed | [9 empty] | Excavation, Plinth Completed, RCC upto 9 Slab Completed
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  |  | Piling Work in process | 11.75 | For Excavation
Excavation |  | 47 | 100% |  | 17.35% |  |  | Excavation in process | 23.5
Plinth |  | 47 | 100% |  |  |  |  | Excavation Completed | 47
RCC (Including podiums) |  | 9 | 18.37% |  |  |  |  | Footing in Process | 11.75 | For Basement & plinth
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 23.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 35.25
External Plaster | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Finishing | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth completed | 47
Occupancy |  | 0 | 0%
17.35%

## B
[11 empty] | Completed | Completed
Construction details: |  | Building No. = 2B + G + P + 2nd to 8th P/R + 1st to 40th Floor | [8 empty] | Excavation, Plinth
Basement | 2 | Ground | 1 | Podium | 1 | Floors | 47 |  |  |  |  | , RCC upto 3 Slab
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 3 Slab Completed | [9 empty] | Excavation, Plinth Completed, RCC upto 3 Slab Completed
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  |  | Piling Work in process | 11.75 | For Excavation
Excavation |  | 47 | 100% |  | 12.45% |  |  | Excavation in process | 23.5
Plinth |  | 47 | 100% |  |  |  |  | Excavation Completed | 47
RCC (Including podiums) |  | 3 | 6.122% |  |  |  |  | Footing in Process | 11.75 | For Basement & plinth
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 23.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 35.25
External Plaster | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Finishing | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth completed | 47
Occupancy |  | 0 | 0%
12.45%

## C% (3) (hidden)
Completed
Construction details: |  | Building No. = B+ G + 1st to 20th Floor | [8 empty] | Excavation work in process, 1st Basement Completed
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 20 |  |  |  | , RCC upto 20 Slab
Stage of construction: |  | Excavation work in process, 1st Basement Completed, RCC upto 20 Slab Completed | [8 empty] | Excavation work in process, 1st Basement Completed, RCC upto 20 Slab Completed
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  |  | Piling Work in process | 5 | For Excavation
Excavation |  | 10 | 50% |  | 45.6% |  |  | Excavation in process | 10
Plinth |  | 15 | 75% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 20 | 95.24% |  |  |  |  | Footing in Process | 5 | For Basement & plinth
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 15
External Plaster | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Finishing | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth completed | 20
Occupancy |  | 0 | 0%
45.6%