## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 02/07/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-07-02
Name of the builder group |  |  |  | Jai Balaji Sai Realtors
Name of the builder company |  |  |  | Jai Balaji Sai Realtors
Name of the Project |  |  |  | Seasons Green
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Sujit Shinde 9702286227
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Sandesh 9819172035
Name / No of the Building |  |  |  | Wing A to H
Name / No of the Existing Building |  |  |  | NA | [6 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC | [6 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51700051575 |  |  |  | #N/A |  |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Seasons Green, Survey No.16, H. No. 2, near Shukla Sadan, Internal Rd, Chanakya Nagar, Khadakpada, Kolivali, Kalyan, Kalyan, Thane - 421301. | [8 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 16, H. No. 2 | [8 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Chanakya Nagar, Khadakpada | [8 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Rd |  | Locality/Village |  | Kolivali |  |  |  |  | Ambernath | Dahanu |  | Pen | Shirur
City |  | Kalyan |  | District |  | Thane |  |  |  |  | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Kalyan |  | Pin Code |  | 421301 | [7 empty] | Mahad | Daund
Nearby Landmark |  | Shukla Sadan |  | Distance from city centre: |  | 5.3KM from Kalyan Railway Station | [7 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [9 empty] | Mangaon | Ambegaon
[14 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [9 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [9 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [9 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Shukla Sadan
West | NA | Existing Rd |  |  | Internal Rd/ Open Plot
North | NA | Existing Rd |  |  | Open Plot
South | NA | Other Plot |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.268987,73.132234
Location Link |  | https://maps.app.goo.gl/nonsNaSaN19L3MSq8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 12070
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.84061
Total FSI availaible for the project |  |  |  | 1.8406
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 22216.16
Total number of Buildings |  |  |  | 08 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kalyan-Dombivli Municipal Corporation (KDMC)
Layout Approval No |  | KDMC/TPD/BP/KD/2022-23/85 |  |  | Dated | 2023-01-25
Approved Floor plan No. |  | KDMC/TPD/BP/KD/2022-23/85 |  |  | Dated | 2023-01-25
Commencement-CC No Valid Up to: |  | KDMC/TPD/BP/KD/2022-23/85 |  |  | Dated | 2023-01-25
Wing A to H = St(Pt)/Gr(Pt) + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 22216.16
Approved no of units |  |  | Flats - 429, Shops - 60
Approved no of Floors |  |  | Wing A to H = St(Pt)/Gr(Pt) + 1st to 7th Floor
Proposed no of Floors |  |  | Wing A to H = St(Pt)/Gr(Pt) + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Swimming Pool, Kids Play Area, Gymnasium, Gazebo, Club House, Sitting Lounge, Car Parking, Stargazing Deck
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = St(Pt)/Gr(Pt) + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed, Brickwork upto 5 Floor, Internal Plaster upto 2 Floor Completed | , Brickwork upto 5 Floor, Internal Plaster upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed, Brickwork upto 5 Floor, Internal Plaster upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 57.5% |  | 80% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 5 | 71.43% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 2 | 28.57% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing B = St(Pt)/Gr(Pt) + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 2 Floor Completed | , Internal Plaster upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 59.64% |  | 81.43% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 2 | 28.57% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing C = St(Pt)/Gr(Pt) + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 2 Floor Completed | , Internal Plaster upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 59.64% |  | 81.43% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 2 | 28.57% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing D = St(Pt)/Gr(Pt) + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 4 Slab Completed | , RCC upto 4 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 4 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 30% |  | 60% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 4 | 50% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing E = St(Pt)/Gr(Pt) + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 4 Slab, Brickwork upto 1 Floor Completed | , RCC upto 4 Slab, Brickwork upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 4 Slab, Brickwork upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 31.07% |  | 60.71% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 4 | 50% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 1 | 14.29% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing F = St(Pt)/Gr(Pt) + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 10% |  | 45% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing G = St(Pt)/Gr(Pt) + 1st to 7th Floor | [5 empty] | Excavation Completed, Footing work Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation | , Footing work Completed
Stage of construction: |  | Excavation Completed, Footing work Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 5% |  | 32.5% |  | Excavation in process | 3.5
Plinth |  | 3.5 | 50% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing H = St(Pt)/Gr(Pt) + 1st to 7th Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 3.5
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 6500
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 12000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 5200
Commercial Area Details : Shop
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 13 |  | 1874.7659 |  | 2812.1488
Wing B |  | 13 |  | 1855.9289 |  | 2783.8933
Wing C |  | 16 |  | 2233.2071 |  | 3349.8106
Wing D |  | 18 |  | 2689.0625 |  | 4033.5937
Total |  | 60 |  | 8652.9643 |  | 12979.4465
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 45 |  | 24214.7601 |  | 35324.5293
Wing B |  | 60 |  | 25354.8151 |  | 36984.0675
Wing C |  | 44 |  | 23754.0609 |  | 34656.5154
Wing D |  | 56 |  | 24093.2743 |  | 35338.8978
Wing E |  | 56 |  | 3470.7861 |  | 5032.6399
Wing F |  | 56 |  | 3470.7861 |  | 5032.6399
Wing G |  | 56 |  | 3470.7861 |  | 5032.6399
Wing H |  | 56 |  | 3470.7861 |  | 5032.6399
Total |  | 429 |  | 111300.0549 |  | 162434.5697
Grand Total |  | 489 |  | 119953.0193 |  | 175414.0161
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
50%
Wing A
Ground Floor For Commercial & Residential
1 |  | Shop | 166.6267 | 0 | 249.9401 | Ground Floor For Commercial & Residential
2 |  | Shop | 116.3588 | 0 | 174.5383
3 |  | Shop | 166.6267 | 0 | 249.9401
4 |  | Shop | 166.6267 | 0 | 249.9401
5 |  | Shop | 143.807 | 0 | 215.7106
6 |  | Shop | 139.3938 | 0 | 209.0907
7 |  | Shop | 166.6267 | 0 | 249.9401 |  |  | 15.4825
8 |  | Shop | 110.6539 | 0 | 165.9809 |  |  | 10.2776
9 |  | Shop | 129.168 | 0 | 193.752
10 |  | Shop | 119.2651 | 0 | 178.8977
11 |  | Shop | 166.6267 | 0 | 249.9401
12 |  | Shop | 116.3588 | 0 | 174.5383
13 |  | Shop | 166.6267 | 0 | 249.9401
Wing B
Ground Floor For Commercial & Residential
1 |  | Shop | 166.6267 | 0 | 249.9401 | Ground Floor For Commercial & Residential
2 |  | Shop | 116.3588 | 0 | 174.5383
3 |  | Shop | 166.6267 | 0 | 249.9401
4 |  | Shop | 143.807 | 0 | 215.7106
5 |  | Shop | 166.6267 | 0 | 249.9401
6 |  | Shop | 110.6539 | 0 | 165.9809
7 |  | Shop | 129.168 | 0 | 193.752
8 |  | Shop | 129.168 | 0 | 193.752
9 |  | Shop | 110.6539 | 0 | 165.9809
10 |  | Shop | 166.6267 | 0 | 249.9401
11 |  | Shop | 166.6267 | 0 | 249.9401
12 |  | Shop | 116.3588 | 0 | 174.5383 |  |  | 10.8096
13 |  | Shop | 166.6267 | 0 | 249.9401
Wing C
Ground Floor For Commercial, Drivers Room & Residential
1 |  | Shop | 166.6267 | 0 | 249.9401 | Ground Floor For Commercial, Drivers Room & Residential
2 |  | Shop | 116.3588 | 0 | 174.5383
3 |  | Shop | 166.6267 | 0 | 249.9401
4 |  | Shop | 166.6267 | 0 | 249.9401
5 |  | Shop | 143.807 | 0 | 215.7106
6 |  | Shop | 139.3938 | 0 | 209.0907
7 |  | Shop | 166.6267 | 0 | 249.9401
8 |  | Shop | 110.6539 | 0 | 165.9809
9 |  | Shop | 129.168 | 0 | 193.752
10 |  | Shop | 119.2651 | 0 | 178.8977
11 |  | Shop | 166.6267 | 0 | 249.9401
12 |  | Shop | 116.3588 | 0 | 174.5383
13 |  | Shop | 166.6267 | 0 | 249.9401
14 |  | Shop | 113.9908 | 0 | 170.9861
15 |  | Shop | 121.4179 | 0 | 182.1269
16 |  | Shop | 123.0325 | 0 | 184.5488
Wing D
Ground Floor For Commercial, Society Office & Parking
1 |  | Shop | 166.6267 | 0 | 249.9401 | Ground Floor For Commercial, Society Office & Parking
2 |  | Shop | 166.6267 | 0 | 249.9401
3 |  | Shop | 166.6267 | 0 | 249.9401
4 |  | Shop | 166.6267 | 0 | 249.9401
5 |  | Shop | 166.6267 | 0 | 249.9401
6 |  | Shop | 166.6267 | 0 | 249.9401
7 |  | Shop | 116.3588 | 0 | 174.5383
8 |  | Shop | 166.6267 | 0 | 249.9401
9 |  | Shop | 143.807 | 0 | 215.7106 |  |  | 13.3495
10 |  | Shop | 166.6267 | 0 | 249.9401
11 |  | Shop | 110.6539 | 0 | 165.9809
12 |  | Shop | 129.168 | 0 | 193.752
13 |  | Shop | 129.168 | 0 | 193.752
14 |  | Shop | 110.6539 | 0 | 165.9809 |  |  | 10.6924
15 |  | Shop | 166.6267 | 0 | 249.9401
16 |  | Shop | 166.6267 | 0 | 249.9401
17 |  | Shop | 116.3588 | 0 | 174.5383
18 |  | Shop | 166.6267 | 0 | 249.9401
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
[5 empty] | 45% |  |  |  |  | 10.764
Wing A
Ground Floor For Residential & Commercial
1 |  | 2BHK | 460.6992 | 0 | 668.0138 | Ground Floor For Residential & Commercial
2 |  | 1BHK | 356.0731 | 0 | 516.306
3 |  | 2BHK | 460.6992 | 0 | 668.0138 |  |  | 41.0401
1st Floor For Residential
101 |  | 2BHK | 550.8832 | 0 | 798.7807 | 1st Floor For Residential
102 |  | 2BHK | 484.281 | 241.5442 | 782.7221
103 |  | 2BHK | 484.281 | 75.5633 | 777.7707
104 |  | 2BHK | 484.281 | 57.0492 | 759.2566
105 |  | 2BHK | 550.8832 | 0 | 798.7807
106 |  | 2BHK | 550.8832 | 0 | 798.7807
2nd to 7th Floor
201 to 701 |  | 2BHK | 550.8832 | 0 | 798.7807 | 2nd to 7th Floor
202 to 702 |  | 2BHK | 550.8832 | 0 | 798.7807
203 to 703 |  | 2BHK | 550.8832 | 0 | 798.7807
204 to 704 |  | 2BHK | 550.8832 | 0 | 798.7807
205 to 705 |  | 2BHK | 550.8832 | 0 | 798.7807
206 to 706 |  | 2BHK | 550.8832 | 0 | 798.7807
Wing B
Ground Floor For Residential & Commercial
1 |  | 1BHK | 346.3855 | 0 | 502.259 | Ground Floor For Residential & Commercial |  | 30.3451
2 |  | 1RK | 222.3842 | 0 | 322.4571
3 |  | 1BHK | 346.3855 | 0 | 502.259
4 |  | 1BHK | 346.3855 | 0 | 502.259
1st Floor For Residential | [8 empty] | Enclose Balcony not included in rera carpet
101 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st Floor For Residential
102 |  | 2BHK | 509.4687 | 56.511 | 795.2407 |  |  | 40.0626
103 |  | 1BHK | 368.7833 | 53.2818 | 588.0175 |  |  | 27.5951
104 |  | 1BHK | 368.7833 | 53.2818 | 588.0175
105 |  | 1BHK | 368.7833 | 56.511 | 591.2467
106 |  | 1BHK | 413.1848 | 0 | 599.1179
107 |  | 1BHK | 413.1848 | 0 | 599.1179
108 |  | 1BHK | 413.1848 | 0 | 599.1179
2nd to 7th Floor
201 to 701 |  | 1BHK | 413.1848 | 0 | 599.1179 | 2nd to 7th Floor
202 to 702 |  | 2BHK | 578.4929 | 0 | 838.8147
203 to 703 |  | 1BHK | 413.1848 | 0 | 599.1179
204 to 704 |  | 1BHK | 413.1848 | 0 | 599.1179
205 to 705 |  | 1BHK | 413.1848 | 0 | 599.1179
206 to 706 |  | 1BHK | 413.1848 | 0 | 599.1179
207 to 707 |  | 1BHK | 413.1848 | 0 | 599.1179
208 to 708 |  | 1BHK | 413.1848 | 0 | 599.1179
Wing C
Ground Floor For Residential, Drivers Room & Commercial
1 |  | 2BHK | 460.6992 | 0 | 668.0138 | Ground Floor For Residential, Drivers Room & Commercial |  | 40.4101
2 |  | 1BHK | 356.0731 | 0 | 516.306
1st Floor For Residential
101 |  | 2BHK | 550.8832 | 0 | 798.7807 | 1st Floor For Residential
102 |  | 2BHK | 484.281 | 241.5442 | 782.7221
103 |  | 2BHK | 484.281 | 75.5633 | 777.7707 |  |  | 40.3741
104 |  | 2BHK | 484.281 | 57.0492 | 759.2566
105 |  | 2BHK | 550.8832 | 0 | 798.7807
106 |  | 2BHK | 550.8832 | 0 | 798.7807
2nd to 7th Floor
201 to 701 |  | 2BHK | 550.8832 | 0 | 798.7807 | 2nd to 7th Floor
202 to 702 |  | 2BHK | 550.8832 | 0 | 798.7807
203 to 703 |  | 2BHK | 550.8832 | 0 | 798.7807
204 to 704 |  | 2BHK | 550.8832 | 0 | 798.7807
205 to 705 |  | 2BHK | 550.8832 | 0 | 798.7807
206 to 706 |  | 2BHK | 550.8832 | 0 | 798.7807
Wing D
1st Floor For Residential
101 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st Floor For Residential
102 |  | 1BHK | 509.4687 | 962.3016 | 979.3051 | 1st Floor For Residential
103 |  | 1BHK | 368.7833 | 53.2818 | 588.0175 | 1st Floor For Residential
104 |  | 1BHK | 368.7833 | 53.2818 | 588.0175 | 1st Floor For Residential
105 |  | 1BHK | 368.7833 | 56.511 | 591.2467 | 1st Floor For Residential
106 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st Floor For Residential
107 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st Floor For Residential
108 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st Floor For Residential
2nd to 7th Floor
201 to 701 |  | 1BHK | 413.1848 | 0 | 599.1179 | 2nd to 7th Floor
202 to 702 |  | 2BHK | 578.4929 | 0 | 838.8147
203 to 703 |  | 1BHK | 413.1848 | 0 | 599.1179
204 to 704 |  | 1BHK | 413.1848 | 0 | 599.1179
205 to 705 |  | 1BHK | 413.1848 | 0 | 599.1179
206 to 706 |  | 1BHK | 413.1848 | 0 | 599.1179
207 to 707 |  | 1BHK | 413.1848 | 0 | 599.1179
208 to 708 |  | 1BHK | 413.1848 | 0 | 599.1179
Wing E
Ground Floor For Parking
1st to 7th Floor For Residential
101 to 701 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
102 to 702 |  | 2BHK | 578.4929 | 0 | 838.8147 | 1st to 7th Floor For Residential
103 to 703 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
104 to 704 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
105 to 705 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
106 to 706 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
107 to 707 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
108 to 708 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
Wing F
Ground Floor For Parking
1st to 7th Floor For Residential
101 to 701 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
102 to 702 |  | 2BHK | 578.4929 | 0 | 838.8147 | 1st to 7th Floor For Residential
103 to 703 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
104 to 704 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
105 to 705 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
106 to 706 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
107 to 707 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
108 to 708 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
Wing G
Ground Floor For Parking
1st to 7th Floor For Residential
101 to 701 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
102 to 702 |  | 2BHK | 578.4929 | 0 | 838.8147 | 1st to 7th Floor For Residential
103 to 703 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
104 to 704 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
105 to 705 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
106 to 706 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
107 to 707 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
108 to 708 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
Wing H
Ground Floor For Parking
1st to 7th Floor For Residential
101 to 701 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
102 to 702 |  | 2BHK | 578.4929 | 0 | 838.8147 | 1st to 7th Floor For Residential
103 to 703 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
104 to 704 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
105 to 705 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
106 to 706 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
107 to 707 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
108 to 708 |  | 1BHK | 413.1848 | 0 | 599.1179 | 1st to 7th Floor For Residential
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
Remarks:
* | Wing A to G = Construction Work in process at the time of visit. Wing H = Work not yet Started.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclosed balcony + Balcony + Chajja Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated approved plans on 12/11/2024.
* | We have received an approved Layout plan, floor plan (not legible), and builder profile. Please provide a legible, approved layout plan, floor plan and sale plan.
* | Since wing H have received CC on 25/01/2023, but as of construction work is not started.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Bapardekar |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Seasons Green
PHOTOGRAPHS OF PROPERTY : |  |  | Seasons Green
Layout :
Google Map :
Wing B
Wing C
Wing E
Wing D
Wing F
Wing G
Wing H
Wing A
F Wing
G Wing
G Wing
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC