## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  |  | : | 25 Hourlife - Tower A1, B1 & C1 |  | Date & Time of Site Visit |  | 03/07/2025 @ 12:40PM
Name of the person met at site & Contact No. |  |  | : | Security |  | Date of Report Release |  | 06/07/2025 | Mansi 8452041560
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr.Fahad
Builder Group Name |  |  | : | Dhruva Woollen Mills Pvt Ltd | Developer Name | : | Dhruva Woollen Mills Pvt Ltd
Developer Office Address |  |  | : | 4th Floor, Runwal & Omkar Esquare, Off, Eastern Express Hwy, opp. Sion-Chunabhatti, Sion East, Signal, Mumbai
Project Address | : | As per ARF | : | 25 hour life, Ghodbunder Rd, next to Rmall, Manpada, Thane West, Thane, Maharashtra 400607
| : | As per Legal Documents | : | 25 hour life, Gut No.2/2, 2/5, 7/1 & 7/2,Ghodbunder Road, Near R-Mall, Panchpakhadi, Manpada, Thane West, Thane, Pin Code - 400607.
| : | As per Actual at site | : | Ghodbunder Road, near R Mall, Manpada, Thane West, Thane, Maharashtra 400607
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Thane Municipal Corporation
RERA Registration No. | : | Building Type A1 = P51700053696 Building Type B1 = P51700048270 Building Type C1 = P51700048278 |  |  | RERA Registration Validity | : | 2029-12-31
Project Launch Date | : | 2022-12-22 |  |  | Construction Start Date | : | 2023-03-01
Proposed Date of Completion (As per RERA) | : | Building Type A1 = 31/12/2030 Building Type B1 = 31/12/2029 Building Type C1 = 31/12/2029 |  |  | Developer Bank Name (As per RERA) | : | ICICI Bank ICIC0000740
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 49701.66
FSI/FAR Permissible | : | 1.1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 73098.03 |  | 1.1
Permissible Built up Area (In Sq.Mt) | : | 73098.03 |  |  | Total Number of Units Planned | : | As per RERA Site Flats = 1450 |  |  |  | 590
Total Number of Units Approved | : | Flats = 1380 |  |  | If Mixed, No. of Commercial Units | : | - |  |  |  | 320
Latitude | : | 19.2333 |  |  | Longitude | : | 72.9777 |  |  |  | 540
Location Link | : | https://goo.gl/maps/897yVqAXnvB4dkEv6 | [8 empty] | 1450
Extra Amenities available | : | Cafeteria/Food Court Outdoor Tennis Courts Banquet Hall Gymnasium Indoor Squash & Badminton Courts Power Back Up Swimming Pool Club House Lift Security Reserved Parking Visitor Parking
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 100M from Manpada Bus Stop
Distance from the nearest School (Km) | : | About 650m from Hari Om English School |  |  | Distance from Hospital (Km) | : | About 300m form Thane Municipal Hospital
Distance from the Main Market (Km) | : | 1. Approx. 700M from Runwal Market. 2. Approx. 400M from Manorama Nagar Market. |  |  | Distance from Railway Station (Km) | : | 5.7KM from Thane Railway Station 8KM from Kalva Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Internal Road | Parking Area | Internal Road |  | Ghodbunder Road
As per Site / Actual |  |  | : | HP Petrol pump / Slum | Sukh Sheetal CHS/ 38ft Road | Manorama Nagar Police Chowki |  | Ghodbunder Road
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Building Type A1 |  | Sale |  | 2P Lvl + Gr/P3 + P4 to P6 + 1st to 50th Floors |  |  | 2P Lvl + Gr/P3 + P4 to P6 + 1st to 50th Floors
Building Type B1 |  | Sale |  | 2P Lvl + Gr/P3 + P4 to P6 + 1st to 55th Floors |  |  | 2P Lvl + Gr/P3 + P4 to P6 + 1st to 50th Floors
Building Type C1 |  | Sale |  | 2P Lvl + Gr/P3 + P4 to P6 + 1st to 55th Floors |  |  | 2P Lvl + Gr/P3 + P4 to P6 + 1st to 50th Floors
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | S05/0218/22/TMC/TD-DP/ TPS/4482/23 Date: 31/10/2023
CC Details | : | S05/0218/22/TMC/TDD/4482/23 Date: 31/10/2023 Valid Up to: Building No. A1 = P1 + P2 + Gr/P3 + P4 to P6 + 1st Floor Building No. B1 & C1 = P1 + P2 + Gr/P3 + P4 to P6 + 1st & 2nd Floor |  |  | Approved Plan Details | : | S05/0218/22/TMC/TD-DP/ TPS/4482/23 Date: 31/10/2023 Valid Up to: Building Type A1, B1 & C1 = 2P Lvl + Gr/P3 + P4 to P6 + 1st to 50th Floors
Environmental Clearance Details | : | - |  |  | Airport Authority Clearance Details | : | -
CC Details | : | S05/0218/22/TMC/TDD/TMCB/TDD/0095/[P/C]/2024/Auto DCR Date: 26/02/2024 Valid Up to: Building No. A1 = 2nd to 26th + Service Floor + 27th to 50th Floor Building No. B1 & C1 = 3rd to 26th + Service Floor + 27th to 50th Floor
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | : | -
Construction Status
Building Type A1 = 2P Lvl + Gr/P3 + P4 to P6 + 1st to 50th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 18 Slab, Brickwork upto 13 Floor, Internal Plaster upto 10.4 Floor, External Plaster upto 10.4 Floor Completed
|  |  |  | 2 | 1 |  | 3 | 50 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 12.5
Excavation |  | 50 |  | 100% | 35.67% |  | Excavation work Completed. Plinth work completed, RCC upto 18 Slab, Brickwork upto 13 Floor, Internal Plaster upto 10.4 Floor, External Plaster upto 10.4 Floor Completed |  | Excavation in process | 25
Plinth |  | 50 |  | 100% |  |  |  |  | Excavation Completed | 50
RCC (Including podiums) |  | 18 |  | 33.33% |  |  |  |  | Footing in Process | 12.5
Brickwork |  | 13 |  | 26% |  |  |  |  | Footing Completed | 25
Internal Plaster |  | 10.4 |  | 20.8% |  |  |  |  | Basement 1 | 37.5
External Plaster |  | 10.4 |  | 20.8% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 50 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building Type B1 = 2P Lvl + Gr/P3 + P4 to P6 + 1st to 55th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 46 Slab, Brickwork upto 41 Floor, Internal Plaster upto 32.8 Floor, External Plaster upto 32.8 Floor Completed
|  |  |  | 2 | 1 |  | 3 | 55 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.75
Excavation |  | 55 |  | 100% | 51.2% |  | Excavation work Completed. Plinth work completed, RCC upto 46 Slab, Brickwork upto 41 Floor, Internal Plaster upto 32.8 Floor, External Plaster upto 32.8 Floor Completed |  | Excavation in process | 27.5
Plinth |  | 55 |  | 100% |  |  |  |  | Excavation Completed | 55
RCC (Including podiums) |  | 46 |  | 77.97% |  |  |  |  | Footing in Process | 13.75
Brickwork |  | 41 |  | 74.55% |  |  |  |  | Footing Completed | 27.5
Internal Plaster |  | 32.8 |  | 59.64% |  |  |  |  | Basement 1 | 41.25
External Plaster |  | 32.8 |  | 59.64% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 55 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building Type C1 = 2P Lvl + Gr/P3 + P4 to P6 + 1st to 55th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 33 Slab, Brickwork upto 29 Floor, Internal Plaster upto 23.2 Floor, External Plaster upto 23.2 Floor Completed
|  |  |  | 2 | 1 |  | 3 | 55 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.75
Excavation |  | 55 |  | 100% | 43.73% |  | Excavation work Completed. Plinth work completed, RCC upto 33 Slab, Brickwork upto 29 Floor, Internal Plaster upto 23.2 Floor, External Plaster upto 23.2 Floor Completed |  | Excavation in process | 27.5
Plinth |  | 55 |  | 100% |  |  |  |  | Excavation Completed | 55
RCC (Including podiums) |  | 33 |  | 55.93% |  |  |  |  | Footing in Process | 13.75
Brickwork |  | 29 |  | 52.73% |  |  |  |  | Footing Completed | 27.5
Internal Plaster |  | 23.2 |  | 42.18% |  |  |  |  | Basement 1 | 41.25
External Plaster |  | 23.2 |  | 42.18% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 55 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 43.53%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 18000 to 18500 | Floor Rise Per Sq. Ft.(on Carpet area) | : | NA
Car Parking Charges |  |  | : | 500000/- | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 4171.3118
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 11900.7804
Distress Value (Rs. Per sqft) | [5 empty] | : | 3337.0494
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area
Building Type A1 |  | Sale |  | Flats | 590 |  | 283685.704
Building Type B1 |  | Sale |  | Flats | 490 |  | 296998.596
Building Type C1 |  | Sale |  | Flats | 300 |  | 253538.4718
Total |  |  |  |  | 1380 |  | 834222.7718
Details of Flats in Building
Flat/Shop No. |  | Description |  | Net Carpet | Balcony Area |  | Attached Terrace area | Gross Carpet Area
[8 empty] | 50% |  | 239
Building Type A1 | [9 empty] | 274
Parking Level 1 & 2 (Basement 1 & 2) For Flushing Tank & Parking
Parking Level 3 (Ground Floor) For Double Height Entrance Lobby, Society Office, Drivers Room, Substation, Meter Room & Parking
Parking Level 4 & 5 (1st & 2nd Podium) For Parking
Parking Level 6 (3rd Podium) For Parking | [8 empty] | 10.76
1st to 4th, 6th to 9th, 11th to 14th, 16th to 19th, 21st to 24th, 26th to 28th, 30th to 33rd, 35th to 38th, 40th to 43rd, 45th to 48th & 50th Floor For Residential
1 |  | 1BHK | 412.108 |  | 35.1852 |  | 0 | 447.2932 | 55.1025 | 3.355 |  | 41.5546
2 |  | 2BHK | 491.4092 |  | 0 |  | 0 | 491.4092 |  | 58.4575 | 629.2365
3 |  | 1BHK | 448.154 |  | 41.2261 |  | 0 | 489.3801 |  |  | 11640875.805 | 8274924.2
4 |  | 1BHK | 448.0464 |  | 41.2261 |  | 0 | 489.2725 | 49.1325 |  | -3365951.605
5 |  | 2BHK | 530.8984 |  | 0 |  | 0 | 530.8984
6 |  | 1BHK | 431.7988 |  | 0 |  | 0 | 431.7988
7 |  | 1BHK | 431.7988 |  | 0 |  | 0 | 431.7988
8 |  | 2BHK | 530.8984 |  | 0 |  | 0 | 530.8984
9 |  | 1BHK | 448.0464 |  | 41.2108 |  | 0 | 489.2572
10 |  | 1BHK | 448.154 |  | 41.2108 |  | 0 | 489.3648
11 |  | 2BHK | 491.4092 |  | 0 |  | 0 | 491.4092
12 |  | 1BHK | 412.108 |  | 35.1852 |  | 0 | 447.2932
5th, 10th, 15th, 20th, 25th, 29th, 34th, 39th, 44th & 49th Floor (Part Refuge Area)
1 |  | 1BHK | 412.108 |  | 35.1852 |  | 0 | 447.2932 | 55.1025 | 3.355 |  | 41.5546
2 |  | 2BHK | 491.4092 |  | 0 |  | 0 | 491.4092 |  | 58.4575 | 629.2365
3 |  | 1BHK | 448.154 |  | 41.2261 |  | 0 | 489.3801 |  |  | 11640875.805 | 8274924.2
4 |  | 1BHK | 448.0464 |  | 41.2261 |  | 0 | 489.2725 | 49.1325 |  | -3365951.605
5 |  | 2BHK | 530.8984 |  | 0 |  | 0 | 530.8984
6 |  | 1BHK | 431.7988 |  | 0 |  | 0 | 431.7988
7 |  | Refuge Area
8 |  | 2BHK | 530.8984 |  | 0 |  | 0 | 530.8984
9 |  | 1BHK | 448.0464 |  | 41.2108 |  | 0 | 489.2572
10 |  | 1BHK | 448.154 |  | 41.2108 |  | 0 | 489.3648
11 |  | 2BHK | 491.4092 |  | 0 |  | 0 | 491.4092
12 |  | 1BHK | 412.108 |  | 35.1852 |  | 0 | 447.2932
Building Type B1 | [9 empty] | 274
Parking Level 1 & 2 (Basement 1 & 2) For Flushing Tank & Parking
Parking Level 3 (Ground Floor) For Entrance Lobby, Society Office, Meter Room & Parking
Parking Level 4 & 5 (1st & 2nd Podium) For Parking
Parking Level 6 (3rd Podium) For Parking | [8 empty] | 10.76
1st to 4th, 6th to 9th, 11th to 14th, 16th to 19th, 21st to 24th, 26th to 28th, 30th to 33rd, 35th to 38th, 40th to 43rd, 45th to 48th & 50th Floor For Residential
1 |  | 2BHK | 631.612 |  | 29.59 |  | 0 | 661.202 | 55.1025 | 3.355 |  | 61.4272
2 |  | 2BHK | 631.612 |  | 29.59 |  | 0 | 661.202 |  | 58.4575 | 629.2365
3 |  | 2BHK | 611.168 |  | 0 |  | 0 | 611.168 |  |  | 11640875.805 | 12232237
4 |  | 2BHK | 564.9 |  | 0 |  | 0 | 564.9 | 49.1325 |  | 591361.195
5 |  | 2BHK | 564.9 |  | 0 |  | 0 | 564.9
6 |  | 2BHK | 564.7924 |  | 0 |  | 0 | 564.7924
7 |  | 2BHK | 564.7924 |  | 0 |  | 0 | 564.7924
8 |  | 2BHK | 611.168 |  | 0 |  | 0 | 611.168
9 |  | 2BHK | 594.8128 |  | 29.59 |  | 0 | 624.4028
10 |  | 2BHK | 594.8128 |  | 29.59 |  | 0 | 624.4028
5th, 10th, 15th, 20th, 25th, 29th, 34th, 39th, 44th & 49th Floor (Part Refuge Area)
1 |  | 2BHK | 631.612 |  | 29.59 |  | 0 | 661.202
2 |  | 2BHK | 631.612 |  | 29.59 |  | 0 | 661.202
3 |  | 2BHK | 611.168 |  | 0 |  | 0 | 611.168
4 |  | 2BHK | 564.9 |  | 0 |  | 0 | 564.9
5 |  | 2BHK | 564.9 |  | 0 |  | 0 | 564.9
6 |  | 2BHK | 564.7924 |  | 0 |  | 0 | 564.7924
7 |  | Refuge Area
8 |  | 2BHK | 611.168 |  | 0 |  | 0 | 611.168
9 |  | 2BHK | 594.8128 |  | 29.59 |  | 0 | 624.4028
10 |  | 2BHK | 594.8128 |  | 29.59 |  | 0 | 624.4028
Building Type C1 | [9 empty] | 274
Parking Level 1 & 2 For Flushing Tank & Parking
Parking Level 3 (Ground Floor) For Entrance Lobby, Society Office, Meter Room, Drivers Room & Parking
Parking Level 4 & 5 (1st & 2nd Podium) For Parking
Parking Level 6 (3rd Podium) For Creche Area & Parking | [8 empty] | 10.76
1st to 4th, 6th to 9th, 11th to 14th, 16th to 19th, 21st to 24th, 26th to 28th, 30th to 33rd, 35th to 38th, 40th to 43rd, 45th to 48th & 50th Floor For Residential
1 |  | 3BHK | 903.4096 |  | 60.794 |  | 0 | 964.2036
2 |  | 2BHK | 631.9348 |  | 26.362 |  | 0 | 658.2968
3 |  | 3BHK | 906.2072 |  | 48.958 |  | 0 | 955.1652
4 |  | 3BHK | 906.2072 |  | 48.958 |  | 0 | 955.1652
5 |  | 2BHK | 631.9348 |  | 26.362 |  | 0 | 658.2968
6 |  | 3BHK | 903.4096 |  | 60.794 |  | 0 | 964.2036
5th, 10th, 15th, 20th, 25th, 29th, 34th, 39th, 44th & 49th Floor (Part Refuge Area)
1 |  | 3BHK | 903.4096 |  | 60.794 |  | 0 | 964.2036
2 |  | 2BHK | 631.9348 |  | 26.362 |  | 0 | 658.2968
3 |  | 3BHK | 906.2072 |  | 48.958 |  | 0 | 955.1652
4 |  | 1BHK | 481.0688 |  | 51.2875 |  | 0 | 532.3564
5 |  | 2BHK | 631.9348 |  | 26.362 |  | 0 | 658.2968 | 55.8505 | 2.4645
6 |  | 3BHK | 903.4096 |  | 60.794 |  | 0 | 964.2036
1st Floor
1st Floor |  | 101 | [5 empty] | 0
1st Floor |  | 102 | [5 empty] | 0
1st Floor |  | 103 | [5 empty] | 0
1st Floor |  | 104 | [5 empty] | 0
1st Floor |  | 105 | [5 empty] | 0
1st Floor |  | 106 | [5 empty] | 0
1st Floor |  | 107 | [5 empty] | 0
1st Floor |  | 108 | [5 empty] | 0
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 201,..,901 | [5 empty] | 0 |  |  |  |  | 201,..,901 | 201 | 901
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 202,..,902 | [5 empty] | 0 |  |  |  |  | 202,..,902 | 202 | 902
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 203,..,903 | [5 empty] | 0 |  |  |  |  | 203,..,903 | 203 | 903
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 204,..,904 | [5 empty] | 0 |  |  |  |  | 204,..,904 | 204 | 904
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 205,..,905 | [5 empty] | 0 |  |  |  |  | 205,..,905 | 205 | 905
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 206,..,906 | [5 empty] | 0 |  |  |  |  | 206,..,906 | 206 | 906
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 207,..,907 | [5 empty] | 0 |  |  |  |  | 207,..,907 | 207 | 907
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 208,..,908 | [5 empty] | 0 |  |  |  |  | 208,..,908 | 208 | 908
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 209,..,909 | [5 empty] | 0 |  |  |  |  | 209,..,909 | 209 | 909
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 210,..,910 | [5 empty] | 0 |  |  |  |  | 210,..,910 | 210 | 910
2nd to 5th Floor
2nd to 5th Floor |  | 201 to 501 | [5 empty] | 0 |  |  |  |  | 201 to 501 | 201 | 501
2nd to 5th Floor |  | 202 to 502 | [5 empty] | 0 |  |  |  |  | 202 to 502 | 202 | 502
2nd to 5th Floor |  | 203 to 503 | [5 empty] | 0 |  |  |  |  | 203 to 503 | 203 | 503
2nd to 5th Floor |  | 204 to 504 | [5 empty] | 0 |  |  |  |  | 204 to 504 | 204 | 504
2nd to 5th Floor |  | 205 to 505 | [5 empty] | 0 |  |  |  |  | 205 to 505 | 205 | 505
2nd to 5th Floor |  | 206 to 506 | [5 empty] | 0 |  |  |  |  | 206 to 506 | 206 | 506
2nd to 5th Floor |  | 207 to 507 | [5 empty] | 0 |  |  |  |  | 207 to 507 | 207 | 507
2nd to 5th Floor |  | 208 to 508 | [5 empty] | 0 |  |  |  |  | 208 to 508 | 208 | 508
2nd to 5th Floor |  | 209 to 509 | [5 empty] | 0 |  |  |  |  | 209 to 509 | 209 | 509
2nd to 5th Floor |  | 210 to 510 | [5 empty] | 0 |  |  |  |  | 210 to 510 | 210 | 510
2nd & 5th Floor
2nd & 5th Floor |  | 201 & 501 | [5 empty] | 0 |  |  |  |  | 201 & 501 | 201 | 501
2nd & 5th Floor |  | 202 & 502 | [5 empty] | 0 |  |  |  |  | 202 & 502 | 202 | 502
2nd & 5th Floor |  | 203 & 503 | [5 empty] | 0 |  |  |  |  | 203 & 503 | 203 | 503
2nd & 5th Floor |  | 204 & 504 | [5 empty] | 0 |  |  |  |  | 204 & 504 | 204 | 504
2nd & 5th Floor |  | 205 & 505 | [5 empty] | 0 |  |  |  |  | 205 & 505 | 205 | 505
2nd & 5th Floor |  | 206 & 506 | [5 empty] | 0 |  |  |  |  | 206 & 506 | 206 | 506
2nd & 5th Floor |  | 207 & 507 | [5 empty] | 0 |  |  |  |  | 207 & 507 | 207 | 507
2nd & 5th Floor |  | 208 & 508 | [5 empty] | 0 |  |  |  |  | 208 & 508 | 208 | 508
2nd & 5th Floor |  | 209 & 509 | [5 empty] | 0 |  |  |  |  | 209 & 509 | 209 | 509
2nd & 5th Floor |  | 210 & 510 | [5 empty] | 0 |  |  |  |  | 210 & 510 | 210 | 510
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Tower A1c, B1 & C1 = Construction work is in process at the time of Visit. Internal visit not allowed. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Balcony 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We have updated revised approved floor plan & C.C (on 02/11/2023). 8. We have considered sale plan for building B1 & C1 provided by builder for flat numbering as flat no in approved floor plan & Area table in the approved plan are different. 9. We have updated revised approved C.C from RERA site (on 05/02/2025). 7. On Site, we meet Mr........(........).
Site & Building/Tower Photographs
Name of the Project |  |  | : | 25 Hourlife - Tower A1, B1 & C1
Project Site Address |  |  | : | 25 hour life, Ghodbunder Rd, next to Rmall, Manpada, Thane West, Thane, Maharashtra 400607
Site Visit Date & Time |  |  | : | 03/07/2025 @ 12:40PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Ajay Songare | Authorized Signatory Name & Signature | :
Building Type C1
Building Type A1
Building Type B1
1A
1B
1C
1A
1B
1C
Note on H6: Rushil Sanghvi or Fahad
Note on E9: Initiation Address
Note on E10: Plan Address
Note on E11: Map Address
Note on C17: Maybe same as RERA Registration Validity or different
Note on H17: From Rera
Note on H20: From RERA
Note on A39: As per Layout
Note on H113: Ready Recknor