## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-03
Project Name |  |  | : | Hiranandani Fortune City - Golden Willows (Acacia, Orchid, Mayflower, Lavender & Marigold) |  | Date & Time of Site Visit |  | 04/07/2025 @12:24 PM
Name of the person met at site & Contact No. |  |  | : | Mr. Anand : 8104964611 |  | Date of Report Release |  | 08/07/2025
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj
Builder Group Name |  |  | : | M/s.Persipina Developers Private Limited | Developer Name | : | M/s.Persipina Developers Private Limited
Developer Office Address |  |  | : | Olympia, 1st Floor, Central Avenue, Hiranandani Business Park, Powai, Mumbai - 400076.
Project Address | : | As per ARF | : | Acacia, Plot Bearing / CTS / Survey / Final Plot No.: 60/1 (Part) at Bhokarpada, Panvel, Raigarh, 410221
| : | As per Legal Documents | : | Hiranandani Fortune City Golden Willows bearing Plot No.RZ-02 on Gut No. 24/1/2 (Old Survey No. 58/1A Part, 58/1/B Part, 59 Part, 60/1 Part, 60/2 Part, 60/3, 60/4 Part, 61/2 Part, 62/1 Part, 62/2 Part), Near NMMC Water Treatment Plant Bhokarpada, Old Mumbai Pune Road, At village Bhokarpada Taluka Panvel Dist. Raigad- 410206.
| : | As per Actual at site | : | Hiranandani Fortune City Golden Willows bearing Plot No.RZ-02 on Gut No. 24/1/2 (Old Survey No. 58/1A Part, 58/1/B Part, 59 Part, 60/1 Part, 60/2 Part, 60/3, 60/4 Part, 61/2 Part, 62/1 Part, 62/2 Part), Near NMMC Water Treatment Plant Bhokarpada, Old Mumbai Pune Road, At village Bhokarpada Taluka Panvel Dist. Raigad- 410206.
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate,
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Maharashtra State Road Development Corporation Limited (MSRDC)
RERA Registration No. | : | Acacia = P52000050196 Orchid = P52000050193 Mayflower = P52000054617 Lavender = P52000054615 Marigold = P52000054616 |  |  | RERA Registration Validity | : | Acacia & Orchid = 31/12/2028 Mayflower, Lavender & Marigold = 31/12/2029
Project Launch Date | : | Acacia & Orchid = 21/03/2023 Mayflower, Lavender & Marigold = 02/02/2024 |  |  | Construction Start Date | : | Acacia & Orchid = 21/03/2023 Mayflower, Lavender & Marigold = 02/02/2024
Proposed Date of Completion (As per RERA) | : | Acacia & Orchid = 31/12/2028 Mayflower, Lavender & Marigold = 31/12/2029 |  |  | Developer Bank Name (As per RERA) | : | Axis Bank Limited IFSC Code = UTIB0000246 |  | 5.607
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 112566
Proposed Built up Area (In Sq.Mt) For Acacia, Orchid & Mayflower | : | 132224.532 |  |  | Proposed Total Built up Area (In Sq.Mt) | : | 451549.96 |  |  | acacia | 281 |  | 1203
Permissible Built up Area (In Sq.Mt) | : | NA |  |  | Total Number of Units Planned | : | As per RERA, Flats = 1203 |  |  | orchid | 281
Total Number of Units Approved | : | Flats = 1203 |  |  | If Mixed, No. of Commercial Units | : | NA |  |  | mayflower | 144
Latitude, Longitude | : | 18.910902,73.196788 |  |  | Landmark | : | Hiranandani Fortune City |  |  | Lavender | 288
Location Link | : | https://maps.app.goo.gl/NuP1q6Um1N6h4R548 | [7 empty] | Marigold | 209
Extra Amenities available | : | Entrance, Drop-off points, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 60M
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 1.90 KM from M.J.P. Office Bus Stop
Distance from the nearest School (Km) | : | About 0.600KM from Hiranandani Trust School |  |  | Distance from Hospital (Km) | : | About 14Km form Gandhi Superspeciality Hospital.
Distance from the Main Market (Km) | : | Approx. 12KM from dmart |  |  | Distance from Railway Station (Km) | : | 15.70 KM from Panvel Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | 20.00 M. Wide Road | Other Plot | Other Plot |  | 15.00 M. Wide Road
As per Site / Actual |  |  | : | Internal Road/ Hiranandani Fortune City buildings | Open plot | Open plot |  | Hiranandani Fortune City buildings
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Acacia |  | Sale |  | Stilt + 2P + 3rd to 38th Floor |  |  | Stilt + 2P + 3rd to 38th Floor
Orchid |  | Sale |  | Stilt + 2P + 3rd to 38th Floor |  |  | Stilt + 2P + 3rd to 38th Floor
Mayflower |  | Sale |  | Stilt + 2P + 3rd to 38th Floor |  |  | Stilt + 2P + 3rd to 38th Floor
Lavender |  | Sale |  | Stilt + 2P + 3rd to 38th Floor |  |  | Stilt + 2P + 3rd to 38th Floor
Marigold |  | Sale |  | Stilt + 2P + 3rd to 38th Floor |  |  | Stilt + 2P + 3rd to 38th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | MSRDC/SPA/ITP-1/RZ02/ RevisedCC/2024/149 Date: 25/01/2024
CC Details For Acacia & Orchid | : | MSRDC/SPA/TP-1/RZ02/CC/ 2023/333 Date: 21/02/2023 Valid Up to: 205820.102 Sqm |  |  | Approved Plan Details For Acacia & Orchid | : | MSRDC/SPA/TP-1/RZ-02/CC/ 2023/333 Date: 21/02/2023
Environmental Clearance Details | : | Date: |  |  | Airport Authority Clearance Details | : | Date:
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
CC Details For Mayflower, Lavender & Marigold | : | MSRDC/SPA/ITP-1/RZ-02/ RevisedCC/2024/149 Date: 25/01/2024 Valid Up to: 226384.321 Sqm |  |  | Approved Plan Details For Mayflower, Lavender & Marigold | : | MSRDC/SPA/ITP-1/RZ02/ RevisedCC/2024/149 Date: 25/01/2024
CC Details For Lavender & Marigold | : | MSRDC/SPA/ITP-1/RZ-02/ RevisedCC/2024/149 Date: 25/01/2024 Valid Up to: 226384.321 Sqm |  |  | Approved Plan Details For Lavender | : | MSRDC/SPA/ITP-1/RZ-02/RevisedCC/ 2024/149 Date: 25/01/2024
CC Details For Marigold | : | MSRDC/SPA/ITP-1/RZ-02/ RevisedCC/2024/149 Date: 25/01/2024 Valid Up to: 226384.321 Sqm |  |  | Approved Plan Details For Marigold | : | MSRDC/SPA/ITP-1/RZ-02/RevisedCC/ 2024/149 Date: 25/01/2024
Construction Status
Acacia= Stilt + 2P + 3rd to 38th Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 25 Slab, Brickwork upto 24 Floor, Internal Plaster upto 19.2 Floor, External Plaster upto 19.2 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 38 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.5
Excavation |  | 38 |  | 100% | 46.71% |  | Excavation work Completed. Plinth work completed, RCC upto 25 Slab, Brickwork upto 24 Floor, Internal Plaster upto 19.2 Floor, External Plaster upto 19.2 Floor Completed |  | Excavation in process | 19
Plinth |  | 38 |  | 100% |  |  |  |  | Excavation Completed | 38
RCC (Including podiums) |  | 25 |  | 64.1% |  |  |  |  | Footing in Process | 9.5
Brickwork |  | 24 |  | 63.16% |  |  |  |  | Footing Completed | 19
Internal Plaster |  | 19.2 |  | 50.53% |  |  |  |  | Basement 1 | 0
External Plaster |  | 19.2 |  | 50.53% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 28.5
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 38 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Orchid= Stilt + 2P + 3rd to 38th Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 27 Slab, Brickwork upto 26 Floor, Internal Plaster upto 20.8 Floor, External Plaster upto 20.8 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 38 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.5
Excavation |  | 38 |  | 100% | 48.47% |  | Excavation work Completed. Plinth work completed, RCC upto 27 Slab, Brickwork upto 26 Floor, Internal Plaster upto 20.8 Floor, External Plaster upto 20.8 Floor Completed |  | Excavation in process | 19
Plinth |  | 38 |  | 100% |  |  |  |  | Excavation Completed | 38
RCC (Including podiums) |  | 27 |  | 69.23% |  |  |  |  | Footing in Process | 9.5
Brickwork |  | 26 |  | 68.42% |  |  |  |  | Footing Completed | 19
Internal Plaster |  | 20.8 |  | 54.74% |  |  |  |  | Basement 1 | 0
External Plaster |  | 20.8 |  | 54.74% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 28.5
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 38 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Mayflower= Stilt + 2P + 3rd to 38th Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 4 Slab Completed
|  |  |  | 0 | 1 |  | 0 | 38 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.5
Excavation |  | 38 |  | 100% | 27.56% |  | Excavation work Completed. Plinth work completed, RCC upto 4 Slab Completed |  | Excavation in process | 19
Plinth |  | 38 |  | 100% |  |  |  |  | Excavation Completed | 38
RCC (Including podiums) |  | 4 |  | 10.26% |  |  |  |  | Footing in Process | 9.5
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 19
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 28.5
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 38 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Lavender= Stilt + 2P + 3rd to 38th Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Footing work Completed
|  |  |  | 0 | 1 |  | 0 | 38 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.5
Excavation |  | 38 |  | 100% | 15% |  | Excavation work Completed. Footing work Completed |  | Excavation in process | 19
Plinth |  | 19 |  | 50% |  |  |  |  | Excavation Completed | 38
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 9.5
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 19
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 28.5
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 38 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Marigold= Stilt + 2P + 3rd to 38th Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed
|  |  |  | 0 | 1 |  | 0 | 38 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.5
Excavation |  | 38 |  | 100% | 26.92% |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed |  | Excavation in process | 19
Plinth |  | 38 |  | 100% |  |  |  |  | Excavation Completed | 38
RCC (Including podiums) |  | 3 |  | 7.692% |  |  |  |  | Footing in Process | 9.5
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 19
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 28.5
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 38 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 32.93%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Gross Carpet area) |  |  | : : | 12500 to 13200 | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  |  | : | 500000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 4750
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 5267.5
Distress Value (Rs. Per sqft) | [5 empty] | : | 3800
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Gross Carpet Area
Acacia |  | - |  | Flats | 281 |  | 154851.2162
Orchid |  | - |  | Flats | 281 |  | 218800.0648
Mayflower |  | - |  | Flats | 144 |  | 190881.5641
Lavender |  | - |  | Flats | 288 |  | 209947.7297
Marigold |  | - |  | Flats | 209 |  | 179431.3914
Total |  |  |  |  | 1203 |  | 953911.9662
Details of Flats in Building
Description |  | Flat/Shop No. |  | Carpet area | Open Balcony |  | Utility Area | Gross Carpet area
50%
Building Acacia
Stilt Floor For Parking, Telecom Room & Meter Room
1st Podium Floor Parking & Entrance Lobby
2nd Podium Floor Parking, Entrance Lobby & Fitness Center
3rd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th, 32nd to 35th, 37th & 38th Floor For Residential
2BHK |  | 1 |  | 566.2079 | 26.0704 |  | 20.204 | 612.4824
2BHK |  | 2 |  | 566.2079 | 26.0704 |  | 20.204 | 612.4824
1BHK |  | 3 |  | 451.4314 | 22.3999 |  | 18.8155 | 492.6468
1BHK |  | 4 |  | 451.4314 | 22.3999 |  | 18.8155 | 492.6468
2BHK |  | 5 |  | 566.2079 | 26.0704 |  | 20.204 | 612.4824
2BHK |  | 6 |  | 566.2079 | 26.0704 |  | 20.204 | 612.4824
1BHK |  | 7 |  | 451.4314 | 22.3999 |  | 18.8155 | 492.6468
1BHK |  | 8 |  | 451.4314 | 22.3999 |  | 18.8155 | 492.6468
6th, 11th, 16th, 21st, 26th, 31st & 36th Floor (Part Refuge Area)
2BHK |  | 1 |  | 566.2079 | 26.0704 |  | 20.204 | 612.4824
2BHK |  | 2 |  | 566.2079 | 26.0704 |  | 20.204 | 612.4824
1BHK |  | 3 |  | 451.4314 | 22.3999 |  | 18.8155 | 492.6468
1BHK |  | 4 |  | 451.4314 | 22.3999 |  | 18.8155 | 492.6468
2BHK |  | 5 |  | 566.2079 | 26.0704 |  | 20.204 | 612.4824
2BHK |  | 6 |  | Refuge Area
1BHK |  | 7 |  | 451.4314 | 22.3999 |  | 18.8155 | 492.6468
1BHK |  | 8 |  | 451.4314 | 22.3999 |  | 18.8155 | 492.6468
Building Orchid
Stilt Floor For Parking, Telecom Room & Meter Room
1st Podium Floor Parking & Entrance Lobby
2nd Podium Floor Parking, Entrance Lobby & Fitness Center
3rd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th, 32nd to 35th, 37th & 38th Floor For Residential
2BHK |  | 1 |  | 699.111 | 55.6606 |  | 21.5926 | 776.3643 | 699.111 | 55.6606 |  | 21.5926
2BHK |  | 2 |  | 699.111 | 55.6606 |  | 21.5926 | 776.3643 | 699.111 | 55.6606 |  | 21.5926
2BHK |  | 3 |  | 708.142 | 52.2162 |  | 20.4624 | 780.8206 | 708.142 | 52.2162 |  | 20.4624
2BHK |  | 4 |  | 708.142 | 52.2162 |  | 20.4624 | 780.8206 | 708.142 | 52.2162 |  | 20.4624
2BHK |  | 5 |  | 699.111 | 55.6606 |  | 21.5926 | 776.3643 | 699.111 | 55.6606 |  | 21.5926
2BHK |  | 6 |  | 699.111 | 55.6606 |  | 21.5926 | 776.3643 | 699.111 | 55.6606 |  | 21.5926
2BHK |  | 7 |  | 708.142 | 52.2162 |  | 20.4624 | 780.8206 | 708.142 | 52.2162 |  | 20.4624
2BHK |  | 8 |  | 708.142 | 52.2162 |  | 20.4624 | 780.8206 | 708.142 | 52.2162 |  | 20.4624
6th, 11th, 16th, 21st, 26th, 31st & 36th Floor (Part Refuge Area)
2BHK |  | 1 |  | 699.111 | 55.6606 |  | 21.5926 | 776.3643
2BHK |  | 2 |  | 699.111 | 55.6606 |  | 21.5926 | 776.3643
2BHK |  | 3 |  | 708.142 | 52.2162 |  | 20.4624 | 780.8206
2BHK |  | 4 |  | 708.142 | 52.2162 |  | 20.4624 | 780.8206
2BHK |  | 5 |  | Refuge Area
2BHK |  | 6 |  | 699.111 | 55.6606 |  | 21.5926 | 776.3643
2BHK |  | 7 |  | 708.142 | 52.2162 |  | 20.4624 | 780.8206
2BHK |  | 8 |  | 708.142 | 52.2162 |  | 20.4624 | 780.8206
Building Mayflower
Stilt Floor For Parking, Lobby & Meter Room
1st Podium Floor Parking & Lobby
2nd Podium Floor Parking, Entrance Lobby, Creche & Fitness Center
3rd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th, 32nd to 35th, 37th & 38th Floor For Residential | [8 empty] | 29
3BHK |  | 1 |  | 1154.5574 | 96.2947 |  | 0 | 1250.8521 | 100.9275
3BHK |  | 2 |  | 1151.0699 | 96.2947 |  | 0 | 1247.3646
3BHK |  | 3 |  | 1166.0211 | 96.2947 |  | 0 | 1262.3158
3BHK |  | 4 |  | 1529.6075 | 99.7177 |  | 0 | 1629.3252
6th, 11th, 16th, 21st, 26th, 31st & 36th Floor (Part Refuge Area) | [8 empty] | 7
2BHK |  | 1 |  | 906.4687 | 96.2947 |  | 0 | 1002.7635
- |  | Refuge Area
2BHK |  | 2 |  | 948.6851 | 96.2947 |  | 0 | 1044.9799
3BHK |  | 3 |  | 1166.0211 | 96.2947 |  | 0 | 1262.3158
3BHK |  | 4 |  | 1529.6075 | 99.7177 |  | 0 | 1629.3252
Building Lavender
Stilt Floor For Parking, Lobby & Meter Room
1st Podium Floor Parking, Divers Room & Lobby
2nd Podium Floor Parking, Society Office, Entrance Lobby, Creche & Fitness Center
3rd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th, 32nd to 35th, 37th & 38th Floor For Residential | [8 empty] | 29
2BHK |  | 1 |  | 651.5987 | 26.3072 |  | 0 | 677.906 | 56.9978 | 2.4437 | 10.764 | 10.764
2BHK |  | 2 |  | 725.2137 | 55.5099 |  | 0 | 780.7237
2BHK |  | 3 |  | 725.2137 | 55.5099 |  | 0 | 780.7237
2BHK |  | 4 |  | 651.5987 | 26.3072 |  | 0 | 677.906
2BHK |  | 5 |  | 650.8022 | 26.3072 |  | 0 | 677.1094
2BHK |  | 6 |  | 725.2137 | 55.5099 |  | 0 | 780.7237
2BHK |  | 7 |  | 725.2137 | 55.5099 |  | 0 | 780.7237
2BHK |  | 8 |  | 649.7581 | 26.3072 |  | 0 | 676.0653
6th, 11th, 16th, 21st, 26th, 31st & 36th Floor (Refuge Balcony at midlanding of Staircase) | [8 empty] | 7
2BHK |  | 1 |  | 651.5987 | 26.3072 |  | 0 | 677.906
2BHK |  | 2 |  | 725.2137 | 55.5099 |  | 0 | 780.7237
2BHK |  | 3 |  | 725.2137 | 55.5099 |  | 0 | 780.7237
2BHK |  | 4 |  | 651.5987 | 26.3072 |  | 0 | 677.906
2BHK |  | 5 |  | 650.8022 | 26.3072 |  | 0 | 677.1094
2BHK |  | 6 |  | 725.2137 | 55.5099 |  | 0 | 780.7237
2BHK |  | 7 |  | 725.2137 | 55.5099 |  | 0 | 780.7237
2BHK |  | 8 |  | 649.7581 | 26.3072 |  | 0 | 676.0653
Building Marigold
Stilt Floor For Parking, Lobby & Meter Room
1st Podium Floor Parking, Divers Room & Lobby
2nd Podium Floor Parking, Society Office, Entrance Lobby, Creche & Fitness Center
3rd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th, 32nd to 35th, 37th & 38th Floor For Residential | [8 empty] | 29
2BHK |  | 1 |  | 724.6325 | 55.5099 |  | 0 | 780.1424
2BHK |  | 2 |  | 722.8349 | 55.5099 |  | 0 | 778.3448
3BHK |  | 3 |  | 908.8906 | 60.6982 |  | 0 | 969.5888 | 75.5715 | 5.6383
3BHK |  | 4 |  | 908.8906 | 60.6982 |  | 0 | 969.5888
2BHK |  | 5 |  | 722.8349 | 55.5099 |  | 0 | 778.3448
2BHK |  | 6 |  | 724.6325 | 55.5099 |  | 0 | 780.1424
6th, 11th, 16th, 21st, 26th, 31st & 36th Floor (Part Refuge Area) | [8 empty] | 7
2BHK |  | 1 |  | 867.2985 | 86.9624 |  | 0 | 954.2609
- |  | - |  | Refuge Area
4BHK |  | 3 |  | 1119.047 | 84.7557 |  | 0 | 1203.8027
3BHK |  | 4 |  | 908.8906 | 60.6982 |  | 0 | 969.5888
2BHK |  | 5 |  | 722.8349 | 55.5099 |  | 0 | 778.3448
2BHK |  | 6 |  | 724.6325 | 55.5099 |  | 0 | 780.1424
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Construction work is in process at the time of Visit.(Internal visit was not allowed). 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Open balcony + Utility Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We have updated revised plans & CC of Building Orchid (on 01/12/2023). 8. We have updated revised plans & CC of Building Mayflower (on 27/03/2024). 9. We have updated revised plans & CC of Building Lavender & Marigold (on 03/05/2024). 10. We have refered approved plan & CC of Building Lavender & Marigold from RERA.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Hiranandani Fortune City - Golden Willows (Acacia, Orchid, Mayflower, Lavender & Marigold) |  |  |  |  | Acacia & Orchid = 31/12/2028
Project Site Address |  |  | : | Acacia, Plot Bearing / CTS / Survey / Final Plot No.: 60/1 (Part) at Bhokarpada, Panvel, Raigarh, 410221 |  |  |  |  | Mayflower, Lavender & Marigold
Site Visit Date & Time |  |  | : | 04/07/2025 @12:24 PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Nitesh patil | Authorized Signatory Name & Signature | :
ACACIA
IRIS
ORCHID
Mayflower
Lavender
Marigold
Acacia
Orchid
Lavender
Mayflower
Marigold
Acacia
Orchid
Note on H6: Rushil Sanghvi or Fahad
Note on E9: Initiation Address
Note on E10: Plan Address
Note on E11: Plan Address
Note on C17: Maybe same as RERA Registration Validity or different
Note on H17: From Rera
Note on H20: From RERA
Note on A39: As per Layout
Note on H149: Ready Recknor