## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-03
Project Name |  | Arihant Aspire Phase III Building 01(Wing E - Catalina) |  | Date & Time of Site Visit |  | 03/07/2025 @04:55 PM
Name of the person met at site & Contact No. |  | Mr. Shaikh : 9321799353 |  | Date of Report Release |  | 06/07/2025
Data from APF Request Form
Branch Name/ID |  | Godrej One, Vikhroli East, Mumbai |  | Request from GHF Employee |  | Miss Ankita Mohite
Builder Group Name |  | Arihant Abode Limited |  | Developer Name |  | Arihant Superstructure Pvt Ltd
Developer Office Address |  | Floor No. 26, Plot No 13/1 - TTC Industrial Area, Thane Belapur Road, Turbhe MIDC, Turbhe, Navi Mumbai, Maharashtra - 400 705.
Project Address | As per ARF | Arihant Aspire ( Phase III), Palaspe Phata, Panvel, Navi Mumbai, Maharashtra 410221
| As per Legal Documents | Arihant Aspire (Phase III) Survey No. 7/5, 14/6, 14/7, 15/1, 15/3, 16, 18/1A, 18/1B, 23/3, 23/4, 24/1A, 149/1 to 5, 150/1 to 7, 153/1 to 153/6, Near Chattrapati Shivaji Vidyalay Palaspe, Mumbai Goa Highway, Palaspe, Palaspe Phata, Panvel, Panvel, Raigad - 410221
| As per Actual at site | Arihant Aspire (Phase III) Survey No. 7/5, 14/6, 14/7, 15/1, 15/3, 16, 18/1A, 18/1B, 23/3, 23/4, 24/1A, 149/1 to 5, 150/1 to 7, 153/1 to 153/6, Near Chattrapati Shivaji Vidyalay Palaspe, Mumbai Goa Highway, Palaspe, Palaspe Phata, Panvel, Panvel, Raigad - 410221
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC, RERA certificate
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Navi Mumbai Airport Influence Notified Area (NAINA)
RERA Registration No. | : | P52000056197 |  | RERA Registration Validity | : | 2031-12-31
Project Launch Date | : | 2024-05-21 |  | Construction Start Date | : | 2024-05-21
Proposed Date of Completion (As per RERA) | : | 2031-12-31 |  | Developer Bank Name (As per RERA) | : | ICICI BANK LIMITED IFSC Code - ICIC0002841
Project Type (Mixed, Residential, Comm.) | : | Residential |  | Plot Area (In Sq.Mt) | : | 66751.62
FSI/FAR Permissible | : | 3 |  | Net Plot Area (In Sq.Mt) | : | 54316.22
Permissible Built up Area (In Sq.Mt) | : | 121217.905 |  | Proposed Built up Area (In Sq.Mt) | : | 57568.098 |  | 57568.098 Sq.M
Total Number of Units Approved | : | Flats = 323 & Shop = 13 |  | Total Number of Units Planned | : | As per RERA Site Flats = 323
Latitude, Longitude | : | 18.9627577,73.1324823 |  | Landmark | : | Chattrapati Shivaji Vidyalay Palaspe
Location Link | : | https://maps.app.goo.gl/AWCVLeCpMPdQjRF29
Extra Amenities available | : | Lawn, Jogging Track, Senior Citizen's Area, Reflexology pathway, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Seating Promenade, Clubhouse, Food Mart, Gym, Basketball Court, Sunken Seating with Planters, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Mini Theater, Temple, etc.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  | Width of the Road | : | 40M
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 1.10KM from Palaspa Bus Stand
Distance from the nearest School (Km) | : | About 1KM from Balaji New English School And Jr. college Palaspe |  | Distance from Hospital (Km) | : | About 2.2KM form ONGC Hospital
Distance from the Main Market (Km) | : | 1. Approx. 1.20 KM from D Mart. 2. Approx. 1.30KM from Reliance SMART Superstore. |  | Distance from Railway Station (Km) | : | 5.70KM from Panvel Railway Station.
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North |  | South | East | West
East |  | Wing F/ 12M Wide Drive Way |  |  | Open Plot
West |  | Wing D/ MH-17 National Highway |  |  | Mumbai-Goa Highway
North |  | Wing B/09M Wide Drive Way |  |  | Open Plot/Kirki River
South |  | 15M Wide Drive Way/Wing H |  |  | Houses / The Club House Aspire
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Building 01 Wing E (Catalina) |  | Sale | 3B + Stilt/Gr + 2P + 3rd to 43rd Floor |  |  | 3B + Stilt/Gr + 2P + 3rd to 43rd Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | CIDCO/NAINA/Panvel/Palaspe/BP-00006/ACC/2023/ 0345 |  |  |  | Date: | 2023-03-16
Approved Plan Details | : | CIDCO/NAINA/Panvel/Palaspe/BP-06/CC/2017/770 Phase III (Wing E - Catalina) = 1st to 3rd Basement Floor |  |  |  | Date: | 2017-10-16
Approved Plan Details | : | CIDCO/NAINA/Panvel/Palaspe/BP-00006/ACC/2023/ 0347 Phase III (Wing E - Catalina) = G + 1st to 43rd Floor |  |  |  | Date: | 2023-03-16
CC Details Valid Up to: |  | CIDCO/NAINA/Panvel/Palaspe/BP-00006/ACC/2023/ 0345 |  |  |  | Date: | 2023-03-16
3 Basements + Ground (Shops+Stilt Parking) + 43 Upper Residential Floors
Environmental Clearance Details | : |  |  |  |  | Date:
Change of User/Zone Certificate Details | : |  |  |  |  | Date:
Airport Authority Clearance Details | : |  |  |  |  | Date:
Other NOC Details | : |  |  |  |  | Date:
Construction Status
Building 01 Wing E (Catalina) = 3B + Stilt/Gr + 2P + 3rd to 43rd Floor . |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed
|  |  | 3 | 1 |  | 0 | 43 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 10.75
Excavation |  | 43 | 100% | 26.7% |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed |  | Excavation in process | 21.5
Plinth |  | 43 | 100% |  |  |  |  | Excavation Completed | 43
RCC (Including podiums) |  | 3 | 6.818% |  |  |  |  | Footing in Process | 8.6
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 17.2
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 25.8
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 34.4
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 43
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
#REF! |  |  | Basement | Ground |  | Podium | Floors | #REF!
|  |  | 0 | 1 |  | 0 | #REF! | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | #REF!
Excavation |  | #REF! | #REF! | #REF! |  | #REF! |  | Excavation in process | #REF!
Plinth |  | #REF! | #REF! |  |  |  |  | Excavation Completed | #REF!
RCC (Including podiums) |  | 0 | #REF! |  |  |  |  | Footing in Process | #REF!
Brickwork |  | 0 | #REF! |  |  |  |  | Footing Completed | #REF!
Internal Plaster |  | 0 | #REF! |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | #REF! |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | #REF! |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | #REF! |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | #REF! |  |  |  |  | Plinth in process | #REF!
Electrical & Sanitary fittings |  | 0 | #REF! |  |  |  |  | Plinth completed | #REF!
Building Common Amenities |  | 0 | #REF!
Possession |  | 0 | #REF!
Construction Status
#REF! |  |  | Basement | Ground |  | Podium | Floors | #REF!
|  |  | 0 | 1 |  | 0 | #REF! | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | #REF!
Excavation |  | #REF! | #REF! | #REF! |  | #REF! |  | Excavation in process | #REF!
Plinth |  | #REF! | #REF! |  |  |  |  | Excavation Completed | #REF!
RCC (Including podiums) |  | 0 | #REF! |  |  |  |  | Footing in Process | #REF!
Brickwork |  | 0 | #REF! |  |  |  |  | Footing Completed | #REF!
Internal Plaster |  | 0 | #REF! |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | #REF! |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | #REF! |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | #REF! |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | #REF! |  |  |  |  | Plinth in process | #REF!
Electrical & Sanitary fittings |  | 0 | #REF! |  |  |  |  | Plinth completed | #REF!
Building Common Amenities |  | 0 | #REF!
Possession |  | 0 | #REF!
Project Completion % | [5 empty] | 26.7%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 9000 to 10000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA |  | 1000
Car Parking Charges |  | 300000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 966.1836
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 5574.136
Distress Value (Rs. Per sqft) |  |  |  |  | : | 772.9469
Unit Details, Nomenclature and Area Details Phase III = Building 01Wing E (Catalina)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Shops |  | - |  | 13 |  | 3586.8608
Total |  | - |  | 13 |  | 3586.8608
Unit Details, Nomenclature and Area Details Phase III = Building 01Wing E (Catalina)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Flats |  | - |  | 323 |  | 197421.8459
Total |  | - |  | 323 |  | 197421.8459
Grand Total |  | - |  | 336 |  | 201008.7067
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
Phase III
Building 01 Wing E (Catalina)
1st to 3rd Basement Floor For Parking
Ground Floor For Commercial, Society Office, Drivers Room & Parking | [8 empty] | 10.764
9 |  | - | Shop | 218.0517 | 0 | 0 | 218.0517
10 |  | - | Shop | 344.2596 | 0 | 0 | 344.2596
11 |  | - | Shop | 240.3332 | 0 | 0 | 240.3332
12 |  | - | Shop | 293.5612 | 0 | 0 | 293.5612
13 |  | - | Shop | 293.023 | 0 | 0 | 293.023
14 |  | - | Shop | 239.4721 | 0 | 0 | 239.4721
15 |  | - | Shop | 344.2596 | 0 | 0 | 344.2596
16 |  | - | Shop | 180.1894 | 0 | 0 | 180.1894
17 |  | - | Shop | 344.2596 | 0 | 0 | 344.2596
18 |  | - | Shop | 293.5612 | 0 | 0 | 293.5612
19 |  | - | Shop | 239.4721 | 0 | 0 | 239.4721
20 |  | - | Shop | 344.2596 | 0 | 0 | 344.2596
21 |  | - | Shop | 212.1584 | 0 | 0 | 212.1584
1st Podium Floor For Parking
2nd Podium Floor For Residential & Parking
1 |  | Parking |  |  |  |  | - | 53.7575
2 | [6 empty] | -
3 |  | - | 2.5BHK | 607.3372 | 83.421 | 0 | 690.7582 | 53.7575 | 53.3375
4 |  | - | 2.5BHK | 607.3372 | 83.421 | 0 | 690.7582
5 |  | - | 2.5BHK | 607.3372 | 83.421 | 0 | 690.7582
6 |  | - | 2.5BHK | 607.3372 | 83.421 | 0 | 690.7582
7 |  | Parking |  |  |  |  | -
8 | [6 empty] | -
3rd to 6th, 8th to 10th, 12th to 14th, 16th to 18th, 20th to 22nd, 24th to 26th, 28th to 30th, 32nd to 34th, 36th to 38th & 40th to 43rd Floor For Residential
1 |  | - | 1BHK | 309.8094 | 99.0288 | 0 | 408.8382 | 27.015 | 9.45 |  |  |  |  | 3681001,..,4301 | 3681001 | 4301
2 |  | - | 2BHK | 463.9607 | 132.3972 | 0 | 596.3579 | 39.7675 | [5 empty] | 3681002,..,4302 | 3681002 | 4302
3 |  | - | 2.5BHK | 611.7719 | 113.022 | 0 | 724.7939 | [6 empty] | 3681003,..,4303 | 3681003 | 4303
4 |  | - | 2.5BHK | 611.7719 | 111.9456 | 0 | 723.7175 | [6 empty] | 3681004,..,4304 | 3681004 | 4304
5 |  | - | 2.5BHK | 611.7719 | 111.9456 | 0 | 723.7175 | [6 empty] | 3681005,..,4305 | 3681005 | 4305
6 |  | - | 2.5BHK | 611.7719 | 113.022 | 0 | 724.7939 | [6 empty] | 3681006,..,4306 | 3681006 | 4306
7 |  | - | 2BHK | 463.9607 | 131.3208 | 0 | 595.2815 | [6 empty] | 3681007,..,4307 | 3681007 | 4307
8 |  | - | 1BHK | 309.8094 | 99.567 | 0 | 409.3764 | 17954.135 | [5 empty] | 3681008,..,4308 | 3681008 | 4308
7th, 11th, 15th, 19th, 23rd, 27th, 31st, 35th & 39th Floor (Part Refuge Area) | [9 empty] | 9000
1 |  | - | 1BHK | 309.8094 | 99.0288 | 0 | 408.8382 | 613.2574 | 7990.12 | 3679544.232 |  |  |  | 71101,..,3901 | 71101 | 3901
2 |  | - | 2BHK | 463.9607 | 132.3972 | 0 | 596.3579 | 894.5368 | 9390.3344 | 5367221.028 |  |  |  | 71102,..,3902 | 71102 | 3902
3 |  | - | 2.5BHK | 611.7719 | 113.022 | 0 | 724.7939 | 1087.1909 | 4507.0281 | 6523145.46 |  |  |  | 71103,..,3903 | 71103 | 3903
4 |  | - | 2.5BHK | 611.7719 | 111.9456 | 0 | 723.7175 | 1085.5763 | 4513.7315 | 6513457.86 |  |  |  | 71104,..,3904 | 71104 | 3904
5 |  | - | 2.5BHK | 611.7719 | 111.9456 | 0 | 723.7175 | 1085.5763 | 4513.7315 | 6513457.86 |  |  |  | 71105,..,3905 | 71105 | 3905
6 |  | - | Refuge Area |  |  |  |  | 0 | #DIV/0! | 0 |  |  |  | 71106,..,3906 | 71106 | 3906
7 |  | - | 2BHK | 463.9607 | 131.3208 | 0 | 595.2815 | 892.9222 | 5487.5999 | 5357533.428 |  |  |  | 71107,..,3907 | 71107 | 3907
8 |  | - | 1BHK | 309.8094 | 99.567 | 0 | 409.3764 | 614.0647 | 9347.5496 | 3684388.032 |  |  |  | 71108,..,3908 | 71108 | 3908
1st Floor
101 |  |  |  | 0 | 0 | 0 | 0
102 | [6 empty] | 0
103 | [6 empty] | 0
104 | [6 empty] | 0
105 | [6 empty] | 0
106 | [6 empty] | 0
107 | [6 empty] | 0
108 | [6 empty] | 0
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor
201,..,901 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 201,..,901 | 201 | 901
202,..,902 | [6 empty] | 0 | [6 empty] | 202,..,902 | 202 | 902
203,..,903 | [6 empty] | 0 | [6 empty] | 203,..,903 | 203 | 903
204,..,904 | [6 empty] | 0 | [6 empty] | 204,..,904 | 204 | 904
205,..,905 | [6 empty] | 0 | [6 empty] | 205,..,905 | 205 | 905
206,..,906 | [6 empty] | 0 | [6 empty] | 206,..,906 | 206 | 906
207,..,907 | [6 empty] | 0 | [6 empty] | 207,..,907 | 207 | 907
208,..,908 | [6 empty] | 0 | [6 empty] | 208,..,908 | 208 | 908
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 201 to 501 | 201 | 501
202 to 502 | [6 empty] | 0 | [6 empty] | 202 to 502 | 202 | 502
203 to 503 | [6 empty] | 0 | [6 empty] | 203 to 503 | 203 | 503
204 to 504 | [6 empty] | 0 | [6 empty] | 204 to 504 | 204 | 504
205 to 505 | [6 empty] | 0 | [6 empty] | 205 to 505 | 205 | 505
206 to 506 | [6 empty] | 0 | [6 empty] | 206 to 506 | 206 | 506
207 to 507 | [6 empty] | 0 | [6 empty] | 207 to 507 | 207 | 507
208 to 508 | [6 empty] | 0 | [6 empty] | 208 to 508 | 208 | 508
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 201 & 501 | 201 | 501
202 & 502 | [6 empty] | 0 | [6 empty] | 202 & 502 | 202 | 502
203 & 503 | [6 empty] | 0 | [6 empty] | 203 & 503 | 203 | 503
204 & 504 | [6 empty] | 0 | [6 empty] | 204 & 504 | 204 | 504
205 & 505 | [6 empty] | 0 | [6 empty] | 205 & 505 | 205 | 505
206 & 506 | [6 empty] | 0 | [6 empty] | 206 & 506 | 206 | 506
207 & 507 | [6 empty] | 0 | [6 empty] | 207 & 507 | 207 | 507
208 & 508 | [6 empty] | 0 | [6 empty] | 208 & 508 | 208 | 508
Project Specific Remarks & Observation
* | Construction work is in process at the time of Visit (Slow Speed).
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Niche
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Please Check for Environmental Clearance Certificate & Fire Noc.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
Site & Building/Tower Photographs
Name of the Project |  |  | Arihant Aspire Phase III Building 01(Wing E - Catalina)
Project Site Address |  |  | Arihant Aspire ( Phase III), Palaspe Phata, Panvel, Navi Mumbai, Maharashtra 410221
Site Visit Date & Time |  |  | 03/07/2025 @04:55 PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr.Ravindra vishwakarma |  | Authorized Signatory Name & Signature
Wing E - Catalina
Wing E - Catalina
Note on C9: SACHIN: As per initiation Mail
Note on C17: Maybe same as RERA Registration Validity or different
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G112: Ready Recknor

## Sheet1
1235.6001
4134.1509

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%