## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-03
Project Name |  |  | : | Arkade Prime |  | Date & Time of Site Visit |  | 03/07/2025 @ 12:56 PM
Name of the person met at site & Contact No. |  |  | : | Mr. Shubham : 8591147469 |  | Date of Report Release |  | 06/07/2025
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Ms Ankita Mohite
Builder Group Name |  |  | : | Arkade Developers Pvt Ltd | Developer Name | : | Arkade Developers Pvt Ltd
Developer Office Address |  |  | : | Arkade house, Office at 2nd Floor, near childerns academy school, A.S.Marg, Ashok Nagar, Kandivali (East), Mumbai 400101
Project Address | : | As per ARF | : | Makwana Rd, Gamdevi, Marol, Andheri East, Mumbai, Maharashtra 400059
| : | As per Legal Documents | : | Proposed Residential Cum Commercial Building on Plot Bearing C.T.S No. 778A of Village Marol, Makwana Road, Andheri (East)
| : | As per Actual at site | : | Arkade Prime, CTS No.778A, Near Jai Antariksha Commercial Building, Makwana Road, Gamdevi, Marol, Andheri, Mumbai Suburban - 400059.
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Municipal Corporation of Greater Mumbai
RERA Registration No. | : | P51800047081 |  |  | RERA Registration Validity | : | Completed
Project Launch Date | : | 2022-08-29 |  |  | Construction Start Date | : | 2022-08-29
Proposed Date of Completion (As per RERA) | : | Completed |  |  | Developer Bank Name (As per RERA) | : | HDFC Bank
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  |  | Plot Area (In Sq.Mt) | : | 1953.6
FSI/FAR Permissible | : | 1.33 |  |  | Proposed Built up Area (In Sq.Mt) | : | 6605.71
Permissible Built up Area (In Sq.Mt) | : | 4900.79 |  |  | Total Number of Units Planned | : | Flats = 110 & Shop = 2
Total Number of Units Approved | : | Flats = 107 |  |  | If Mixed, No. of Commercial Units | : | Shop = 2 & Office = 2
Latitude, Longitude | : | 19.1091836,72.8813281
Location Link | : | https://goo.gl/maps/QXBktHRXKRyLGxLj6
Extra Amenities available | : | Gymnasium, Kids Play Area, Terrace Garden, Banquet Hall, Seat Out Area, 24*7 Security, Yoga, Electrical Vehicle Charging Point, 24*7 Water Supply
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Upper
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 0.280KM from Marol Naka Bus Stop
Distance from the nearest School (Km) | : | About 0.650KM from School |  |  | Distance from Hospital (Km) | : | About 1.1KM form Hospital
Distance from the Main Market (Km) | : | 1. Approx. 1KM from Brihanmumbai Municipal Corporation Market. |  |  | Distance from Railway Station (Km) | : | 4.1KM from Andheri Railway Station 5.4KM from Vile Parle Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Building | Building | Building |  | Road
As per Site / Actual |  |  | : | Antariksh Thakur | Vedanta | Jai Antariksha commercial building |  | Road
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Wing A |  | Sale |  | Gr + 1st to 13th Floor |  |  | Gr + 1st to 13th Floor
Wing B |  | Sale |  | Gr + 1st to 13th Floor |  |  | Gr + 1st to 13th(Pt) Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | P-9876/2021/(778-A)/K/E WARD/MAROL/337 Date: 29/03/2023
CC Details | : | P-9876/2021/(778-A)/K/E Ward/MAROL/FCC/1/Amend Date: 11/06/2024 Valid Up to: Full C.C. up to top of 13th floor for Wing-A and Wing-B i.e. ht. 41.85m. AGL as per last approved plans dated 22/04/2024. Valid Upto Date : 28/08/2024 |  |  | Approved Plan Details | : | P-9876/2021/(778-A)/K/E WARD/MAROL/337 Date: 29/03/2023 |  | Attached Airport and Fire NOC in MIS
Part OC Details Valid Up to: | : | P-9876/2021/(778-A)/K/E Ward/MAROL/OCC/1/New Date: 01/04/2024 Ground +1 commercial only |  |  | Airport Authority Clearance Details | : | SNCR/WEST/B/010622/6-16658 Date:04/03/2022 Valid up to - 57.13 M (AMSL) Valid Upto Date: 03/03/2030 |  | Environmental Clearance Details
OC Details | : | P-9876/2021/(778-A)/K/E Ward/MAROL/OCC/1/New Date: 27/01/2025 wing A & B = Ground floor + 1st floor + 2nd floor +3rd to 13th floors
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
Construction Status
Wing A & B = Gr + 1st to 13th Floor |  |  | : | Basement | Ground |  | Podium | Floors | All work completed. Please provide OC.
|  |  |  | 0 | 1 |  | 0 | 13 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 3.25
Excavation |  | 13 |  | 100% | 100% |  | All work Completed. OC Received. |  | Excavation in process | 6.5
Plinth |  | 13 |  | 100% |  |  |  |  | Excavation Completed | 13
RCC (Including podiums) |  | 14 |  | 100% |  |  |  |  | Footing in Process | 2.6
Brickwork |  | 13 |  | 100% |  |  |  |  | Footing Completed | 5.2
Internal Plaster |  | 13 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 13 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 13 |  | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 13 |  | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 13 |  | 100% |  |  |  |  | Plinth in process | 9.1
Electrical & Sanitary fittings |  | 13 |  | 100% |  |  |  |  | Plinth completed | 13
Building Common Amenities |  | 13 |  | 100%
Possession |  | 13 |  | 100%
Construction Status
Wing B - Gr + 1st to 13th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 12 Floor, Flooring & Fitting upto 12 Floor, Wooden Work upto 12 Floor, Electrical & Sanitary fittings upto 12 Floor, Finishing upto 8 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 13 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 3.25
Excavation |  | 13 |  | 100% | 84.62% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 12 Floor, Flooring & Fitting upto 12 Floor, Wooden Work upto 12 Floor, Electrical & Sanitary fittings upto 12 Floor, Finishing upto 8 Floor Completed |  | Excavation in process | 6.5
Plinth |  | 13 |  | 100% |  |  |  |  | Excavation Completed | 13
RCC (Including podiums) |  | 14 |  | 100% |  |  |  |  | Footing in Process | 2.6
Brickwork |  | 13 |  | 100% |  |  |  |  | Footing Completed | 5.2
Internal Plaster |  | 13 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 13 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 12 |  | 92.31% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 12 |  | 92.31% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 12 |  | 92.31% |  |  |  |  | Plinth in process | 9.1
Electrical & Sanitary fittings |  | 12 |  | 92.31% |  |  |  |  | Plinth completed | 13
Building Common Amenities |  | 8 |  | 61.54%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 100%
PSF Rates & Other Charges | [10 empty] | 1BHK | 1.14 | 24308.3952 | 27033.8074
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area |  |  |  | 2BHK | 1.6 | 24769.4137 | 26974.9095
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 23500 to 24500 | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA | [6 empty] | 27007.355
Car Parking Charges |  |  | : | 800000/- | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 7752.7
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 15109.62
Distress Value (Rs. Per sqft) | [5 empty] | : | 6202.16
Commercial Area Details :
Building & Wing |  | Sale |  | Shops | No. of Unit |  | Total Carpet Area | Total Saleable Area
Wing A (Shops) |  | Sale |  | Shops | 2 |  | 3117.362 | 4831.9112
Wing A (Offices) |  | Sale |  | Offices | 2 |  | 2177.1266 | 3374.5463
Total |  | Sale |  | - | 4 |  | 5294.4887 | 8206.4575
Residential Area Details :
Building & Wing |  | Sale |  | Flats | No. of Unit |  | Total Carpet Area | Total Saleable Area
Wing A |  | Sale |  | Flats | 57 |  | 31804.0679 | 49296.3052
Wing B |  | Sale |  | Flats | 50 |  | 27130.662 | 42052.5261
Total |  | - |  | - | 107 |  | 58934.7299 | 91348.8313
Total |  | - |  | - | 111 |  | 64229.2186 | 99555.2888
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
55%
Wing A
Ground Floor for Commercial & Parking | [10 empty] | 10.764
Ground Floor for Commercial & Parking |  | 1 |  | Shop | 948.739 |  | 0 | 1470.5454
|  | 2 |  | Shop Duplex with 1st Floor | 2168.6231 |  | 0 | 3361.3658 |  |  | 74.0074 | 125.8949 | 199.9023
1st Floor for Commercial
1st Floor for Commercial |  | 1 |  | Office | 1122.2546 |  | 0 | 1739.4947
|  | 2 |  | Office | 1054.872 |  | 0 | 1635.0516
|  | - |  | Duplex Shop With Ground Floor
2nd Floor for Residential & (Society Office, Entrance Loby)
2nd Floor for Residential & (Society Office, Entrance Loby) |  | 3 |  | 2BHK | 657.2498 |  | 0 | 1018.7373 | [6 empty] | 201,..,201 | 201 | 201
|  | 4 |  | 2BHK | 657.2498 |  | 0 | 1018.7373 | [6 empty] | 202,..,202 | 202 | 202
|  | 5 |  | 2BHK | 605.2597 |  | 0 | 938.1526 | [6 empty] | 203,..,203 | 203 | 203
3rd Floor
3rd Floor |  | 1 |  | 1BHK | 452.5186 |  | 0 | 701.4038 | [6 empty] | 301 to 301 | 301 | 301
|  | 2 |  | 1BHK | 425.3933 |  | 0 | 659.3596 | [6 empty] | 302 to 302 | 302 | 302
|  | 3 |  | 2BHK | 659.0797 |  | 0 | 1021.5736 | [6 empty] | 303 to 303 | 303 | 303
|  | 4 |  | 2BHK | 659.0797 |  | 0 | 1021.5736 |  | z |  |  |  |  | 304 to 304 | 304 | 304
|  | 5 |  | 2BHK | 605.2597 |  | 0 | 938.1526 | [6 empty] | 305 to 305 | 305 | 305
4th to 7th, 9th to 12th Floor
4th to 7th, 9th to 12th Floor |  | 1 |  | 1BHK | 425.3933 |  | 0 | 659.3596 | [6 empty] | 401 to 1201 | 401 | 1201
|  | 2 |  | 1BHK | 425.3933 |  | 0 | 659.3596 | [6 empty] | 402 to 1202 | 402 | 1202
|  | 3 |  | 2BHK | 659.0797 |  | 0 | 1021.5736 | [6 empty] | 403 to 1203 | 403 | 1203
|  | 4 |  | 2BHK | 659.0797 |  | 0 | 1021.5736 | [6 empty] | 404 to 1204 | 404 | 1204
|  | 5 |  | 2BHK | 605.2597 |  | 0 | 938.1526 | [6 empty] | 405 to 1205 | 405 | 1205
8th Floor (Part Refuge Area)
8th Floor (Part Refuge Area) |  | 1 |  | 1BHK | 425.3933 |  | 0 | 659.3596 | [6 empty] | #REF! | #REF! | 801
|  | 2 |  | 1BHK | 425.3933 |  | 0 | 659.3596 | [6 empty] | #REF! | #REF! | 802
|  | 3 |  | 2BHK | 659.0797 |  | 0 | 1021.5736 | [6 empty] | #REF! | #REF! | 803
|  | 4 |  | Refuge Area | [10 empty] | #REF! | #REF! | 804
|  | 5 |  | 2BHK | 605.2597 |  | 0 | 938.1526 | [6 empty] | #REF! | #REF! | 805
13th Floor
13th Floor |  | 1 |  | 1BHK | 425.3933 |  | 0 | 659.3596 | [6 empty] | 1301 to 1301 | 1301 | 1301
|  | 2 |  | 1BHK | 425.3933 |  | 0 | 659.3596 | [6 empty] | 1302 to 1302 | 1302 | 1302
|  | 3 |  | 2BHK | 659.0797 |  | 0 | 1021.5736 | [6 empty] | 1303 to 1303 | 1303 | 1303
|  | 4 |  | 2BHK | 659.0797 |  | 0 | 1021.5736 | [6 empty] | 1304 to 1304 | 1304 | 1304
|  | 5 |  | 2BHK | 605.2597 |  | 0 | 938.1526 | [6 empty] | 1305 to 1305 | 1305 | 1305
Wing B
Ground Floor, 1st Floor for Parking
2nd Floor for Parking & Amenity (Fitness Center, Garden, Swimming Pool & Kids Play Area)
3rd Floor for Residentail
3rd Floor for Residentail |  | 1 |  | 1BHK | 453.3797 |  | 0 | 702.7385 | [6 empty] | 301 to 301 | 301 | 301
|  | 2 |  | 1BHK | 453.3797 |  | 0 | 702.7385 | [6 empty] | 302 to 302 | 302 | 302
|  | 3 |  | 2BHK | 589.4366 |  | 0 | 913.6268 | [6 empty] | 303 to 303 | 303 | 303
|  | 4 |  | 2BHK | 630.1246 |  | 0 | 976.6931 | [6 empty] | 304 to 304 | 304 | 304
|  | 5 |  | 2BHK | 628.51 |  | 0 | 974.1904 | [6 empty] | 305 to 305 | 305 | 305
4th to 7th, 9th to 12th Floor
4th to 7th, 9th to 12th Floor |  | 1 |  | 1BHK | 425.3933 |  | 0 | 659.3596 | [6 empty] | 401 to 1201 | 401 | 1201
|  | 2 |  | 1BHK | 425.3933 |  | 0 | 659.3596 | [6 empty] | 402 to 1202 | 402 | 1202
|  | 3 |  | 2BHK | 589.4366 |  | 0 | 913.6268 | [6 empty] | 403 to 1203 | 403 | 1203
|  | 4 |  | 2BHK | 630.1246 |  | 0 | 976.6931 | [6 empty] | 404 to 1204 | 404 | 1204
|  | 5 |  | 2BHK | 628.51 |  | 0 | 974.1904 | [6 empty] | 405 to 1205 | 405 | 1205
8th Floor (Part Refuge Area)
8th Floor (Part Refuge Area) |  | 1 |  | Refuge Area | [10 empty] | #REF! | #REF! | 801
|  | 2 | [12 empty] | #REF! | #REF! | 802
|  | 3 |  | 3BHK | 829.7968 |  | 0 | 1286.185 | [6 empty] | #REF! | #REF! | 803
|  | 4 |  | 2BHK | 630.1246 |  | 0 | 976.6931 | [6 empty] | #REF! | #REF! | 804
|  | 5 |  | 2BHK | 628.51 |  | 0 | 974.1904 | [6 empty] | #REF! | #REF! | 805
13th Floor (Part Terrace Area)
13th Floor (Part Terrace Area) |  | 1 |  | 1BHK | 425.3933 |  | 0 | 659.3596 | [6 empty] | 1301 to 1301 | 1301 | 1301
|  | 2 |  | MP Room | 271.1452 |  | 0 | 420.275 | [6 empty] | 1302 to 1302 | 1302 | 1302
|  | 3 |  | Terrace Area | [10 empty] | 1303 to 1303 | 1303 | 1303
|  | 4 | [12 empty] | 1304 to 1304 | 1304 | 1304
|  | 5 | [12 empty] | 1305 to 1305 | 1305 | 1305
Project Specific Remarks & Observation
Remarks / Observations | : | 1. All Work Completed. OC Received. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We have updated Approved layout plan & Floor plan of Wing A & B (on 29/03/2023). 8. We have updated OC from MCGM Site on 29/04/2025. | [6 empty] | Construction work is in process at the time of Visit.(Internal Visit Not Allowed)
Site & Building/Tower Photographs
Name of the Project |  |  | : | Arkade Prime
Project Site Address |  |  | : | Makwana Rd, Gamdevi, Marol, Andheri East, Mumbai, Maharashtra 400059
Site Visit Date & Time |  |  | : | 03/07/2025 @ 12:56 PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Ganesh Wadkar | Authorized Signatory Name & Signature | :
Arkade Prime
Jai Antariksha Building
Note on H6: Rushil Sanghvi or Fahad
Note on E9: Initiation Address
Note on E10: Plan Address
Note on E11: Map Address
Note on H17: From Rera
Note on H20: From RERA
Note on H96: Ready Recknor