## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  |  | : | Ashar Arize |  | Date & Time of Site Visit |  | 10/07/2025 @05:09 PM |  | 2025-04-29 | 2025-07-10
Name of the person met at site & Contact No. |  |  | : | Mr. Sachin 8652208309 |  | Date of Report Release |  | 11/07/2025 |  |  | 72
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Ankita Mohite
Builder Group Name |  |  | : | Ms Ashar Ventures | Developer Name | : | Ms Ashar Ventures
Developer Office Address |  |  | : | 11th Floor, Ashar IT Park, Jayshri Baug, Road No. 16/Z, Wagle Industrial Estate, Thane West, Thane, Maharashtra 400604
Project Address | : | As per ARF | : | Ashar Arize Galleria, Plot Bearing Cts No. 2459, 2460, 2461, 2490, 2491, 2492, 2546, 2547 At Thane (M Corp.), Thane, Thane, 400605
| : | As per Legal Documents | : | Ashar Arize, CTS No. 2459, 2460, 2461, 2490, 2491, 2492, 2546, 2547, Village - Kalwa, Tal & Dist Thane 400605.
| : | As per Actual at site | : | Pune - Mumbai Hwy, behind Sahyadri School, off Old, Jai Trimurti Cooperative Housing Society, Budhaji Nagar, Kalwa, Thane, Maharashtra 400605
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate, NOC
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | The Municipal Corporation Of The City Of Thane
RERA Registration No. | : | Ashar Arize N.M.M. Society Tower A = P51700034211 Ashar Arize Tower B And C = P51700034565 Ashar Arize Galleria = P51700034721 |  |  | RERA Registration Validity | : | 31/01/2027
Project Launch Date | : | 2022-06-06 |  |  | Construction Start Date | : | Ashar Arize N.M.M. Society Tower A = 11/04/2022 Ashar Arize Tower B And C = 25/03/2022 Ashar Arize Galleria = 20/04/2022
Proposed Date of Completion (As per RERA) | : | 31/01/2027 |  |  | Developer Bank Name (As per RERA) | : | ICICI Bank IFSC Code - ICIC0001887
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  |  | Plot Area (In Sq.Mt) | : | 13163.24
FSI/FAR Permissible | : | 1.1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 76617.31
Permissible Built up Area (In Sq.Mt) | : | 76617.31 |  |  | Total Number of Units Planned | : | As per RERA Site Flats = 1095 & Shop = 44 |  |  | 396 | 390 | 309
Total Number of Units Approved | : | Flats = 1088 |  |  | If Mixed, No. of Commercial Units | : | Shop = 44 |  |  | 44 |  | 1095
Latitude, Longitude | : | 19.197961, 72.995628 |  |  | Landmark | : | Sahkar Vidya Prasarak Mandal Secondary School |  |  |  | 1027
Location Link | : | https://goo.gl/maps/pCWA2x9pnfKhpiuVA
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 500 M from Rasayani Bus Stop
Distance from the nearest School (Km) | : | About 300m from Sahkar Vidya Prasarak Mandal Secondary School |  |  | Distance from Hospital (Km) | : | About 950m form Aarogya Multi Specialty Hospital
Distance from the Main Market (Km) | : | 1. Approx. 600m from Sai Farmer S Market. 2. Approx. 3.1 from Thane wholesell market |  |  | Distance from Railway Station (Km) | : | 800m from Kalva Railway Station 4.2KM from Thane Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | 6M Wide Fire Engine Driveway | 30M Wide Proposed Dp Road | 6M Wide Driveway/30M Wide Proposed Dp Road |  | 18M Wide Proposed Dp Road
As per Site / Actual |  |  | : | Sahkar Vidya Prasarak Mandal Secondary School | Kalwa EMU CarShed/ Kalva Railway Station | Nala |  | N.M.M. Society
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Wing A |  | Residential |  | LG + UG + 1P + Upper Stilt + 1st to 29(Pt) Floor |  |  | LG + UG + 1P + Upper Stilt + 1st to 29(Pt) Floor
Wing B |  | Residential |  | LG + UG + 1P + 2P (Pt) + Upper Stilt + 1st to 39th + 40th (Recreation) (Pt) Floors |  |  | LG + UG + 1P + 2P (Pt) + Upper Stilt + 1st to 39th + 40th (Recreation) (Pt) Floors
Wing C |  | Residentia |  | LG + UG + 1P + 2P (Pt) + Upper Stilt + 1st to 39th + 40th (Pt) Floors |  |  | LG + UG + 1P + 2P (Pt) + Upper Stilt + 1st to 39th + 40th (Pt) Floors
Wing D = Gr + 1st Floor |  | Commercial |  | Ground Floor (Commercial) |  |  | Ground Floor (Commercial)
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | V.P.S08/0114/21/TMC/TDD/4088/22 Date: 20/06/2022
CC Details Valid Up to: | : | S08/0114/21/TMC/TDD/4209/22 Date: 27/09/2022 Wing A = LG + UG + 1P + Upper Stilt + 1st to 29(Pt) Floors Wing B = LG + UG + 1P + 2P (Pt) + Upper Stilt + 1st to 39th Floors + 40th (Recreation) (Pt) Floors Wing C = LG + UG + 1P + 2P (Pt) + Upper Stilt + 1st to 39th Floors + 40th (Pt) Floors Wing D = Ground Floor (Commercial) |  |  | Approved Plan Details | : | V.P.S08/0114/21/TMC/TDD/4088/22 Date: 20/06/2022
Environmental Clearance Details | : | SIA/MH/MIS/273309/2022 Date:13/09/2022 |  |  | Fire NOC Details | : | TMC/CFO/M/HR/98/73 Date : 20/06/2022 Valid Upto: Wing A = Gr + 1st & 2nd Podium + 1st to 28th + 29th (Pt) Floor = Height 102.00M Wing B = Gr + 1st to 3rd Podium + 1st to 30th Floor Heights = 109.35M. Wing C = 1st to 3rd Podium + 1st Floor to 29 Floor Height = 106.30M. Commercial Building Wing D = Gr + 1st Floor = 9.25M.
Change of User/Zone Certificate Details | : | - |  |  | Fire NOC Details | :
Construction Status
Wing A = LG + UG + 1P + Upper Stilt + 1st to 29(Pt) Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 27 Floor, Flooring & Fitting upto 25 Floor, Wooden Work upto 22 Floor, Electrical & Sanitary fittings upto 22 Floor Completed
|  |  |  | 1 | 2 |  | 1 | 29 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 7.25
Excavation |  | 29 |  | 100% | 77.07% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 27 Floor, Flooring & Fitting upto 25 Floor, Wooden Work upto 22 Floor, Electrical & Sanitary fittings upto 22 Floor Completed |  | Excavation in process | 14.5
Plinth |  | 29 |  | 100% |  |  |  |  | Excavation Completed | 29
RCC (Including podiums) |  | 32 |  | 100% |  |  |  |  | Footing in Process | 7.25
Brickwork |  | 29 |  | 100% |  |  |  |  | Footing Completed | 14.5
Internal Plaster |  | 29 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 29 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 27 |  | 93.1% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 25 |  | 86.21% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 22 |  | 75.86% |  |  |  |  | Plinth in process | 21.75
Electrical & Sanitary fittings |  | 22 |  | 75.86% |  |  |  |  | Plinth completed | 29 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Wing B & C = LG + UG + 1P + 2P (Pt) + Upper Stilt + 1st to 39th + 40th (Pt) Floors. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 38 Floor, Flooring & Fitting upto 36 Floor, Wooden Work upto 34 Floor, Electrical & Sanitary fittings upto 34 Floor, Finishing upto 10 Floor Completed
|  |  |  | 1 | 2 |  | 1 | 40 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 10
Excavation |  | 40 |  | 100% | 80.5% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 38 Floor, Flooring & Fitting upto 36 Floor, Wooden Work upto 34 Floor, Electrical & Sanitary fittings upto 34 Floor, Finishing upto 10 Floor Completed |  | Excavation in process | 20
Plinth |  | 40 |  | 100% |  |  |  |  | Excavation Completed | 40
RCC (Including podiums) |  | 43 |  | 100% |  |  |  |  | Footing in Process | 10
Brickwork |  | 40 |  | 100% |  |  |  |  | Footing Completed | 20
Internal Plaster |  | 40 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 40 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 38 |  | 95% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 36 |  | 90% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 34 |  | 85% |  |  |  |  | Plinth in process | 30
Electrical & Sanitary fittings |  | 34 |  | 85% |  |  |  |  | Plinth completed | 40 |  | #VALUE!
Building Common Amenities |  | 10 |  | 25%
Possession |  | 0 |  | 0%
Construction Status
Wing C = LG + UG + 1P + 2P (Pt) + Upper Stilt + 1st to 39th + 40th (Pt) Floors. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 37 Floor, Flooring & Fitting upto 35 Floor, Wooden Work upto 30 Floor, Electrical & Sanitary fittings upto 28 Floor Completed
|  |  |  | 1 | 2 |  | 1 | 40 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 10
Excavation |  | 40 |  | 100% | 77% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 37 Floor, Flooring & Fitting upto 35 Floor, Wooden Work upto 30 Floor, Electrical & Sanitary fittings upto 28 Floor Completed |  | Excavation in process | 20
Plinth |  | 40 |  | 100% |  |  |  |  | Excavation Completed | 40
RCC (Including podiums) |  | 43 |  | 100% |  |  |  |  | Footing in Process | 10
Brickwork |  | 40 |  | 100% |  |  |  |  | Footing Completed | 20
Internal Plaster |  | 40 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 40 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 37 |  | 92.5% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 35 |  | 87.5% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 30 |  | 75% |  |  |  |  | Plinth in process | 30
Electrical & Sanitary fittings |  | 28 |  | 70% |  |  |  |  | Plinth completed | 40 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Wing D = Gr + 1st Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing, Flooring & Fitting, Wooden Work, Electrical & Sanitary fittings upto 0.5 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 78.75% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing, Flooring & Fitting, Wooden Work, Electrical & Sanitary fittings upto 0.5 Floor Completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 2 |  | 100% |  |  |  |  | Footing in Process | 0.25
Brickwork |  | 1 |  | 100% |  |  |  |  | Footing Completed | 0.5
Internal Plaster |  | 1 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 1 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 1 |  | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 1 |  | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 1 |  | 100% |  |  |  |  | Plinth in process | 0.75
Electrical & Sanitary fittings |  | 0.5 |  | 50% |  |  |  |  | Plinth completed | 1 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 79.2%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area |  |  | Brochuer
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 16000 to 17000 | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA |  | 14500 to 15500 to 17000 & 5L to 7L parking Ankita & vaibhav
Car Parking Charges |  |  | : | 700000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 2471.2003
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 6549.6098
Distress Value (Rs. Per sqft) | [5 empty] | : | 1976.9602
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Wing D |  | Sale |  | Shop | 44 |  | 17803.9886 | 28486.3818
Unit Details, Nomenclature and Area Details (Residential)
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Wing A |  | Sale |  | Flat | 397 |  | 200884.0111 | 301326.0167
Wing B |  | Sale |  | Flat | 382 |  | 194156.1882 | 291234.2823
Wing C |  | Sale |  | Flat | 309 |  | 174134.8253 | 261202.2379
Total |  | - |  | - | 1088 |  | 569175.0246 | 853762.5369
Grand Total |  | - |  | - | 1132 |  | 586979.0132 | 882248.9187
Details of Flats in Building
Floor |  | Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
60%
Wing D
Upper Ground Floor For Commercial & Parking
Upper Ground Floor For Commercial & Parking |  | 1 |  | Shop | 326.9027 | 0 | 0 | 523.0443 |  | 10.764
|  | 2 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 3 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 4 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 5 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 6 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 7 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 8 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 9 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 10 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 11 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 12 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 13 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 14 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 15 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 16 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 17 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 18 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 19 |  | Shop | 326.9027 | 0 | 0 | 523.0443
|  | 20 |  | Shop | 366.7295 | 0 | 0 | 586.7672
|  | 21 |  | Shop | 382.5526 | 0 | 0 | 612.0841
|  | 22 |  | Shop | 382.5526 | 0 | 0 | 612.0841
|  | 23 |  | Shop | 382.5526 | 0 | 0 | 612.0841
|  | 24 |  | Shop | 382.5526 | 0 | 0 | 612.0841
|  | 25 |  | Shop | 382.5526 | 0 | 0 | 612.0841
|  | 26 |  | Shop | 600.9541 | 0 | 0 | 961.5266 | 55.176
|  | 27 |  | Shop | 764.8898 | 0 | 0 | 1223.8237 | 71.06
|  | 28 |  | Shop | 597.9402 | 0 | 0 | 956.7043
|  | 29 |  | Shop | 392.6707 | 0 | 0 | 628.2732
|  | 30 |  | Shop | 392.6707 | 0 | 0 | 628.2732
|  | 31 |  | Shop | 392.6707 | 0 | 0 | 628.2732
|  | 32 |  | Shop | 392.6707 | 0 | 0 | 628.2732
|  | 33 |  | Shop | 392.6707 | 0 | 0 | 628.2732
|  | 34 |  | Shop | 392.6707 | 0 | 0 | 628.2732
|  | 35 |  | Shop | 392.6707 | 0 | 0 | 628.2732
|  | 36 |  | Shop | 593.9145 | 0 | 0 | 950.2631
|  | 37 |  | Shop | 764.8898 | 0 | 0 | 1223.8237
|  | 38 |  | Shop | 590.5399 | 0 | 0 | 944.8639
|  | 39 |  | Shop | 441.2153 | 0 | 0 | 705.9445
|  | 40 |  | Shop | 442.0613 | 0 | 0 | 707.2981
|  | 41 |  | Shop | 442.0613 | 0 | 0 | 707.2981
|  | 42 |  | Shop | 442.0613 | 0 | 0 | 707.2981
|  | 43 |  | Shop | 442.0613 | 0 | 0 | 707.2981
|  | 44 |  | Shop | 442.0613 | 0 | 0 | 707.2981
Floor |  | Flat No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
50%
Wing A
Lower Ground Floor For Meter Room, Fire Control Room, Rehab RWH Tank & Parking
Upper Ground Floor For Parking
1st Podium Floor For Parking
2nd Podium Floor/ Upper Stilt Floor For Entrance Lobby, Society Office, Creche, Fitness Center & Parking | [13 empty] | 10.764
1st Floor For Residential | [8 empty] | 48.255 | 50.85 | -2.595
1st Floor For Residential |  | 1 |  | 2BHK | 547.3494 |  | 0 | 821.0241 | 49.1375 | 52.15 | -3.0125
|  | 2 |  | 2BHK | 561.3426 | 0 | 0 | 842.0139 | 38.424 | 40.65 | -2.226
|  | 3 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 4 |  | 1BHK | 432.9281 | 0 | 0 | 649.3921 |  |  | 19823.9561
|  | 5 |  | 1BHK | 443.9074 | 0 | 0 | 665.861
|  | 6 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 7 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 8 |  | 1BHK | 443.9074 | 0 | 0 | 665.861 | 38.424 | 40.65 | -2.226
|  | 9 |  | 1BHK | 432.9281 | 0 | 0 | 649.3921
|  | 10 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 11 |  | 2BHK | 561.3426 | 0 | 0 | 842.0139
|  | 12 |  | 2BHK | 547.3494 | 0 | 0 | 821.0241
|  | 13 |  | 1BHK | 437.6642 | 0 | 0 | 656.4964 |  |  | 16907.9384
|  | 14 |  | 1BHK | 437.6642 | 0 | 0 | 656.4964
2nd, 3rd & 5th Floor
2nd, 3rd & 5th Floor |  | 1 |  | 2BHK | 547.3494 | 0 | 0 | 821.0241
|  | 2 |  | 2BHK | 658.6492 | 0 | 0 | 987.9737
|  | 3 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 4 |  | 1BHK | 432.9281 | 0 | 0 | 649.3921
|  | 5 |  | 1BHK | 443.9074 | 0 | 0 | 665.861
|  | 6 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 7 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 8 |  | 1BHK | 443.9074 | 0 | 0 | 665.861
|  | 9 |  | 1BHK | 432.9281 | 0 | 0 | 649.3921
|  | 10 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 11 |  | 2BHK | 658.6492 | 0 | 0 | 987.9737
|  | 12 |  | 2BHK | 547.3494 | 0 | 0 | 821.0241
|  | 13 |  | 1BHK | 437.6642 | 0 | 0 | 656.4964
|  | 14 |  | 1BHK | 437.6642 | 0 | 0 | 656.4964
4th Floor (Part Refuge Area)
4th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 547.3494 | 0 | 0 | 821.0241
|  | 2 |  | 2BHK | 658.6492 | 0 | 0 | 987.9737
|  | 3 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 4 |  | 1BHK | 432.9281 | 0 | 0 | 649.3921
|  | 5 |  | 1BHK | 443.9074 | 0 | 0 | 665.861
|  | 6 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 7 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 8 |  | 1BHK | 443.9074 | 0 | 0 | 665.861
|  | 9 |  | 1BHK | 432.9281 | 0 | 0 | 649.3921
|  | 10 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 11 |  | 2BHK | 658.6492 | 0 | 0 | 987.9737
|  | 12 |  | 2BHK | 547.3494 | 0 | 0 | 821.0241
|  | 13 |  | 1BHK | 437.6642 | 0 | 0 | 656.4964
|  | 14 |  | Refuge Area
6th to 8th & 10th to 13th & 15th Floor
6th to 8th & 10th to 13th & 15th Floor |  | 1 |  | 2BHK | 547.3494 | 0 | 0 | 821.0241
|  | 2 |  | 2BHK | 658.6492 | 0 | 0 | 987.9737
|  | 3 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 4 |  | 2BHK | 549.5022 | 0 | 0 | 824.2533
|  | 5 |  | 1BHK | 443.9074 | 0 | 0 | 665.861
|  | 6 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 7 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 8 |  | 1BHK | 443.9074 | 0 | 0 | 665.861
|  | 9 |  | 2BHK | 549.5022 | 0 | 0 | 824.2533
|  | 10 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 11 |  | 2BHK | 658.6492 | 0 | 0 | 987.9737
|  | 12 |  | 2BHK | 547.3494 | 0 | 0 | 821.0241
|  | 13 |  | 1BHK | 437.6642 | 0 | 0 | 656.4964
|  | 14 |  | 1BHK | 437.6642 | 0 | 0 | 656.4964
9th & 14th (Part Refuge Area)
9th & 14th (Part Refuge Area) |  | 1 |  | 2BHK | 547.3494 |  | 0 | 821.0241
|  | 2 |  | 2BHK | 658.6492 | 0 | 0 | 987.9737
|  | 3 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 4 |  | 2BHK | 549.5022 | 0 | 0 | 824.2533
|  | 5 |  | 1BHK | 443.9074 | 0 | 0 | 665.861
|  | 6 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 7 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 8 |  | 1BHK | 443.9074 | 0 | 0 | 665.861
|  | 9 |  | 2BHK | 549.5022 | 0 | 0 | 824.2533
|  | 10 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 11 |  | 2BHK | 658.6492 | 0 | 0 | 987.9737
|  | 12 |  | 2BHK | 547.3494 | 0 | 0 | 821.0241
|  | 13 |  | 1BHK | 437.6642 | 0 | 0 | 656.4964
|  | 14 |  | Refuge Area
16th to 18th, 20th to 23rd & 25th to 27th Floor
16th to 18th, 20th to 23rd & 25th to 27th Floor |  | 1 |  | 2BHK | 547.3494 | 0 | 0 | 821.0241
|  | 2 |  | 2BHK | 703.535 | 0 | 0 | 1055.3026
|  | 3 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 4 |  | 2BHK | 549.5022 | 0 | 0 | 824.2533
|  | 5 |  | 1BHK | 443.9074 | 0 | 0 | 665.861
|  | 6 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 7 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 8 |  | 1BHK | 443.9074 | 0 | 0 | 665.861
|  | 9 |  | 2BHK | 549.5022 | 0 | 0 | 824.2533
|  | 10 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 11 |  | 2BHK | 703.535 | 0 | 0 | 1055.3026
|  | 12 |  | 2BHK | 547.3494 | 0 | 0 | 821.0241
|  | 13 |  | 1BHK | 437.6642 | 0 | 0 | 656.4964
|  | 14 |  | 1BHK | 437.6642 | 0 | 0 | 656.4964
19th & 24th Floor (Part Refuge Area)
19th & 24th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 547.3494 | 0 | 0 | 821.0241
|  | 2 |  | 2BHK | 703.535 | 0 | 0 | 1055.3026
|  | 3 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 4 |  | 2BHK | 549.5022 | 0 | 0 | 824.2533
|  | 5 |  | 1BHK | 443.9074 | 0 | 0 | 665.861
|  | 6 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 7 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 8 |  | 1BHK | 443.9074 | 0 | 0 | 665.861
|  | 9 |  | 2BHK | 549.5022 | 0 | 0 | 824.2533
|  | 10 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 11 |  | 2BHK | 703.535 | 0 | 0 | 1055.3026
|  | 12 |  | 2BHK | 547.3494 | 0 | 0 | 821.0241
|  | 13 |  | 1BHK | 437.6642 | 0 | 0 | 656.4964
|  | 14 |  | Refuge Area
28th Floor
28th Floor |  | 1 |  | 2BHK | 547.3494 | 0 | 0 | 821.0241
|  | 2 |  | 2BHK | 703.535 | 0 | 0 | 1055.3026
|  | 3 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 4 |  | 2BHK | 549.5022 | 0 | 0 | 824.2533
|  | 5 |  | 1BHK | 443.9074 | 0 | 0 | 665.861
|  | 6 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 7 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 9 |  | 4BHK | 1063.0526 | 0 | 0 | 1594.579
|  | 10 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 11 |  | 2BHK | 703.535 | 0 | 0 | 1055.3026
|  | 12 |  | 2BHK | 547.3494 | 0 | 0 | 821.0241
|  | 13 |  | 1BHK | 437.6642 | 0 | 0 | 656.4964
|  | 14 |  | 1BHK | 437.6642 | 0 | 0 | 656.4964
29th Floor
|  | 1 |  | Void
29th Floor |  | 2 |  | 2BHK | 703.535 | 0 | 0 | 1055.3026
|  | 3 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 4 |  | 2BHK | 549.5022 | 0 | 0 | 824.2533
|  | 5 |  | 1BHK | 443.9074 | 0 | 0 | 665.861
|  | 6 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 7 |  | 1BHK | 444.8761 | 0 | 0 | 667.3142
|  | 9 |  | 4BHK | 1063.0526 | 0 | 0 | 1594.579
|  | 10 |  | 1BHK | 437.5566 | 0 | 0 | 656.3349
|  | 11 |  | 2BHK | 703.535 | 0 | 0 | 1055.3026
|  | 13 |  | 1BHK | 437.6642 | 0 | 0 | 656.4964
|  | 14 |  | 1BHK | 437.6642 | 0 | 0 | 656.4964
Wing B
Lower Ground Floor For Meter Room, Fire Control Room, Drivers Room, Fire Tank, Domestic Tank & Parking
Upper Ground Floor For Parking
1st Podium Floor For Parking
2nd Podium Floor For Entrance Lobby & Parking
Stilt Floor For Entrance Lobby, Society Office, Amenities & Parking | [10 empty] | Brochuer | 99 Acre | MIS
1st, 3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd to 36th, 38th to 39th Floor For Residential | [8 empty] | 36.5587 |  | 17706.0791 | 12095.5108 | 9500
1st, 3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd to 36th, 38th to 39th Floor For Residential |  | 1 |  | 1BHK | 457.47 | 0 | 0 | 686.205 |  |  | 11804.0527
|  | 2 |  | 1BHK | 457.47 | 0 | 0 | 686.205 |  |  | 11324.4298
|  | 3 |  | 1BHK | 476.8452 | 0 | 0 | 715.2678 |  |  | 11324.4298
|  | 4 |  | 1BHK | 476.8452 | 0 | 0 | 715.2678 |  |  | 11324.4298
|  | 5 |  | 1BHK | 476.8452 | 0 | 0 | 715.2678
|  | 6 |  | 1BHK | 476.8452 | 0 | 0 | 715.2678
|  | 7 |  | 2BHK | 660.802 | 0 | 0 | 991.2029 |  |  | 11501.1765
|  | 8 |  | 2BHK | 644.5483 | 0 | 0 | 966.8225 |  |  | 11791.2029 | 12308.3609
|  | 9 |  | 1BHK | 457.47 | 0 | 0 | 686.205
|  | 10 |  | 1BHK | 457.47 | 0 | 0 | 686.205 | [5 empty] | 10.764
2nd, 7th, 12th, 17th, 22nd, 27th, 32nd & 37th Floor (Part Refuge Area)
2nd, 7th, 12th, 17th, 22nd, 27th, 32nd & 37th Floor (Part Refuge Area) |  | 1 |  | 1BHK | 457.47 | 0 | 0 | 686.205
|  | 2 |  | 1BHK | 457.47 | 0 | 0 | 686.205
|  | 3 |  | 1BHK | 476.8452 | 0 | 0 | 715.2678 |  |  |  | 382
|  | 4 |  | 1BHK | 476.8452 | 0 | 0 | 715.2678
|  | 5 |  | 1BHK | 476.8452 | 0 | 0 | 715.2678
|  | 6 |  | 1BHK | 476.8452 | 0 | 0 | 715.2678
|  | 7 |  | 2BHK | 660.802 | 0 | 0 | 991.2029
|  | 8 |  | 2BHK | 644.5483 | 0 | 0 | 966.8225
|  | 9 |  | 2BHK | 601.7345 | 0 | 0 | 902.6018
|  | 10 |  | Refuge Area | [9 empty] | 10.764
40th Floor For Recreational Floor
Wing C
Lower Ground Floor For Meter Room, Pump Room, Rain Water Tank, Domestic Tank Drivers Room & Parking
Upper Ground Floor For Parking
1st Podium Floor For Parking
2nd Podium Floor For Entrance Lobby & Parking
Stilt Floor For Entrance Lobby, Guest Room, Recreational Area, Pantry, Amenities & Parking | [13 empty] | 10.764
1st, 3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd to 36th, 38th to 39th Floor For Residential
1st, 3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd to 36th, 38th to 39th Floor For Residential |  | 1 |  | 2BHK | 644.5483 | 0 | 0 | 966.8225
|  | 2 |  | 2BHK | 663.0624 | 0 | 0 | 994.5936
|  | 3 |  | 1BHK | 476.8452 | 0 | 0 | 715.2678 |  |  |  | 309
|  | 4 |  | 1BHK | 476.8452 | 0 | 0 | 715.2678
|  | 5 |  | 2BHK | 663.0624 | 0 | 0 | 994.5936
|  | 6 |  | 2BHK | 644.5483 | 0 | 0 | 966.8225
|  | 7 |  | 1BHK | 457.47 | 0 | 0 | 686.205
|  | 8 |  | 1BHK | 457.47 | 0 | 0 | 686.205 | [5 empty] | 10.764
2nd, 7th, 12th, 17th, 22nd, 27th, 32nd & 37th Floor (Part Refuge Area)
2nd, 7th, 12th, 17th, 22nd, 27th, 32nd & 37th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 644.5483 | 0 | 0 | 966.8225
|  | 2 |  | 2BHK | 663.0624 | 0 | 0 | 994.5936
|  | 3 |  | 1BHK | 476.8452 | 0 | 0 | 715.2678
|  | 4 |  | 1BHK | 476.8452 | 0 | 0 | 715.2678
|  | 5 |  | 2BHK | 663.0624 | 0 | 0 | 994.5936
|  | 6 |  | 2BHK | 644.5483 | 0 | 0 | 966.8225
|  | 7 |  | 1BHK | 457.47 | 0 | 0 | 686.205
|  | 8 |  | Refuge Area
40th Floor For Residential & part terrace area
40th Floor For Residential & part terrace area |  | Terrace Area
|  | 2 |  | 2BHK | 663.0624 | 0 | 0 | 994.5936
|  | 3 |  | 1BHK | 476.8452 | 0 | 0 | 715.2678
|  | 4 |  | 1BHK | 476.8452 | 0 | 0 | 715.2678
|  | 5 |  | 2BHK | 663.0624 | 0 | 0 | 994.5936
|  | 6 |  | 2BHK | 644.5483 | 0 | 0 | 966.8225
|  | 7 |  | Terrace Area
|  | 8 | [11 empty] | 10.764
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Construction work is in process at the time of Visit. Internal visit was not allowed. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Balcony. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. On Site, we meet Mr. Sachin 8652208309 8. A wing Flat 8 & 9 is merged at 28th & 29th Floor. 9. We have updated revised C.C (on 02/05/2023). Nala is on the east side of the project.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Ashar Arize
Project Site Address |  |  | : | Ashar Arize Galleria, Plot Bearing Cts No. 2459, 2460, 2461, 2490, 2491, 2492, 2546, 2547 At Thane (M Corp.), Thane, Thane, 400605
Site Visit Date & Time |  |  | : | 10/07/2025 @05:09 PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Gangaram parshuram Lambore | Authorized Signatory Name & Signature | :
A Wing
B Wing
C Wing
D Wing
D Wing
Railway Track
Nala
Ashar Arize
Wing D
Note on H6: Rushil Sanghvi or Fahad
Note on E9: Initiation Address
Note on E10: Plan Address
Note on E11: Map Address
Note on C17: Maybe same as RERA Registration Validity or different
Note on H17: From Rera
Note on H20: From RERA
Note on A39: As per Layout
Note on H129: Ready Recknor