## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  | Ashar Pulse (Tower 1 & 2) |  | Date & Time of Site Visit |  | 04/07/2025 @11:00 AM
Name of the person met at site & Contact No. |  | Security |  | Date of Report Release |  | 06/07/2025
Data from APF Request Form
Branch Name/ID |  | Godrej One, Vikhroli East, Mumbai |  | Request from GHF Employee |  | Miss. Ankita Mohite
Builder Group Name |  | Ms Ashar Ventures |  | Developer Name |  | Ms Ashar Ventures
Developer Office Address |  | S.No 254 PT, 256 PT, 277 PT, 278 PT & 279 PT, Ashar IT Park, Road No 16z, Wagale Estate, Near Agriculture Office, Thane, Thane - 400604
Project Address | As per ARF | (Building name, CTS No., Plot No., Survey No., Road., Locality/Village., Near by Landmark., City., District., Taluka., Pin Code -)
| As per Legal Documents | Ashar Pulse, Survey No.106, Hissa No.15, Survey No.406, Hissa No.B/2, Survey No.390/A, Hissa No.390/B (Pt), Survey No.373,Survey No.406/A, Hissa No.B/3, near Runwal Regency, Majiwade Village Road, Sainath Nagar, Majiwade, Thane West, Thane, Thane - 400607.
| As per Actual at site | Ashar Pulse, Survey No.106, Hissa No.15, Survey No.406, Hissa No.B/2, Survey No.390/A, Hissa No.390/B (Pt), Survey No.373,Survey No.406/A, Hissa No.B/3, near Runwal Regency, Majiwade Village Road, Sainath Nagar, Majiwade, Thane West, Thane, Thane - 400607.
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC, RERA certificate, NOC
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Slum Rehabilitation Authority (SRA)
RERA Registration No. | : | P51700047432 |  | RERA Registration Validity | : | 2028-12-30
Project Launch Date | : |  |  | Construction Start Date | :
Proposed Date of Completion (As per RERA) | : | 2028-12-30 |  | Developer Bank Name (As per RERA) | : | ICICI BANK IFSC Code ICIC0001887
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  | Plot Area (In Sq.Mt) | :
FSI/FAR Permissible | : |  |  | Net Plot Area (In Sq.Mt) | :
Permissible Built up Area (In Sq.Mt) | : |  |  | Proposed Built up Area (In Sq.Mt) | :
Total Number of Units Approved | : | Flats = & Shop = |  | Total Number of Units Planned | : | As per RERA Site Flats = & Shop =
Latitude, Longitude | : | 19.2141394,72.9782467 |  | Landmark | : | Runwal Regency
Location Link | : | https://maps.app.goo.gl/JwuXtzKtRxs9hXtG8
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  | Width of the Road | : | 9m
Distance from Train stand (Km) | : | 3.9 KM from Thane Railway Station |  | Distance from Bus stand (Km) | : | 10 M from Majiwade Bus Stop
Distance from the nearest School (Km) | : | About 4KM from School |  | Distance from Hospital (Km) | : | About 4K form Hospital
Distance from the Main Market (Km) | : | 1. Approx. 2KM from Village Market. 2. Approx. 10KM from Panvel Main Market. |  | Distance from Railway Station (Km) | : | 5.4KM from Somatne Railway Station 10.5KM from Panvel Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North | South | East | West
East |  | Other Plot |  |  | Building
West |  | 60 M W Road |  |  | Ghodbunder Road
North |  | 20 M W Road |  |  | Majiwade Village Road
South |  | Other Plot |  |  | Other Plot
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Tower A1 |  | Sale | B + G + M + 3P + 1st to 54th Floors |  |  | B + G + M + 3P + 1st to 54th Floors
Tower A2 |  | Sale | B + G + M + 3P + 1st to 54th Floors |  |  | B + G + M + 3P + 1st to 54th Floors
Tower A3 |  | Sale
Tower A4 |  | Sale
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : |  |  |  |  | Date:
Approved Plan Details | : |  |  |  |  | Date:
CC Details Valid Up to: |  | MMR/SRA/ENG/043/SEC-5/STGOVT/AP |  |  |  | Date: | 2024-01-24
This CC is further extended for RCC Frame Work of Basement + Ground + Mezzanine + 1st Podium/Comm. + 2nd Podium/Comm. + 3rd Podium/Club House + 1st to 54th Upper Floors With LMR & OHWT of Sale Building A1 & A2 With Mechanical Parking Tower as per approved amended plans dtd. 08/11/2023.
Environmental Clearance Details | : |  |  |  |  | Date:
Change of User/Zone Certificate Details | : |  |  |  |  | Date:
Airport Authority Clearance Details | : |  |  |  |  | Date:
Other NOC Details | : |  |  |  |  | Date:
Construction Status
Tower A1 & A2 = B + G + M + 3P + 1st to 54th Floors |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 36 Slab, Brickwork upto 32 Floor, Internal Plaster upto 25.6 Floor, External Plaster upto 25.6 Floor Completed
|  |  | 1 | 1 |  | 3 | 54 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.5
Excavation |  | 54 | 100% | 45.85% |  | Excavation work Completed. Plinth work completed, RCC upto 36 Slab, Brickwork upto 32 Floor, Internal Plaster upto 25.6 Floor, External Plaster upto 25.6 Floor Completed |  | Excavation in process | 27
Plinth |  | 54 | 100% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 36 | 62.07% |  |  |  |  | Footing in Process | 13.5
Brickwork |  | 32 | 59.26% |  |  |  |  | Footing Completed | 27
Internal Plaster |  | 25.6 | 47.41% |  |  |  |  | Basement 1 | 0
External Plaster |  | 25.6 | 47.41% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 40.5
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 54
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Tower A2 = B + G + M + 3P + 1st to 54th Floors |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 29 Slab, Brickwork upto 25 Floor, Internal Plaster upto 20 Floor, External Plaster upto 20 Floor Completed
|  |  | 1 | 1 |  | 3 | 54 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.5
Excavation |  | 54 | 100% | 41.67% |  | Excavation work Completed. Plinth work completed, RCC upto 29 Slab, Brickwork upto 25 Floor, Internal Plaster upto 20 Floor, External Plaster upto 20 Floor Completed |  | Excavation in process | 27
Plinth |  | 54 | 100% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 29 | 50% |  |  |  |  | Footing in Process | 13.5
Brickwork |  | 25 | 46.3% |  |  |  |  | Footing Completed | 27
Internal Plaster |  | 20 | 37.04% |  |  |  |  | Basement 1 | 0
External Plaster |  | 20 | 37.04% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 40.5
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 54
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 45.85%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 16000 to 17000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 400000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 3846.1538
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 12783.3519
Distress Value (Rs. Per sqft) |  |  |  |  | : | 3076.9231
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Total |  | - |  | 0 |  | 0 | 0
Unit Details, Nomenclature and Area Details (Flats)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Total |  | - |  | 0 |  | 0 | 0
Grand Total |  | - |  | 0 |  | 0
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
1st Floor
101 |  |  |  | 0 | 0 | 0 | 0
102 | [6 empty] | 0
103 | [6 empty] | 0
104 | [6 empty] | 0
105 | [6 empty] | 0
106 | [6 empty] | 0
107 | [6 empty] | 0
108 | [6 empty] | 0
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor
201,..,901 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 201,..,901 | 201 | 901
202,..,902 | [6 empty] | 0 | [5 empty] | 202,..,902 | 202 | 902
203,..,903 | [6 empty] | 0 | [5 empty] | 203,..,903 | 203 | 903
204,..,904 | [6 empty] | 0 | [5 empty] | 204,..,904 | 204 | 904
205,..,905 | [6 empty] | 0 | [5 empty] | 205,..,905 | 205 | 905
206,..,906 | [6 empty] | 0 | [5 empty] | 206,..,906 | 206 | 906
207,..,907 | [6 empty] | 0 | [5 empty] | 207,..,907 | 207 | 907
208,..,908 | [6 empty] | 0 | [5 empty] | 208,..,908 | 208 | 908
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 201 to 501 | 201 | 501
202 to 502 | [6 empty] | 0 | [5 empty] | 202 to 502 | 202 | 502
203 to 503 | [6 empty] | 0 | [5 empty] | 203 to 503 | 203 | 503
204 to 504 | [6 empty] | 0 | [5 empty] | 204 to 504 | 204 | 504
205 to 505 | [6 empty] | 0 | [5 empty] | 205 to 505 | 205 | 505
206 to 506 | [6 empty] | 0 | [5 empty] | 206 to 506 | 206 | 506
207 to 507 | [6 empty] | 0 | [5 empty] | 207 to 507 | 207 | 507
208 to 508 | [6 empty] | 0 | [5 empty] | 208 to 508 | 208 | 508
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 201 & 501 | 201 | 501
202 & 502 | [6 empty] | 0 | [5 empty] | 202 & 502 | 202 | 502
203 & 503 | [6 empty] | 0 | [5 empty] | 203 & 503 | 203 | 503
204 & 504 | [6 empty] | 0 | [5 empty] | 204 & 504 | 204 | 504
205 & 505 | [6 empty] | 0 | [5 empty] | 205 & 505 | 205 | 505
206 & 506 | [6 empty] | 0 | [5 empty] | 206 & 506 | 206 | 506
207 & 507 | [6 empty] | 0 | [5 empty] | 207 & 507 | 207 | 507
208 & 508 | [6 empty] | 0 | [5 empty] | 208 & 508 | 208 | 508
Project Specific Remarks & Observation
* | Construction work is in process at the time of Visit. Internal visit was not allowed.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | Refrence |  |  | Building Name
* | Type of Building |  |  | Sale Building |  | Rehab Building
* | Approved Plans |  |  | Tower A1 | Tower A2 | Tower B1
* | Rera |  |  | Tower 1 Wing A | Tower 2 Wing B | -
* | We are releasing stage updation report
* | Remark for NOCs
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
Site & Building/Tower Photographs
Name of the Project |  |  | Ashar Pulse (Tower 1 & 2)
Project Site Address |  |  | Ashar Pulse, Survey No.106, Hissa No.15, Survey No.406, Hissa No.B/2, Survey No.390/A, Hissa No.390/B (Pt), Survey No.373,Survey No.406/A, Hissa No.B/3, near Runwal Regency, Majiwade Village Road, Sainath Nagar, Majiwade, Thane West, Thane, Thane - 400607.
Site Visit Date & Time |  |  | 04/07/2025 @11:00 AM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr.Ajay Songare |  | Authorized Signatory Name & Signature
Sale Bldg
Rehab Bldg
A1
A2
B1
Tower A1
Tower A2
Rehab Tower
Sale Tower
Tower A1
Tower A2
Note on C9: SACHIN: As per initiation Mail
Note on C17: Maybe same as RERA Registration Validity or different
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G98: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%