## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  | 78 Lake Town |  | Date & Time of Site Visit |  | 05/07/2025 @ 01:46 PM
Name of the person met at site & Contact No. |  | Mr Saurabh 9920255826 |  | Date of Report Release |  | 08/07/2025
Data from APF Request Form
Branch Name/ID |  | Mumbai-RO Thane |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | M/s. Anirdesh Developers Private Limited |  | Developer Name |  | M/s. Anirdesh Developers Private Limited
Developer Office Address |  | 2nd Floor, Citi Mall, New Link Road, Near Infiniti Mall, Oshiwara, Andheri West, Tal. Andheri, Dist. Mumbai 400053.
Project Address | As per ARF | Ajmera 78 Lake Town Sahyadri Nagar, Samarth Nagar, Bhandup West, Mumbai, Maharashtra 400078.
| As per Legal Documents | Proposed Slum Rehabilitation Scheme on plot bearing CTS No.200 (Pt), 214, 214/1 to 2, 215, 215/1 to 2, 216, 216/1 to 117, 217, 217/1 to 122 of Village Kanjur, at Jamil nagar, Bhandup (W), Mumbai 400 078. 'S' Ward For Shree Sai Smartha SRA Co-Operative Housing Society Shree Swami Smartha SRA Co-Operative Housing Society Jai Shree Ram SRA Co-Operative Housing Society Shree Siddhi SRA Co-Operative Housing Society Mangalnurti SRA Co-Operative Housing Society Om Sai SRA Co-Operative Housing Society
| As per Actual at site | Ajmera 78 Lake Town, Sahyadri Nagar, Samarth Nagar, Bhandup West, Mumbai, Maharashtra 400078
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC, RERA certificate, Fire NOC, EC
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Slum Rehabilitation Authority (SRA)
RERA Registration No. | : | P51800055387 |  | RERA Registration Validity | : | 2029-02-01
Project Launch Date | : | 2024-03-22 |  | Construction Start Date | : | 2024-03-01
Proposed Date of Completion (As per RERA) | : | 2029-02-01 |  | Developer Bank Name (As per RERA) | : | ICICI Bank
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  | Plot Area (In Sq.Mt) | : | 27633.53
FSI/FAR Permissible | : | 1 |  | Net Plot Area (In Sq.Mt) | : | 25517.51
Permissible Built up Area (In Sq.Mt) | : | 60551.81 |  | Proposed Built up Area (In Sq.Mt) | : | 32861.27
Total Number of Units Approved | : | Sale Flat = 436 Sale Shop = 1 Rehab Shop = 14 |  | Total Number of Units Planned | : | As per RERA Site, Sale Flat = 436 Sale Shop = 1 Rehab Shop = 14
Latitude, Longitude | : | 19.144028,72.926250 |  | Landmark | : | Kalimata Mandir
Location Link | : | https://maps.app.goo.gl/LFdSF2WJPRq5FPCaA
Extra Amenities available | : | Gym, Indoor Games, Swimming Pool, Basketball Court, Jogging Track, Tennis Court, Vitrified tiles flooring, Granite Kitchen Platform, Decorative Entrance, Landscaping & Garden, etc.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developed |  | Class of Locality | : | Upper
Type of Road | : | Bitumen |  | Width of the Road | : | 18m
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 0.35 KM from Sahyadri Nagar Bus Stop
Distance from the nearest School (Km) | : | About 1KM from Mandar Vidyamandir |  | Distance from Hospital (Km) | : | About 0.11 KM from Medicare Hospital
Distance from the Main Market (Km) | : | 1. Approx. 0.60 KM from Vegetable Market. 2. Approx. 0.65 KM from Fruit Market. |  | Distance from Railway Station (Km) | : | 1.70 KM from Bhandup Railway Station 2.60 KM from Kanjurmarg Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North | South | East | West
East |  | CTS No. 243 |  |  | Slum Area
West |  | 13.40 M. Wide Road |  |  | Jamil Nagar Road
North |  | Other Plot |  |  | Slum Area
South |  | 13.40 M. Wide Road |  |  | Samarth Nagar Road
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Building No.1 (Wing D) |  | Sale | 1B + LG + G + 1st to 30th Floor |  |  | 1B + LG + G + 1st to 30th Floor
Building No.1 (Wing E) |  | Sale | 1B + LG + G + 1st to 30th Floor |  |  | 1B + LG + G + 1st to 30th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | SRA/ENG/S/MCGM & PVT/0002/20110418/AP/R1 |  |  |  | Date: | 2023-02-21
Approved Plan Details | : | SRA/ENG/S/MCGM & PVT/0002/20110418/AP/R1 |  |  |  | Date: | 2023-02-21
CC Details Valid Up to: |  | SRA/MCGM & PVT/0002/20110418/AP/R1 |  |  |  | Date: | 2024-03-01
This C.C is granted for work upto Plinth Level.
Fire NOC No. Valid Up to : | : | P-16901/2023/(200 ( PT ) And Other)/S Ward/TIRANDAZ/SRA-CFO/1/New Wing D & E = Basement + Lower Ground floor + Ground floor + 1st to 30th upper Residential Floors = 94.83 mtrs Height |  |  |  | Date: | 2023-07-07
Environmental Clearance Details | : | SIA/MH/INFRA2/449449/2023 S.No.200(Pt), 214, 214/1 to 2, 215, 215/1 to 2, 216, 216/1 to 117, 217, 217/1 to 122 Proposed BUA= 210642.07 Sq.M Composite Building No.1 (Wing D & E) = B + LG + G + 1st to 30th Floors |  |  |  | Date: | 2024-02-07
Change of User/Zone Certificate Details | : |  |  |  |  | Date:
Airport Authority Clearance Details | : |  |  |  |  | Date:
Construction Status
Building No.1 (Wing D)= 1B + LG + G + 1st to 30th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Footing work is process
|  |  | 1 | 2 |  | 0 | 30 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 13% |  | Excavation work Completed. Footing work is process |  | Excavation in process | 15
Plinth |  | 6 | 20% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 6
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 12
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 19.5
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 27
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Building No.1 (Wing E)= 1B + LG + G + 1st to 30th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work in process
|  |  | 1 | 2 |  | 0 | 30 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 7.5
Excavation |  | 15 | 50% | 5% |  | Excavation work in process |  | Excavation in process | 15
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 6
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 12
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 19.5
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 27
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 9%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 23000 to 24000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 700000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 5293.5712
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 12417.317
Distress Value (Rs. Per sqft) |  |  |  |  | : | 4234.8569
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Building No.1 (Wing E) |  | Rehab |  | 14 |  | 1836.446 |  | OK
|  | Sale |  | 1 |  | 378.1393 |  | OK
Total |  | - |  | 15 |  | 2214.5854 |  | OK
Unit Details, Nomenclature and Area Details (Residential)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Building No.1 (Wing D) |  | Sale |  | 203 |  | 81512.8603 |  | 81177.0235
Building No.1 (Wing E) |  | Sale |  | 233 |  | 94116.105 |  | 93435.8202
Total |  | - |  | 436 |  | 175628.9654
Grand Total |  | - |  | 451 |  | 177843.5507
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale /Rehab | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
Building No.1
Wing E
Basement Floor For Parking, Fire Water Tank & Domestic Tank
Lower Ground Floor For Parking & Entrance Lobby
Ground Floor For Commercial Entrance Lobby & Parking
1 |  | Rehab | Shop | 200.2104 | 0 | 0 | 200.2104
2 |  | Rehab | Shop | 75.7786 | 0 | 0 | 75.7786
3 |  | Rehab | Shop | 79.7612 | 0 | 0 | 79.7612
4 |  | Rehab | Shop | 239.8219 | 0 | 0 | 239.8219
5 |  | Rehab | Shop | 263.8256 | 0 | 0 | 263.8256
6 |  | Rehab | Shop | 30.0316 | 0 | 0 | 30.0316
7 |  | Rehab | Shop | 49.5144 | 0 | 0 | 49.5144
8 |  | Rehab | Shop | 284.3849 | 0 | 0 | 284.3849
9 |  | Rehab | Shop | 61.3548 | 0 | 0 | 61.3548
10 |  | Rehab | Shop | 173.0851 | 0 | 0 | 173.0851
11 |  | Rehab | Shop | 194.3978 | 0 | 0 | 194.3978
12 |  | Rehab | Shop | 39.8268 | 0 | 0 | 39.8268 | 381.5041
13 |  | Sale | Shop | 378.1393 | 0 | 0 | 378.1393
14 |  | Rehab | Shop | 76.6397 | 0 | 0 | 76.6397
15 |  | Rehab | Shop | 67.8132 | 0 | 0 | 67.8132
Wing D
Basement Floor For Parking, Fire Water Tank & Domestic Tank
Lower Ground Floor For Parking & Entrance Lobby
Ground Floor For Meter Room & Parking | [7 empty] | 1
1st Floor For Residential
1 |  | Sale | 1BHK | 383.8442 | 0 | 0 | 383.8442
2 |  | Sale | 1BHK | 412.3688 | 0 | 55.9728 | 468.3416
3 |  | Sale | 1BHK | 412.3688 | 0 | 55.9728 | 468.3416 | 22500
4 |  | Sale | 1BHK | 412.3688 | 0 | 55.9728 | 468.3416
5 |  | Sale | 1BHK | 412.3688 | 0 | 55.9728 | 468.3416
6 |  | Sale | 1BHK | 383.5213 | 0 | 55.9728 | 439.4941
7 |  | Sale | 1BHK | 383.5213 | 0 | 55.9728 | 439.4941 | 25
2nd to 7th, 9th to 14th, 16th to 21st, 23rd to 28th & 30th Floor | [12 empty] | 2701,..,3001 | 2701 | 3001
1 |  | Sale | 1BHK | 383.8442 | 0 | 0 | 383.8442 | 23186.4884 |  |  |  |  | 2702,..,3002 | 2702 | 3002
2 |  | Sale | 1BHK | 412.3688 | 0 | 0 | 412.3688 | [5 empty] | 2703,..,3003 | 2703 | 3003
3 |  | Sale | 1BHK | 412.3688 | 0 | 0 | 412.3688 | [5 empty] | 2704,..,3004 | 2704 | 3004
4 |  | Sale | 1BHK | 412.3688 | 0 | 0 | 412.3688 | [5 empty] | 2705,..,3005 | 2705 | 3005
5 |  | Sale | 1BHK | 412.3688 | 0 | 0 | 412.3688 | [5 empty] | 2706,..,3006 | 2706 | 3006
6 |  | Sale | 1BHK | 383.5213 | 0 | 0 | 383.5213 | [5 empty] | 2707,..,3007 | 2707 | 3007
7 |  | Sale | 1BHK | 383.5213 | 0 | 0 | 383.5213 | 3
8th, 15th & 22nd Floor For Residential (Part Refuge Area) | [12 empty] | 801,..,2201 | 801 | 2201
1 |  | Sale | 1BHK | 383.8442 | 0 | 0 | 383.8442 | [5 empty] | 802,..,2202 | 802 | 2202
2 |  | Refuge Area | [10 empty] | 803,..,2203 | 803 | 2203
3 | [12 empty] | 804,..,2204 | 804 | 2204
4 |  | Sale | 1BHK | 412.3688 | 0 | 0 | 412.3688 | [5 empty] | 805,..,2205 | 805 | 2205
5 |  | Sale | 1BHK | 412.3688 | 0 | 0 | 412.3688 | [5 empty] | 806,..,2206 | 806 | 2206
6 |  | Sale | 1BHK | 383.5213 | 0 | 0 | 383.5213 | [5 empty] | 807,..,2207 | 807 | 2207
7 |  | Sale | 1BHK | 383.5213 | 0 | 0 | 383.5213 | 1
29th Floor For Residential (Part Refuge Area) | [12 empty] | 201,..,2901 | 201 | 2901
1 |  | Sale | 1BHK | 383.8442 | 0 | 0 | 383.8442 | [5 empty] | 202,..,2902 | 202 | 2902
2 |  | Refuge Area | [10 empty] | 203,..,2903 | 203 | 2903
3 |  | Sale | 1.5BHK | 465.1071 | 0 | 0 | 465.1071 | 52.7382 |  |  |  |  | 204,..,2904 | 204 | 2904
4 |  | Sale | 1BHK | 412.3688 | 0 | 0 | 412.3688 | [5 empty] | 205,..,2905 | 205 | 2905
5 |  | Sale | 1BHK | 412.3688 | 0 | 0 | 412.3688 | [5 empty] | 206,..,2906 | 206 | 2906
6 |  | Sale | 1BHK | 383.5213 | 0 | 0 | 383.5213 | [5 empty] | 207,..,2907 | 207 | 2907
7 |  | Sale | 1BHK | 383.5213 | 0 | 0 | 383.5213
Wing E | [7 empty] | 1
1st Floor For Residential | [12 empty] | 101,..,101 | 101 | 101
1 |  | Sale | 1BHK | 382.7678 | 0 | 0 | 382.7678 | [5 empty] | 102,..,102 | 102 | 102
2 |  | Sale | 1BHK | 412.2612 | 0 | 55.9728 | 468.234 | [5 empty] | 103,..,103 | 103 | 103
3 |  | Sale | 1BHK | 412.2612 | 0 | 55.9728 | 468.234 | [5 empty] | 104,..,104 | 104 | 104
4 |  | Sale | 1BHK | 412.2612 | 0 | 55.9728 | 468.234 | [5 empty] | 105,..,105 | 105 | 105
5 |  | Sale | 1BHK | 411.9383 | 0 | 55.9728 | 467.9111 | [5 empty] | 106,..,106 | 106 | 106
6 |  | Sale | 1BHK | 411.9383 | 0 | 55.9728 | 467.9111 | [5 empty] | 107,..,107 | 107 | 107
7 |  | Sale | 1BHK | 382.7678 | 0 | 0 | 382.7678 | [5 empty] | 108,..,108 | 108 | 108
8 |  | Sale | 1BHK | 382.7678 | 0 | 64.584 | 447.3518 | 25
2nd to 7th, 10th to 14th, 17th to 21st, 24rd to 28th & 30th Floor | [12 empty] | 2701,..,3001 | 2701 | 3001
1 |  | Sale | 1BHK | 382.7678 | 0 | 0 | 382.7678 | [5 empty] | 2702,..,3002 | 2702 | 3002
2 |  | Sale | 1BHK | 412.2612 | 0 | 0 | 412.2612 | [5 empty] | 2703,..,3003 | 2703 | 3003
3 |  | Sale | 1BHK | 412.2612 | 0 | 0 | 412.2612 | [5 empty] | 2704,..,3004 | 2704 | 3004
4 |  | Sale | 1BHK | 412.2612 | 0 | 0 | 412.2612 | [5 empty] | 2705,..,3005 | 2705 | 3005
5 |  | Sale | 1BHK | 411.9383 | 0 | 0 | 411.9383 | [5 empty] | 2706,..,3006 | 2706 | 3006
6 |  | Sale | 1BHK | 411.9383 | 0 | 0 | 411.9383 | [5 empty] | 2707,..,3007 | 2707 | 3007
7 |  | Sale | 1BHK | 382.7678 | 0 | 0 | 382.7678 | [5 empty] | 2708,..,3008 | 2708 | 3008
8 |  | Sale | 1BHK | 382.7678 | 0 | 0 | 382.7678 | 3
9th, 16th & 23rd Floor | [12 empty] | 801,..,2201 | 801 | 2201
1 |  | Sale | 1BHK | 382.7678 | 0 | 0 | 382.7678 | [5 empty] | 802,..,2202 | 802 | 2202
2 |  | Sale | 1BHK | 412.2612 | 0 | 0 | 412.2612 | [5 empty] | 803,..,2203 | 803 | 2203
3 |  | Sale | 1BHK | 412.2612 | 0 | 55.9728 | 468.234 | [5 empty] | 804,..,2204 | 804 | 2204
4 |  | Sale | 1BHK | 412.2612 | 0 | 55.9728 | 468.234 | [5 empty] | 805,..,2205 | 805 | 2205
5 |  | Sale | 1BHK | 411.9383 | 0 | 0 | 411.9383 | [5 empty] | 806,..,2206 | 806 | 2206
6 |  | Sale | 1BHK | 411.9383 | 0 | 0 | 411.9383 | [5 empty] | 807,..,2207 | 807 | 2207
7 |  | Sale | 1BHK | 382.7678 | 0 | 0 | 382.7678 | [5 empty] | 808,..,2208 | 808 | 2208
8 |  | Sale | 1BHK | 382.7678 | 0 | 0 | 382.7678 | 1
8th, 15th & 22nd Floor For Residential ( Part Refuge Area) | [12 empty] | 201,..,2901 | 201 | 2901
1 |  | Sale | 1BHK | 382.7678 | 0 | 0 | 382.7678 | [5 empty] | 202,..,2902 | 202 | 2902
2 |  | Sale | 1BHK | 412.2612 | 0 | 0 | 412.2612 | [5 empty] | 203,..,2903 | 203 | 2903
3 |  | Refuge Area | [10 empty] | 204,..,2904 | 204 | 2904
4 | [12 empty] | 205,..,2905 | 205 | 2905
5 |  | Sale | 1BHK | 411.9383 | 0 | 0 | 411.9383 | [5 empty] | 206,..,2906 | 206 | 2906
6 |  | Sale | 1BHK | 411.9383 | 0 | 0 | 411.9383 | [5 empty] | 207,..,2907 | 207 | 2907
7 |  | Sale | 1BHK | 382.7678 | 0 | 0 | 382.7678 | [5 empty] | 208,..,2908 | 208 | 2908
8 |  | Sale | 1BHK | 382.7678 | 0 | 0 | 382.7678
29th Floor For Residential (Part Refuge Area)
1 |  | Sale | 1BHK | 382.7678 | 0 | 0 | 382.7678
2 |  | Sale | 1.5BHK | 464.9994 | 0 | 0 | 464.9994
3 |  | Refuge Area
4 |  | Sale | 1BHK | 412.2612 | 0 | 0 | 412.2612
5 |  | Sale | 1BHK | 411.9383 | 0 | 0 | 411.9383
6 |  | Sale | 1BHK | 411.9383 | 0 | 0 | 411.9383
7 |  | Sale | 1BHK | 382.7678 | 0 | 0 | 382.7678
8 |  | Sale | 1BHK | 382.7678 | 0 | 0 | 382.7678
Project Specific Remarks & Observation
* | Construction work is in process at the time of Visit (Slow Speed). Construction work was not active at the time of Visit. (labour Not found) All work completed. Wait for OC / OC received. Work not yet Started.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony Area.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
Site & Building/Tower Photographs
Name of the Project |  |  | 78 Lake Town
Project Site Address |  |  | Ajmera 78 Lake Town Sahyadri Nagar, Samarth Nagar, Bhandup West, Mumbai, Maharashtra 400078.
Site Visit Date & Time |  |  | 05/07/2025 @ 01:46 PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr. Nainesh Tambe |  | Authorized Signatory Name & Signature
Wing D
Wing E
N
Note on C9: SACHIN: As per initiation Mail
Note on C10: SACHIN: As per plans
Note on C11: SACHIN: As per maps
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G96: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0