## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  |  | : | Runwal Enchanted |  | Date of Site Visit |  | 04/07/2025 @11:44 AM
Project Name As Per RERA |  |  | : : | Code Name ­ Enchanted - Tower D Runwal Lands End - Tower F
Name of the person met at site & Contact No. |  |  | : | Mr. Vishwakarma |  | Date of Report Release |  | 07/07/2025
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Ms. Ankita Mohite
Builder Group Name |  |  | : | Runwal Developers | Developer Name | : | Runwal Developers
Developer Office Address |  |  | : | 4th Floor, Runwal & Omkar Esquare, Off, Eastern Express Hwy, opp. Sion-Chunabhatti Signal, Sion East, Mumbai.
Project Address | : | As per ARF | : | Runwal Enchanted, Near - Kia Service Center, Village - Kolshet, Thane West, Taluka - Thane, Maharashtra 400607
| : | As per Legal Documents | : | Runwal Enchanted, survey No. 1/1,,1/2A, 1/2B, 1/3, 1/4A, 1/4B, 1/4C, 1/4D,1/5, 1/6,1/7, 1/8, 1/10, 1/11, 1/12, 1/13, 1/15, 2/1A, 2/1B, 2/1C, & Others, Near - Kia Service Center, Village - Kolshet, Thane West, Taluka - Thane, Maharashtra 400607
| : | As per Actual at site | : | Runwal Enchanted, Near - Kia Service Center, Village - Kolshet, Thane West, Thane, Maharashtra 400607
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate, NOC
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Thane Municipal Corporation
RERA Registration No. | : | Code Name ­ Enchanted - Tower D = P51700033799 Runwal Lands End - Tower F = P51700046298 |  |  | RERA Registration Validity | : | 2028-06-30
Project Launch Date | : | 2022-02-16 |  |  | Construction Start Date | : | 2022-03-08
Proposed Date of Completion (As per RERA) | : | 2028-06-30 |  |  | Developer Bank Name (As per RERA) | : | ICICI Bank Limied IFSC Code - ICIC0000740
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 34671.67
FSI/FAR Permissible | : | 1.1952 |  |  | Proposed Built up Area (In Sq.Mt) | : | 169803.6
Permissible Built up Area (In Sq.Mt) | : | 106238.92 |  |  | Total Number of Units Planned | : | As per RERA Site : Flats = 1345 |  | 673
Total Number of Units Approved | : | Flats = 1226 |  |  | If Mixed, No. of Commercial Units | : | Shop = NA |  | 672
Latitude | : | 19.2402 |  |  | Longitude | : | 72.9924 |  | 1345
Location Link | : | https://goo.gl/maps/K8tNLCbNspdMa2Us9 | [6 empty] | 2017
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 0.5 KM from Kolshet Bus Stop
Distance from the nearest School (Km) | : | About 2.8KM from Orchids The International School Thane |  |  | Distance from Hospital (Km) | : | About 3.7KM form Horizon Prime Hospital
Distance from the Main Market (Km) | : | 1. Approx. 5.1 KM from Wagbil Market. 2. Approx. 5.2KM from D-Mart. |  |  | Distance from Railway Station (Km) | : | 8.7 KM from Thane Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Kolshet Road | Open Plot | Open Plot |  | Open Plot
As per Site / Actual |  |  | : | Kolshet Road | Open Plot | Open Plot |  | Open Plot
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Tower D |  | Sale |  | 2B + Gr + 1P to 5P + Upper Gr + 1st to 25th Floor + S + 50th Floor |  |  | 2B + Gr + 1P to 5P + Upper Gr + 1st to 25th Floor + S + 49th Floor
Tower F |  | Sale |  | 2B + Gr + 1P to 5P + Upper Gr + 1st to 25th Floor + S + 50th Floor |  |  | 2B + Gr + 1P to 5P + Upper Gr + 1st to 25th Floor + S + 49th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | S05/0096/15TMC/TD-DP/TPS/0127/(P/C) Date: 30/04/2024
CC Details | : | S05/0096/15-TMC/TDD/0127/(P/C) /2024 Date: 30/04/2024 Valid Up to: D & F Wing = 2B + Gr + 1P to 5P + Upper Gr + 1st to 25th Floor + Service Floor + 26th to 35th Floor |  |  | Approved Plan Details | : | S05/0096/15TMC/TD-DP/TPS/0127/(P/C) Date: 30/04/2024
Environmental Clearance Details | : |  |  |  | Airport Authority Clearance Details | :
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
Construction Status
Tower D = 2B + Gr + 1P to 5P + Upper Gr + 1st to 25th Floor + S + 50th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 22 Slab, Brickwork upto 15 Floor, Internal Plaster upto 12 Floor, External Plaster upto 12 Floor Completed
|  |  |  | 2 | 2 |  | 5 | 50 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 12.5
Excavation |  | 50 |  | 100% | 37.35% |  | Excavation work Completed. Plinth work completed, RCC upto 22 Slab, Brickwork upto 15 Floor, Internal Plaster upto 12 Floor, External Plaster upto 12 Floor Completed |  | Excavation in process | 25
Plinth |  | 50 |  | 100% |  |  |  |  | Excavation Completed | 50
RCC (Including podiums) |  | 22 |  | 38.6% |  |  |  |  | Footing in Process | 12.5
Brickwork |  | 15 |  | 30% |  |  |  |  | Footing Completed | 25
Internal Plaster |  | 12 |  | 24% |  |  |  |  | Basement 1 | 37.5
External Plaster |  | 12 |  | 24% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 50
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower F = 2B + Gr + 1P to 5P + Upper Gr + 1st to 25th Floor + S + 50th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 2 Floor Completed
|  |  |  | 2 | 2 |  | 5 | 50 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 12.5
Excavation |  | 50 |  | 100% | 28.71% |  | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 2 Floor Completed |  | Excavation in process | 25
Plinth |  | 50 |  | 100% |  |  |  |  | Excavation Completed | 50
RCC (Including podiums) |  | 8 |  | 14.04% |  |  |  |  | Footing in Process | 12.5
Brickwork |  | 2 |  | 4% |  |  |  |  | Footing Completed | 25
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 37.5
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 50
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 33.03%
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area |  | 4
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 19000 - 20000 | Floor Rise Per Sq. Ft. (on Carpet area) | : | 50/- from 5th Floor
Car Parking Charges |  |  | : | 700000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 1858.0453
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 8574.8792
Distress Value (Rs. Per sqft) | [5 empty] | : | 1486.4363
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Tower D |  | Sale |  | Flats | 613 |  | 294722.518 | 471556.0287
Tower F |  | Sale |  | Flats | 613 |  | 281861.7984 | 450978.8774
Total |  |  |  |  | 1226 |  | 576584.3164 | 922534.9062
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
60%
Tower D
1st & 2nd Basement Floor For Parking | [9 empty] | 10.764
Ground Floor For Society Office, Drivers Room, Meter Room & Transformer Room
1st Podium Floor For Parking
1st Podium to 5th Podium Floor for Residential & Parking
1st Podium to 5th Podium Floor for Residential & Parking |  | 1 |  | 2 | 587.2838 | 0 | 0 | 939.6541 | 47.3005 | 2.877
|  | 2 |  | 1.5 | 507.9532 | 0 | 0 | 812.7251
|  | 3 |  | 1 | 354.6738 | 0 | 0 | 567.4781
|  | 4 |  | 1 | 354.6738 | 0 | 0 | 567.4781 | 31.2846
|  | 5 |  | 1.5 | 507.9532 | 0 | 0 | 812.7251
|  | 6 |  | 2 | 626.7877 | 0 | 0 | 1002.8604
Upper Stilt Floor for Residential, Fitness Center, Creche & Amenity Area
Upper Stilt Floor for Residential, Fitness Center, Creche & Amenity Area |  | 1 |  | 2 | 587.2838 | 0 | 0 | 939.6541
|  | 2 |  | 1.5 | 507.9532 | 0 | 0 | 812.7251
|  | 3 |  | 1 | 354.6738 | 0 | 0 | 567.4781
|  | 4 |  | 1 | 354.6738 | 0 | 0 | 567.4781
|  | 5 |  | 1.5 | 507.9532 | 0 | 0 | 812.7251
|  | 6 |  | 2 | 626.7877 | 0 | 0 | 1002.8604
1st, 6th, 11th, 15th, 20th, 25th, 29th, 34th, 39th, 44th, 49th Floor For Residential (Part Refuge Area)
1st, 6th, 11th, 15th, 20th, 25th, 29th, 34th, 39th, 44th, 49th Floor For Residential (Part Refuge Area) |  | 1 |  | 2 | 626.7877 | 0 | 0 | 1002.8604 |  |  | 1601,..,4901 | 1601 | 4901
|  | 2 |  | 1 | 389.8721 | 0 | 0 | 623.7953 | 34.4445 |  | 1602,..,4902 | 1602 | 4902
|  | 3 |  | 1 | 417.8585 | 0 | 0 | 668.5736 |  | 2.52 | 1603,..,4903 | 1603 | 4903
|  | 4 |  | 1 | 417.8585 | 0 | 0 | 668.5736 |  |  | 1604,..,4904 | 1604 | 4904
|  | 5 |  | 1 | 389.8721 | 0 | 0 | 623.7953 |  |  | 1605,..,4905 | 1605 | 4905
|  | 6 |  | 2 | 587.2838 | 0 | 0 | 939.6541 |  |  | 1606,..,4906 | 1606 | 4906
|  | 7 |  | 2 | 587.2838 | 0 | 0 | 939.6541 | 19922.2236 |  | 1607,..,4907 | 1607 | 4907
|  | 8 |  | Refuge Area |  |  |  |  | #DIV/0! |  | 1608,..,4908 | 1608 | 4908
|  | 9 |  | 1 | 354.6738 | 0 | 0 | 567.4781 |  |  | 1609,..,4909 | 1609 | 4909
|  | 10 |  | 1 | 354.6738 | 0 | 0 | 567.4781 |  |  | 1610,..,4910 | 1610 | 4910
|  | 11 |  | 1.5 | 507.9532 | 0 | 0 | 812.7251 |  |  | 1611,..,4911 | 1611 | 4911
|  | 12 |  | 2 | 626.7877 | 0 | 0 | 1002.8604 |  |  | 1612,..,4912 | 1612 | 4912
2nd to 5th, 7th to 10th, 12th to 14th, 16th to 19th, 21st to 24th, 26th to 28th, 30th to 33rd, 35th to 38th, 40th to 43rd, 45th to 48th Floor For Residential
2nd to 5th, 7th to 10th, 12th to 14th, 16th to 19th, 21st to 24th, 26th to 28th, 30th to 33rd, 35th to 38th, 40th to 43rd, 45th to 48th Floor For Residential |  | 1 |  | 2 | 626.7877 | 0 | 0 | 1002.8604 |  |  | 2571001,..,4801 | 2571001 | 4801
|  | 2 |  | 1 | 389.8721 | 0 | 0 | 623.7953 |  |  | 2571002,..,4802 | 2571002 | 4802
|  | 3 |  | 1 | 417.8585 | 0 | 0 | 668.5736 |  |  | 2571003,..,4803 | 2571003 | 4803
|  | 4 |  | 1 | 417.8585 | 0 | 0 | 668.5736 |  |  | 2571004,..,4804 | 2571004 | 4804
|  | 5 |  | 1 | 389.8721 | 0 | 0 | 623.7953 |  |  | 2571005,..,4805 | 2571005 | 4805
|  | 6 |  | 2 | 587.2838 | 0 | 0 | 939.6541 |  |  | 2571006,..,4806 | 2571006 | 4806
|  | 7 |  | 2 | 587.2838 | 0 | 0 | 939.6541 |  |  | 2571007,..,4807 | 2571007 | 4807
|  | 8 |  | 1.5 | 507.9532 | 0 | 0 | 812.7251 |  |  | 2571008,..,4808 | 2571008 | 4808
|  | 9 |  | 1 | 354.6738 | 0 | 0 | 567.4781 |  |  | 2571009,..,4809 | 2571009 | 4809
|  | 10 |  | 1 | 354.6738 | 0 | 0 | 567.4781 |  |  | 2571010,..,4810 | 2571010 | 4810
|  | 11 |  | 1.5 | 507.9532 | 0 | 0 | 812.7251 |  |  | 2571011,..,4811 | 2571011 | 4811
|  | 12 |  | 2 | 626.7877 | 0 | 0 | 1002.8604 |  |  | 2571012,..,4812 | 2571012 | 4812
Service Floor Between 25th To 26th Floor For Pump Room, Flushing Water Tank, Fire & Domestic Water Tank
Tower F
1st & 2nd Basement Floor For Parking
Ground Floor For Society Office, Drivers Room, Meter Room, Transformer Room & Parking Area
1st Podium to 5th Podium Floor for Residential & Parking
1st Podium to 5th Podium Floor for Residential & Parking |  | 1 |  | 2 | 542.8285 | 0 | 0 | 868.5256
|  | 2 |  | 1 | 390.6256 | 0 | 0 | 625.0009
|  | 3 |  | 1 | 354.1356 | 0 | 0 | 566.617 | 31.5188
|  | 4 |  | 1 | 354.1356 | 0 | 0 | 566.617
|  | 5 |  | 1 | 390.6256 | 0 | 0 | 625.0009
|  | 6 |  | 2 | 560.5891 | 0 | 0 | 896.9426 | 48.5263
Upper Ground Floor for Residential & Amenities
Upper Ground Floor for Residential & Amenities |  | 1 |  | 2 | 542.8285 | 0 | 0 | 868.5256 | 16027.1608
|  | 2 |  | 1 | 390.6256 | 0 | 0 | 625.0009 | 20331.1952
|  | 3 |  | 1 | 354.1356 | 0 | 0 | 566.617
|  | 4 |  | 1 | 354.1356 | 0 | 0 | 566.617
|  | 5 |  | 1 | 390.6256 | 0 | 0 | 625.0009
|  | 6 |  | 2 | 560.5891 | 0 | 0 | 896.9426
1st, 6th, 11th, 15th, 20th, 25th, 29th, 34th, 39th, 44th, 49th Floor For Residential (Part Refuge Area)
1st, 6th, 11th, 15th, 20th, 25th, 29th, 34th, 39th, 44th, 49th Floor For Residential (Part Refuge Area) |  | 1 |  | 2 | 542.8285 | 0 | 0 | 868.5256 |  |  | 1601,..,4901 | 1601 | 4901
|  | 2 |  | Refuge Area | [6 empty] | 1602,..,4902 | 1602 | 4902
|  | 3 |  | 1 | 354.1356 | 0 | 0 | 566.617 |  |  | 1603,..,4903 | 1603 | 4903
|  | 4 |  | 1 | 354.1356 | 0 | 0 | 566.617 |  |  | 1604,..,4904 | 1604 | 4904
|  | 5 |  | 1 | 390.6256 | 0 | 0 | 625.0009 |  |  | 1605,..,4905 | 1605 | 4905
|  | 6 |  | 2 | 560.5891 | 0 | 0 | 896.9426 |  |  | 1606,..,4906 | 1606 | 4906
|  | 7 |  | 2 | 598.6937 | 0 | 0 | 957.9099 |  |  | 1607,..,4907 | 1607 | 4907
|  | 8 |  | 1 | 429.8065 | 0 | 0 | 687.6904 |  |  | 1608,..,4908 | 1608 | 4908
|  | 9 |  | 1 | 445.0914 | 0 | 0 | 712.1462 |  |  | 1609,..,4909 | 1609 | 4909
|  | 10 |  | 1 | 445.0914 | 0 | 0 | 712.1462 | 36.234 | 2.415 | 1610,..,4910 | 1610 | 4910
|  | 11 |  | 1 | 429.8065 | 0 | 0 | 687.6904 |  |  | 1611,..,4911 | 1611 | 4911
|  | 12 |  | 2 | 581.0407 | 0 | 0 | 929.6652 | 47.0602 | 2.877 | 1612,..,4912 | 1612 | 4912
2nd to 5th, 7th to 10th, 12th to 14th, 16th to 19th, 21st to 24th, 26th to 28th, 30th to 33rd, 35th to 38th, 40th to 43rd, 45th to 48th Floor For Residential
2nd to 5th, 7th to 10th, 12th to 14th, 16th to 19th, 21st to 24th, 26th to 28th, 30th to 33rd, 35th to 38th, 40th to 43rd, 45th to 48th Floor For Residential |  | 1 |  | 2 | 542.8285 | 0 | 0 | 868.5256 |  |  | 2571001,..,4801 | 2571001 | 4801
|  | 2 |  | 1 | 390.6256 | 0 | 0 | 625.0009 |  |  | 2571002,..,4802 | 2571002 | 4802
|  | 3 |  | 1 | 354.1356 | 0 | 0 | 566.617 |  |  | 2571003,..,4803 | 2571003 | 4803
|  | 4 |  | 1 | 354.1356 | 0 | 0 | 566.617 |  |  | 2571004,..,4804 | 2571004 | 4804
|  | 5 |  | 1 | 390.6256 | 0 | 0 | 625.0009 |  |  | 2571005,..,4805 | 2571005 | 4805
|  | 6 |  | 2 | 560.5891 | 0 | 0 | 896.9426 |  |  | 2571006,..,4806 | 2571006 | 4806
|  | 7 |  | 2 | 598.6937 | 0 | 0 | 957.9099 |  |  | 2571007,..,4807 | 2571007 | 4807
|  | 8 |  | 1.5 | 429.8065 | 0 | 0 | 687.6904 |  |  | 2571008,..,4808 | 2571008 | 4808
|  | 9 |  | 1 | 445.0914 | 0 | 0 | 712.1462 |  |  | 2571009,..,4809 | 2571009 | 4809
|  | 10 |  | 1 | 445.0914 | 0 | 0 | 712.1462 |  |  | 2571010,..,4810 | 2571010 | 4810
|  | 11 |  | 1.5 | 429.8065 | 0 | 0 | 687.6904 |  |  | 2571011,..,4811 | 2571011 | 4811
|  | 12 |  | 2 | 581.0407 | 0 | 0 | 929.6652 |  |  | 2571012,..,4812 | 2571012 | 4812
Service Floor Between 25th To 26th Floor For Pump Room, Flushing Water Tank, Fire & Domestic Water Tank
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Wing D = Construction work is in process at the time of Visit. Wing F = Construction work is in process at the time of Visit. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + Utility Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We have done APF for Tower D & F as it is registered on RERA Site. 8. We have updated approved floor plan & C.C of D & F Tower (on 08/05/2024). 7. On Site, we meet Mr........(........).
Site & Building/Tower Photographs
Name of the Project |  |  | : | Runwal Enchanted
Project Site Address |  |  | : | Runwal Enchanted, Near - Kia Service Center, Village - Kolshet, Thane West, Taluka - Thane, Maharashtra 400607
Site Visit Date & Time |  |  | : | 04/07/2025 @11:44 AM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr.Ajay Songare | Authorized Signatory Name & Signature | :
Wing D
Wing F
N
N
Basement
Gr. Floor
Upper Gr. Floor
Tower D
Tower D
Tower F