## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  |  | : | Bellanza Phase 1 ­ Wing A, B, C |  | Date & Time of Site Visit |  | 07/07/2025 @04:00PM
Project Name as per RERA |  |  | : | Bellanza Phase 1 ­ Wing A, B, C at The Prestige City
Name of the person met at site & Contact No. |  |  | : | Ms.Arpita 7795805135 |  | Date of Report Release |  | 08/07/2025 |  | 2025-04-26 | 2025-07-07
Data from APF Request Form | [10 empty] | 72
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr .Suraj Khare
Builder Group Name |  |  | : | Ariisto Developers Private Limited | Developer Name | : | Prestige Estates Projects Limited
Developer Office Address |  |  | : | 1001 C BKC Capital, BKC west
Project Address | : | As per ARF | : | Bellanza Phase 1 ­ Wing A, B, C at The Prestige City, Village. Mulund, Situated Near. Veena Nagar, Road - Agrawal Road, Mulund West, Kurla, Mumbai, Maharashtra - 400080
| : | As per Legal Documents | : | Bellanza Phase 1 ­ Wing A, B, C at The Prestige City, CTS No. 19/1 to 19/13, Village. Mulund, Veena Nagar, Road - Agrawal Road, Mulund West, Kurla, Mumbai, Maharashtra - 400080
| : | As per Actual at site | : | Bellanza Phase 1 ­ Wing A, B, C at The Prestige City, Village. Mulund, Veena Nagar, Road - Agrawal Road, Mulund West, Mumbai, Kurla, Maharashtra - 400080
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate, NOC
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Slum Rehabilitation Authority
RERA Registration No. | : | P51800045339 |  |  | RERA Registration Validity | : | 2026-12-31
Project Launch Date | : | 2022-09-28 |  |  | Construction Start Date | : | 2022-05-12
Proposed Date of Completion (As per RERA) | : | 2026-12-31 |  |  | Developer Bank Name (As per RERA) | : | Kotak Mahindra Bank IFSC Code - KKBK0000422
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 23125 |  | 21573
FSI/FAR Permissible | : | 3 |  |  | Proposed Built up Area (In Sq.Mt) | : | 79419.72
Permissible Built up Area (In Sq.Mt) | : | - |  |  | Total Number of Units Planned | : | As per RERA Site - Flats = 848 |  | 848 | 830 | 18
Total Number of Units Approved | : | Flats = 848 |  |  | If Mixed, No. of Commercial Units | : | Shop = NA
Latitude | : | 19.1845 |  |  | Longitude | : | 72.9408
Location Link | : | https://goo.gl/maps/GHpdSw58Hxzxmpr96
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 500 M from Swapna Nagari Bus Stop
Distance from the nearest School (Km) | : | About 850M from St. George High School |  |  | Distance from Hospital (Km) | : | About 1KM form Apex Hospitals Mulund
Distance from the Main Market (Km) | : | 1. Approx. 1KM from Shree Balaji Supermarket. 2. Approx. 3KM from Mulund Main Market. |  |  | Distance from Railway Station (Km) | : | 4.5KM from Mulund Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Open Plot | Road | Siesta |  | Road
As per Site / Actual |  |  | : | Open Plot | Road | Siesta at Ariisto Heaven |  | Road
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
A Wing |  | Sale |  | B + Gr + 1st to 7th P + 8th to 54th Floor |  |  | B + Gr + 1st to 7th P + 8th to 54th Floor
B Wing |  | Sale |  | B + Gr + 1st to 7th P + 8th to 54th Floor |  |  | B + Gr + 1st to 7th P + 8th to 54th Floor
C Wing |  | Sale |  | B + Gr + 1st to 7th P + 8th to 54th Floor |  |  | B + Gr + 1st to 7th P + 8th to 54th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | SRA/DDTP/0548/T/PL/layout Date: 24/03/2022
CC Details | : | SRA/DDTP/518/T/PL/AP Date:13/04/2022 Valid Up to: This CC is endorsed a plinth C.C for wing 'A', wing 'B', 'C', 'D', 'E' and 'F" together with common basement of sale building No - 2 as per amended approved plan dated 13/04/2022. |  |  | Approved Plan Details | : | SRA/DDTP/0518/T/PL/AP Date: 13/04/2022
Environmental Clearance Details | : | SEAC-2014/CR-92/TC-1 Date: 11/03/2016 |  |  | Airport Authority Clearance Details | : | BT-1/NOCC/CS/MUM/14/NOCAS /247/1356/702-05 Date: 05/08/2014
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
Construction Status
Wing A = B + Gr + 1st to 7th P + 8th to 54th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 48.6 Floor, External Plaster upto 48.6 Floor, External Plumbing, Elevation and Waterproofing upto 30 Floor, Flooring & Fitting upto 36 Floor, Wooden Work upto 20 Floor, Electrical & Sanitary fittings upto 20 Floor Completed
|  |  |  | 1 | 1 |  | 0 | 54 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.5
Excavation |  | 54 |  | 100% | 70.8% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 48.6 Floor, External Plaster upto 48.6 Floor, External Plumbing, Elevation and Waterproofing upto 30 Floor, Flooring & Fitting upto 36 Floor, Wooden Work upto 20 Floor, Electrical & Sanitary fittings upto 20 Floor Completed |  | Excavation in process | 27
Plinth |  | 54 |  | 100% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 55 |  | 100% |  |  |  |  | Footing in Process | 13.5
Brickwork |  | 54 |  | 100% |  |  |  |  | Footing Completed | 27
Internal Plaster |  | 48.6 |  | 90% |  |  |  |  | Basement 1 | 0
External Plaster |  | 48.6 |  | 90% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 30 |  | 55.56% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 36 |  | 66.67% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 20 |  | 37.04% |  |  |  |  | Plinth in process | 40.5
Electrical & Sanitary fittings |  | 20 |  | 37.04% |  |  |  |  | Plinth completed | 54 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Wing B & C = B + Gr + 1st to 7th P + 8th to 54th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 48.6 Floor, External Plaster upto 48.6 Floor, External Plumbing, Elevation and Waterproofing upto 25 Floor, Flooring & Fitting upto 30 Floor, Wooden Work upto 15 Floor, Electrical & Sanitary fittings upto 15 Floor Completed
|  |  |  | 1 | 1 |  | 0 | 54 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.5
Excavation |  | 54 |  | 100% | 68.76% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 48.6 Floor, External Plaster upto 48.6 Floor, External Plumbing, Elevation and Waterproofing upto 25 Floor, Flooring & Fitting upto 30 Floor, Wooden Work upto 15 Floor, Electrical & Sanitary fittings upto 15 Floor Completed |  | Excavation in process | 27
Plinth |  | 54 |  | 100% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 55 |  | 100% |  |  |  |  | Footing in Process | 13.5
Brickwork |  | 54 |  | 100% |  |  |  |  | Footing Completed | 27
Internal Plaster |  | 48.6 |  | 90% |  |  |  |  | Basement 1 | 0
External Plaster |  | 48.6 |  | 90% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 25 |  | 46.3% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 30 |  | 55.56% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 15 |  | 27.78% |  |  |  |  | Plinth in process | 40.5
Electrical & Sanitary fittings |  | 15 |  | 27.78% |  |  |  |  | Plinth completed | 54 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 69.44%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 19500 to 21000 | Floor Rise Per Sq. Ft. (on Carpet area) | : | 80/- from 4th Floor
Car Parking Charges |  |  | : | 10,00,000/- | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 6815.3103
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 14070.9773
Distress Value (Rs. Per sqft) | [5 empty] | : | 5452.2482
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
A Wing |  | Sale |  | Flats | 290 |  | 245660.0983 | 393056.1573 | 290
B Wing |  | Sale |  | Flats | 281 |  | 242461.0375 | 387937.66 | 281
C Wing |  | Sale |  | Flats | 277 |  | 252515.0441 | 404024.0705 | 277
Total |  |  |  |  | 848 |  | 740636.1799 | 1185017.8879
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
60%
A Wing
Basement Floor For Parking
Ground Floor For Parking
1st Podium Floor For Parking
2nd Podium Floor For Parking
3rd Podium Floor For Parking & Residential
3rd Podium Floor For Parking & Residential |  | 1 |  | 3BHK | 1020.6425 |  | 0 | 1633.028 | 1012
|  | 2 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
|  | 3 |  | 3BHK | 882.0022 |  | 0 | 1411.2035
4th Podium Floor For Parking & Residential
4th Podium Floor For Parking & Residential |  | 1 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
|  | 2 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
|  | 3 |  | 3BHK | 882.0022 |  | 0 | 1411.2035
|  | 4 |  | Parking Area |  |  |  | 0
|  | 5 |  | Parking Area |  |  |  | 0
|  | 6 |  | 2BHK | 724.9554 |  | 0 | 1159.9286
5th Podium Floor For Parking & Residential
5th Podium Floor For Parking & Residential |  | 1 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
|  | 2 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
|  | 3 |  | 3BHK | 882.0022 |  | 0 | 1411.2035
|  | 4 |  | Parking Area |  |  |  | 0
|  | 5 |  | Parking Area |  |  |  | 0
|  | 6 |  | 2BHK | 724.9554 |  | 0 | 1159.9286
6th Podium Floor For Parking & Residential
6th Podium Floor For Parking & Residential |  | 1 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
|  | 2 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
|  | 3 |  | 3BHK | 882.0022 |  | 0 | 1411.2035
|  | 4 |  | Parking Area |  |  |  | 0
|  | 5 |  | Parking Area |  |  |  | 0
|  | 6 |  | 2BHK | 724.9554 |  | 0 | 1159.9286
7th Podium Floor For Parking & Residential
7th Podium Floor For Parking & Residential |  | 1 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
|  | 2 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
|  | 3 |  | Parking Area |  |  |  | 0
|  | 4 |  | Parking Area |  |  |  | 0
|  | 5 |  | Parking Area |  |  |  | 0
|  | 6 |  | 2BHK | 724.9554 |  | 0 | 1159.9286
8th Podium Floor For Parking, Residential & Club House
8th Podium Floor For Parking, Residential & Club House |  | 1 |  | 3BHK | 1012.0313 |  | 0 | 1619.25
|  | 2 |  | 3BHK | 1012.0313 |  | 0 | 1619.25
9th Podium Floor For Parking, Residential, Steam & Sauna
9th Podium Floor For Parking, Residential, Steam & Sauna |  | 1 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
|  | 2 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
10th Floor For Residential & Sauna Area
10th Floor For Residential & Sauna Area |  | 1 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
|  | 2 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
|  | 3 |  | Sauna Area
|  | 4 |  | Sauna Area
|  | 5 |  | 2BHK | 724.9554 |  | 0 | 1159.9286
|  | 6 |  | 2BHK | 724.9554 |  | 0 | 1159.9286
11th to 13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41st, 44th to 49th & 51st to 54th Floor For Residential
11th to 13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41st, 44th to 49th & 51st to 54th Floor For Residential |  | 1 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
|  | 2 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
|  | 3 |  | 3BHK | 886.9536 |  | 0 | 1419.1258
|  | 4 |  | 3BHK | 886.9536 |  | 0 | 1419.1258
|  | 5 |  | 2BHK | 724.9554 |  | 0 | 1159.9286
|  | 6 |  | 2BHK | 724.9554 |  | 0 | 1159.9286
14th, 21st, 28th, 35th & 42nd Floor For Residential
14th, 21st, 28th, 35th & 42nd Floor For Residential |  | 1 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
|  | 2 |  | 3BHK | 1020.6425 |  | 0 | 1633.028
|  | 3 |  | 3BHK | 886.9536 |  | 0 | 1419.1258
|  | 4 |  | 3BHK | 886.9536 |  | 0 | 1419.1258
|  | 5 |  | 2BHK | 724.9554 |  | 0 | 1159.9286
|  | 6 |  | 2BHK | 724.9554 |  | 0 | 1159.9286
15th, 22nd, 29th, 36th & 43rd Floor For Residential (Part Refuge Area)
15th, 22nd, 29th, 36th & 43rd Floor For Residential (Part Refuge Area) |  | 1 |  | MP Room | 171.04 |  | 0 | 273.6639
|  | 2 |  | MP Room | 171.04 |  | 0 | 273.6639
|  | 3 |  | 3BHK | 886.9536 |  | 0 | 1419.1258
|  | 4 |  | 3BHK | 886.9536 |  | 0 | 1419.1258
|  | 5 |  | 2BHK | 724.9554 |  | 0 | 1159.9286
|  | 6 |  | 2BHK | 724.9554 |  | 0 | 1159.9286
50th Floor For Residential (Part Refuge Area)
50th Floor For Residential (Part Refuge Area) |  | 1 |  | MP Room | 171.04 |  | 0 | 273.6639
|  | 2 |  | MP Room | 171.04 |  | 0 | 273.6639
|  | 3 |  | 3BHK | 886.9536 |  | 0 | 1419.1258
|  | 4 |  | 3BHK | 886.9536 |  | 0 | 1419.1258
|  | 5 |  | 2BHK | 724.9554 |  | 0 | 1159.9286
|  | 6 |  | 2BHK | 724.9554 |  | 0 | 1159.9286
B Wing
Basement Floor For Parking
Ground Floor For Parking
1st Podium Floor For Parking
2nd Podium Floor For Parking
3rd Podium Floor For Parking & Residential
3rd Podium Floor For Parking & Residential |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
4th Podium Floor For Parking & Residential
4th Podium Floor For Parking & Residential |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562 | 21803.1053
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 3 |  | 2BHK | 758.0009 |  | 0 | 1212.8014 | 20976.2289
|  | 4 |  | Parking Area |  |  |  | 0
|  | 5 |  | Parking Area |  |  |  | 0
|  | 6 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
5th Podium Floor For Parking & Residential
5th Podium Floor For Parking & Residential |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 3 |  | 2BHK | 758.0009 |  | 0 | 1212.8014 | 20976.2289
|  | 4 |  | Parking Area |  |  |  | 0
|  | 5 |  | Parking Area |  |  |  | 0
|  | 6 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
6th Podium Floor For Parking & Residential
6th Podium Floor For Parking & Residential |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 3 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 4 |  | Parking Area |  |  |  | 0
|  | 5 |  | Parking Area |  |  |  | 0
|  | 6 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
7th Podium Floor For Parking & Residential
7th Podium Floor For Parking & Residential |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 3 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 4 |  | Parking Area |  |  |  | 0
|  | 5 |  | Parking Area |  |  |  | 0
|  | 6 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
8th Podium Floor For Residential & Double Height
8th Podium Floor For Residential & Double Height |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
9th Podium Floor For Residential & Double Height
9th Podium Floor For Residential & Double Height |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
10th Floor For Residential
10th Floor For Residential |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562 | 22376.8713
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 3 |  | 2BHK | 758.0009 |  | 0 | 1212.8014 | 28627.9351
|  | 4 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 5 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 6 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
11th to 13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41st, 44th to 49th & 51st to 54th Floor For Residential
11th to 13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41st, 44th to 49th & 51st to 54th Floor For Residential |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 3 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 4 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 5 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 6 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
14th, 21st, 28th, 35th & 42nd Floor For Residential
14th, 21st, 28th, 35th & 42nd Floor For Residential |  | 1 |  | 4BHK (Duplex with 15th, 22nd, 29th, 36th & 43rd) | 1536.9916 |  | 0 | 2459.1865
14th, 21st, 28th, 35th & 42nd Floor For Residential |  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 3 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 4 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 5 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 6 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
15th, 22nd, 29th, 36th & 43rd Floor For Residential (Part Refuge Area)
15th, 22nd, 29th, 36th & 43rd Floor For Residential (Part Refuge Area) |  | 1 |  | 4BHK (Duplex with 14th, 21st, 28th, 35th & 42nd)
|  | 2 |  | Refuge Area
|  | 3 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 4 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 5 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 6 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
50th Floor For Residential (Part Refuge Area)
50th Floor For Residential (Part Refuge Area) |  | 1 |  | 3BHK | 1294.0481 |  | 0 | 2070.4769
|  | 2 |  | Refuge Area
|  | 3 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 4 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 5 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 6 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
C Wing
Basement Floor For Parking
Ground Floor For Parking
1st Podium Floor For Parking
2nd Podium Floor For Parking
3rd Podium Floor For Parking & Residential
3rd Podium Floor For Parking & Residential |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
4th Podium Floor For Parking & Residential
4th Podium Floor For Parking & Residential |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 3 |  | Parking Area | 736.0423 |  | 0 | 1177.6677
|  | 4 |  | Parking Area |  |  |  | 0
|  | 5 |  | Parking Area |  |  |  | 0
|  | 6 |  | 2BHK | 758.3238 |  | 0 | 1213.3181
5th Podium Floor For Parking & Residential
5th Podium Floor For Parking & Residential |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 3 |  | Parking Area | 758.0009 |  | 0 | 1212.8014
|  | 4 |  | Parking Area |  |  |  | 0
|  | 5 |  | Parking Area |  |  |  | 0
|  | 6 |  | 2BHK | 758.3238 |  | 0 | 1213.3181
6th Podium Floor For Parking & Residential
6th Podium Floor For Parking & Residential |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 3 |  | Parking Area | 736.0423 |  | 0 | 1177.6677
|  | 4 |  | Parking Area |  |  |  | 0
|  | 5 |  | Parking Area |  |  |  | 0
|  | 6 |  | 2BHK | 758.3238 |  | 0 | 1213.3181
7th Podium Floor For Parking & Residential
7th Podium Floor For Parking & Residential |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 3 |  | Parking Area | 758.0009 |  | 0 | 1212.8014
|  | 4 |  | Parking Area |  |  |  | 0
|  | 5 |  | Parking Area |  |  |  | 0
|  | 6 |  | 2BHK | 758.3238 |  | 0 | 1213.3181
8th Podium Floor For Residential & Double Height
8th Podium Floor For Residential & Double Height |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
9th Podium Floor For Residential & Double Height
9th Podium Floor For Residential & Double Height |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
10th Floor For Residential
10th Floor For Residential |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 3 |  | 3BHK | 903.0996 |  | 0 | 1444.9594
|  | 4 |  | 3BHK | 903.0996 |  | 0 | 1444.9594
|  | 5 |  | 2BHK | 758.3238 |  | 0 | 1213.3181
|  | 6 |  | 2BHK | 758.3238 |  | 0 | 1213.3181
11th to 13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41st, 44th to 49th & 51st to 54th Floor For Residential
11th to 13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41st, 44th to 49th & 51st to 54th Floor For Residential |  | 1 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 3 |  | 3BHK | 903.0996 |  | 0 | 1444.9594
|  | 4 |  | 3BHK | 903.0996 |  | 0 | 1444.9594
|  | 5 |  | 2BHK | 758.3238 |  | 0 | 1213.3181
|  | 6 |  | 2BHK | 758.3238 |  | 0 | 1213.3181
14th, 21st, 28th, 35th & 42nd Floor For Residential
14th, 21st, 28th, 35th & 42nd Floor For Residential |  | 1 |  | 4BHK (Duplex with 15th, 22nd, 29th, 36th & 43rd) | 1536.9916 |  | 0 | 2459.1865
|  | 2 |  | 3BHK | 1045.7226 |  | 0 | 1673.1562
|  | 3 |  | 3BHK | 903.0996 |  | 0 | 1444.9594
|  | 4 |  | 3BHK | 903.0996 |  | 0 | 1444.9594
|  | 5 |  | 2BHK | 758.3238 |  | 0 | 1213.3181
|  | 6 |  | 2BHK | 758.3238 |  | 0 | 1213.3181
15th, 22nd, 29th, 36th & 43rd Floor For Residential (Part Refuge Area)
15th, 22nd, 29th, 36th & 43rd Floor For Residential (Part Refuge Area) |  | 1 |  | 4BHK (Duplex with 14th, 21st, 28th, 35th & 42nd)
|  | 2 |  | Refuge Area
|  | 3 |  | 3BHK | 903.0996 |  | 0 | 1444.9594
|  | 4 |  | 3BHK | 903.0996 |  | 0 | 1444.9594
|  | 5 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
|  | 6 |  | 2BHK | 758.0009 |  | 0 | 1212.8014
50th Floor For Residential (Part Refuge Area)
50th Floor For Residential (Part Refuge Area) |  | 1 |  | 3BHK | 1294.0481 |  | 0 | 2070.4769
|  | 2 |  | Refuge Area
|  | 3 |  | 3BHK | 903.0996 |  | 0 | 1444.9594
|  | 4 |  | 3BHK | 903.0996 |  | 0 | 1444.9594
|  | 5 |  | 2BHK | 758.3238 |  | 0 | 1213.3181
|  | 6 |  | 2BHK | 758.3238 |  | 0 | 1213.3181
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Construction work is in process at the time of Visit. Internal visit was not allowed. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + Deck Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We have updated the revised construction table on dated 21/11/2024, which is shared with us by the Godrej officials 8. Please Provide latest approved plans & revised CC. 7. On Site, we meet Mr.Chiny Jaiswal (Sale) -8147170638.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Bellanza Phase 1 ­ Wing A, B, C
Project Site Address |  |  | : | Bellanza Phase 1 ­ Wing A, B, C at The Prestige City, Village. Mulund, Situated Near. Veena Nagar, Road - Agrawal Road, Mulund West, Kurla, Mumbai, Maharashtra - 400080
Site Visit Date & Time |  |  | : | 07/07/2025 @04:00PM
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Nainesh Tambe | Authorized Signatory Name & Signature | :