## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  |  | : | Bellanza Phase 2 ­ Wing D, E, F |  | Date & Time of Site Visit |  | 07/07/2025 @04:00 PM
Project Name as per RERA |  |  | : | Bellanza Phase 2 ­ Wing D, E, F at The Prestige City | [5 empty] | 2025-04-26 | 2025-07-07
Name of the person met at site & Contact No. |  |  | : | Ms.Reshma 8867832933 |  | Date of Report Release |  | 08/07/2025 |  |  | 72
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr .Suraj Khare
Builder Group Name |  |  | : | Ariisto Developers Private Limited | Developer Name | : | Prestige Mulund Realty Private Limited
Developer Office Address |  |  | : | 1001 C BKC Capital, BKC west
Project Address | : | As per ARF | : | Bellanza Phase 2 ­ Wing D, E, F at The Prestige City, Village. Mulund, Situated Near. Veena Nagar, Road - Agrawal Road, Mulund West, Kurla, Mumbai, Maharashtra - 400080
| : | As per Legal Documents | : | Bellanza Phase 2 ­ Wing D, E, F at The Prestige City, CTS No. 19/1 to 19/13, Village. Mulund, Veena Nagar, Road - Agrawal Road, Mulund West, Kurla, Mumbai, Maharashtra - 400080
| : | As per Actual at site | : | Bellanza Phase 2 ­ Wing D, E, F at The Prestige City, Village. Mulund, Veena Nagar, Road - Agrawal Road, Mulund West, Mumbai, Kurla, Maharashtra - 400080
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate, NOC
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Slum Rehabilitation Authority
RERA Registration No. | : | P51800046488 |  |  | RERA Registration Validity | : | 2027-06-30
Project Launch Date | : | 2022-09-28 |  |  | Construction Start Date | : | 2022-08-06
Proposed Date of Completion (As per RERA) | : | 2027-06-30 |  |  | Developer Bank Name (As per RERA) | : | Kotak Mahindra Bank IFSC Code - KKBK0000422
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 23125 |  | 21573
FSI/FAR Permissible | : | 3 |  |  | Proposed Built up Area (In Sq.Mt) | : | 79419.72
Permissible Built up Area (In Sq.Mt) | : | - |  |  | Total Number of Units Planned | : | As per RERA Site - Flats = 799 |  | 848 | 830 | 18
Total Number of Units Approved | : | Flats = 799 |  |  | If Mixed, No. of Commercial Units | : | Shop = NA
Latitude | : | 19.1845 |  |  | Longitude | : | 72.9408
Location Link | : | https://goo.gl/maps/GHpdSw58Hxzxmpr96
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 500 M from Swapna Nagari Bus Stop
Distance from the nearest School (Km) | : | About 850M from St. George High School |  |  | Distance from Hospital (Km) | : | About 1KM form Apex Hospitals Mulund
Distance from the Main Market (Km) | : | 1. Approx. 1KM from Shree Balaji Supermarket. 2. Approx. 3KM from Mulund Main Market. |  |  | Distance from Railway Station (Km) | : | 4.5KM from Mulund Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Open Plot | Road | Siesta |  | Road
As per Site / Actual |  |  | : | Open Plot | Road | Siesta at Ariisto Heaven |  | Road
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
D Wing |  | Sale |  | B + Gr + 1st to 9th P + 10th to 54th Floor |  |  | B + Gr + 1st to 9th P + 10th to 54th Floor
E Wing |  | Sale |  | B + Gr + 1st to 9th P + 10th to 54th Floor |  |  | B + Gr + 1st to 9th P + 10th to 54th Floor
F Wing |  | Sale |  | B + Gr + 1st to 9th P + 10th to 54th Floor |  |  | B + Gr + 1st to 9th P + 10th to 54th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | SRA/DDTP/0518/5/D4 Date: 01/07/2022 |  |  |  | :
Approved Plan Details | : | SRA/DDTP/0518/T/PL/AP Date: 27/02/2023
CC Details | : | SRA/DDTP/518/T/PL/AP Date: 26/08/2024 Valid Up to: This C.C is further extended for full work i.e upto 54th floor top + OHWT & LMR for Wing A, B, C, D, E, & F of sale building No. 2 as per last approved plan dated 27/02/2023. | [8 empty] | Approved upto: D Wing - B + Gr + 1st to 7th P + 8th to 46th Floor E & F Wing - B + Gr + 1st to 7th P + 8th to 9th Floor SRA/DDTP/0518/T/PL/AP Date: 27/02/2023 For - D Wing - 4803, E Wing - 2302 & F wing - 3004
Environmental Clearance Details | : | SEAC-2014/CR-92/TC-1 Date: 11/03/2016 |  |  | Airport Authority Clearance Details | : | BT-1/NOCC/CS/MUM/14/NOCAS /247/1356/702-05 Date: 05/08/2014
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
Construction Status
Wing D = B + Gr + 1st to 9th P + 10th to 54th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 41 Slab, Brickwork upto 40 Floor, Internal Plaster upto 36 Floor, External Plaster upto 36 Floor, External Plumbing, Elevation and Waterproofing upto 20 Floor, Flooring & Fitting upto 20 Floor Completed
|  |  |  | 1 | 1 |  | 0 | 54 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.5
Excavation |  | 54 |  | 100% | 56.23% |  | Excavation work Completed. Plinth work completed, RCC upto 41 Slab, Brickwork upto 40 Floor, Internal Plaster upto 36 Floor, External Plaster upto 36 Floor, External Plumbing, Elevation and Waterproofing upto 20 Floor, Flooring & Fitting upto 20 Floor Completed |  | Excavation in process | 27
Plinth |  | 54 |  | 100% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 41 |  | 74.55% |  |  |  |  | Footing in Process | 13.5
Brickwork |  | 40 |  | 74.07% |  |  |  |  | Footing Completed | 27
Internal Plaster |  | 36 |  | 66.67% |  |  |  |  | Basement 1 | 0
External Plaster |  | 36 |  | 66.67% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 20 |  | 37.04% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 20 |  | 37.04% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 40.5
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 54 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Wing E = B + Gr + 1st to 9th P + 10th to 54th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 42 Slab, Brickwork upto 41 Floor, Internal Plaster upto 32.8 Floor, External Plaster upto 32.8 Floor, External Plumbing, Elevation and Waterproofing upto 25 Floor, Flooring & Fitting upto 25 Floor Completed
|  |  |  | 1 | 1 |  | 0 | 54 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.5
Excavation |  | 54 |  | 100% | 57.87% |  | Excavation work Completed. Plinth work completed, RCC upto 42 Slab, Brickwork upto 41 Floor, Internal Plaster upto 32.8 Floor, External Plaster upto 32.8 Floor, External Plumbing, Elevation and Waterproofing upto 25 Floor, Flooring & Fitting upto 25 Floor Completed |  | Excavation in process | 27
Plinth |  | 54 |  | 100% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 42 |  | 76.36% |  |  |  |  | Footing in Process | 13.5
Brickwork |  | 41 |  | 75.93% |  |  |  |  | Footing Completed | 27
Internal Plaster |  | 32.8 |  | 60.74% |  |  |  |  | Basement 1 | 0
External Plaster |  | 32.8 |  | 60.74% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 25 |  | 46.3% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 25 |  | 46.3% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 40.5
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 54 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Wing F = B + Gr + 1st to 9th P + 10th to 54th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 54 Slab, Brickwork upto 53 Floor, Internal Plaster upto 42.4 Floor, External Plaster upto 42.4 Floor, External Plumbing, Elevation and Waterproofing upto 35 Floor, Flooring & Fitting upto 30 Floor, Wooden Work upto 20 Floor, Electrical & Sanitary fittings upto 20 Floor Completed
|  |  |  | 1 | 1 |  | 0 | 54 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.5
Excavation |  | 54 |  | 100% | 69.03% |  | Excavation work Completed. Plinth work completed, RCC upto 54 Slab, Brickwork upto 53 Floor, Internal Plaster upto 42.4 Floor, External Plaster upto 42.4 Floor, External Plumbing, Elevation and Waterproofing upto 35 Floor, Flooring & Fitting upto 30 Floor, Wooden Work upto 20 Floor, Electrical & Sanitary fittings upto 20 Floor Completed |  | Excavation in process | 27
Plinth |  | 54 |  | 100% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 54 |  | 98.18% |  |  |  |  | Footing in Process | 13.5
Brickwork |  | 53 |  | 98.15% |  |  |  |  | Footing Completed | 27
Internal Plaster |  | 42.4 |  | 78.52% |  |  |  |  | Basement 1 | 0
External Plaster |  | 42.4 |  | 78.52% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 35 |  | 64.81% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 30 |  | 55.56% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 20 |  | 37.04% |  |  |  |  | Plinth in process | 40.5
Electrical & Sanitary fittings |  | 20 |  | 37.04% |  |  |  |  | Plinth completed | 54 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 61.04%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 22000 to 23000 | Floor Rise Per Sq. Ft. (on Carpet area) | : | 80/- from 4th Floor |  | 21000-22000 Rate revised by Sachin sir Due to unit report
Car Parking Charges |  |  | : | 10,00,000/- | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 6815.3103
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 14070.9773
Distress Value (Rs. Per sqft) | [5 empty] | : | 5452.2482
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
D Wing |  | Sale |  | Flats | 266 |  | 243301.2917 | 389282.0667 | 290
E Wing |  | Sale |  | Flats | 273 |  | 227182.1886 | 363491.5017 | 281
F Wing |  | Sale |  | Flats | 260 |  | 218959.3494 | 350334.959 | 277
Total |  |  |  |  | 799 |  | 689442.8297 | 1103108.5275
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
60%
D Wing
Basement Floor For Parking, Fire Tank, Pump Room
Ground Floor For Parking & Substation
1st Podium Floor For Parking | [8 empty] | 1
2nd Podium Floor For Residential ( Part Parking Area) | [8 empty] | 1
2nd Podium Floor For Residential ( Part Parking Area) |  | 1 |  | 3BHK | 992.6346 |  | 0 | 1588.2153 |  |  |  | 1012 | 10.764
2nd Podium Floor For Residential ( Part Parking Area) |  | 2 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
2nd Podium Floor For Residential ( Part Parking Area) |  | 3 |  | Parking Area | [7 empty] | 1012
2nd Podium Floor For Residential ( Part Parking Area) |  | 4
2nd Podium Floor For Residential ( Part Parking Area) |  | 5 |  | Void Lobby Area
3rd Podium Floor (Part Parking Area) | [8 empty] | 1
3rd Podium Floor (Part Parking Area) |  | 1 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
3rd Podium Floor (Part Parking Area) |  | 2 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
3rd Podium Floor (Part Parking Area) |  | 3 |  | Parking Area
3rd Podium Floor (Part Parking Area) |  | 4
3rd Podium Floor (Part Parking Area) |  | 5
3rd Podium Floor (Part Parking Area) |  | 6 |  | 2BHK | 676.4055 |  | 0 | 1082.2487
4th Podium Floor (Part Parking Area) | [8 empty] | 1
4th Podium Floor (Part Parking Area) |  | 1 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
4th Podium Floor (Part Parking Area) |  | 2 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
4th Podium Floor (Part Parking Area) |  | 3 |  | Parking Area |  |  |  | 0
4th Podium Floor (Part Parking Area) |  | 4 | [5 empty] | 0
4th Podium Floor (Part Parking Area) |  | 5 | [5 empty] | 0
4th Podium Floor (Part Parking Area) |  | 6 |  | 2BHK | 676.4055 |  | 0 | 1082.2487
5th Podium Floor (Part Parking Area) | [8 empty] | 1
5th Podium Floor (Part Parking Area) |  | 1 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
5th Podium Floor (Part Parking Area) |  | 2 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
5th Podium Floor (Part Parking Area) |  | 3 |  | Parking Area |  |  |  | 0
5th Podium Floor (Part Parking Area) |  | 4 | [5 empty] | 0
5th Podium Floor (Part Parking Area) |  | 5 | [5 empty] | 0
5th Podium Floor (Part Parking Area) |  | 6 |  | 2BHK | 676.4055 |  | 0 | 1082.2487
6th Podium Floor (Part Parking Area) | [8 empty] | 1
6th Podium Floor (Part Parking Area) |  | 1 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
6th Podium Floor (Part Parking Area) |  | 2 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
6th Podium Floor (Part Parking Area) |  | 3 |  | Parking Area |  |  |  | 0
6th Podium Floor (Part Parking Area) |  | 4 |  | Parking Area |  |  |  | 0
6th Podium Floor (Part Parking Area) |  | 5 |  | Parking Area |  |  |  | 0
6th Podium Floor (Part Parking Area) |  | 6 |  | 2BHK | 676.4055 |  | 0 | 1082.2487
7th Podium Floor (Part Parking Area) | [8 empty] | 1
7th Podium Floor (Part Parking Area) |  | 1 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
7th Podium Floor (Part Parking Area) |  | 2 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
7th Podium Floor (Part Parking Area) |  | 3 |  | Parking Area |  |  |  | 0
7th Podium Floor (Part Parking Area) |  | 4 |  | Parking Area |  |  |  | 0
7th Podium Floor (Part Parking Area) |  | 5 |  | Parking Area |  |  |  | 0
7th Podium Floor (Part Parking Area) |  | 6 |  | 2BHK | 676.4055 |  | 0 | 1082.2487
Service Floor In between 7th & 8th Floor | [8 empty] | 1
8th & 9th Floor For Amenities (Kids Play Area, Creche, Yoga, Gym & Meditation Room) | [8 empty] | 1
10th Floor Service Floor | [8 empty] | 1
11th Floor | [8 empty] | 1
11th Floor |  | 1 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
11th Floor |  | 2 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
11th Floor |  | 3 |  | 6BHK Duplex with 12th Floor | 3094.481 |  | 0 | 4951.1696
11th Floor |  | 6 |  | 3BHK | 1380.4109 |  | 0 | 2208.6574 |  | 10.764
12th Floor | [8 empty] | 1
12th Floor |  | 1 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
12th Floor |  | 2 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
12th Floor |  | 3 |  | Duplex with 11th Floor
12th Floor |  | 5 |  | 2BHK | 763.0115 |  | 0 | 1220.8184
12th Floor |  | 6 |  | 2BHK | 763.0115 |  | 0 | 1220.8184
13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41th, 44th to 49th & 51st to 54th Floor | [8 empty] | 31 | 5
13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41th, 44th to 49th & 51st to 54th Floor |  | 1 |  | 3BHK | 992.6346 |  | 0 | 1588.2153 |  | 5
13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41th, 44th to 49th & 51st to 54th Floor |  | 2 |  | 3BHK | 992.6346 |  | 0 | 1588.2153 |  | 5
13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41th, 44th to 49th & 51st to 54th Floor |  | 3 |  | 3BHK | 934.833 |  | 0 | 1495.7327 |  | 5
13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41th, 44th to 49th & 51st to 54th Floor |  | 4 |  | 3BHK | 934.833 |  | 0 | 1495.7327 |  | 3
13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41th, 44th to 49th & 51st to 54th Floor |  | 5 |  | 2BHK | 763.0115 |  | 0 | 1220.8184 |  | 23
13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41th, 44th to 49th & 51st to 54th Floor |  | 6 |  | 2BHK | 763.0115 |  | 0 | 1220.8184
Service Floor Inbetween 27th & 28th Floor | [9 empty] | 5
14th, 21st, 28th, 35th & 42nd Floor | [8 empty] | 5
14th, 21st, 28th, 35th & 42nd Floor |  | 1 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
14th, 21st, 28th, 35th & 42nd Floor |  | 2 |  | 4BHK (Duplex with 15th, 22nd, 29th, 36th & 43rd Floor) | 1583.6223 |  | 0 | 2533.7957
14th, 21st, 28th, 35th & 42nd Floor |  | 3 |  | 3BHK | 934.833 |  | 0 | 1495.7327
14th, 21st, 28th, 35th & 42nd Floor |  | 4 |  | 3BHK | 934.833 |  | 0 | 1495.7327
14th, 21st, 28th, 35th & 42nd Floor |  | 5 |  | 2BHK | 763.0115 |  | 0 | 1220.8184
14th, 21st, 28th, 35th & 42nd Floor |  | 6 |  | 2BHK | 763.0115 |  | 0 | 1220.8184
15th, 22nd, 29th, 36th & 43rd Floor For Residential (Part Refuge Area) | [8 empty] | 5
15th, 22nd, 29th, 36th & 43rd Floor For Residential (Part Refuge Area) |  | 1 |  | Refuge Area |  |  |  | 0
15th, 22nd, 29th, 36th & 43rd Floor For Residential (Part Refuge Area) |  | 2 |  | Duplex with 14th, 21st, 28th, 35th & 42nd Floor |  |  |  | 0
15th, 22nd, 29th, 36th & 43rd Floor For Residential (Part Refuge Area) |  | 3 |  | 3BHK | 934.833 |  | 0 | 1495.7327
15th, 22nd, 29th, 36th & 43rd Floor For Residential (Part Refuge Area) |  | 4 |  | 3BHK | 934.833 |  | 0 | 1495.7327
15th, 22nd, 29th, 36th & 43rd Floor For Residential (Part Refuge Area) |  | 5 |  | 2BHK | 763.0115 |  | 0 | 1220.8184
15th, 22nd, 29th, 36th & 43rd Floor For Residential (Part Refuge Area) |  | 6 |  | 2BHK | 763.0115 |  | 0 | 1220.8184
50th Floor (Part Refuge Area) | [8 empty] | 1
50th Floor (Part Refuge Area) |  | 1 |  | Refuge Area |  |  |  | 0
|  | 2 |  | 3BHK | 992.6346 |  | 0 | 1588.2153
|  | 3 |  | 3BHK | 934.833 |  | 0 | 1495.7327
|  | 4 |  | 3BHK | 934.833 |  | 0 | 1495.7327
|  | 5 |  | 2BHK | 763.0115 |  | 0 | 1220.8184
|  | 6 |  | 2BHK | 763.0115 |  | 0 | 1220.8184
E Wing
Basement Floor For Parking, Domestic Tank & Pump Room
Ground Floor For Parking & Substaion
1st Podium Floor For Parking | [8 empty] | 1
2nd Podium Floor For Residential ( Void Lobby Area) | [8 empty] | 1
2nd Podium Floor For Residential ( Void Lobby Area) |  | 1 |  | 3BHK | 928.5457 |  | 0 | 1485.6731 |  | 10.764
|  | 2 |  | 3BHK | 928.5457 |  | 0 | 1485.6731
|  | 3 |  | Void Lobby Area
4
5
6
3rd Podium Floor (Part Parking Area) | [8 empty] | 1
3rd Podium Floor (Part Parking Area) |  | 1 |  | 3BHK | 928.5457 |  | 0 | 1485.6731 |  | 24554.5266
|  | 2 |  | 3BHK | 928.5457 |  | 0 | 1485.6731
|  | 3 |  | 2BHK | 714.5046 |  | 0 | 1143.2074 |  | 22253.1797
|  | 4 |  | Parking Area |  |  |  | 0
|  | 5 |  | Parking Area |  |  |  | 0
|  | 6 |  | 2BHK | 714.5046 |  | 0 | 1143.2074
4th Podium Floor (Part Parking Area) | [8 empty] | 1
4th Podium Floor (Part Parking Area) |  | 1 |  | 3BHK | 928.5457 |  | 0 | 1485.6731
|  | 2 |  | 3BHK | 928.5457 |  | 0 | 1485.6731
|  | 3 |  | 2BHK | 714.5046 |  | 0 | 1143.2074 |  | 22253.1797
|  | 4 |  | Parking Area |  |  |  | 0
|  | 5 |  | Parking Area |  |  |  | 0
|  | 6 |  | 2BHK | 714.5046 |  | 0 | 1143.2074
5th Podium Floor (Part Parking Area) | [8 empty] | 1
5th Podium Floor (Part Parking Area) |  | 1 |  | 3BHK | 928.5457 |  | 0 | 1485.6731
|  | 2 |  | 3BHK | 928.5457 |  | 0 | 1485.6731 | `
|  | 3 |  | 2BHK | 714.5046 |  | 0 | 1143.2074
|  | 4 |  | Parking Area |  |  |  | 0
|  | 5 |  | Parking Area |  |  |  | 0
|  | 6 |  | 2BHK | 714.5046 |  | 0 | 1143.2074
6th Podium Floor (Part Amenity Area) | [8 empty] | 1
6th Podium Floor (Part Amenity Area) |  | 1 |  | 3BHK | 928.5457 |  | 0 | 1485.6731
|  | 2 |  | 3BHK | 928.5457 |  | 0 | 1485.6731
|  | 3 |  | 2BHK | 714.5046 |  | 0 | 1143.2074
|  | 4 |  | Amenity Area |  |  |  | 0
|  | 5 |  | Amenity Area |  |  |  | 0
|  | 6 |  | 2BHK | 714.5046 |  | 0 | 1143.2074
7th Podium Floor (Part Amenity Area) | [8 empty] | 1
7th Podium Floor (Part Amenity Area) |  | 1 |  | 3BHK | 928.5457 |  | 0 | 1485.6731
|  | 2 |  | 3BHK | 928.5457 |  | 0 | 1485.6731
|  | 3 |  | 2BHK | 714.5046 |  | 0 | 1143.2074
|  | 4 |  | Amenity Area |  |  |  | 0
|  | 5 |  | Amenity Area |  |  |  | 0
|  | 6 |  | 2BHK | 714.5046 |  | 0 | 1143.2074
Service Floor In between 7th & 8th Floor
8th & 9th Floor For Amenities ( Yoga, Gym, Zumba & Rooms) | [8 empty] | 2
10th Floor For Service Floor | [8 empty] | 1
11th Floor | [8 empty] | 1
11th Floor |  | 1 |  | 3BHK | 928.5457 | 928.5457 | 0 | 1485.6731
|  | 2 |  | 3BHK | 928.5457 | 928.5457 | 0 | 1485.6731
|  | 3 |  | 3BHK | 1533.9615 | 1533.9615 | 0 | 2454.3384
|  | 6 |  | 4BHK | 1516.3268 | 1516.3268 | 0 | 2426.1229
12th Floor | [8 empty] | 1
12th Floor |  | 1 |  | 3BHK | 928.5457 | 928.5457 | 0 | 1485.6731
|  | 2 |  | 3BHK | 928.5457 | 928.5457 | 0 | 1485.6731
|  | 3 |  | 2BHK | 714.5046 | 714.5046 | 0 | 1143.2074
|  | 4 |  | 2BHK | 714.5046 | 714.5046 | 0 | 1143.2074
|  | 5 |  | 2BHK | 714.5046 | 714.5046 | 0 | 1143.2074
|  | 6 |  | 2BHK | 714.5046 | 714.5046 | 0 | 1143.2074
13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41th, 44th to 49th & 51st to 54th Floor | [8 empty] | 31
13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41th, 44th to 49th & 51st to 54th Floor |  | 1 |  | 3BHK | 928.5457 | 928.5457 | 0 | 1485.6731
|  | 2 |  | 3BHK | 928.5457 | 928.5457 | 0 | 1485.6731
|  | 3 |  | 2BHK | 763.5885 | 763.5885 | 0 | 1221.7416
|  | 4 |  | 2BHK | 763.5885 | 763.5885 | 0 | 1221.7416
|  | 5 |  | 2BHK | 763.5885 | 763.5885 | 0 | 1221.7416
|  | 6 |  | 2BHK | 763.5885 | 763.5885 | 0 | 1221.7416
Service Floor Inbetween 27th & 28th Floor
14th, 21st, 28th, 35th & 42nd Floor | [8 empty] | 5
14th, 21st, 28th, 35th & 42nd Floor |  | 1 |  | 4BHK (Duplex with 15th, 22nd, 29th, 36th & 43rd Floor) | 1543.3843 | 1543.3843 | 0 | 2469.4149
|  | 2 |  | 3BHK | 928.5457 | 928.5457 | 0 | 1485.6731
|  | 3 |  | 2BHK | 763.5885 | 763.5885 | 0 | 1221.7416
|  | 4 |  | 2BHK | 763.5885 | 763.5885 | 0 | 1221.7416
|  | 5 |  | 2BHK | 763.5885 | 763.5885 | 0 | 1221.7416
|  | 6 |  | 2BHK | 763.5885 | 763.5885 | 0 | 1221.7416
15th, 22nd, 29th, 36th & 43rd Floor (Part Refuge Area) | [8 empty] | 5
15th, 22nd, 29th, 36th & 43rd Floor (Part Refuge Area) |  | 1 |  | Duplex with 14th, 21st, 28th, 35th & 42nd Floor
|  | 2 |  | Refuge Area
|  | 3 |  | 2BHK | 763.5885 | 763.5885 | 0 | 1221.7416
|  | 4 |  | 2BHK | 763.5885 | 763.5885 | 0 | 1221.7416
|  | 5 |  | 2BHK | 763.5885 | 763.5885 | 0 | 1221.7416
|  | 6 |  | 2BHK | 763.5885 | 763.5885 | 0 | 1221.7416
50th Floor (Part Refuge Area) | [8 empty] | 1
50th Floor (Part Refuge Area) |  | 1 |  | 3BHK | 1059.7578 | 1543.3843 | 0 | 1695.6124
|  | 2 |  | Refuge Area
|  | 3 |  | 2BHK | 763.5885 | 763.5885 | 0 | 1221.7416
|  | 4 |  | 2BHK | 763.5885 | 763.5885 | 0 | 1221.7416
|  | 5 |  | 2BHK | 763.5885 | 763.5885 | 0 | 1221.7416
|  | 6 |  | 2BHK | 763.5885 | 763.5885 | 0 | 1221.7416
F Wing
Basement Floor For Parking & RW Tank
Ground Floor For Parking
1st Podium Floor For Parking | [8 empty] | 1
2nd Podium Floor For Residential (Part Void Lobby Area) | [8 empty] | 1
2nd Podium Floor For Residential (Part Void Lobby Area) |  | 1 |  | 3BHK | 876.1735 |  | 0 | 1401.8775 |  | 10.764
3rd Podium Floor (Part Parking Area) | [8 empty] | 1
3rd Podium Floor (Part Parking Area) |  | 1 |  | 3BHK | 876.1735 |  | 0 | 1401.8775
|  | 6 |  | 2BHK | 714.5046 |  | 0 | 1143.2074
4th Podium Floor (Part Parking Area) | [8 empty] | 1
4th Podium Floor (Part Parking Area) |  | 1 |  | 3BHK | 876.1735 |  | 0 | 1401.8775
|  | 6 |  | 2BHK | 714.5046 |  | 0 | 1143.2074
5th Podium Floor (Part Parking Area) | [8 empty] | 1
5th Podium Floor (Part Parking Area) |  | 1 |  | 3BHK | 876.1735 |  | 0 | 1401.8775
|  | 6 |  | 2BHK | 714.5046 |  | 0 | 1143.2074
6th Podium Floor (Part Amenity Area) | [8 empty] | 1
6th Podium Floor (Part Amenity Area) |  | 1 |  | 3BHK | 876.1735 |  | 0 | 1401.8775
|  | 6 |  | 2BHK | 714.5046 |  | 0 | 1143.2074
7th Podium Floor (Part Amenity Area) | [8 empty] | 1
7th Podium Floor (Part Amenity Area) |  | 1 |  | 3BHK | 876.1735 |  | 0 | 1401.8775
|  | 6 |  | 2BHK | 714.5046 |  | 0 | 1143.2074
Service Floor Inbetween 7th & 8th Floor
8th & 9th Floor For Amenities (Pantry, Cafe, Banquet Hall, Club, Business Center, Library, Music Room & Pool Area) | [8 empty] | 2
10th Floor For Service Area (Amenities Area Below) | [8 empty] | 1
11th Floor For Residential | [8 empty] | 1
11th Floor For Residential |  | 1 |  | 3BHK | 876.1735 | 876.1735 | 0 | 1401.8775
|  | 2 |  | 3BHK | 876.1735 | 876.1735 | 0 | 1401.8775
|  | 3 |  | 5BHK Duplex with 12th Floor | 3166.8775 | 3166.8775 | 0 | 5067.004
|  | 6 |  | 4BHK | 1516.3268 | 1516.3268 | 0 | 2426.1229
12th Floor | [8 empty] | 1
12th Floor |  | 1 |  | 3BHK | 876.1735 | 876.1735 | 0 | 1401.8775
|  | 2 |  | 3BHK | 876.1735 | 876.1735 | 0 | 1401.8775
|  | 3 |  | Duplex with 11th Floor
|  | 5 |  | 2BHK | 714.5046 | 714.5046 | 0 | 1143.2074
|  | 6 |  | 2BHK | 714.5046 | 714.5046 | 0 | 1143.2074
13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41th, 44th to 49th & 51st to 54th Floor | [8 empty] | 31
13th, 16th to 20th, 23rd to 27th, 30th to 34th, 37th to 41th, 44th to 49th & 51st to 54th Floor |  | 1 |  | 3BHK | 876.1735 | 876.1735 | 0 | 1401.8775
|  | 2 |  | 3BHK | 876.1735 | 876.1735 | 0 | 1401.8775
|  | 3 |  | 3BHK | 819.6409 | 819.6409 | 0 | 1311.4255
|  | 4 |  | 3BHK | 819.6409 | 819.6409 | 0 | 1311.4255
|  | 5 |  | 2BHK | 773.2761 | 773.2761 | 0 | 1237.2417
|  | 6 |  | 2BHK | 773.2761 | 773.2761 | 0 | 1237.2417
Service Floor In between 27th & 28th Floor | [8 empty] | 5
14th, 21st, 28th, 35th & 42nd Floor
14th, 21st, 28th, 35th & 42nd Floor |  | 1 |  | 4BHK (Duplex with 15th, 22nd, 29th, 36th & 43rd Floor) | 1425.6111 | 876.1735 | 0 | 2280.9777
|  | 2 |  | 3BHK | 876.1735 | 876.1735 | 0 | 1401.8775
|  | 3 |  | 3BHK | 819.6409 | 819.6409 | 0 | 1311.4255
|  | 4 |  | 3BHK | 819.6409 | 819.6409 | 0 | 1311.4255
|  | 5 |  | 2BHK | 773.2761 | 773.2761 | 0 | 1237.2417
|  | 6 |  | 2BHK | 773.2761 | 773.2761 | 0 | 1237.2417
15th, 22nd, 29th, 36th & 43rd Floor (Part Refuge Area) | [8 empty] | 5
15th, 22nd, 29th, 36th & 43rd Floor (Part Refuge Area) |  | 1 |  | Duplex with 14th, 21st, 28th, 35th & 42nd Floor
|  | 2 |  | Refuge Area
|  | 3 |  | 3BHK | 819.6409 | 819.6409 | 0 | 1311.4255
|  | 4 |  | 3BHK | 819.6409 | 819.6409 | 0 | 1311.4255
|  | 5 |  | 2BHK | 773.2761 | 773.2761 | 0 | 1237.2417
|  | 6 |  | 2BHK | 773.2761 | 773.2761 | 0 | 1237.2417
50th Floor (Part Refuge Area) | [8 empty] | 1
50th Floor (Part Refuge Area) |  | 1 |  | 3BHK | 876.1735 | 876.1735 | 0 | 1401.8775
|  | 2 |  | Refuge Area
|  | 3 |  | 3BHK | 819.6409 | 819.6409 | 0 | 1311.4255
|  | 4 |  | 3BHK | 819.6409 | 819.6409 | 0 | 1311.4255
|  | 5 |  | 2BHK | 773.2761 | 773.2761 | 0 | 1237.2417
|  | 6 |  | 2BHK | 773.2761 | 773.2761 | 0 | 1237.2417
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Construction work is in process at the time of Visit (labour found). 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + Deck Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. On Site, we meet Ms Sakina CRM. 8. We have updated the revised construction table on dated 21/11/2024, which is shared with us by the Godrej officials. 9. We have updated revised approved plan & CC (on 21/03/2025). 10. Provide latest approved layout plan (dtd 27/02/2023). | [6 empty] | We have updated approved floor plan for Flats of D Wing - 4803, E Wing - 2302 & F wing - 3004 only (on 30/05/2023).
Site & Building/Tower Photographs
Name of the Project |  |  | : | Bellanza Phase 2 ­ Wing D, E, F
Project Site Address |  |  | : | Bellanza Phase 2 ­ Wing D, E, F at The Prestige City, Village. Mulund, Situated Near. Veena Nagar, Road - Agrawal Road, Mulund West, Kurla, Mumbai, Maharashtra - 400080
Site Visit Date & Time |  |  | : | 07/07/2025 @04:00 PM
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr.Nainesh Tambe | Authorized Signatory Name & Signature | :

## Sheet1
2
1
2
2
2
1
1
4
86
44
28
26
26
6
58
22
28
22
24
116
32
84
28
2
2
78
26
43
1
797