## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  |  | : | Godrej Emerald |  | Date of Site Visit |  | 04/07/2025 @ 12:29 PM |  | 2025-04-26 | 2025-07-04
Name of the person met at site & Contact No. |  |  | : | Miss. Shikha - 8657526891. |  | Date of Report Release |  | 07/07/2025 |  |  | 69
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr Suraj Khare
Builder Group Name |  |  | : | M/s.Godrej Properties Ltd. | Developer Name | : | M/s.Godrej Properties Ltd.
Developer Office Address |  |  | : | 5th Floor, Building Name - Godrej One, Street - Pirojshanagar, Locality - Vikhroli East - 400079.
Project Address | : | As per ARF | : | Godrej Emerald, Survey No.91/1/1A, 1/2B, 1/3C, 2A, 2B, 2C, 3A, 3B, 103/1, 2, 3A, 3B, 4, 5/B/1, 5/B/2, 107/7A,7B, 7C, 8A, 8B, 8C, 8D, 11A, 11B & 11C & others, near Lodha Splendora / Rumah Bali, Village - Bhayandarpada, Ghodbunder Road, Thane, Thane (W), Thane, Thane - 400615.
| : | As per Legal Documents | : | Godrej Emerald, Survey No.91/1/1A, 1/2B, 1/3C, 2A, 2B, 2C, 3A, 3B, 103/1, 2, 3A, 3B, 4, 5/B/1, 5/B/2, 107/7A,7B, 7C, 8A, 8B, 8C, 8D, 11A, 11B & 11C & others, near Lodha Splendora / Rumah Bali, Village - Bhayandarpada, Ghodbunder Road, Thane, Thane (W), Thane, Thane - 400615.
| : | As per Actual at site | : | Godrej Emerald,near Lodha Splendora / Rumah Bali, Ghodbunder Road, Thane, Thane (W), Thane, Thane - 400615.
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | :
RERA Registration No. | : | P51700000120 |  |  | RERA Registration Validity | : | 2026-06-30
Project Launch Date | : | 2017-07-05 |  |  | Construction Start Date | : | 2017-07-05
Proposed Date of Completion (As per RERA) | : | 2026-06-30
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 43621.52
FSI/FAR Permissible | : | 1.1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 10250.94 |  |  |  | 1208
Permissible Built up Area (In Sq.Mt) | : | 128119.91 |  |  | Total Number of Units Planned | : | Flats = 1208
Total Number of Units Approved | : | Flats = 424 |  |  | If Mixed, No. of Commercial Units | : | Shop = NA
Latitude | : | 19.2812 |  |  | Longitude | : | 72.9513
Location Link | : | https://goo.gl/maps/hi4steFvPBgbhcH88
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Distance from Railway Station (Km) | : | : 14.6 Km from Thane Railway Station |  |  | Distance from Bus stand (Km) | : | : 14.6 Km from Thane Railway Station
Distance from the nearest School (Km) | : | About 4KM from School |  |  | Distance from Hospital (Km) | : | About 4K form Hospital
Distance from the Main Market (Km) | : | 1. Approx. 2KM from Village Market. 2. Approx. 10KM from Panvel Main Market. |  |  |  | :
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Golibar Road | Road | Rumah Bali |  | Road
As per Site / Actual |  |  | : | Golibar Road | Agri Koli Maidan | Rumah Bali |  | Sitaram mandir
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Tower 1 & 2 |  | Sale |  | LG1 + LG2 + UG + 1P + Upper Stilt + 1st to 30th Floor |  |  | LG1 + LG2 + UG + 1P + Upper Stilt + 1st to 30th Floor
Tower 3 to 7 |  | Sale |  | 2B + G + 1P + 1st to 27th Floor |  |  | 2B + G + 1P + 1st to 27th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | S06/0084/10/TMC/TD-DP/TPS/4447/23 Date: 21/07/2023
CC Details | : | V.P.No.S06/0084/10/TMC/TDD/1902/16 Date: 24/08/2016 Valid Upto: Building No. 3 to 7 = 2B + G + 1P + 1st to 27th Floor |  |  | Approved Plan Details Building No. 1 & 2 | : | S06/0084/10/TMC/TD-DP/TPS/4447/23 Date: 21/07/2023
| : | V.P.No.S06/0084/10/TMC/TDDP/TPS/2502/18 Date: 02/02/2018 Valid Upto: Building No. 1 & 2 = 2B + G + 1P + 1st to 27th Floor |  |  |  | : | Building No. 1 & 2 = LG1 + LG2 + UG + 1P + Upper Stilt + 1st to 30th Floor
| : | S06/0084/10/TMC/TDD/4447/23 Date: 21/07/2023 Valid Upto: Building No. 1 & 2 = 28th to 30th Floor |  |  |  | :
Environmental Clearance Details | : |  |  |  | Airport Authority Clearance Details | :
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
Construction Status
Building No. 1 & 2 = LG1 + LG2 + UG + 1P + Upper Stilt + 1st to 30th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing, Flooring & Fitting upto 29 Floor, Wooden Work upto 28 Floor, Electrical & Sanitary fittings upto 28 Floor, Finishing upto 25 Floor Completed
|  |  |  | 2 | 1 |  | 2 | 30 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 7.5
Excavation |  | 30 |  | 100% | 87.67% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing, Flooring & Fitting upto 29 Floor, Wooden Work upto 28 Floor, Electrical & Sanitary fittings upto 28 Floor, Finishing upto 25 Floor Completed |  | Excavation in process | 15
Plinth |  | 30 |  | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 33 |  | 100% |  |  |  |  | Footing in Process | 7.5
Brickwork |  | 30 |  | 100% |  |  |  |  | Footing Completed | 15
Internal Plaster |  | 30 |  | 100% |  |  |  |  | Basement 1 | 22.5
External Plaster |  | 30 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 30 |  | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 29 |  | 96.67% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 28 |  | 93.33% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 28 |  | 93.33% |  |  |  |  | Plinth completed | 30 |  | #VALUE!
Building Common Amenities |  | 25 |  | 83.33%
Possession |  | 0 |  | 0%
Construction Status
Building No. 2 = LG1 + LG2 + UG + 1P + Upper Stilt + 1st to 30th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 15 Floor, Flooring & Fitting upto 10 Floor, Wooden Work upto 10 Floor, Electrical & Sanitary fittings upto 10 Floor Completed
|  |  |  | 2 | 1 |  | 2 | 30 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 7.5
Excavation |  | 30 |  | 100% | 67.5% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 15 Floor, Flooring & Fitting upto 10 Floor, Wooden Work upto 10 Floor, Electrical & Sanitary fittings upto 10 Floor Completed |  | Excavation in process | 15
Plinth |  | 30 |  | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 33 |  | 100% |  |  |  |  | Footing in Process | 7.5
Brickwork |  | 30 |  | 100% |  |  |  |  | Footing Completed | 15
Internal Plaster |  | 30 |  | 100% |  |  |  |  | Basement 1 | 22.5
External Plaster |  | 30 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 15 |  | 50% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 10 |  | 33.33% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 10 |  | 33.33% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 10 |  | 33.33% |  |  |  |  | Plinth completed | 30 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building No. 3 to 7 = 2B + G + 1P + 1st to 27th Floor |  |  | : | Basement | Ground |  | Podium | Floors | All work completed. Please provide OC.
|  |  |  | 2 | 1 |  | 1 | 27 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 6.75
Excavation |  | 27 |  | 100% | 100% |  | All work completed. Please provide OC. |  | Excavation in process | 13.5
Plinth |  | 27 |  | 100% |  |  |  |  | Excavation Completed | 27
RCC (Including podiums) |  | 29 |  | 100% |  |  |  |  | Footing in Process | 6.75
Brickwork |  | 27 |  | 100% |  |  |  |  | Footing Completed | 13.5
Internal Plaster |  | 27 |  | 100% |  |  |  |  | Basement 1 | 20.25
External Plaster |  | 27 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 27 |  | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 27 |  | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 27 |  | 100% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 27 |  | 100% |  |  |  |  | Plinth completed | 27 |  | #VALUE!
Building Common Amenities |  | 27 |  | 100%
Possession |  | 27 |  | 100%
Project Completion % | [6 empty] | 96.48%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 17,000/-
Car Parking Charges |  |  | : | 500000/- | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 2081.0108
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 7840.9513
Distress Value (Rs. Per sqft) | [5 empty] | : | 1664.8086
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Building No.1 |  | Sale |  | Flats | 183 |  | 162198.3283 | 243297.4924
Building No.2 |  | Sale |  | Flats | 241 |  | 168594.8905 | 252892.3357
Total |  |  |  |  | 424 |  | 330793.2187 | 496189.8281
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
50%
Building no 1
Lower Ground Floor For Parking
Upper Ground Floor For Parking & Residential
Upper Ground Floor For Parking & Residential |  | 1 |  | 3BHK | 947.81 |  | 0 | 1421.715
Upper Ground Floor For Parking & Residential |  | 2 |  | 3BHK | 858.2396 |  | 0 | 1287.3593
Upper Ground Floor For Parking & Residential |  | 3 |  | 3BHK | 872.8194 |  | 0 | 1309.2291
1st Podium Floor For Parking & Residential
1st Podium Floor For Parking & Residential |  | 1 |  | 3BHK | 947.81 |  | 0 | 1421.715
|  | 2 |  | 3BHK | 858.2396 |  | 0 | 1287.3593
|  | 3 |  | 3BHK | 872.8194 |  | 0 | 1309.2291
Upper stilt Floor For Kids Play area, Entrance Lobby & Residential
Upper stilt Floor For Kids Play area, Entrance Lobby & Residential |  | 1 |  | 3BHK | 947.81 |  | 0 | 1421.715
|  | 2 |  | 3BHK | 858.2396 |  | 0 | 1287.3593
|  | 3 |  | 3BHK | 872.8194 |  | 0 | 1309.2291
1st to 4th, 6th to 8th, 10th to 13th, 15th to 18th, 20th to 23rd, 25th to 27th Floor
1st to 4th, 6th to 8th, 10th to 13th, 15th to 18th, 20th to 23rd, 25th to 27th Floor |  | 1 |  | 3BHK | 947.81 |  | 0 | 1421.715 |  | 16112770.4556
|  | 2 |  | 3BHK | 858.2396 |  | 0 | 1287.3593 |  | 14590072.4112
|  | 3 |  | 3BHK | 872.8194 |  | 0 | 1309.2291 |  | 14837929.6572
|  | 4 |  | 3BHK | 867.6957 |  | 0 | 1301.5436 |  | 14750827.3692
|  | 5 |  | 3BHK | 859.2568 |  | 0 | 1288.8851 |  | 14607364.7772
|  | 6 |  | 3BHK | 930.8244 |  | 0 | 1396.2367 |  | 15824015.3916
5th, 9th, 14th, 19th & 24th Floor (Part Refuge Area)
5th, 9th, 14th, 19th & 24th Floor (Part Refuge Area) |  | 1 |  | 3BHK | 947.81 |  | 0 | 1421.715
|  | 2 |  | 3BHK | 858.2396 |  | 0 | 1287.3593
|  | 3 |  | Refuge Area
|  | 4 |  | 3BHK | 867.6957 |  | 0 | 1301.5436
|  | 5 |  | 3BHK | 859.2568 |  | 0 | 1288.8851
|  | 6 |  | 3BHK | 930.8244 |  | 0 | 1396.2367
28th Floor
28th Floor |  | 1 |  | 3BHK | 947.81 |  | 0 | 1421.715
|  | 2 |  | 3BHK | 858.2396 |  | 0 | 1287.3593
|  | 3 |  | 3BHK | 872.8194 |  | 0 | 1309.2291
|  | 4 |  | 3BHK | 867.6957 |  | 0 | 1301.5436
|  | 5 |  | 3BHK | 859.2568 |  | 0 | 1288.8851
|  | 6 |  | 3BHK | 930.8244 |  | 0 | 1396.2367
29th Floor (Part Refuge Area)
29th Floor (Part Refuge Area) |  | 1 |  | 3BHK | 947.81 |  | 0 | 1421.715
|  | 2 |  | 3BHK | 858.2396 |  | 0 | 1287.3593
|  | 3 |  | Refuge Area
|  | 4 |  | 3BHK | 867.6957 |  | 0 | 1301.5436
|  | 5 |  | 3BHK | 859.2568 |  | 0 | 1288.8851
|  | 6 |  | 3BHK | 930.8244 |  | 0 | 1396.2367
30th Floor (Part Terrace Area)
30th Floor (Part Terrace Area) |  | 1 |  | 3BHK | 935.1763 |  | 0 | 1402.7645
|  | 2 |  | 2BHK | 687.9272 |  | 0 | 1031.8909
|  | 3 |  | 2BHK | 701.4899 |  | 0 | 1052.2348
|  | 4 |  | 2BHK | 705.7955 |  | 0 | 1058.6932
|  | 5 |  | 2BHK | 689.2189 |  | 0 | 1033.8284
|  | 6 |  | 3BHK | 916.2991 |  | 0 | 1374.4487
Building no 2
Lower Ground Floor For Parking
Upper Ground Floor For Parking & Residential
Upper Ground Floor For Parking & Residential |  | 1 |  | 2BHK | 750.6921 |  | 0 | 1126.0382 |  | 720.7574
Upper Ground Floor For Parking & Residential |  | 2 |  | 2BHK | 653.4663 |  | 0 | 980.1994
Upper Ground Floor For Parking & Residential |  | 3 |  | 2BHK | 653.4663 |  | 0 | 980.1994
Upper Ground Floor For Parking & Residential |  | 4 |  | 2BHK | 750.6921 |  | 0 | 1126.0382
1st Podium Floor For Parking & Residential
1st Podium Floor For Parking & Residential |  | 1 |  | 2BHK | 750.6921 |  | 0 | 1126.0382
|  | 2 |  | 2BHK | 653.4663 |  | 0 | 980.1994
|  | 3 |  | 2BHK | 653.4663 |  | 0 | 980.1994
|  | 4 |  | 2BHK | 750.6921 |  | 0 | 1126.0382
Upper stilt Floor For Kids Play area, Entrance Lobby & Residential
Upper stilt Floor For Kids Play area, Entrance Lobby & Residential |  | 1 |  | 2BHK | 750.6921 |  | 0 | 1126.0382
|  | 2 |  | 2BHK | 653.4663 |  | 0 | 980.1994
|  | 3 |  | 2BHK | 653.4663 |  | 0 | 980.1994
|  | 4 |  | 2BHK | 750.6921 |  | 0 | 1126.0382
1st floor For Residential
1st floor For Residential |  | 1 |  | 2BHK | 750.6921 |  | 0 | 1126.0382
|  | 2 |  | 2BHK | 653.4663 |  | 0 | 980.1994
|  | 3 |  | 2BHK | 653.4663 |  | 0 | 980.1994
|  | 4 |  | 2BHK | 750.6921 |  | 0 | 1126.0382
|  | 5 |  | 2BHK | 747.6405 |  | 0 | 1121.4608
|  | 6 |  | 2BHK | 650.4147 |  | 0 | 975.622
|  | 7 |  | 2BHK | 650.4147 |  | 0 | 975.622
|  | 8 |  | 2BHK | 747.6405 |  | 0 | 1121.4608
2nd to 4th, 6th to 8th, 10th to 13th, 15th to 18th, 20th to 23rd, 25th to 27th Floor
2nd to 4th, 6th to 8th, 10th to 13th, 15th to 18th, 20th to 23rd, 25th to 27th Floor |  | 1 |  | 2BHK | 750.6921 |  | 0 | 1126.0382
|  | 2 |  | 2BHK | 653.4663 |  | 0 | 980.1994
|  | 3 |  | 2BHK | 653.4663 |  | 0 | 980.1994
|  | 4 |  | 2BHK | 750.6921 |  | 0 | 1126.0382
|  | 5 |  | 2BHK | 747.6405 |  | 0 | 1121.4608
|  | 6 |  | 2BHK | 650.4147 |  | 0 | 975.622
|  | 7 |  | 2BHK | 650.4147 |  | 0 | 975.622
|  | 8 |  | 2BHK | 747.6405 |  | 0 | 1121.4608
5th, 9th, 14th, 19th & 24 floor For Residential (Part Refuge Area)
5th, 9th, 14th, 19th & 24 floor For Residential (Part Refuge Area) |  | 1 |  | Refuge Area
2
|  | 3 |  | 2BHK | 653.4663 |  | 0 | 980.1994
|  | 4 |  | 2BHK | 750.6921 |  | 0 | 1126.0382
|  | 5 |  | 2BHK | 747.6405 |  | 0 | 1121.4608
|  | 6 |  | 2BHK | 650.4147 |  | 0 | 975.622
|  | 7 |  | 2BHK | 650.4147 |  | 0 | 975.622
|  | 8 |  | 2BHK | 747.6405 |  | 0 | 1121.4608
28th & 30th Floor
28th & 30th Floor |  | 1 |  | 2BHK | 720.7574 |  | 0 | 1081.1362
|  | 2 |  | 2BHK | 656.2811 |  | 0 | 984.4216
|  | 3 |  | 2BHK | 656.2811 |  | 0 | 984.4216
|  | 4 |  | 2BHK | 724.0943 |  | 0 | 1086.1414
|  | 5 |  | 2BHK | 720.9727 |  | 0 | 1081.4591
|  | 6 |  | 2BHK | 667.2604 |  | 0 | 1000.8905
|  | 7 |  | 2BHK | 667.2604 |  | 0 | 1000.8905
|  | 8 |  | 2BHK | 717.7435 |  | 0 | 1076.6153
29th Floor (Part Refuge Area)
29th Floor (Part Refuge Area) |  | 1 |  | Refuge Area
|  | 2 |  | 2BHK | 656.2811 |  | 0 | 984.4216
|  | 3 |  | 2BHK | 656.2811 |  | 0 | 984.4216
|  | 4 |  | 2BHK | 724.0943 |  | 0 | 1086.1414
|  | 5 |  | 2BHK | 720.9727 |  | 0 | 1081.4591
|  | 6 |  | 2BHK | 667.2604 |  | 0 | 1000.8905
|  | 7 |  | 2BHK | 667.2604 |  | 0 | 1000.8905
|  | 8 |  | 2BHK | 717.7435 |  | 0 | 1076.6153
Project Specific Remarks & Observation
Remarks / Observations | : | 1.Building No. 1 & 2 = Finishing work is in process at the time of Visit. Internal visit was not allowed. Building No. 3 to 7 = All work completed. Please provide OC. 2. We have considered rate by verifying it from market inquire. 3. Car parking is subjected to authentic documentation. 4. We have updated revised approved floor plan & C.C For Building No. 1 & Building No. 2 (on 25/08/2023). 4. On Site, we meet Mr. Shikha - 8657526891
Site & Building/Tower Photographs
Name of the Project |  |  | : | Godrej Emerald
Project Site Address |  |  | : | Godrej Emerald, Survey No.91/1/1A, 1/2B, 1/3C, 2A, 2B, 2C, 3A, 3B, 103/1, 2, 3A, 3B, 4, 5/B/1, 5/B/2, 107/7A,7B, 7C, 8A, 8B, 8C, 8D, 11A, 11B & 11C & others, near Lodha Splendora / Rumah Bali, Village - Bhayandarpada, Ghodbunder Road, Thane, Thane (W), Thane, Thane - 400615.
Site Visit Date & Time |  |  | : | 04/07/2025 @ 12:29 PM
Layout Plan
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Ajay | Authorized Signatory Name & Signature | :
Tower 1 & 2
Tower 3, 4 & 5
Tower
6 & 7