## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  |  | : | Godrej Five Gardens |  | Date & Time of Site Visit |  | 03/07/2025 @02:05PM
Name of the person met at site & Contact No. |  |  | : | NA |  | Date of Report Release |  | 04/07/2025
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Ms. Ankita Mohite
Builder Group Name |  |  | : | Godrej Projects Development Ltd. | Developer Name | : | Godrej Projects Development Ltd.
Developer Office Address |  |  | : | Unit No- 5C, 5th Floor, Godrej One, GODREJ ONE, Unit No. 5C, 5th Floor, Pirojshanagar, Vikhroli, Mumbai, Maharashtra 400079.
Project Address | : | As per ARF | : | Godrej Five Gardens, Plot No.: 691/10 ,698/10 ,699/10 at Fnorth­400019, Ward FNorth, Mumbai City, 400019 |  |  |  |  | initiation
| : | As per Legal Documents | : | Godrej Five Gardens, Proposed Redevelopment of Agrawal Nagar, Bearing CTS No.691/10,698/10 & 699/10 at Fnorth, Dr.Babasaheb Ambedkar Road, Matunga East, Near M19 Central, Dadar, Mumbai- 400019.
| : | As per Actual at site | : | Agarwal Nagar, Dr Baba Saheb Ambedkar Road, Matunga East, Mumbai, Maharashtra 400019
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Municipal Corporation of Greater Mumbai
RERA Registration No. | : | P51900048424 |  |  | RERA Registration Validity | : | 2028-12-31
Project Launch Date | : | 2023-01-03 |  |  | Construction Start Date | : | 2023-01-03
Proposed Date of Completion (As per RERA) | : | 2028-12-31 |  |  | Developer Bank Name (As per RERA) | : | Axis Bank UTIB0004702
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 5634.68
FSI/FAR Permissible | : | 3 |  |  | Proposed Built up Area (In Sq.Mt) | : | 17320.18
Permissible Built up Area (In Sq.Mt) | : | 17320.18 |  |  | Total Number of Units Planned | : | As per RERA Site Flats = 77
Total Number of Units Approved | : | Flats = 77 |  |  | If Mixed, No. of Commercial Units | : | -
Latitude, Longitude | : | 19.0190831, 72.8523168 |  |  |  | :
Location Link | : | https://goo.gl/maps/iA5SejgEhAdLgTvQ9?coh=178572&entry=tt
Extra Amenities available | : | Indoor Games, Sky Gym, Creative Corner, Work From Garden, Senior Citizen Seating, Pet Park, Jogging Track, Multipurpose Play Court, Fitness Center & Pool Deck
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle/Upper
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 0.950 KM from Matunga East Bus Stop
Distance from the nearest School (Km) | : | About 0.950KM from St. Joseph's High School |  |  | Distance from Hospital (Km) | : | About 1.3K form Don Bosco Muncipal Hospital
Distance from the Main Market (Km) | : | 1. Approx. 1Km from Matunga Market. 2. Approx. 2.4KM from Gandhi Market. |  |  | Distance from Railway Station (Km) | : | 1.1KM from Matunga Railway Station 1.4KM from Wadala Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Dr Baba Saheb Ambedkar Road | Jame Jamshed Road | Building |  | Building
As per Site / Actual |  |  | : | Mittal Gardenia | Pragati Paradise | Jame Jamshed Road |  | Dr Baba Saheb Ambedkar Road
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Wing B |  | Sale |  | Wing B = Gr + 1st to 33rd Floor |  |  | Wing B = Gr + 1st to 33rd Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | P-6671/2021/(691/10 And Other) /F/ North/ MATUNGA/337/1/New Date: 18/04/2023
CC Details | : | P-6671/2021/(691/10 And Other)/F/North/MATUNGA/FCC/1/New Date: 03/07/2024 Valid Upto Date: 18/12/2024 This Further C. C. IS ISSUED UPTO TOP OF 34th FLOOR FOR WING ‘A’ (REHAB WING) INCLUDING OHT & LIFT MACHINE ROOM AND UPTO TOP OF 29th FLOOR FOR Wing ‘B’ (Sale Wing) As Per Last Approved Plan Dated. 19.04.2023 Subject To Taking All Precautions During Construction In Regards Of Air Polution Guidlines Issued U/No. Mgc/F/1102 Dtd. 25.10.2023 And D.O.NO. CAP-2023/CR-170/TC-2 DTD. 27.10.2023. |  |  | Approved Plan Details | : | P-6671/2021/(691/10 And Other) /F/ North/ MATUNGA/337/1/New Date: 18/04/2023
Environmental Clearance Details | : | Date: |  |  | Airport Authority Clearance Details | : | Date:
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
Construction Status
Wing B = Gr + 1st to 33rd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 10 Slab, Brickwork upto 9 Floor, Internal Plaster upto 7.2 Floor, External Plaster upto 7.2 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 33 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8.25
Excavation |  | 33 |  | 100% | 34.81% |  | Excavation work Completed. Plinth work completed, RCC upto 10 Slab, Brickwork upto 9 Floor, Internal Plaster upto 7.2 Floor, External Plaster upto 7.2 Floor Completed |  | Excavation in process | 16.5
Plinth |  | 33 |  | 100% |  |  |  |  | Excavation Completed | 33
RCC (Including podiums) |  | 10 |  | 29.41% |  |  |  |  | Footing in Process | 6.6
Brickwork |  | 9 |  | 27.27% |  |  |  |  | Footing Completed | 13.2
Internal Plaster |  | 7.2 |  | 21.82% |  |  |  |  | Basement 1 | 0
External Plaster |  | 7.2 |  | 21.82% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 23.1
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 33
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 34.81%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 74,000 to 76,000 | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  |  | : | 1500000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 11119.4723
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 25954.1063
Distress Value (Rs. Per sqft) | [5 empty] | : | 8895.5779
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Wing B |  | Sale |  | Flats | 77 |  | 104405.418 | 161828.3979
Total |  | 0 |  | 0 | 77 |  | 104405.418 | 161828.3979
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
55%
Wing B
Basement Floor For Tanks
Ground Floor For Entrance Lobby & Meter Room | [8 empty] | 1st & 2nd
Service Floor In between Ground Floor & 3rd Floor | [9 empty] | 10.764
3rd Floor For Residential
3rd Floor For Residential |  | 1 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666 |  | 127.7956
|  | 2 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
4th Floor
4th Floor |  | 1 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
4th Floor |  | 2 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
5th Floor
5th Floor |  | 1 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
5th Floor |  | 2 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
6th Floor
6th Floor |  | 1 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
6th Floor |  | 2 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
7th Floor (Part Refuge area)
7th Floor (Part Refuge area) |  | 1 |  | Society Office & Refuge Area
7th Floor (Part Refuge area) |  | 2 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
8th Floor
8th Floor |  | 1 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
8th Floor |  | 2 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
9th Floor
9th Floor |  | 1 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
9th Floor |  | 2 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
10th & 11th Floor
10th & 11th Floor |  | 1 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
10th & 11th Floor |  | 2 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
12th, 13th, 15th to 20th, 22nd to 26th & 29th to 32nd Floor
12th, 13th, 15th to 20th, 22nd to 26th & 29th to 32nd Floor |  | 1 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
|  | 2 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
|  | 3 |  | 3BHK | 1282.423 |  | 0 | 1987.7556
14th & 21st Floor (Part Refuge Area)
14th & 21st Floor (Part Refuge Area) |  | 1 |  | Society Office & Refuge Area
|  | 2 |  | 3BHK | 1408.0388 |  | 0 | 2182.4602
|  | 3 |  | 3BHK | 1282.423 |  | 0 | 1987.7556 |  | 119.17
27th Floor
27th Floor |  | 1 |  | 4BHK Duplex with 28th floor | 1994.8921 |  | 0 | 3092.0828
|  | 2 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
|  | 3 |  | 3BHK | 1282.423 |  | 0 | 1987.7556
28th Floor (Part Refuge Area)
28th Floor (Part Refuge Area) |  | 1 |  | Duplex with 27th floor & Refuge Area
|  | 2 |  | 3BHK | 1371.0107 |  | 0 | 2125.0666
|  | 3 |  | 3BHK | 1282.423 |  | 0 | 1987.7556
33rd Floor For Fitness Center & Pool Deck
1st Floor
1st Floor |  | 101 | [5 empty] | 0
1st Floor |  | 102 | [5 empty] | 0
1st Floor |  | 103 | [5 empty] | 0
1st Floor |  | 104 | [5 empty] | 0
1st Floor |  | 105 | [5 empty] | 0
1st Floor |  | 106 | [5 empty] | 0
1st Floor |  | 107 | [5 empty] | 0
1st Floor |  | 108 | [5 empty] | 0
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 201,..,901 | [5 empty] | 0 |  |  | 201,..,901 | 201 | 901
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 202,..,902 | [5 empty] | 0 |  |  | 202,..,902 | 202 | 902
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 203,..,903 | [5 empty] | 0 |  |  | 203,..,903 | 203 | 903
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 204,..,904 | [5 empty] | 0 |  |  | 204,..,904 | 204 | 904
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 205,..,905 | [5 empty] | 0 |  |  | 205,..,905 | 205 | 905
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 206,..,906 | [5 empty] | 0 |  |  | 206,..,906 | 206 | 906
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 207,..,907 | [5 empty] | 0 |  |  | 207,..,907 | 207 | 907
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 208,..,908 | [5 empty] | 0 |  |  | 208,..,908 | 208 | 908
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 209,..,909 | [5 empty] | 0 |  |  | 209,..,909 | 209 | 909
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 210,..,910 | [5 empty] | 0 |  |  | 210,..,910 | 210 | 910
2nd to 5th Floor
2nd to 5th Floor |  | 201 to 501 | [5 empty] | 0 |  |  | 201 to 501 | 201 | 501
2nd to 5th Floor |  | 202 to 502 | [5 empty] | 0 |  |  | 202 to 502 | 202 | 502
2nd to 5th Floor |  | 203 to 503 | [5 empty] | 0 |  |  | 203 to 503 | 203 | 503
2nd to 5th Floor |  | 204 to 504 | [5 empty] | 0 |  |  | 204 to 504 | 204 | 504
2nd to 5th Floor |  | 205 to 505 | [5 empty] | 0 |  |  | 205 to 505 | 205 | 505
2nd to 5th Floor |  | 206 to 506 | [5 empty] | 0 |  |  | 206 to 506 | 206 | 506
2nd to 5th Floor |  | 207 to 507 | [5 empty] | 0 |  |  | 207 to 507 | 207 | 507
2nd to 5th Floor |  | 208 to 508 | [5 empty] | 0 |  |  | 208 to 508 | 208 | 508
2nd to 5th Floor |  | 209 to 509 | [5 empty] | 0 |  |  | 209 to 509 | 209 | 509
2nd to 5th Floor |  | 210 to 510 | [5 empty] | 0 |  |  | 210 to 510 | 210 | 510
2nd & 5th Floor
2nd & 5th Floor |  | 201 & 501 | [5 empty] | 0 |  |  | 201 & 501 | 201 | 501
2nd & 5th Floor |  | 202 & 502 | [5 empty] | 0 |  |  | 202 & 502 | 202 | 502
2nd & 5th Floor |  | 203 & 503 | [5 empty] | 0 |  |  | 203 & 503 | 203 | 503
2nd & 5th Floor |  | 204 & 504 | [5 empty] | 0 |  |  | 204 & 504 | 204 | 504
2nd & 5th Floor |  | 205 & 505 | [5 empty] | 0 |  |  | 205 & 505 | 205 | 505
2nd & 5th Floor |  | 206 & 506 | [5 empty] | 0 |  |  | 206 & 506 | 206 | 506
2nd & 5th Floor |  | 207 & 507 | [5 empty] | 0 |  |  | 207 & 507 | 207 | 507
2nd & 5th Floor |  | 208 & 508 | [5 empty] | 0 |  |  | 208 & 508 | 208 | 508
2nd & 5th Floor |  | 209 & 509 | [5 empty] | 0 |  |  | 209 & 509 | 209 | 509
2nd & 5th Floor |  | 210 & 510 | [5 empty] | 0 |  |  | 210 & 510 | 210 | 510
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Construction work in process. Internal Visit not allowed. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Deck area + Utility Area + Servant Room. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. Every 3BHK flat consist of individual Servant Room. 8. We have updated Approved CC (On 06/02/2025). 9. Validity of CC is expired on 18/12/2024. Please provide latest CC. 7. On Site, we meet Mr........(........).
Site & Building/Tower Photographs
Name of the Project |  |  | : | Godrej Five Gardens
Project Site Address |  |  | : | Godrej Five Gardens, Plot No.: 691/10 ,698/10 ,699/10 at Fnorth­400019, Ward FNorth, Mumbai City, 400019
Site Visit Date & Time |  |  | : | 03/07/2025 @02:05PM
Layout
Existing Layout Plan
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Karan Misal | Authorized Signatory Name & Signature | :
Wing B
Wing B
Wing A
Note on H6: Rushil Sanghvi or Fahad
Note on E9: Initiation Address
Note on E10: Initiation Address
Note on E11: Map Address
Note on C17: Maybe same as RERA Registration Validity or different
Note on H17: From Rera
Note on H20: From RERA
Note on A39: As per Layout
Note on H78: Ready Recknor