## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02 | 2025-04-28 | 2025-07-26
Project Name |  |  | : | Godrej Reserve Wing 1 to 5 |  | Date & Time of Site Visit |  | 26/07/2025 @ 02:00PM |  | 89
Name of the person met at site & Contact No. |  |  | : | Mr. Harsh - 8082092003 |  | Date of Report Release |  | 30/07/2025 | Mr. Aakash 8655887352 |  | Mr. Sachin Shewale CRM 9324555766
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | Godrej Properties Limited | Developer Name | : | Godrej Properties Limited
Developer Office Address |  |  | : | Godrej one
Project Address | : | As per ARF | : | Godrej Reserve, Plot Bearing / CTS / Survey / Final Plot No.: 124, 125, 126, 127, 127/1, 128, 146, 146/1, 146/2, 146/3, 146/4, 146/5, 146/6, 146/7 at Akurli, Borivali, Mumbai Suburban, 400101
| : | As per Legal Documents | : | Godrej Reserve Wing 1, 2, 3, 4 & 5, CTS No.124, 125, 126, 127, 127/1, 128, 146, 146/1 to 7, near E.S.I.S. Hospital, Akurli Road, Ashok Nagar, Akurli, Kandivali East, Borivali, Mumbai - 400101.
| : | As per Actual at site | : | Godrej Reserve Wing 1, 2, 3, 4 & 5, CTS No.124, 125, 126, 127, 127/1, 128, 146, 146/1 to 7, near E.S.I.S. Hospital, Akurli Road, Ashok Nagar, Akurli, Kandivali East, Borivali, Mumbai - 400101.
Documents Provided by GHF |  |  | : | Approved Plans, CC, Airport Noc, Fire Noc & RERA certificate.
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Municipal Corporation of Greater Mumbai (MCGM)
RERA Registration No. | : | Wing 1 = P51800054703 Wing 2 = P51800079457 Wing 3 = P51800055694 Wing 4 = P51800054691 Wing 5 = P51800054690 |  |  | RERA Registration Validity | : | 2030-06-30
Project Launch Date | : | 2024-02-06 |  |  | Construction Start Date | : | 2024-03-01
Proposed Date of Completion (As per RERA) | : | 2030-06-30 |  |  | Developer Bank Name (As per RERA) | : | Axis Bank IFSC Code = UTIB0000004
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Net Plot Area (In Sq.Mt) | : | 46149.87
FSI/FAR Permissible | : | 2.21 |  |  | Proposed Built up Area (In Sq.Mt) | : | 214252.84
Permissible Built up Area (In Sq.Mt) | : | 132952.91 |  |  | Total Number of Units Planned | : | As per RERA Site Flats = 1584 |  | 1105
Total Number of Units Approved | : | Flats = 1584 |  |  | If Mixed, No. of Commercial Units | : | Shop = 00
Latitude, Longitude | : | 19.200726,72.859308 |  |  | Landmark | : | E.S.I.S. Hospital
Location Link | : | https://maps.app.goo.gl/vPaBTHPxXKJ55ULV9
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Lawn, Zen Garden, Jogging Track, Senior Citizen's Area, Outdoor Activity Lawn, Swimming Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Yoga/Aerobics Room, Indoor games, etc
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 27.45 M
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 200M from Sambhaji Nagar Bus Stop
Distance from the nearest School (Km) | : | About 750M from Pioneer Public School |  |  | Distance from Hospital (Km) | : | About 550M form E.S.I.S. Hospital
Distance from the Main Market (Km) | : | 1. Approx. 550M from Kandivali Local Market. 2. Approx. 850M from Growel's 101 Mall |  |  | Distance from Railway Station (Km) | : | 800M from Kandivali Railway Station 900M from Akurli Metro Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | 27.45 M. Wide Akurli Road | Other Plot | Sub Plot E, G/Western Express Highway |  | Sub Plot B & C/Other Plot
As per Site / Actual |  |  | : | Akurli road | Arkade Group/ Children's Academy, Ashok Nagar | Open Plot/Western Express Highway |  | Nagwekar Apartments No. 2/Ashok Chakravarti Road
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Wing 1 |  | Sale |  | LG + UG + P1 + 2nd to 7th Podium/Pt Resi. + 8th Podium Top/Pt Resi. + 1 Service Floor + 9th to 52nd Floor |  |  | LG + UG + P1 + 2nd to 7th Podium/Pt Resi. + 8th Podium Top/Pt Resi. + 1 Service Floor + 9th to 52nd Floor
Wing 2 |  | Sale |  | LG + UG + P1 + 2nd to 6th Podium/Pt Resi. + 7th Podium Top/Pt Resi. + 8th Service Floor + 9th to 52nd Floor |  |  | LG + UG + P1 + 2nd to 6th Podium/Pt Resi. + 7th Podium Top/Pt Resi. + 8th Service Floor + 9th to 44th Floor |  |  | LG + UG + P1 + 2nd to 6th Podium/Pt Resi. + 7th Podium Top/Pt Resi. + 8th Service Floor + 9th to 44th Floor
Wing 3 |  | Sale |  | LG + UG + P1 + 2nd to 7th Podium/Pt Resi. + 8th Podium Top/Pt Resi. + 1 Service Floor + 9th to 52nd Floor |  |  | LG + UG + P1 + 2nd to 7th Podium/Pt Resi. + 8th Podium Top/Pt Resi. + 1 Service Floor + 9th to 51st Floor
Wing 4 |  | Sale |  | LG + UG + P1 + 2nd to 7th Podium/Pt Resi. + 8th Podium Top/Pt Resi. + 1 Service Floor + 9th to 52nd Floor |  |  | LG + UG + P1 + 2nd to 7th Podium/Pt Resi. + 8th Podium Top/Pt Resi. + 1 Service Floor + 9th to 51st Floor
Wing 5 |  | Sale |  | LG + UG + P1 + 2nd to 7th Podium/Pt Resi. + 8th Podium Top/Pt Resi. + 1 Service Floor + 9th to 52nd Floor |  |  | LG + UG + P1 + 2nd to 7th Podium/Pt Resi. + 8th Podium Top/Pt Resi. + 1 Service Floor + 9th to 51st Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | P-17708/2023/(124 AND OTHER)/R/SWARD/AKURLIR/S/337/4/AMEND Date: 24/02/2025 | [7 empty] | P-17708/2023/(124 AND OTHER)/R/S WARD/AKURLIR/S/337/4/AMEND
Approved Plan Details Wing 1, 3, 4, 5 | : | P-17708/2023/(124 And Other)/R/S Ward/AKURLI-R/S/337/3/Amend Date: 22/10/2024
Approved Plan Details Wing 2 | : | P-17708/2023/(124 AND OTHER)/R/SWARD/AKURLIR/S/337/4/AMEND Date: 24/02/2025
CC Details | : | P-17708/2023/(124 And Other)/R/S Ward/AKURLI-R/S/FCC/1/New Date: 26/03/2025 Date Valid Up to: 25/03/2026 Valid Up to: This C.C. is extended further for Wing 1 comprising of Lower Ground + Upper Ground + 1st Podium + 2nd to 6th podiums for part Parking and part residential + 7th top podium part for residential and part for Amenity + 8th service floor + 9th to 52nd upper residential floors + LMR & OHT, Wing 3 & 4 comprising of Upper Ground + 1st Podium + 2nd to 6th podiums for part Parking and part residential + 7th top podium part for residential and part for Amenity + 8th service floor + 9th to 51st upper residential floors + LMR & OHT, Wing 5 comprising of Upper Ground + 1st Podium + 2nd to 6th podiums for part Parking and part residential + 7th top podium part for residential and part for Amenity + 8th service floor + 9th to 25th upper residential floors and re-endorsed for Retail & Wing 2 up to Plinth level as per approved amended plans dated 24.02.2025.
CC Details | : | P-17708/2023/(124 And Other)/R/S Ward/AKURLI-R/S/FCC/1/Amend Date: 06/06/2025 Date Valid Up to: 05/06/2026 Valid Up to: This C.C. is extended further for Wing No. 2, 4 & 5 comprising of Upper Ground + 1st Podium + 2nd to 6th podiums for part Parking and part residential + 7th top podium part for residential and part for Amenity + 8th service floor + 9th to 35th upper floors and re-endorsement C.C for Retail Portion (i.e. up to Lower Ground + Top slab of Upper Ground), Wing 1 up to 52nd floors (Terrace, to the top of OHT and LMR) and Wing No. 3, up to 51st floors, (Terrace, to the top of OHT and LMR),) as per approved amended plans dated. 24.02.2025.
CC Details | : | P-17708/2023/(124 And Other)/R/S Ward/AKURLI-R/S/FCC/2/Amend Date: 07/07/2025 Date Valid Up to: 24/01/2026 Valid Up to: This C.C. is extended further for Wing no 2 comprising of Upper Ground + 1st Podium + 2nd to 6th podiums forpart Parking and part residential + 7th top podium part for residential and part for Amenity + 8th service floor + 9th to 28th upper floors & CC for Retail Portion (i.e. up to Lower Ground + Top slab of Upper Ground) and Wing 4 & 5 comprising of Upper Ground + 1st Podium + 2nd to 6th podiums for part Parking and part residential + 7th top podium part for residential and part for Amenity + 8th service floor + 9th to 27th upper residential floors and re-endorsement C.C for Wing 1 up to 52nd floors (Terrace, to the top of OHT and LMR) and Wing No. 3, up to 51st floors, (Terrace, to the top of OHT and LMR),)as per approved amended plans dated. 24.02.2025.
Fire NOC Details | : | P-17708/2023/(124 And Other)/R/ S Ward/AKURLI-R/S-CFO/1/New Date: 03/11/2023 Valid Upto: Wing ‘1’ to ‘6’. Each wing having common lower ground floor part on stilt + upper ground floor part on stilt + 1st to 8thpodium floors with part residential floors + Service floor. Wing ‘1’ to ‘5’ are having 1st to 52nd upper residential floors with a total height of 166.40 mtrs. |  |  |  | :
Airport Authority Clearance Details | : | JUHU/WEST/B/071323/769164 Date: 07/08/2023 Valid Upto : Permissible Top Elevation in mtrs Above Mean Sea Level(ASML) = 211.02 M(Required) Valid Upto Date: 06/08/2023
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | : | -
Construction Status
Wing 4= LG + UG + P1 + 2nd to 7th Podium/Pt Resi. + 8th Podium Top/Pt Resi. + 1 Service Floor + 9th to 52nd Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Work not yet Started.
|  |  |  | 3 | 1 |  | 0 | 52 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13
Excavation |  | 0 |  | 0% | 0% |  | Work not yet Started. |  | Excavation in process | 26
Plinth |  | 0 |  | 0% |  |  |  |  | Excavation Completed | 52
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 10.4
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 20.8
Door & Window Frames |  | 0 |  | 0% |  |  |  |  | Basement 1 | 31.2
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 41.6
Ext.Plaster |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Plumb.& Electri. |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Painting |  | 0 |  | 0% |  |  |  |  | Plinth completed | 52
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status | [8 empty] | table updated 18/11/2024
Wing 1 & 3 = LG + UG + 1st Podium + 2nd to 7th Podium/Pt Resi. + 8th Podium Top/Pt Resi. + 1 Service Floor + 9th to 52nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed
|  |  |  | 1 | 1 |  | 0 | 52 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13
Excavation |  | 52 |  | 100% | 25.94% |  | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed |  | Excavation in process | 26
Plinth |  | 52 |  | 100% |  |  |  |  | Excavation Completed | 52
RCC (Including podiums) |  | 2 |  | 3.774% |  |  |  |  | Footing in Process | 13
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 26
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 39
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 52
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Wing 2 = LG + UG + 1st Podium + 2nd to 7th Podium/Pt Resi. + 8th Podium Top/Pt Resi. + 1 Service Floor + 9th to 52nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 1 | 1 |  | 0 | 52 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13
Excavation |  | 52 |  | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 26
Plinth |  | 52 |  | 100% |  |  |  |  | Excavation Completed | 52
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 13
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 26
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 39
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 52
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status | [8 empty] | table updated 18/11/2024
Wing 4 = LG + UG + 1st Podium + 2nd to 7th Podium/Pt Resi. + 8th Podium Top/Pt Resi. + 1 Service Floor + 9th to 52nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 1 | 1 |  | 0 | 52 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13
Excavation |  | 52 |  | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 26
Plinth |  | 52 |  | 100% |  |  |  |  | Excavation Completed | 52
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 13
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 26
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 39
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 52
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status | [8 empty] | table updated 18/11/2024
Wing 5 = LG + UG + 1st Podium + 2nd to 7th Podium/Pt Resi. + 8th Podium Top/Pt Resi. + 1 Service Floor + 9th to 52nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed
|  |  |  | 1 | 1 |  | 0 | 52 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13
Excavation |  | 52 |  | 100% | 25.47% |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed |  | Excavation in process | 26
Plinth |  | 52 |  | 100% |  |  |  |  | Excavation Completed | 52
RCC (Including podiums) |  | 1 |  | 1.887% |  |  |  |  | Footing in Process | 13
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 26
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 39
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 52
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 25.47%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 32000 to 34000 | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA |  | 29000 TO 30000 Changed by Ankita on Call Floor Rise asked to remove
Car Parking Charges |  |  | : | 1200000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 6931.4381
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 15523.0398
Distress Value (Rs. Per sqft) | [5 empty] | : | 5545.1505
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Gross Carpet Area
Wing 1 |  | Sale |  | Flats | 272 |  | 426109.833
Wing 2 |  | Sale |  | Flats | 216 |  | 332954.6744
Wing 3 |  | Sale |  | Flats | 368 |  | 324569.8962
Wing 4 |  | Sale |  | Flats | 368 |  | 324658.2547
Wing 5 |  | Sale |  | Flats | 360 |  | 359163.769
Total |  |  |  |  | 1584 |  | 1767456.4274 | 0
Details of Flats in Building
Flat/Shop No. |  | Description |  | Carpet area | Deck + Utility |  | Attached Terrace area | Gross Carpet area
Sub Plot A Building No. 1
Wing 1
Lower Ground Floor For Parking
Upper Ground Floor Entrance Lobby, Meter Room, Panel Room, Fire Control Room & Parking
1st Podium Floor For Parking
2nd To 7th Podium Floor For Residential & Parking
1 |  | Parking
2
3 |  | 4BHK | 4BHK | 1777.5885 | 167.8732 | 169.1659 | 0 | 1945.4617 | 157.0171 | 164.442 |  | 10.764 | 10.764
4 |  | 3BHK | 3BHK | 1257.9715 | 90.5791 | 90.5791 | 0 | 1348.5505
5 |  | 3BHK | 3BHK | 1257.9715 | 90.5791 | 90.5791 | 0 | 1348.5505
6 |  | Parking
8th Podium Floor For Residential (Part Refuge Area), Parking & Amenity Area
1 |  | Parking & Amenity Area | [12 empty] | #REF! | #REF! | 801
2 | [14 empty] | #REF! | #REF! | 802
3 |  | 4BHK | 4BHK | 1770.0537 | 169.1659 | 169.1659 | 0 | 1939.2196 | [6 empty] | #REF! | #REF! | 803
4 |  | Refuge Area | [12 empty] | #REF! | #REF! | 804
5 | [14 empty] | #REF! | #REF! | 805
6 |  | Parking & Amenity Area | [12 empty] | #REF! | #REF! | 806
9th to 14th, 16th to 21st, 23rd to 28th Floor For Residential
1 |  | 3BHK | 3BHK | 1257.9715 | 90.5791 | 90.5791 | 0 | 1348.5505 | [6 empty] | 901 to 2801 | 901 | 2801
2 |  | 3BHK | 3BHK | 1257.9715 | 90.5791 | 90.5791 | 0 | 1348.5505 | [6 empty] | 902 to 2802 | 902 | 2802
3 |  | 4BHK | 4BHK | 1770.0537 | 170.0701 | 169.1659 | 0 | 1940.1238 | [6 empty] | 903 to 2803 | 903 | 2803
4 |  | 3BHK | 3BHK | 1257.9715 | 90.5791 | 90.5791 | 0 | 1348.5505 | [6 empty] | 904 to 2804 | 904 | 2804
5 |  | 3BHK | 3BHK | 1257.9715 | 90.5791 | 90.5791 | 0 | 1348.5505 | [6 empty] | 905 to 2805 | 905 | 2805
6 |  | 4BHK | 4BHK | 1770.0537 | 170.0701 | 169.1659 | 0 | 1940.1238 | [6 empty] | 906 to 2806 | 906 | 2806
15th & 22nd Floor (Part Refuge Area)
1 |  | 3BHK | 3BHK | 1257.9715 | 90.5791 | 90.5791 | 0 | 1348.5505 | [6 empty] | 1501 to 2201 | 1501 | 2201
2 |  | 3BHK | 3BHK | 1257.9715 | 90.5791 | 90.5791 | 0 | 1348.5505 | [6 empty] | 1502 to 2202 | 1502 | 2202
3 |  | 4BHK | 4BHK | 1770.0537 | 170.0701 | 169.1659 | 0 | 1940.1238 | [6 empty] | 1503 to 2203 | 1503 | 2203
4 |  | Refuge Area | [12 empty] | 1504 to 2204 | 1504 | 2204
5 | [14 empty] | 1505 to 2205 | 1505 | 2205
6 |  | 4BHK | 4BHK | 1770.0537 | 170.0701 | 169.1659 | 0 | 1940.1238 | [6 empty] | 1506 to 2206 | 1506 | 2206
29th, 36th & 43rd Floor (Part Refuge Area)
1 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 2901 to 4301 | 2901 | 4301
2 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 2902 to 4302 | 2902 | 4302
3 |  | 4BHK | 4BHK | 1802.2058 | 170.0701 | 169.1659 | 0 | 1972.2759 | [6 empty] | 2903 to 4303 | 2903 | 4303
4 |  | Refuge Area | [12 empty] | 2904 to 4304 | 2904 | 4304
5 | [14 empty] | 2905 to 4305 | 2905 | 4305
6 |  | 4BHK | 4BHK | 1802.2058 | 170.0701 | 169.1659 | 0 | 1972.2759 | [6 empty] | 2906 to 4306 | 2906 | 4306
30th to 35th, 37th to 42nd, 44th to 47th Floor
1 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 3001 to 4701 | 3001 | 4701
2 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 3002 to 4702 | 3002 | 4702
3 |  | 4BHK | 4BHK | 1802.2058 | 170.0701 | 169.1659 | 0 | 1972.2759 | [6 empty] | 3003 to 4703 | 3003 | 4703
4 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 3004 to 4704 | 3004 | 4704
5 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 3005 to 4705 | 3005 | 4705
6 |  | 4BHK | 4BHK | 1802.2058 | 170.0701 | 169.1659 | 0 | 1972.2759 | [6 empty] | 3006 to 4706 | 3006 | 4706
48th, 49th, 51st & 52nd Floor
1 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 4801 to 5201 | 4801 | 5201
2 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 4802 to 5202 | 4802 | 5202
3 |  | 4BHK | 4BHK | 1802.2058 | 170.0701 | 169.1659 | 0 | 1972.2759 | [6 empty] | 4803 to 5203 | 4803 | 5203
4 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 4804 to 5204 | 4804 | 5204
5 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 4805 to 5205 | 4805 | 5205
6 |  | 4BHK | 4BHK | 1802.2058 | 170.0701 | 169.1659 | 0 | 1972.2759 | [6 empty] | 4806 to 5206 | 4806 | 5206
50th Floor (Part Refuge Area)
1 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 501 to 5001 | 501 | 5001
2 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 502 to 5002 | 502 | 5002
3 |  | 4BHK | 4BHK | 1802.2058 | 170.0701 | 169.1659 | 0 | 1972.2759 | [6 empty] | 503 to 5003 | 503 | 5003
4 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 504 to 5004 | 504 | 5004
5 |  | Refuge Area | [12 empty] | 505 to 5005 | 505 | 5005
6 |  | 4BHK | 4BHK | 1802.2058 | 170.0701 | 169.1659 | 0 | 1972.2759 | [6 empty] | 506 to 5006 | 506 | 5006
Wing 2
Lower Ground Floor For Parking
Upper Ground Floor Entrance Lobby, Meter Room, Panel Room, Fire Control Room & Parking
1st Podium Floor For Parking
2nd To 6th Podium Floor For Residential & Parking
1 |  | Parking
2
3 | [8 empty] | 157.0171 | 164.442 |  | 10.764 | 10.764
4 |  | 3BHK | 3BHK | 1264.6032 | 90.9084 | 90.5791 | 0 | 1355.5116
5 |  | 3BHK | 3BHK | 1264.6032 | 90.9084 | 90.5791 | 0 | 1355.5116
6 |  | Parking
7th Podium Floor For Residential (Part Refuge Area), Parking & Amenity Area
1 |  | Parking & Amenity Area | [12 empty] | #REF! | #REF! | 701
2 | [14 empty] | #REF! | #REF! | 702
3 | [14 empty] | #REF! | #REF! | 703
4 |  | Refuge Area | [12 empty] | #REF! | #REF! | 704
5 | [14 empty] | #REF! | #REF! | 705
6 |  | Parking & Amenity Area | [12 empty] | #REF! | #REF! | 706
8th Floor (Service Floor)
9th to 14th, 16th to 21st Floor For Residential
1 |  | 3BHK | 3BHK | 1264.6032 | 90.9084 | 90.5791 | 0 | 1355.5116 | [6 empty] | 901 to 2101 | 901 | 2101
2 |  | 3BHK | 3BHK | 1264.6032 | 90.9084 | 90.5791 | 0 | 1355.5116 | [6 empty] | 902 to 2102 | 902 | 2102
3 |  | 4BHK | 4BHK | 1752.8722 | 172.2401 | 169.1659 | 0 | 1925.1123 | [6 empty] | 903 to 2103 | 903 | 2103
4 |  | 3BHK | 3BHK | 1264.6032 | 90.9084 | 90.5791 | 0 | 1355.5116 | [6 empty] | 904 to 2104 | 904 | 2104
5 |  | 3BHK | 3BHK | 1264.6032 | 90.9084 | 90.5791 | 0 | 1355.5116 | [6 empty] | 905 to 2105 | 905 | 2105
6 |  | 4BHK | 4BHK | 1729.3421 | 172.2401 | 169.1659 | 0 | 1901.5822 | [6 empty] | 906 to 2106 | 906 | 2106
15th Floor (Part Refuge Area)
1 |  | 3BHK | 3BHK | 1264.6032 | 90.9084 | 90.5791 | 0 | 1355.5116 | [6 empty] | 101 to 1501 | 101 | 1501
2 |  | 3BHK | 3BHK | 1264.6032 | 90.9084 | 90.5791 | 0 | 1355.5116 | [6 empty] | 102 to 1502 | 102 | 1502
3 |  | 4BHK | 4BHK | 1752.8722 | 172.2401 | 169.1659 | 0 | 1925.1123 | [6 empty] | 103 to 1503 | 103 | 1503
4 |  | Refuge Area | [12 empty] | 104 to 1504 | 104 | 1504
5 | [14 empty] | 105 to 1505 | 105 | 1505
6 |  | 4BHK | 4BHK | 1729.3421 | 172.2401 | 169.1659 | 0 | 1901.5822 | [6 empty] | 106 to 1506 | 106 | 1506
22nd, 29th, 36th & 43rd Floor (Part Refuge Area)
1 |  | 3BHK | 3BHK | 1264.6032 | 90.9084 | 90.5791 | 0 | 1355.5116 | [6 empty] | 2201 to 4301 | 2201 | 4301
2 |  | 3BHK | 3BHK | 1264.6032 | 90.9084 | 90.5791 | 0 | 1355.5116 | [6 empty] | 2202 to 4302 | 2202 | 4302
3 |  | 4BHK | 4BHK | 1752.8722 | 172.2401 | 169.1659 | 0 | 1925.1123 | [6 empty] | 2203 to 4303 | 2203 | 4303
4 |  | Refuge Area | [12 empty] | 2204 to 4304 | 2204 | 4304
5 | [14 empty] | 2205 to 4305 | 2205 | 4305
6 |  | 4BHK | 4BHK | 1729.3421 | 172.2401 | 169.1659 | 0 | 1901.5822 | [6 empty] | 2206 to 4306 | 2206 | 4306
23rd to 28th, 30th to 35th, 37th to 42nd, 44th Floor
1 |  | 3BHK | 3BHK | 1264.6032 | 90.9084 | 90.5791 | 0 | 1355.5116 | [6 empty] | 2301 to 4401 | 2301 | 4401
2 |  | 3BHK | 3BHK | 1264.6032 | 90.9084 | 90.5791 | 0 | 1355.5116 | [6 empty] | 2302 to 4402 | 2302 | 4402
3 |  | 4BHK | 4BHK | 1752.8722 | 172.2401 | 169.1659 | 0 | 1925.1123 | [6 empty] | 2303 to 4403 | 2303 | 4403
4 |  | 3BHK | 3BHK | 1264.6032 | 90.9084 | 90.5791 | 0 | 1355.5116 | [6 empty] | 2304 to 4404 | 2304 | 4404
5 |  | 3BHK | 3BHK | 1264.6032 | 90.9084 | 90.5791 | 0 | 1355.5116 | [6 empty] | 2305 to 4405 | 2305 | 4405
6 |  | 4BHK | 4BHK | 1729.3421 | 172.2401 | 169.1659 | 0 | 1901.5822 | [6 empty] | 2306 to 4406 | 2306 | 4406
48th, 49th, 51st & 52nd Floor
1 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 4801 to 5201 | 4801 | 5201
2 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 4802 to 5202 | 4802 | 5202
3 |  | 4BHK | 4BHK | 1802.2058 | 170.0701 | 169.1659 | 0 | 1972.2759 | [6 empty] | 4803 to 5203 | 4803 | 5203
4 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 4804 to 5204 | 4804 | 5204
5 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 4805 to 5205 | 4805 | 5205
6 |  | 4BHK | 4BHK | 1802.2058 | 170.0701 | 169.1659 | 0 | 1972.2759 | [6 empty] | 4806 to 5206 | 4806 | 5206
50th Floor (Part Refuge Area)
1 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 501 to 5001 | 501 | 5001
2 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 502 to 5002 | 502 | 5002
3 |  | 4BHK | 4BHK | 1802.2058 | 170.0701 | 169.1659 | 0 | 1972.2759 | [6 empty] | 503 to 5003 | 503 | 5003
4 |  | 3BHK | 3BHK | 1275.1648 | 90.5791 | 90.5791 | 0 | 1365.7439 | [6 empty] | 504 to 5004 | 504 | 5004
5 |  | Refuge Area | [12 empty] | 505 to 5005 | 505 | 5005
6 |  | 4BHK | 4BHK | 1802.2058 | 170.0701 | 169.1659 | 0 | 1972.2759 | [6 empty] | 506 to 5006 | 506 | 5006
Wing 3
Lower Ground Floor For Parking
Upper Ground Floor Entrance Lobby, Meter Room, Panel Room, Fire Control Room & Parking | [11 empty] | 10.764 | 10.764
1st Podium Floor Floor For Residential & Parking | [8 empty] | 1
1 |  | Parking | [12 empty] | 101 & 101 | 101 | 101
2 | [14 empty] | 102 & 102 | 102 | 102
3 |  | 2BHK |  | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | 103 & 103 | 103 | 103
4 |  | 2BHK | 2BHK | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | 104 & 104 | 104 | 104
5 |  | Entrance Lobby Below | [12 empty] | 105 & 105 | 105 | 105
6 | [14 empty] | 106 & 106 | 106 | 106
7 | [14 empty] | 107 & 107 | 107 | 107
8 | [14 empty] | 108 & 108 | 108 | 108
2nd To 7th Podium Floor For Residential & Parking | [8 empty] | 6
1 |  | Parking | [12 empty] | 201 & 701 | 201 | 701
2 | [14 empty] | 202 & 702 | 202 | 702
3 |  | 2BHK |  | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | 203 & 703 | 203 | 703
4 |  | 2BHK | 2BHK | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | 204 & 704 | 204 | 704
5 |  | 3BHK | 3BHK | 977.8846 | 68.3837 | 68.3837 | 0 | 1046.2683 | [6 empty] | 205 & 705 | 205 | 705
6 |  | 3BHK | 3BHK | 977.8846 | 68.3837 | 68.3837 | 0 | 1046.2683 | [6 empty] | 206 & 706 | 206 | 706
7 |  | 2BHK | 2BHK | 661.9107 | 60.8866 | 60.8866 | 0 | 722.7972 | [6 empty] | 207 & 707 | 207 | 707
8 |  | Parking | [12 empty] | 208 & 708 | 208 | 708
8th Podium Floor For Residential (Part Refuge Area), Parking & Amenity Area | [8 empty] | 1
1 |  | Lobby Entrance For Amenity Area | [12 empty] | #REF! | #REF! | 801
2 | [14 empty] | #REF! | #REF! | 802
3 |  | 2BHK |  | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | #REF! | #REF! | 803
4 |  | 2BHK | 2BHK | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | #REF! | #REF! | 804
5 |  | Refuge Area | [12 empty] | #REF! | #REF! | 805
6 | [14 empty] | #REF! | #REF! | 806
7 |  | 2BHK | 2BHK | 661.9107 | 60.8866 | 60.8866 | 0 | 722.7972 | [6 empty] | #REF! | #REF! | 807
8 |  | Parking | [12 empty] | #REF! | #REF! | 808
9th to 14th, 16th to 21st, 23rd to 28th Floor For Residential | [8 empty] | 18
1 |  | 3BHK | 3BHK | 999.8131 | 62.5065 | 62.5065 | 0 | 1062.3196 | [6 empty] | 901 & 2801 | 901 | 2801
2 |  | 3BHK | 3BHK | 999.8131 | 62.5065 | 62.5065 | 0 | 1062.3196 | [6 empty] | 902 & 2802 | 902 | 2802
3 |  | 2BHK |  | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | 903 & 2803 | 903 | 2803
4 |  | 2BHK | 2BHK | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | 904 & 2804 | 904 | 2804
5 |  | 3BHK | 3BHK | 977.8846 | 68.3837 | 68.3837 | 0 | 1046.2683 | [6 empty] | 905 & 2805 | 905 | 2805
6 |  | 3BHK | 3BHK | 977.8846 | 68.3837 | 68.3837 | 0 | 1046.2683 | [6 empty] | 906 & 2806 | 906 | 2806
7 |  | 2BHK | 2BHK | 661.9107 | 60.8866 | 60.8866 | 0 | 722.7972 | [6 empty] | 907 & 2807 | 907 | 2807
8 |  | 2BHK | 2BHK | 661.9107 | 60.8866 | 60.8866 | 0 | 722.7972 | [6 empty] | 908 & 2808 | 908 | 2808
15th & 22nd Floor (Part Refuge Area) | [8 empty] | 2
1 |  | 3BHK | 3BHK | 999.8131 | 62.5065 | 62.5065 | 0 | 1062.3196 | [6 empty] | 1501 & 2201 | 1501 | 2201
2 |  | 3BHK | 3BHK | 999.8131 | 62.5065 | 62.5065 | 0 | 1062.3196 | [6 empty] | 1502 & 2202 | 1502 | 2202
3 |  | 2BHK |  | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | 1503 & 2203 | 1503 | 2203
4 |  | 2BHK | 2BHK | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | 1504 & 2204 | 1504 | 2204
5 |  | Refuge Area | [12 empty] | 1505 & 2205 | 1505 | 2205
6 | [14 empty] | 1506 & 2206 | 1506 | 2206
7 |  | 2BHK | 2BHK | 661.9107 | 60.8866 | 60.8866 | 0 | 722.7972 | [6 empty] | 1507 & 2207 | 1507 | 2207
8 |  | 2BHK | 2BHK | 661.9107 | 60.8866 | 60.8866 | 0 | 722.7972 | [6 empty] | 1508 & 2208 | 1508 | 2208
30th to 35th, 37th to 42nd, 44th to 47th Floor | [8 empty] | 16
1 |  | 3BHK | 3BHK | 1012.9419 | 63.4861 | 62.5065 | 0 | 1076.428 | [6 empty] | 3001 & 4701 | 3001 | 4701
2 |  | 3BHK | 3BHK | 1012.9419 | 63.4861 | 62.5065 | 0 | 1076.428 | [6 empty] | 3002 & 4702 | 3002 | 4702
3 |  | 2BHK |  | 659.4834 | 63.6927 | 62.9683 | 0 | 723.1761 | [6 empty] | 3003 & 4703 | 3003 | 4703
4 |  | 2BHK | 2BHK | 659.4834 | 63.6927 | 62.9683 | 0 | 723.1761 | [6 empty] | 3004 & 4704 | 3004 | 4704
5 |  | 3BHK | 3BHK | 991.3343 | 68.3837 | 68.3837 | 0 | 1059.718 | [6 empty] | 3005 & 4705 | 3005 | 4705
6 |  | 3BHK | 3BHK | 991.3343 | 68.3837 | 68.3837 | 0 | 1059.718 | [6 empty] | 3006 & 4706 | 3006 | 4706
7 |  | 2BHK | 2BHK | 665.8664 | 62.3666 | 60.8866 | 0 | 728.233 | [6 empty] | 3007 & 4707 | 3007 | 4707
8 |  | 2BHK | 2BHK | 665.8664 | 62.3666 | 60.8866 | 0 | 728.233 | [6 empty] | 3008 & 4708 | 3008 | 4708
29th, 36th & 43rd Floor (Part Refuge Area) | [8 empty] | 3
1 |  | 3BHK | 3BHK | 1012.9419 | 63.4861 | 62.5065 | 0 | 1076.428 | [6 empty] | 2901 & 4301 | 2901 | 4301
2 |  | 3BHK | 3BHK | 1012.9419 | 63.4861 | 62.5065 | 0 | 1076.428 | [6 empty] | 2902 & 4302 | 2902 | 4302
3 |  | 2BHK |  | 659.4834 | 63.6927 | 62.9683 | 0 | 723.1761 | [6 empty] | 2903 & 4303 | 2903 | 4303
4 |  | 2BHK | 2BHK | 659.4834 | 63.6927 | 62.9683 | 0 | 723.1761 | [6 empty] | 2904 & 4304 | 2904 | 4304
5 |  | Refuge Area | [12 empty] | 2905 & 4305 | 2905 | 4305
6 | [14 empty] | 2906 & 4306 | 2906 | 4306
7 |  | 2BHK | 2BHK | 665.8664 | 62.3666 | 60.8866 | 0 | 728.233 | [6 empty] | 2907 & 4307 | 2907 | 4307
8 |  | 2BHK | 2BHK | 665.8664 | 62.3666 | 60.8866 | 0 | 728.233 | [6 empty] | 2908 & 4308 | 2908 | 4308
48th, 49th & 51st Floor | [8 empty] | 3
1 |  | 3BHK | 3BHK | 1012.9419 | 63.4861 | 62.5065 | 0 | 1076.428 | [6 empty] | 401 & 5101 | 401 | 5101
2 |  | 3BHK | 3BHK | 1012.9419 | 63.4861 | 62.5065 | 0 | 1076.428 | [6 empty] | 402 & 5102 | 402 | 5102
3 |  | 2BHK |  | 659.4834 | 63.6927 | 62.9683 | 0 | 723.1761 | [6 empty] | 403 & 5103 | 403 | 5103
4 |  | 2BHK | 2BHK | 659.4834 | 63.6927 | 62.9683 | 0 | 723.1761 | [6 empty] | 404 & 5104 | 404 | 5104
5 |  | 3BHK | 3BHK | 991.3343 | 68.3837 | 68.3837 | 0 | 1059.718 | [6 empty] | 405 & 5105 | 405 | 5105
6 |  | 3BHK | 3BHK | 991.3343 | 68.3837 | 68.3837 | 0 | 1059.718 | [6 empty] | 406 & 5106 | 406 | 5106
7 |  | 2BHK | 2BHK | 665.8664 | 62.3666 | 60.8866 | 0 | 728.233 | [6 empty] | 407 & 5107 | 407 | 5107
8 |  | 2BHK | 2BHK | 665.8664 | 62.3666 | 60.8866 | 0 | 728.233 | [6 empty] | 408 & 5108 | 408 | 5108
50th Floor (Part Refuge Area) | [8 empty] | 1
1 |  | 3BHK | 3BHK | 1012.9419 | 63.4861 | 62.5065 | 0 | 1076.428 | [6 empty] | 501 & 5001 | 501 | 5001
2 |  | 3BHK | 3BHK | 1012.9419 | 63.4861 | 62.5065 | 0 | 1076.428 | [6 empty] | 502 & 5002 | 502 | 5002
3 |  | 2BHK |  | 659.4834 | 63.6927 | 62.9683 | 0 | 723.1761 | [6 empty] | 503 & 5003 | 503 | 5003
4 |  | 2BHK | 2BHK | 659.4834 | 63.6927 | 62.9683 | 0 | 723.1761 | [6 empty] | 504 & 5004 | 504 | 5004
5 |  | 3BHK | 3BHK | 991.3343 | 68.3837 | 68.3837 | 0 | 1059.718 | [6 empty] | 505 & 5005 | 505 | 5005
6 |  | Refuge Area | [12 empty] | 506 & 5006 | 506 | 5006
7 |  | 2BHK | 2BHK | 665.8664 | 62.3666 | 60.8866 | 0 | 728.233 | [6 empty] | 507 & 5007 | 507 | 5007
8 |  | 2BHK | 2BHK | 665.8664 | 62.3666 | 60.8866 | 0 | 728.233 | [6 empty] | 508 & 5008 | 508 | 5008
Wing 4
Lower Ground Floor For Parking
Upper Ground Floor Entrance Lobby, Meter Room, Panel Room, Fire Control Room & Parking | [11 empty] | 10.764 | 10.764
1st Podium Floor Floor For Residential & Parking | [8 empty] | 1
1 |  | Parking | [12 empty] | 101 & 101 | 101 | 101
2 | [14 empty] | 102 & 102 | 102 | 102
3 | [14 empty] | 103 & 103 | 103 | 103
4 | [14 empty] | 104 & 104 | 104 | 104
5 |  | Entrance Lobby Below | [12 empty] | 105 & 105 | 105 | 105
6 | [14 empty] | 106 & 106 | 106 | 106
7 |  | 2BHK | 2BHK | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | 107 & 107 | 107 | 107
8 |  | 2BHK | 2BHK | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | 108 & 108 | 108 | 108
2nd To 7th Podium Floor For Residential & Parking | [8 empty] | 6
1 |  | Parking | [12 empty] | 201 & 701 | 201 | 701
2 | [14 empty] | 202 & 702 | 202 | 702
3 | [14 empty] | 203 & 703 | 203 | 703
4 |  | 2BHK | 2BHK | 661.9107 | 60.8866 | 60.8866 | 0 | 722.7972 | [6 empty] | 204 & 704 | 204 | 704
5 |  | 3BHK | 3BHK | 977.8846 | 68.3837 | 68.3837 | 0 | 1046.2683 | [6 empty] | 205 & 705 | 205 | 705
6 |  | 3BHK | 3BHK | 977.8846 | 68.3837 | 68.3837 | 0 | 1046.2683 | [6 empty] | 206 & 706 | 206 | 706
7 |  | 2BHK | 2BHK | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | 207 & 707 | 207 | 707
8 |  | 2BHK | 2BHK | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | 208 & 708 | 208 | 708
8th Podium Floor For Residential (Part Refuge Area), Parking & Amenity Area | [8 empty] | 1
1 |  | Parking & Amenity Area | [12 empty] | #REF! | #REF! | 801
2 | [14 empty] | #REF! | #REF! | 802
3 | [14 empty] | #REF! | #REF! | 803
4 |  | 2BHK | 2BHK | 661.9107 | 60.8866 | 60.8866 | 0 | 722.7972 | [6 empty] | #REF! | #REF! | 804
5 |  | Refuge Area | [12 empty] | #REF! | #REF! | 805
6 | [14 empty] | #REF! | #REF! | 806
7 |  | 2BHK | 2BHK | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | #REF! | #REF! | 807
8 |  | 2BHK | 2BHK | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | #REF! | #REF! | 808
9th to 14th, 16th to 21st, 23rd to 28th Floor For Residential | [8 empty] | 18
1 |  | 3BHK | 3BHK | 999.8131 | 62.5065 | 62.5065 | 0 | 1062.3196 | [6 empty] | 901 & 2801 | 901 | 2801
2 |  | 3BHK | 3BHK | 999.8131 | 62.5065 | 62.5065 | 0 | 1062.3196 | [6 empty] | 902 & 2802 | 902 | 2802
3 |  | 2BHK |  | 661.9107 | 60.8866 | 60.8866 | 0 | 722.7972 | [6 empty] | 903 & 2803 | 903 | 2803
4 |  | 2BHK | 2BHK | 661.9107 | 60.8866 | 60.8866 | 0 | 722.7972 | [6 empty] | 904 & 2804 | 904 | 2804
5 |  | 3BHK | 3BHK | 977.8846 | 68.3837 | 68.3837 | 0 | 1046.2683 | [6 empty] | 905 & 2805 | 905 | 2805
6 |  | 3BHK | 3BHK | 977.8846 | 68.3837 | 68.3837 | 0 | 1046.2683 | [6 empty] | 906 & 2806 | 906 | 2806
7 |  | 2BHK | 2BHK | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | 907 & 2807 | 907 | 2807
8 |  | 2BHK | 2BHK | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | 908 & 2808 | 908 | 2808
15th & 22nd Floor (Part Refuge Area) | [8 empty] | 2
1 |  | 3BHK | 3BHK | 999.8131 | 62.5065 | 62.5065 | 0 | 1062.3196 | [6 empty] | 1501 & 2201 | 1501 | 2201
2 |  | 3BHK | 3BHK | 999.8131 | 62.5065 | 62.5065 | 0 | 1062.3196 | [6 empty] | 1502 & 2202 | 1502 | 2202
3 |  | 2BHK |  | 661.9107 | 60.8866 | 60.8866 | 0 | 722.7972 | [6 empty] | 1503 & 2203 | 1503 | 2203
4 |  | 2BHK | 2BHK | 661.9107 | 60.8866 | 60.8866 | 0 | 722.7972 | [6 empty] | 1504 & 2204 | 1504 | 2204
5 |  | Refuge Area | [12 empty] | 1505 & 2205 | 1505 | 2205
6 | [14 empty] | 1506 & 2206 | 1506 | 2206
7 |  | 2BHK | 2BHK | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | 1507 & 2207 | 1507 | 2207
8 |  | 2BHK | 2BHK | 656.2326 | 62.9683 | 62.9683 | 0 | 719.201 | [6 empty] | 1508 & 2208 | 1508 | 2208
29th & 36th, 43rd Floor (Part Refuge Area) | [8 empty] | 3
1 |  | 3BHK | 3BHK | 1009.2682 | 63.4861 | 63.4861 | 0 | 1072.7542 | [6 empty] | 2901 & 4301 | 2901 | 4301
2 |  | 3BHK | 3BHK | 1009.2682 | 63.4861 | 63.4861 | 0 | 1072.7542 | [6 empty] | 2902 & 4302 | 2902 | 4302
3 |  | 2BHK |  | 663.7944 | 62.3666 | 62.3666 | 0 | 726.161 | [6 empty] | 2903 & 4303 | 2903 | 4303
4 |  | 2BHK | 2BHK | 663.7944 | 62.3666 | 62.3666 | 0 | 726.161 | [6 empty] | 2904 & 4304 | 2904 | 4304
5 |  | Refuge Area | [12 empty] | 2905 & 4305 | 2905 | 4305
6 | [14 empty] | 2906 & 4306 | 2906 | 4306
7 |  | 2BHK | 2BHK | 657.4813 | 63.6927 | 63.6927 | 0 | 721.174 | [6 empty] | 2907 & 4307 | 2907 | 4307
8 |  | 2BHK | 2BHK | 657.4813 | 63.6927 | 63.6927 | 0 | 721.174 | [6 empty] | 2908 & 4308 | 2908 | 4308
30th to 35th, 37th to 42nd, 44th to 47th Floor | [8 empty] | 16
1 |  | 3BHK | 3BHK | 1014.7879 | 63.4861 | 63.4861 | 0 | 1078.274 | [6 empty] | 3001 & 4701 | 3001 | 4701
2 |  | 3BHK | 3BHK | 1014.7879 | 63.4861 | 63.4861 | 0 | 1078.274 | [6 empty] | 3002 & 4702 | 3002 | 4702
3 |  | 2BHK |  | 665.8664 | 62.3666 | 62.3666 | 0 | 728.233 | [6 empty] | 3003 & 4703 | 3003 | 4703
4 |  | 2BHK | 2BHK | 665.8664 | 62.3666 | 62.3666 | 0 | 728.233 | [6 empty] | 3004 & 4704 | 3004 | 4704
5 |  | 3BHK | 3BHK | 993.1803 | 68.3837 | 68.3837 | 0 | 1061.564 | [6 empty] | 3005 & 4705 | 3005 | 4705
6 |  | 3BHK | 3BHK | 993.1803 | 68.3837 | 68.3837 | 0 | 1061.564 | [6 empty] | 3006 & 4706 | 3006 | 4706
7 |  | 2BHK | 2BHK | 657.4813 | 63.6927 | 63.6927 | 0 | 721.174 | [6 empty] | 3007 & 4707 | 3007 | 4707
8 |  | 2BHK | 2BHK | 657.4813 | 63.6927 | 63.6927 | 0 | 721.174 | [6 empty] | 3008 & 4708 | 3008 | 4708
50th Floor (Part Refuge Area) | [8 empty] | 1
1 |  | 3BHK | 3BHK | 1018.7609 | 63.4861 | 63.4861 | 0 | 1082.247 | [6 empty] | 501 & 5001 | 501 | 5001
2 |  | 3BHK | 3BHK | 1018.7609 | 63.4861 | 63.4861 | 0 | 1082.247 | [6 empty] | 502 & 5002 | 502 | 5002
3 |  | 2BHK |  | 665.8664 | 62.3666 | 62.3666 | 0 | 728.233 | [6 empty] | 503 & 5003 | 503 | 5003
4 |  | 2BHK | 2BHK | 665.8664 | 62.3666 | 62.3666 | 0 | 728.233 | [6 empty] | 504 & 5004 | 504 | 5004
5 |  | Refuge Area | [12 empty] | 505 & 5005 | 505 | 5005
6 |  | 3BHK | 3BHK | 996.2222 | 68.3837 | 68.3837 | 0 | 1064.6059 | [6 empty] | 506 & 5006 | 506 | 5006
7 |  | 2BHK | 2BHK | 659.4834 | 63.6927 | 63.6927 | 0 | 723.1761 | [6 empty] | 507 & 5007 | 507 | 5007
8 |  | 2BHK | 2BHK | 659.4834 | 63.6927 | 63.6927 | 0 | 723.1761 | [6 empty] | 508 & 5008 | 508 | 5008
48th, 49th & 51st Floor | [8 empty] | 3
1 |  | 3BHK | 3BHK | 1018.7609 | 63.4861 | 63.4861 | 0 | 1082.247 | [6 empty] | 401 & 5101 | 401 | 5101
2 |  | 3BHK | 3BHK | 1018.7609 | 63.4861 | 63.4861 | 0 | 1082.247 | [6 empty] | 402 & 5102 | 402 | 5102
3 |  | 2BHK |  | 665.8664 | 62.3666 | 62.3666 | 0 | 728.233 | [6 empty] | 403 & 5103 | 403 | 5103
4 |  | 2BHK | 2BHK | 665.8664 | 62.3666 | 62.3666 | 0 | 728.233 | [6 empty] | 404 & 5104 | 404 | 5104
5 |  | 3BHK | 3BHK | 996.2222 | 68.3837 | 68.3837 | 0 | 1064.6059 | [6 empty] | 405 & 5105 | 405 | 5105
6 |  | 3BHK | 3BHK | 996.2222 | 68.3837 | 68.3837 | 0 | 1064.6059 | [6 empty] | 406 & 5106 | 406 | 5106
7 |  | 2BHK | 2BHK | 659.4834 | 63.6927 | 63.6927 | 0 | 723.1761 | [6 empty] | 407 & 5107 | 407 | 5107
8 |  | 2BHK | 2BHK | 659.4834 | 63.6927 | 63.6927 | 0 | 723.1761 | [6 empty] | 408 & 5108 | 408 | 5108
Wing 5
Lower Ground Floor For Parking | [12 empty] | 10.764 | 10.764
Upper Ground Floor Entrance Lobby, Meter Room, Panel Room, Fire Control Room & Parking
1st Podium Floor Floor For Residential & Parking
1 |  | Parking | [12 empty] | 101 & 101 | 101 | 101
2 | [14 empty] | 102 & 102 | 102 | 102
3 | [14 empty] | 103 & 103 | 103 | 103
4 |  | 2BHK | 2BHK | 710.875 | 60.2461 | 60.2461 | 0 | 771.1211 | [6 empty] | 104 & 104 | 104 | 104
5 |  | Entrance Lobby Below | [12 empty] | 105 & 105 | 105 | 105
6 | [14 empty] | 106 & 106 | 106 | 106
7 |  | Parking | [12 empty] | 107 & 107 | 107 | 107
8 | [14 empty] | 108 & 108 | 108 | 108
2nd To 7th Podium Floor For Residential & Parking | [8 empty] | 6
1 |  | Parking | [12 empty] | 201 & 701 | 201 | 701
2 | [14 empty] | 202 & 702 | 202 | 702
3 | [14 empty] | 203 & 703 | 203 | 703
4 |  | 2BHK | 2BHK | 710.875 | 60.2461 | 60.2461 | 0 | 771.1211 | [6 empty] | 204 & 704 | 204 | 704
5 |  | 3BHK | 3BHK | 1150.0236 | 81.6718 | 81.6718 | 0 | 1231.6955 | [6 empty] | 205 & 705 | 205 | 705
6 |  | 3BHK | 3BHK | 1150.0236 | 81.6718 | 81.6718 | 0 | 1231.6955 | [6 empty] | 206 & 706 | 206 | 706
7 |  | 2BHK | 2BHK | 710.875 | 60.2461 | 60.2461 | 0 | 771.1211 | [6 empty] | 207 & 707 | 207 | 707
8 |  | Parking | [12 empty] | 208 & 708 | 208 | 708
8th Podium Floor For Residential (Part Refuge Area), Parking & Amenity Area | [8 empty] | 1
1 |  | Parking & Amenity Area | [12 empty] | #REF! | #REF! | 801
2 | [14 empty] | #REF! | #REF! | 802
3 | [14 empty] | #REF! | #REF! | 803
4 |  | 2BHK | 2BHK | 710.875 | 60.2461 | 60.2461 | 0 | 771.1211 | [6 empty] | #REF! | #REF! | 804
5 |  | Refuge Area | [12 empty] | #REF! | #REF! | 805
6 | [14 empty] | #REF! | #REF! | 806
7 |  | 2BHK | 2BHK | 710.875 | 60.2461 | 60.2461 | 0 | 771.1211 | [6 empty] | #REF! | #REF! | 807
8 |  | Parking & Amenity Area | [12 empty] | #REF! | #REF! | 808
9th to 14th, 16th to 21st, 23rd to 28th Floor For Residential | [8 empty] | 18
1 |  | 3BHK | 3BHK | 1150.0236 | 81.3963 | 81.3963 | 0 | 1231.4199 | [6 empty] | 901 & 2801 | 901 | 2801
2 |  | 3BHK | 3BHK | 1150.0236 | 81.3963 | 81.3963 | 0 | 1231.4199 | [6 empty] | 902 & 2802 | 902 | 2802
3 |  | 2BHK | 2BHK | 710.875 | 60.2461 | 60.2461 | 0 | 771.1211 | [6 empty] | 903 & 2803 | 903 | 2803
4 |  | 2BHK | 2BHK | 710.875 | 60.2461 | 60.2461 | 0 | 771.1211 | [6 empty] | 904 & 2804 | 904 | 2804
5 |  | 3BHK | 3BHK | 1150.0236 | 81.6718 | 81.6718 | 0 | 1231.6955 | [6 empty] | 905 & 2805 | 905 | 2805
6 |  | 3BHK | 3BHK | 1150.0236 | 81.6718 | 81.6718 | 0 | 1231.6955 | [6 empty] | 906 & 2806 | 906 | 2806
7 |  | 2BHK | 2BHK | 710.875 | 60.2461 | 60.2461 | 0 | 771.1211 | [6 empty] | 907 & 2807 | 907 | 2807
8 |  | 2BHK | 2BHK | 710.875 | 60.2461 | 60.2461 | 0 | 771.1211 | [6 empty] | 908 & 2808 | 908 | 2808
15th & 22nd Floor (Part Refuge Area) | [8 empty] | 2
1 |  | 3BHK | 3BHK | 1150.0236 | 81.3963 | 81.3963 | 0 | 1231.4199 | [6 empty] | 1501 & 2201 | 1501 | 2201
2 |  | 3BHK | 3BHK | 1150.0236 | 81.3963 | 81.3963 | 0 | 1231.4199 | [6 empty] | 1502 & 2202 | 1502 | 2202
3 |  | 2BHK | 2BHK | 710.875 | 60.2461 | 60.2461 | 0 | 771.1211 | [6 empty] | 1503 & 2203 | 1503 | 2203
4 |  | 2BHK | 2BHK | 710.875 | 60.2461 | 60.2461 | 0 | 771.1211 | [6 empty] | 1504 & 2204 | 1504 | 2204
5 |  | Refuge Area | [12 empty] | 1505 & 2205 | 1505 | 2205
6 | [14 empty] | 1506 & 2206 | 1506 | 2206
7 |  | 2BHK | 2BHK | 710.875 | 60.2461 | 60.2461 | 0 | 771.1211 | [6 empty] | 1507 & 2207 | 1507 | 2207
8 |  | 2BHK | 2BHK | 710.875 | 60.2461 | 60.2461 | 0 | 771.1211 | [6 empty] | 1508 & 2208 | 1508 | 2208
29th, 36th & 43rd Floor (Part Refuge Area) | [8 empty] | 3
1 |  | 3BHK | 3BHK | 1164.6874 | 81.3963 | 81.3963 | 0 | 1246.0837 | [6 empty] | 2901 & 4301 | 2901 | 4301
2 |  | 3BHK | 3BHK | 1164.6874 | 81.3963 | 81.3963 | 0 | 1246.0837 | [6 empty] | 2902 & 4302 | 2902 | 4302
3 |  | 2BHK | 2BHK | 716.0546 | 61.484 | 61.484 | 0 | 777.5386 | [6 empty] | 2903 & 4303 | 2903 | 4303
4 |  | 2BHK | 2BHK | 716.0546 | 61.484 | 61.484 | 0 | 777.5386 | [6 empty] | 2904 & 4304 | 2904 | 4304
5 |  | Refuge Area | [12 empty] | 2905 & 4305 | 2905 | 4305
6 | [14 empty] | 2906 & 4306 | 2906 | 4306
7 |  | 2BHK | 2BHK | 716.0546 | 61.484 | 61.484 | 0 | 777.5386 | [6 empty] | 2907 & 4307 | 2907 | 4307
8 |  | 2BHK | 2BHK | 716.0546 | 61.484 | 61.484 | 0 | 777.5386 | [6 empty] | 2908 & 4308 | 2908 | 4308
30th to 35th, 37th to 42nd & 44th to 47th Floor | [8 empty] | 16
1 |  | 3BHK | 3BHK | 1164.6874 | 81.3963 | 81.3963 | 0 | 1246.0837 | [6 empty] | 3001 & 4701 | 3001 | 4701
2 |  | 3BHK | 3BHK | 1164.6874 | 81.3963 | 81.3963 | 0 | 1246.0837 | [6 empty] | 3002 & 4702 | 3002 | 4702
3 |  | 2BHK | 2BHK | 716.0546 | 61.484 | 61.484 | 0 | 777.5386 | [6 empty] | 3003 & 4703 | 3003 | 4703
4 |  | 2BHK | 2BHK | 716.0546 | 61.484 | 61.484 | 0 | 777.5386 | [6 empty] | 3004 & 4704 | 3004 | 4704
5 |  | 3BHK | 3BHK | 1166.4226 | 81.6718 | 81.6718 | 0 | 1248.0944 | [6 empty] | 3005 & 4705 | 3005 | 4705
6 |  | 3BHK | 3BHK | 1166.4226 | 81.6718 | 81.6718 | 0 | 1248.0944 | [6 empty] | 3006 & 4706 | 3006 | 4706
7 |  | 2BHK | 2BHK | 716.0546 | 61.484 | 61.484 | 0 | 777.5386 | [6 empty] | 3007 & 4707 | 3007 | 4707
8 |  | 2BHK | 2BHK | 716.0546 | 61.484 | 61.484 | 0 | 777.5386 | [6 empty] | 3008 & 4708 | 3008 | 4708
50th Floor (Part Refuge Area) | [8 empty] | 1
1 |  | 3BHK | 3BHK | 1164.6874 | 81.3963 | 81.3963 | 0 | 1246.0837 | [6 empty] | 501 & 5001 | 501 | 5001
2 |  | 3BHK | 3BHK | 1164.6874 | 81.3963 | 81.3963 | 0 | 1246.0837 | [6 empty] | 502 & 5002 | 502 | 5002
3 |  | 2BHK | 2BHK | 716.0546 | 61.484 | 61.484 | 0 | 777.5386 | [6 empty] | 503 & 5003 | 503 | 5003
4 |  | 2BHK | 2BHK | 716.0546 | 61.484 | 61.484 | 0 | 777.5386 | [6 empty] | 504 & 5004 | 504 | 5004
5 |  | 3BHK | 3BHK | 1166.4226 | 81.6718 | 81.6718 | 0 | 1248.0944 | [6 empty] | 505 & 5005 | 505 | 5005
6 |  | Refuge Area | [12 empty] | 506 & 5006 | 506 | 5006
7 |  | 2BHK | 2BHK | 716.0546 | 61.484 | 61.484 | 0 | 777.5386 | [6 empty] | 507 & 5007 | 507 | 5007
8 |  | 2BHK | 2BHK | 716.0546 | 61.484 | 61.484 | 0 | 777.5386 | [6 empty] | 508 & 5008 | 508 | 5008
48th, 49th & 51st Floor | [8 empty] | 3
1 |  | 3BHK | 3BHK | 1164.6874 | 81.3963 | 81.3963 | 0 | 1246.0837 | [6 empty] | 401 & 5101 | 401 | 5101
2 |  | 3BHK | 3BHK | 1164.6874 | 81.3963 | 81.3963 | 0 | 1246.0837 | [6 empty] | 402 & 5102 | 402 | 5102
3 |  | 2BHK | 2BHK | 716.0546 | 61.484 | 61.484 | 0 | 777.5386 | [6 empty] | 403 & 5103 | 403 | 5103
4 |  | 2BHK | 2BHK | 716.0546 | 61.484 | 61.484 | 0 | 777.5386 | [6 empty] | 404 & 5104 | 404 | 5104
5 |  | 3BHK | 3BHK | 1166.4226 | 81.6718 | 81.6718 | 0 | 1248.0944 | [6 empty] | 405 & 5105 | 405 | 5105
6 |  | 3BHK | 3BHK | 1166.4226 | 81.6718 | 81.6718 | 0 | 1248.0944 | [6 empty] | 406 & 5106 | 406 | 5106
7 |  | 2BHK | 2BHK | 716.0546 | 61.484 | 61.484 | 0 | 777.5386 | [6 empty] | 407 & 5107 | 407 | 5107
8 |  | 2BHK | 2BHK | 716.0546 | 61.484 | 61.484 | 0 | 777.5386 | [6 empty] | 408 & 5108 | 408 | 5108
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Construction work is in process at the time of Visit (Slow Speed). Internal Visit was not allowed. 2. We considered Carpet area as per Approved Plan. 3. We considered Gross carpet area = Net carpet + Deck + Utility. 4. We have considered rate by verifying it from market inquire. 5. Car parking is subjected to authentic documentation. 6. We have updated Wing 2 (On 15/03/2025). 7. We have updated revised approved plans & CC For Wing 1, 3, 4 & 5 (On 29/11/2024). 8. We have updated revised CC from MCGM site (on 30/07/2025).
Site & Building/Tower Photographs
Name of the Project |  |  | : | Godrej Reserve Wing 1 to 5
Project Site Address |  |  | : | Godrej Reserve, Plot Bearing / CTS / Survey / Final Plot No.: 124, 125, 126, 127, 127/1, 128, 146, 146/1, 146/2, 146/3, 146/4, 146/5, 146/6, 146/7 at Akurli, Borivali, Mumbai Suburban, 400101
Site Visit Date & Time |  |  | : | 26/07/2025 @ 02:00PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Rahul Salve | Authorized Signatory Name & Signature | :
WING 5
WING 4
WING 1
WING 3
WING 2
Wing 5
Wing 4
Wing 3
Wing 2
Wing 1
Note on E9: Initiation Address
Note on E10: Plan Address
Note on E11: Map Address
Note on C17: Maybe same as RERA Registration Validity or different
Note on H17: From Rera
Note on H20: From RERA
Note on A39: As per Layout
Note on H152: Ready Recknor

## Wing1(1,2 & 4,5) (hidden)
Wing 1
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
2 | Living | 3.65 | 7.33 | 26.7545 |  |  |  | 0 |  |  | 0
4 | Kitchen | 3.55 | 2.45 | 8.6975 |  |  |  | 0 |  |  | 0 | 31.16 | Planter
5 | Store | 2.58 | 1.67 | 4.3086 |  |  |  | 0 |  |  | 0 | 31.16 | Planter
| Bed1 | 3.35 | 4.27 | 14.3045 |  |  |  | 0 |  |  | 0
| Bed2 | 3.65 | 4.58 | 16.717 |  |  |  | 0 |  |  | 0
| Bed3 | 3.83 | 3.35 | 12.8305 |  |  |  | 0 |  |  | 0
| Dining | 1.08 | 3.35 | 3.618 |  |  |  | 0 |  |  | 0
| Store WC | 1.58 | 1.07 | 1.6906 |  |  |  | 0 |  |  | 0
| C. Toilet 1 | 2.45 | 1.53 | 3.7485 |  |  |  | 0 |  |  | 0
| C. WC | 1.88 | 1.53 | 2.8764 |  |  |  | 0 |  |  | 0
| Bed 1 Toi | 1.53 | 2.5 | 3.825 |  |  |  | 0 |  |  | 0 |  | 5.76
| Bed 2 Toi | 2.45 | 1.53 | 3.7485 |  |  |  | 0 |  |  | 0
| Pass 1 | 3.68 | 1.05 | 3.864 |  |  |  | 0 |  |  | 0
| Pass 2 | 0.9 | 1.05 | 0.945 |  |  |  | 0 |  |  | 0
| Main Foyer | 1.23 | 3.78 | 4.6494 |  |  |  | 0 |  |  | 0
| Bed 2 Foyer 1 | 1.68 | 1.08 | 1.8144 |  |  |  | 0 |  |  | 0
| Bed 2 Foyer 2 | 1.68 | 0.6 | 1.008 |  |  |  | 0 |  |  | 0
| Bed 2 Foyer 3 | 1.1 | 1.78 | 1.958 |  |  |  | 0 |  |  | 0
| Total |  |  | 117.3584 |  |  | 0 | 0 |  | 0 | 0
| Utility | 1.53 | 1.85 | 2.8305 | CB |  |  | 0 |  |  | 0
| Deck | 3.65 | 1.53 | 5.5845 | FB |  |  | 0 |  |  | 0
| Total |  |  | 8.415 |  |  | 0 | 0 |  | 0 | 0
| Grand Total |  |  | 125.7734 | Sqm
|  |  |  | 1353.8249 | Sqft

## Wing1(3&6) (hidden)
Wing 1
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
3 |  | L | W | A |  | L | W | A | L | W | A
6 | Living | 7.43 | 5.48 | 40.7164 |  |  |  | 0 |  |  | 0
| Kitchen | 2.75 | 3.65 | 10.0375 |  |  |  | 0 |  |  | 0 | 31.16 | Planter
| Store | 1.93 | 1.53 | 2.9529 |  |  |  | 0 |  |  | 0 | 31.16 | Planter
| Bed1 | 3.35 | 4.28 | 14.338 |  |  |  | 0 |  |  | 0
| Bed2 | 3.98 | 3.65 | 14.527 |  |  |  | 0 |  |  | 0
| Bed3 | 3.65 | 4.28 | 15.622 |  |  |  | 0 |  |  | 0
| Bed4 | 3.65 | 5.58 | 20.367 |  |  |  | 0 |  |  | 0
| Store WC | 0.98 | 1.83 | 1.7934 |  |  |  | 0 |  |  | 0
| Bed 1 Toi | 1.53 | 2.45 | 3.7485 |  |  |  | 0 |  |  | 0
| Bed 2 Toi | 1.53 | 2.45 | 3.7485 |  |  |  | 0 |  |  | 0
| Bed 3 Toi | 1.53 | 2.45 | 3.7485 |  |  |  | 0 |  |  | 0
| Bed 4 Toi | 1.78 | 2.75 | 4.895 |  |  |  | 0 |  |  | 0
| Common WC | 1.53 | 1.83 | 2.7999 |  |  |  | 0 |  |  | 0
| Bed 4 WIW | 1.53 | 3.05 | 4.6665 |  |  |  | 0 |  |  | 0 |  | 5.76
| Main Passage | 5.38 | 1.53 | 8.2314 |  |  |  | 0 |  |  | 0
| Store pass | 1 | 1.93 | 1.93 |  |  |  | 0 |  |  | 0
| Living to Bed pass | 1.93 | 1.53 | 2.9529 |  |  |  | 0 |  |  | 0
| Bed 3 pass | 1.63 | 1.72 | 2.8036 |  |  |  | 0 |  |  | 0
| Bed 4 pass | 1.63 | 0.9 | 1.467 |  |  |  | 0 |  |  | 0
| Main Foyer | 2.58 | 1.2 | 3.096 |  |  |  | 0 |  |  | 0
| Total |  |  | 164.442 |  |  | 0 | 0 |  | 0 | 0
| Utility | 2.23 | 1.45 | 3.2335 | CB |  |  | 0 |  |  | 0
| Deck | 7.43 | 1.68 | 12.4824 | FB |  |  | 0 |  |  | 0
| Total |  |  | 15.7159 |  |  | 0 | 0 |  | 0 | 0
| Grand Total |  |  | 180.1579 | Sqm
|  |  |  | 1939.2196 | Sqft

## W4(F1&2) (hidden)
Wing 4
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
2 | Living | 3.35 | 6.1 | 20.435 |  |  |  | 0 |  |  | 0
| Kitchen | 3.05 | 2.45 | 7.4725 |  |  |  | 0 |  |  | 0 | 31.16 | Planter
| Bed1 | 3.35 | 4.28 | 14.338 |  |  |  | 0 |  |  | 0
| Bed2 | 3.05 | 3.98 | 12.139 |  |  |  | 0 |  |  | 0
| Bed3 | 3.85 | 3.48 | 13.398 |  |  |  | 0 |  |  | 0
| Dining | 0.98 | 3.48 | 3.4104 |  |  |  | 0 |  |  | 0
| C. Toilet 1 | 1.53 | 2.45 | 3.7485 |  |  |  | 0 |  |  | 0
| Bed 1 Toi | 1.53 | 2.45 | 3.7485 |  |  |  | 0 |  |  | 0 |  | 5.76
| Bed 3 Toi | 1.53 | 2.45 | 3.7485 |  |  |  | 0 |  |  | 0
| Pass 1 | 3.35 | 0.93 | 3.1155 |  |  |  | 0 |  |  | 0
| Pass 2 | 1.63 | 1.73 | 2.8199 |  |  |  | 0 |  |  | 0
| Main Foyer | 1.23 | 3.07 | 3.7761 |  |  |  | 0 |  |  | 0
| Total |  |  | 92.1499 |  |  | 0 | 0 |  | 0 | 0
| Utility | 1.08 | 1.85 | 1.998 | CB |  |  | 0 |  |  | 0
| Deck | 2.93 | 1.3 | 3.809 | FB |  |  | 0 |  |  | 0
| Total |  |  | 5.807 |  |  | 0 | 0 |  | 0 | 0
| Grand Total |  |  | 97.9569 | Sqm
|  |  |  | 1054.4081 | Sqft

## W4(F3&4) (hidden)
Wing 4
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
3 |  | L | W | A |  | L | W | A | L | W | A
4 | Living | 3.25 | 5.48 | 17.81 |  |  |  | 0 |  |  | 0
0 | Kitchen | 2.13 | 2.75 | 5.8575 |  |  |  | 0 |  |  | 0 | 31.16 | Planter
| Bed1 | 3.05 | 3.65 | 11.1325 |  |  |  | 0 |  |  | 0
| Bed2 | 3 | 0.78 | 2.34 |  |  |  | 0 |  |  | 0
|  | 3.2 | 3.18 | 10.176 |  |  |  | 0 |  |  | 0
| Dining | 0.73 | 3.23 | 2.3579 |  |  |  | 0 |  |  | 0
| C. Toilet 1 | 2.28 | 1.38 | 3.1464 |  |  |  | 0 |  |  | 0
| Bed 1 Toi | 2.28 | 1.38 | 3.1464 |  |  |  | 0 |  |  | 0 |  | 5.76
| Pass 1 | 1.53 | 0.93 | 1.4229 |  |  |  | 0 |  |  | 0
| Pass 2 | 1 | 0.3 | 0.3 |  |  |  | 0 |  |  | 0
| Main Foyer | 2.84 | 1.23 | 3.4932 |  |  |  | 0 |  |  | 0
| Total |  |  | 61.1828 |  |  | 0 | 0 |  | 0 | 0
| Utility | 1.73 | 1.05 | 1.8165 | CB |  |  | 0 |  |  | 0
| Deck | 3 | 1.28 | 3.84 | FB |  |  | 0 |  |  | 0
| Total |  |  | 5.6565 |  |  | 0 | 0 |  | 0 | 0
| Grand Total |  |  | 66.8393 | Sqm
|  |  |  | 719.4582 | Sqft

## W4(F5&6) (hidden)
Wing 4
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
5 |  | L | W | A |  | L | W | A | L | W | A
6 | Living | 3.35 | 6.1 | 20.435 |  |  |  | 0 |  |  | 0
0 | Kitchen | 3.05 | 2.45 | 7.4725 |  |  |  | 0 |  |  | 0 | 31.16 | Planter
| Bed1 | 3.05 | 3.98 | 12.139 |  |  |  | 0 |  |  | 0
| Bed2 | 3.35 | 4.28 | 14.338 |  |  |  | 0 |  |  | 0
| Bed3 | 4.05 | 3.48 | 14.094 |  |  |  | 0 |  |  | 0
| Dining | 0.98 | 3.48 | 3.4104 |  |  |  | 0 |  |  | 0
| C. Toilet 1 | 1.53 | 2.45 | 3.7485 |  |  |  | 0 |  |  | 0
| Bed 1 Toi | 1.53 | 2.45 | 3.7485 |  |  |  | 0 |  |  | 0 |  | 5.76
| Bed 2 Toi | 1.53 | 2.45 | 3.7485 |  |  |  | 0 |  |  | 0
| Pass 1 | 3.43 | 0.93 | 3.1899 |  |  |  | 0 |  |  | 0
| Main Foyer | 1.23 | 3.08 | 3.7884 |  |  |  | 0 |  |  | 0
| Total |  |  | 90.1127 |  |  | 0 | 0 |  | 0 | 0
| Utility | 1.08 | 1.85 | 1.998 | CB |  |  | 0 |  |  | 0
| Deck | 3.35 | 1.3 | 4.355 | FB |  |  | 0 |  |  | 0
| Total |  |  | 6.353 |  |  | 0 | 0 |  | 0 | 0
| Grand Total |  |  | 96.4657 | Sqm
|  |  |  | 1038.3568 | Sqft

## W4(F7&8) (hidden)
Wing 4
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
7 |  | L | W | A |  | L | W | A | L | W | A
8 | Living | 5.48 | 3.05 | 16.714 |  |  |  | 0 |  |  | 0
0 | Kitchen | 2.13 | 2.75 | 5.8575 |  |  |  | 0 |  |  | 0 | 31.16 | Planter
| Bed1 | 3.65 | 3.05 | 11.1325 |  |  |  | 0 |  |  | 0
| Bed2 | 3.95 | 3.2 | 12.64 |  |  |  | 0 |  |  | 0
| Dining | 2.87 | 0.93 | 2.6691 |  |  |  | 0 |  |  | 0
| C. Toilet 1 | 1.4 | 2.28 | 3.192 |  |  |  | 0 |  |  | 0
| Bed 1 Toi | 1.4 | 2.33 | 3.262 |  |  |  | 0 |  |  | 0 |  | 5.76
| Pass 1 | 0.93 | 1.7 | 1.581 |  |  |  | 0 |  |  | 0
| Pass 2 | 0.93 | 0.8 | 0.744 |  |  |  | 0 |  |  | 0
| Main Foyer | 2.58 | 1.23 | 3.1734 |  |  |  | 0 |  |  | 0
| Total |  |  | 60.9655 |  |  | 0 | 0 |  | 0 | 0
| Utility | 1.83 | 1.08 | 1.9764 | CB |  |  | 0 |  |  | 0
| Deck | 1.27 | 3.05 | 3.8735 | FB |  |  | 0 |  |  | 0
| Total |  |  | 5.8499 |  |  | 0 | 0 |  | 0 | 0
| Grand Total |  |  | 66.8154 | Sqm
|  |  |  | 719.201 | Sqft

## W5(F1&2) (hidden)
Wing 5
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
2 | Living | 3.65 | 6.85 | 25.0025 |  |  |  | 0 |  |  | 0
0 | Kitchen | 3.35 | 2.45 | 8.2075 |  |  |  | 0 |  |  | 0 | 31.16 | Planter
| Bed1 | 3.4 | 4.28 | 14.552 |  |  |  | 0 |  |  | 0
| Bed2 | 3.73 | 4.56 | 17.0088 |  |  |  | 0 |  |  | 0
| Bed3 | 3.88 | 3.42 | 13.2696 |  |  |  | 0 |  |  | 0
| Dining | 1.24 | 3.42 | 4.2408 |  |  |  | 0 |  |  | 0
| C. WC | 1.63 | 1.53 | 2.4939 |  |  |  | 0 |  |  | 0
| Bed 1 Toi | 1.53 | 2.45 | 3.7485 |  |  |  | 0 |  |  | 0 |  | 5.76
| Bed 2 Toi | 2.53 | 1.53 | 3.8709 |  |  |  | 0 |  |  | 0
| Bed 3 Toi | 2.45 | 1.53 | 3.7485 |  |  |  | 0 |  |  | 0
| Pass 1 | 3.48 | 1.03 | 3.5844 |  |  |  | 0 |  |  | 0
| Pass 2 | 1 | 1.03 | 1.03 |  |  |  | 0 |  |  | 0
| Main Foyer | 1.23 | 2.77 | 3.4071 |  |  |  | 0 |  |  | 0
| Bed 2 Pass 1 | 2.73 | 1.05 | 2.8665 |  |  |  | 0 |  |  | 0
| Bed 2 Pass 2 | 1.68 | 0.62 | 1.0416 |  |  |  | 0 |  |  | 0
| Bed 2 Pass 3 | 1.05 | 0.77 | 0.8085 |  |  |  | 0 |  |  | 0
| Total |  |  | 108.8811 |  |  | 0 | 0 |  | 0 | 0
| Utility | 1.28 | 1.83 | 2.3424 | CB |  |  | 0 |  |  | 0
| Deck | 3.65 | 1.43 | 5.2195 | FB |  |  | 0 |  |  | 0
| Total |  |  | 7.5619 |  |  | 0 | 0 |  | 0 | 0
| Grand Total |  |  | 116.443 | Sqm
|  |  |  | 1253.3925 | Sqft

## W5(F3&4) (hidden)
Wing 5
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
3 |  | L | W | A |  | L | W | A | L | W | A
4 | Living | 3.2 | 5.65 | 18.08 |  |  |  | 0 |  |  | 0
0 | Kitchen | 2.35 | 3.05 | 7.1675 |  |  |  | 0 |  |  | 0 | 31.16 | Planter
0 | Bed1 | 3.05 | 3.65 | 11.1325 |  |  |  | 0 |  |  | 0
| Bed2 | 3.2 | 3.65 | 11.68 |  |  |  | 0 |  |  | 0
|  | 3 | 0.65 | 1.95 |  |  |  | 0 |  |  | 0
| Dining | 1.02 | 3.28 | 3.3456 |  |  |  | 0 |  |  | 0
| C. Toilet 1 | 2.45 | 1.53 | 3.7485 |  |  |  | 0 |  |  | 0
| Bed 1 Toi | 2.55 | 1.53 | 3.9015 |  |  |  | 0 |  |  | 0 |  | 5.76
| Pass 1 | 1.1 | 1.02 | 1.122 |  |  |  | 0 |  |  | 0
| Pass 2 | 1.08 | 1.02 | 1.1016 |  |  |  | 0 |  |  | 0
| Main Foyer | 2.73 | 1.23 | 3.3579 |  |  |  | 0 |  |  | 0
| Total |  |  | 66.5871 |  |  | 0 | 0 |  | 0 | 0
| Utility | 1.9 | 1.08 | 2.052 | CB |  |  | 0 |  |  | 0
| Deck | 3 | 1.22 | 3.66 | FB |  |  | 0 |  |  | 0
| Total |  |  | 5.712 |  |  | 0 | 0 |  | 0 | 0
| Grand Total |  |  | 72.2991 | Sqm
|  |  |  | 778.2275 | Sqft

## W5(F5&6) (hidden)
Wing 1
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
5 |  | L | W | A |  | L | W | A | L | W | A
6 | Living | 3.65 | 6.85 | 25.0025 |  |  |  | 0 |  |  | 0
0 | Kitchen | 3.35 | 2.45 | 8.2075 |  |  |  | 0 |  |  | 0 | 31.16 | Planter
| Bed1 | 3.4 | 4.28 | 14.552 |  |  |  | 0 |  |  | 0
| Bed2 | 3.73 | 4.56 | 17.0088 |  |  |  | 0 |  |  | 0
| Bed3 | 3.88 | 3.43 | 13.3084 |  |  |  | 0 |  |  | 0
| Dining | 1.24 | 3.42 | 4.2408 |  |  |  | 0 |  |  | 0
| C. WC | 1.63 | 1.53 | 2.4939 |  |  |  | 0 |  |  | 0
| Bed 1 Toi | 1.53 | 2.45 | 3.7485 |  |  |  | 0 |  |  | 0 |  | 5.76
| Bed 2 Toi | 2.53 | 1.53 | 3.8709 |  |  |  | 0 |  |  | 0
| Bed 3 Toilet | 2.45 | 1.53 | 3.7485 |  |  |  | 0 |  |  | 0
| Pass 1 | 3.48 | 1.03 | 3.5844 |  |  |  | 0 |  |  | 0
| Pass 2 | 1 | 1.03 | 1.03 |  |  |  | 0 |  |  | 0
| Main Foyer | 1.23 | 2.77 | 3.4071 |  |  |  | 0 |  |  | 0
| Bed 2 Foyer 1 | 2.73 | 1.05 | 2.8665 |  |  |  | 0 |  |  | 0
| Bed 2 Foyer 2 | 1.68 | 0.62 | 1.0416 |  |  |  | 0 |  |  | 0
| Bed 2 Foyer 3 | 1.05 | 0.77 | 0.8085 |  |  |  | 0 |  |  | 0
| Total |  |  | 108.9199 |  |  | 0 | 0 |  | 0 | 0
| Utility | 1.28 | 1.85 | 2.368 | CB |  |  | 0 |  |  | 0
| Deck | 3.65 | 1.43 | 5.2195 | FB |  |  | 0 |  |  | 0
| Total |  |  | 7.5875 |  |  | 0 | 0 |  | 0 | 0
| Grand Total |  |  | 116.5074 | Sqm
|  |  |  | 1254.0857 | Sqft

## W5(F7&8) (hidden)
Wing 5
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
7 |  | L | W | A |  | L | W | A | L | W | A
8 | Living | 3.2 | 5.65 | 18.08 |  |  |  | 0 |  |  | 0
0 | Kitchen | 2.35 | 3.05 | 7.1675 |  |  |  | 0 |  |  | 0 | 31.16 | Planter
0 | Bed1 | 3.05 | 3.65 | 11.1325 |  |  |  | 0 |  |  | 0
| Bed2 | 3.2 | 3.65 | 11.68 |  |  |  | 0 |  |  | 0
|  | 3 | 0.65 | 1.95 |  |  |  | 0 |  |  | 0
| Dining | 1.02 | 3.28 | 3.3456 |  |  |  | 0 |  |  | 0
| C. Toilet 1 | 2.45 | 1.53 | 3.7485 |  |  |  | 0 |  |  | 0
| Bed 1 Toi | 2.55 | 1.53 | 3.9015 |  |  |  | 0 |  |  | 0 |  | 5.76
| Pass 1 | 1.1 | 1.02 | 1.122 |  |  |  | 0 |  |  | 0
| Pass 2 | 1.08 | 1.02 | 1.1016 |  |  |  | 0 |  |  | 0
| Main Foyer | 2.73 | 1.23 | 3.3579 |  |  |  | 0 |  |  | 0
| Total |  |  | 66.5871 |  |  | 0 | 0 |  | 0 | 0
| Utility | 1.9 | 1.08 | 2.052 | CB |  |  | 0 |  |  | 0
| Deck | 3 | 1.22 | 3.66 | FB |  |  | 0 |  |  | 0
| Total |  |  | 5.712 |  |  | 0 | 0 |  | 0 | 0
| Grand Total |  |  | 72.2991 | Sqm
|  |  |  | 778.2275 | Sqft