## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  |  | : | Kalpataru Srushti |  | Date & Time of Site Visit |  | 03/07/2025 @05:50PM
Project Name as per RERA |  |  | : | Sector 2A - Wing A, B, C, G, H, J, K & L
Name of the person met at site & Contact No. |  |  | : | Mr. Sidhharth Sharma 9137593076 |  | Date of Report Release |  | 03/07/2025
Data from APF Request Form
Branch Name/ID |  |  | : | Mumbai-RO Thane | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | Eversmile Properties Private Limited | Developer Name | : | M/s.Kalapatu Developers
Developer Office Address |  |  | : | Kalpataru Ltd.101, Kalpataru Synergy,Opp. Grand Hyatt, Santacruz (E),Mumbai, India 400 055
Project Address | : | As per ARF | : | Sector 1, Srishti Complex, Mira Road, Mira Bhayandar, Maharashtra 401107 | [5 empty] | As per plan
| : | As per Legal Documents | : | New Survey No. 63, 65, 66, 67, 68, 64/2, 39, 49, 50, 51, 52, 60/1, 62/1, 60/2, 61, 62/2, 4, 79, 71, 74, 76, 77, 78, 69, 70, 75, (Old Survey No. 231, 232, 233, 234, 235, 240/2, 207, 217, 218, 219, 220, 228/1, 230/1, 228/2, 229/, 230/2, 175, 187, 236, 238, 239, 244, 255, 256, 257, 258) At Village - Penkarpada, Mira Road (East), Tal & Dist. Thane - 401107 | [5 empty] | Old Survey No. 231, 232, 233, 234, 235, 240/2, 207, 217, 218, 219, 220, 228/1, 230/1, 228/2, 229/, 230/2, 175, 187, 236, 238, 239, 244, 255, 256, 257, 258
| : | As per Actual at site | : | Sector 2A, Near Bhakti Vedant Hospital, Penkarpada, Poonam Sagar Road, Mira Road | [5 empty] | New Survey No. 63, 65, 66, 67, 68, 64/2, 39, 49, 50, 51, 52, 60/1, 62/1, 60/2, 61, 62/2, 4, 79, 71, 74, 76, 77, 78, 69, 70, 75
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, EC & Fire Noc
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Mira-Bhayandar Municipal Corporation
RERA Registration No. | : | Sector 2A Wing A = P51700029367 Wing B = P51700028685 Wing C = P51700033851 Wing G = P51700029365 Wing H = P51700028686 Wing J, K, L = PR1338082400025 |  |  | RERA Registration Validity | : | Sector 2A - Wing A = 30/06/2027 Sector 2A - Wing B = 30/12/2027 Sector 2A - Wing C = 30/06/2027 Sector 2A - Wing G = 29/06/2028 Sector 2A - Wing H = 30/12/2027 Sector 2A - Wing J, K, L = 31/12/2029
Project Launch Date | : | Sector 2A - Wing A = 29/05/2021 Wing B = 25/03/2021 Wing C = 14/03/2022 Wing G = 29/05/2021 Wing H = 25/03/2021 Wing J, K & L = 03/10/2024 |  |  | Construction Start Date | : | Sector 2A - Wing A = 29/05/2021 Wing B = 25/03/2021 Wing C = 14/03/2022 Wing G = 14/08/2023 Wing H = 10/03/2023 Wing J, K & L = 03/10/2024
Proposed Date of Completion (As per RERA) | : | Sector 2A - Wing A = 30/06/2027 Sector 2A - Wing B = 30/12/2027 Sector 2A - Wing C = 30/06/2027 Sector 2A - Wing G = 29/06/2028 Sector 2A - Wing H = 30/12/2027 Sector 2A - Wing J, K, L = 31/12/2029 |  |  | Developer Bank Name (As per RERA) | : | HDFC Bank Ltd IFSC Code - HDFC0000060
Project Type (Mixed, Residential, Comm.) | : | Mixed |  |  | Plot Area (In Sq.Mt) | : | 576801.39 |  | 262771.98 | 1.1 | 1.1 | 0.44255
FSI/FAR Permissible | : | 1.1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 396864.18 |  | 289049.18 |  | 1.5426
Permissible Built up Area (In Sq.Mt) | : | 434375.34 |  |  | Total Number of Units Planned | : | Flats = 1336 & Shop = 11 |  | 405339.84 |  | g = 289 h = 360 | 1996
Total Number of Units Approved | : | Flats = 1742 |  |  | If Mixed, No. of Commercial Units | : | Shop = 15, Offices = 6 |  | 382618.57
Latitude | : | 19.2724 |  |  | Longitude | : | 72.8687
Location Link | : | https://maps.app.goo.gl/SKAReTZvxMMFap1C6 | [6 empty] | 416267.09
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 1.4 KM from MBMT Bus Depot
Distance from the nearest School (Km) | : | About 0.65KM from N. L. Dalmia High School |  |  | Distance from Hospital (Km) | : | About 0.3KM form Bhaktivedanta Hospital
Distance from the Main Market (Km) | : | 1. Approx. 1.8KM from Weekly Market. 2. Approx. 2.2KM from Mira Road Market. |  |  | Distance from Railway Station (Km) | : | 2.1 KM from Mira road Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Other Plot | Sector II | New S. No. (62/2) (Old S. No. 230/2) |  | Hospital / R. P. Road
As per Site / Actual |  |  | : | Samruddhi CHS | Yayati Building | Shanti Garden Sector 3 |  | Srishti Road
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Sector 2A - Wing A |  | Sale |  | 2B + G/St + 2P + 1st to 33rd Floor |  |  | 2B + G/St + 2P + 1st to 33rd Floor
Sector 2A - Wing B |  | Sale |  | 2B + G/St + 2P + 1st to 33rd Floor |  |  | 2B + G/St + 2P + 1st to 33rd Floor
Sector 2A - Wing C |  | Sale |  | 2B + G/St + 2P + 1st to 33rd Floor |  |  | 2B + G/St + 2P + 1st to 33rd Floor
Sector 2A - Wing G |  | Sale |  | 2B + G/St + 2P + 1st to 33rd Floor |  |  | 2B + G/St + 2P + 1st to 33rd Floor
Sector 2A - Wing H |  | Sale |  | 2B + G/St + 2P + 1st to 33rd Floor |  |  | 2B + G/St + 2P + 1st to 33rd Floor
Sector 2A - Wing J |  | Sale |  | 2B + G/St + 2P + 1st to 36th Floor |  |  | 2B + G/St + 2P + 1st to 36th Floor
Sector 2A - Wing K |  | Sale |  | 2B + G/St + 2P + 1st to 36th Floor |  |  | 2B + G/St + 2P + 1st to 36th Floor
Sector 2A - Wing L |  | Sale |  | 2B + G/St + 2P + 1st to 36th Floor |  |  | 2B + G/St + 2P + 1st to 36th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | MBMC/RB/2024/APL/00014 |  |  | Date: |  | 2024-07-19
Approved Plan Details (Wing A, B & C) Wing G & H | : | MBMNP/NR/4622/2021-22 |  |  | Date: |  | 2022-03-31
Approved Plan Details Wing G & H | : | MBMNP/NR/1561/2023-24 Date: |  |  | Date: |  | 2023-08-14
Approved Plan Details Wing J, K & L | : | MBMC/RB/2024/APL/00014 |  |  | Date: |  | 2024-07-19
CC Details (Wing A, B & C) | : | MNP/NR/4622/2021-22 Valid Up to: Wing A, B & C = 2B + G/St + 2P + 1st to 33rd Floor. |  |  | Date: | : | 2022-03-31
CC Details (Wing G & H) | : | MNP/NR/1561/2023-24 Valid Up to: Wing G & H = 2B + G/St + 2 Part Podium + 1st to 33rd Floor. |  |  | Date: | : | 2023-08-14
Environmental Clearance Details | : | Date: |  |  | Airport Authority Clearance Details | : | Date:
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
CC Details (Wing J, K & L) | : | MBMC/RB/2024/APL/00014 Valid Up to: Wing J, K & L = 2B + G/St + 2 Podium + 1st Floor to 36th Floor |  |  | Date: | : | 2024-07-19
EC Details Valid Up to: | : | SIA/MH/MIS/238569/2021 |  |  | Date: | : | 2023-04-12
Old Survey Nos.233(pt), 235(pt) & 256(pt) New Survey Nos.66(pt), 68(pt) and 69(pt) Proposed BUA = 323656.18 Sq.Mt Wing A, B, C & L = 2B + G/St + 2 Podium + 1st Floor to 33rd Floor Wing D = 3B + G + 2P + 1st to 33rd Floor Wing E to H = 3B + G + 2P + 1st to 31st Floor Wing J = 2B + G + 1st to 4th Floor Wing K = 2B + G+ 2P + 1st to 3th Floor
Fire NOC Details | : | MBMC/FIRE/404/2021-22 |  |  | Date: | : | 2021-06-24 |  | Construction table updated 19/11/2024
|  | Wing A & B = 2B + G/St + 2 Podium + 1st Floor to 33rd Floor Wing G & H = 2B + G/St + 2 Podium + 1st Floor to 30th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 24 Floor, Flooring & Fitting upto 21 Floor, Wooden Work upto 17 Floor Completed
Construction Status | [8 empty] | All work Completed. OC Received.
Sector 2A - Wing A = 2B + G/St + 2P + 1st to 33rd Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Piling Work in process | 8.25
|  |  |  | 2 | 1 |  | 2 | 33 | Excavation in process | 16.5
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Excavation Completed | 33
Excavation |  | 33 |  | 100% | 71.29% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 24 Floor, Flooring & Fitting upto 21 Floor, Wooden Work upto 17 Floor Completed |  | Footing in Process | 8.25
Plinth |  | 33 |  | 100% |  |  |  |  | Footing Completed | 16.5
RCC (Including podiums) |  | 36 |  | 100% |  |  |  |  | Basement 1 | 24.75
Brickwork |  | 33 |  | 100% |  |  |  |  | Basement 2 | 0
Internal Plaster |  | 33 |  | 100% |  |  |  |  | Basement 3 | 0
External Plaster |  | 33 |  | 100% |  |  |  |  | Basement 4 | 0
External Plumbing, Elevation and Waterproofing |  | 24 |  | 72.73% |  |  |  |  | Plinth in process | 0
Flooring & Fitting |  | 21 |  | 63.64% |  |  |  |  | Plinth completed | 33
Wooden Work |  | 17 |  | 51.52%
Electrical & Sanitary fittings |  | 0 |  | 0%
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0% |  |  |  |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 22 Floor, Flooring & Fitting upto 20 Floor, Wooden Work upto 12 Floor Completed
Construction Status | [8 empty] | All work Completed. OC Received.
Sector 2A - Wing B = 2B + G/St + 2P + 1st to 33rd Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Piling Work in process | 8.25
|  |  |  | 2 | 1 |  | 2 | 33 | Excavation in process | 16.5
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Excavation Completed | 33
Excavation |  | 33 |  | 100% | 70.3% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 22 Floor, Flooring & Fitting upto 20 Floor, Wooden Work upto 12 Floor Completed |  | Footing in Process | 8.25
Plinth |  | 33 |  | 100% |  |  |  |  | Footing Completed | 16.5
RCC (Including podiums) |  | 36 |  | 100% |  |  |  |  | Basement 1 | 24.75
Brickwork |  | 33 |  | 100% |  |  |  |  | Basement 2 | 0
Internal Plaster |  | 33 |  | 100% |  |  |  |  | Basement 3 | 0
External Plaster |  | 33 |  | 100% |  |  |  |  | Basement 4 | 0
External Plumbing, Elevation and Waterproofing |  | 22 |  | 66.67% |  |  |  |  | Plinth in process | 0
Flooring & Fitting |  | 20 |  | 60.61% |  |  |  |  | Plinth completed | 33
Wooden Work |  | 12 |  | 36.36%
Electrical & Sanitary fittings |  | 0 |  | 0%
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0% |  |  |  |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 20 Floor, Flooring & Fitting upto 20 Floor, Wooden Work upto 10 Floor Completed
Construction Status | [8 empty] | All work Completed. OC Received.
Sector 2A - Wing C = 2B + G/St + 2P + 1st to 33rd Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Piling Work in process | 8.25
|  |  |  | 2 | 1 |  | 2 | 33 | Excavation in process | 16.5
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Excavation Completed | 33
Excavation |  | 33 |  | 100% | 69.85% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 20 Floor, Flooring & Fitting upto 20 Floor, Wooden Work upto 10 Floor Completed |  | Footing in Process | 8.25
Plinth |  | 33 |  | 100% |  |  |  |  | Footing Completed | 16.5
RCC (Including podiums) |  | 36 |  | 100% |  |  |  |  | Basement 1 | 24.75
Brickwork |  | 33 |  | 100% |  |  |  |  | Basement 2 | 0
Internal Plaster |  | 33 |  | 100% |  |  |  |  | Basement 3 | 0
External Plaster |  | 33 |  | 100% |  |  |  |  | Basement 4 | 0
External Plumbing, Elevation and Waterproofing |  | 20 |  | 60.61% |  |  |  |  | Plinth in process | 0
Flooring & Fitting |  | 20 |  | 60.61% |  |  |  |  | Plinth completed | 33
Wooden Work |  | 10 |  | 30.3% |  |  |  |  | REFERED From Builder Site
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | https://www.kalpataru.com/thane/srishtinamaah?&utm_source=Google&utm_medium=CPC&utm_campaign=SB_Kalpataru_SrishtiNamaah_Google_Leads_Search_Brand_May24&utm_term=srishti%20namaah&gad_source=1&gbraid=0AAAAAqZgYJnnGMtn6EUxnlHcjxEfQiPCL&gclid=CjwKCAjwwqfABhBcEiwAZJjC3vf91qQesDAbJegrRjNn9iK4Q5sxZuwdfVz_CydFUUALG12666bRZhoCOp4QAvD_BwE
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0% |  |  |  |  | Excavation work Completed. Plinth work completed, RCC upto 29 Slab, Brickwork upto 26 Floor, Internal Plaster upto 20.8 Floor, External Plaster upto 20.8 Floor, External Plumbing, Elevation and Waterproofing upto 15 Floor, Flooring & Fitting upto 6 Floor Completed
Construction Status | [8 empty] | All work Completed. OC Received.
Sector 2A - Wing G = 2B + G/St + 2P + 1st to 33rd Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Piling Work in process | 8.25
|  |  |  | 2 | 1 |  | 2 | 33 | Excavation in process | 16.5
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Excavation Completed | 33
Excavation |  | 33 |  | 100% | 56.32% |  | Excavation work Completed. Plinth work completed, RCC upto 29 Slab, Brickwork upto 26 Floor, Internal Plaster upto 20.8 Floor, External Plaster upto 20.8 Floor, External Plumbing, Elevation and Waterproofing upto 15 Floor, Flooring & Fitting upto 6 Floor Completed |  | Footing in Process | 8.25
Plinth |  | 33 |  | 100% |  |  |  |  | Footing Completed | 16.5
RCC (Including podiums) |  | 29 |  | 80.56% |  |  |  |  | Basement 1 | 24.75
Brickwork |  | 26 |  | 78.79% |  |  |  |  | Basement 2 | 0
Internal Plaster |  | 20.8 |  | 63.03% |  |  |  |  | Basement 3 | 0
External Plaster |  | 20.8 |  | 63.03% |  |  |  |  | Basement 4 | 0
External Plumbing, Elevation and Waterproofing |  | 15 |  | 45.45% |  |  |  |  | Plinth in process | 0
Flooring & Fitting |  | 6 |  | 18.18% |  |  |  |  | Plinth completed | 33
Wooden Work |  | 0 |  | 0%
Electrical & Sanitary fittings |  | 0 |  | 0%
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0% |  |  |  |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 22 Floor, Flooring & Fitting upto 16 Floor, Wooden Work upto 5 Floor Completed
Construction Status | [8 empty] | All work Completed. OC Received.
Sector 2A - Wing H = 2B + G/St + 2P + 1st to 33rd Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Piling Work in process | 8.25
|  |  |  | 2 | 1 |  | 2 | 33 | Excavation in process | 16.5
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Excavation Completed | 33
Excavation |  | 33 |  | 100% | 68.56% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 22 Floor, Flooring & Fitting upto 16 Floor, Wooden Work upto 5 Floor Completed |  | Footing in Process | 8.25
Plinth |  | 33 |  | 100% |  |  |  |  | Footing Completed | 16.5
RCC (Including podiums) |  | 36 |  | 100% |  |  |  |  | Basement 1 | 24.75
Brickwork |  | 33 |  | 100% |  |  |  |  | Basement 2 | 0
Internal Plaster |  | 33 |  | 100% |  |  |  |  | Basement 3 | 0
External Plaster |  | 33 |  | 100% |  |  |  |  | Basement 4 | 0
External Plumbing, Elevation and Waterproofing |  | 22 |  | 66.67% |  |  |  |  | Plinth in process | 0
Flooring & Fitting |  | 16 |  | 48.48% |  |  |  |  | Plinth completed | 33
Wooden Work |  | 5 |  | 15.15%
Electrical & Sanitary fittings |  | 0 |  | 0%
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0% |  |  |  |  | Excavation work Completed. 1st Basement Completed
Construction Status | [8 empty] | All work Completed. OC Received.
Sector 2A - Wing J = 2B + G/St + 2P + 1st to 36th Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Piling Work in process | 9
|  |  |  | 2 | 1 |  | 2 | 36 | Excavation in process | 18
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Excavation Completed | 36
Excavation |  | 36 |  | 100% | 20% |  | Excavation work Completed. 1st Basement Completed |  | Footing in Process | 9
Plinth |  | 27 |  | 75% |  |  |  |  | Footing Completed | 18
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Basement 1 | 27
Brickwork |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Plinth completed | 36
Wooden Work |  | 0 |  | 0%
Electrical & Sanitary fittings |  | 0 |  | 0%
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0% |  |  |  |  | Excavation work Completed. 1st Basement Completed
Construction Status | [8 empty] | All work Completed. OC Received.
Sector 2A - Wing K = 2B + G/St + 2P + 1st to 36th Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Piling Work in process | 9
|  |  |  | 2 | 1 |  | 2 | 36 | Excavation in process | 18
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Excavation Completed | 36
Excavation |  | 36 |  | 100% | 20% |  | Excavation work Completed. 1st Basement Completed |  | Footing in Process | 9
Plinth |  | 27 |  | 75% |  |  |  |  | Footing Completed | 18
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Basement 1 | 27
Brickwork |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Plinth completed | 36
Wooden Work |  | 0 |  | 0%
Electrical & Sanitary fittings |  | 0 |  | 0%
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0% |  |  |  |  | Excavation work Completed. Footing work Completed
Construction Status | [8 empty] | All work Completed. OC Received.
Sector 2A - Wing L = 2B + G/St + 2P + 1st to 36th Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Piling Work in process | 9
|  |  |  | 2 | 1 |  | 2 | 36 | Excavation in process | 18
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Excavation Completed | 36
Excavation |  | 36 |  | 100% | 15% |  | Excavation work Completed. Footing work Completed |  | Footing in Process | 9
Plinth |  | 18 |  | 50% |  |  |  |  | Footing Completed | 18
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Basement 1 | 27
Brickwork |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Plinth completed | 36
Wooden Work |  | 0 |  | 0%
Electrical & Sanitary fittings |  | 0 |  | 0%
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 48.92%
PSF Rates & Other Charges | [9 empty] | Rushil | 2023-04-29
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 20000 to 21000 | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA |  |  |  | 25500
Rate of Shop Per Sq. Ft. (on Carpet area) |  |  | : : | 28000 |  |  |  |  | 26350 |  |  |  | 17000
Rate of Office Per Sq. Ft. (on Carpet area) |  |  | : : | 25500 |  |  |  |  | 27200 |  | 18133.3333 |  | 16451.6129
Car Parking Charges |  |  | : | 6,00,000/- | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | - |  |  | visitor | axis | market
Other Charges |  |  | : |  | Other Charges | : | - |  |  | 18000 | 20000 | 17200
Guideline Values | [8 empty] | 17000
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 3381.6425
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 8779.2642
Distress Value (Rs. Per sqft) | [5 empty] | : | 2705.314
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Wing C |  | Sale |  | Shop | 11 |  | 6485.7567 | 10052.9229
Wing J |  | Sale |  | Shop | 4 |  | 1986.169 | 3078.5619
Wing J |  | Sale |  | Office | 6 |  | 3644.8013 | 5649.442 | 25500
Total |  | - |  | - | 21 |  | 12116.7269 | 18780.9268
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Wing A |  | Sale |  | Flats | 228 |  | 148784.0628 | 230615.2973
Wing B |  | Sale |  | Flats | 227 |  | 145764.4099 | 225934.8353
Wing C |  | Sale |  | Flats | 225 |  | 135124.2594 | 209442.6021
Wing G |  | Sale |  | Flats | 289 |  | 172072.4235 | 266712.2564
Wing H |  | Sale |  | Flats | 113 |  | 45983.2214 | 71273.9931
Wing J |  | Sale |  | Flats | 174 |  | 221345.4365 | 343085.4266
Wing K |  | Sale |  | Flats | 243 |  | 187534.0398 | 290677.7616
Wing L |  | Sale |  | Flats | 243 |  | 186491.5604 | 289061.9186
Total |  | - |  | - | 1742 |  | 1243099.4136 | 1926804.0911
Grand Total |  | - |  | - | 1763 |  | 1255216.1405 | 1945585.0178
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
55%
Wing A
2nd Basement Floor for Parking
1st Basement Floor for Parking
Ground Floor for Meter Room, Driver Room & Parking | [12 empty] | 14058437.3748
1st Podium Floor for Residential & Parking | [12 empty] | 9238990.9248
1st Podium Floor for Residential & Parking |  | 2 |  | 3BHK | 826.9669 |  | 0 | 1281.7987 |  |  |  |  | 10428394.626
|  | 3 |  | 2BHK | 543.4701 |  | 0 | 842.3786 |  |  |  |  | 0
|  | 4 |  | 2BHK | 613.435 |  | 0 | 950.8242 |  |  |  |  | 0
2nd Podium Floor for Amenities | [8 empty] | 19907.1746 | 16188.5945 | 99A |  | 14176647.6228 | 101,..,101 | 101 | 101
1st Floor for Residential | [9 empty] | 17987.3272 | 99A |  | 14176647.6228 | 102,..,102 | 102 | 102
1st Floor for Residential |  | 1 |  | 3BHK | 833.9204 |  | 0 | 1292.5767 |  |  |  |  | 9278790.8148 | 103,..,103 | 103 | 103
|  | 2 |  | 3BHK | 833.9204 |  | 0 | 1292.5767 |  |  |  |  | 10477819.6848 | 104,..,104 | 104 | 104
|  | 3 |  | 2BHK | 545.8112 |  | 0 | 846.0074 |  |  |  |  | 10477819.6848 | 105,..,105 | 105 | 105
|  | 4 |  | 2BHK | 616.3423 |  | 0 | 955.3306 |  |  |  |  | 9370138.4244 | 106,..,106 | 106 | 106
|  | 5 |  | 2BHK | 616.3423 |  | 0 | 955.3306 |  |  |  |  | 9370138.4244 | 107,..,107 | 107 | 107
|  | 6 |  | 2BHK | 551.1846 |  | 0 | 854.3362 |  |  |  |  | 0
|  | 7 |  | 2BHK | 551.1846 |  | 0 | 854.3362 | 17387.7497 | 99A |  |  | 14176647.6228 | 25701,..,3301 | 25701 | 3301
2nd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th, 32nd & 33rd Floor | [12 empty] | 14176647.6228 | 25702,..,3302 | 25702 | 3302
2nd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th, 32nd & 33rd Floor |  | 1 |  | 3BHK | 833.9204 |  | 0 | 1292.5767 |  |  |  |  | 9278790.8148 | 25703,..,3303 | 25703 | 3303
|  | 2 |  | 3BHK | 833.9204 |  | 0 | 1292.5767 |  |  |  |  | 10477819.6848 | 25704,..,3304 | 25704 | 3304
|  | 3 |  | 2BHK | 545.8112 |  | 0 | 846.0074 |  |  |  |  | 10477819.6848 | 25705,..,3305 | 25705 | 3305
|  | 4 |  | 2BHK | 616.3423 |  | 0 | 955.3306 |  |  |  |  | 9370138.4244 | 25706,..,3306 | 25706 | 3306
|  | 5 |  | 2BHK | 616.3423 |  | 0 | 955.3306 | 20354.3418 |  |  |  | 9370138.4244 | 25707,..,3307 | 25707 | 3307
|  | 6 |  | 2BHK | 551.1846 |  | 0 | 854.3362 |  |  |  |  | 0
|  | 7 |  | 2BHK | 551.1846 |  | 0 | 854.3362 |  |  |  |  | 14176647.6228 | 61101,..,3101 | 61101 | 3101
6th, 11th, 16th, 21st, 26th & 31st Floor (Part Refuge Area) | [12 empty] | 14176647.6228 | 61102,..,3102 | 61102 | 3102
6th, 11th, 16th, 21st, 26th & 31st Floor (Part Refuge Area) |  | 1 |  | 3BHK | 833.9204 |  | 0 | 1292.5767 |  |  |  |  | 9278790.8148 | 61103,..,3103 | 61103 | 3103
|  | 2 |  | 3BHK | 833.9204 |  | 0 | 1292.5767 |  |  |  |  | 10477819.6848 | 61104,..,3104 | 61104 | 3104
|  | 3 |  | 2BHK | 545.8112 |  | 0 | 846.0074 |  |  |  |  | 10477819.6848 | 61105,..,3105 | 61105 | 3105
|  | 4 |  | 2BHK | 616.3423 |  | 0 | 955.3306 |  |  |  |  | 0 | 61106,..,3106 | 61106 | 3106
|  | 5 |  | 2BHK | 616.3423 |  | 0 | 955.3306 |  |  |  |  | 9370138.4244 | 61107,..,3107 | 61107 | 3107
|  | 6 |  | Refuge Area | [8 empty] | 0
|  | 7 |  | 2BHK | 551.1846 |  | 0 | 854.3362 |  |  |  |  | 0
Wing B | [12 empty] | 0
2nd Basement Floor for Parking | [12 empty] | 0
1st Basement Floor for Parking | [12 empty] | 0
Ground Floor for Meter Room & Parking | [12 empty] | 10401623.4816
1st Podium Floor for Residential & Parking | [12 empty] | 9159391.1448
1st Podium Floor for Residential & Parking |  | 2 |  | 2BHK | 611.8602 |  | 0 | 948.3833 |  |  |  |  | 0
|  | 3 |  | 2BHK | 538.7877 |  | 0 | 835.121 |  |  |  |  | 0
2nd Podium Floor for Amenities | [8 empty] | 15069.6334 |  |  |  | 10419098.8356 | 101,..,101 | 101 | 101
1st Floor for Residential | [12 empty] | 10419098.8356 | 102,..,102 | 102 | 102
1st Floor for Residential |  | 1 |  | 2BHK | 612.8882 |  | 0 | 949.9767 |  |  |  |  | 9199191.0348 | 103,..,103 | 103 | 103
|  | 2 |  | 2BHK | 612.8882 |  | 0 | 949.9767 |  |  |  |  | 13621864.6044 | 104,..,104 | 104 | 104
|  | 3 |  | 2BHK | 541.1289 |  | 0 | 838.7498 |  |  |  |  | 13621864.6044 | 105,..,105 | 105 | 105
|  | 4 |  | 3BHK | 801.2862 |  | 0 | 1241.9935 |  |  |  |  | 9350375.7204 | 106,..,106 | 106 | 106
|  | 5 |  | 3BHK | 801.2862 |  | 0 | 1241.9935 |  |  |  |  | 9350375.7204 | 107,..,107 | 107 | 107
|  | 6 |  | 2BHK | 550.0221 |  | 0 | 852.5343 |  |  |  |  | 0
|  | 7 |  | 2BHK | 550.0221 |  | 0 | 852.5343 |  |  |  |  | 10419098.8356 | 25701,..,3001 | 25701 | 3001
2nd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th Floor | [12 empty] | 10419098.8356 | 25702,..,3002 | 25702 | 3002
2nd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th Floor |  | 1 |  | 2BHK | 612.8882 |  | 0 | 949.9767 |  |  |  |  | 9199191.0348 | 25703,..,3003 | 25703 | 3003
|  | 2 |  | 2BHK | 612.8882 |  | 0 | 949.9767 |  |  |  |  | 13621864.6044 | 25704,..,3004 | 25704 | 3004
|  | 3 |  | 2BHK | 541.1289 |  | 0 | 838.7498 |  |  |  |  | 13621864.6044 | 25705,..,3005 | 25705 | 3005
|  | 4 |  | 3BHK | 801.2862 |  | 0 | 1241.9935 |  |  |  |  | 9350375.7204 | 25706,..,3006 | 25706 | 3006
|  | 5 |  | 3BHK | 801.2862 |  | 0 | 1241.9935 |  |  |  |  | 9350375.7204 | 25707,..,3007 | 25707 | 3007
|  | 6 |  | 2BHK | 550.0221 |  | 0 | 852.5343 |  |  |  |  | 0
|  | 7 |  | 2BHK | 550.0221 |  | 0 | 852.5343 |  |  |  |  | 10419098.8356 | 6101,..,2601 | 6101 | 2601
6th, 11th, 16th, 21st, 26th Floor (Part Refuge Area) | [12 empty] | 10419098.8356 | 6102,..,2602 | 6102 | 2602
6th, 11th, 16th, 21st, 26th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 612.8882 |  | 0 | 949.9767 |  |  |  |  | 9199191.0348 | 6103,..,2603 | 6103 | 2603
|  | 2 |  | 2BHK | 612.8882 |  | 0 | 949.9767 |  |  |  |  | 13621864.6044 | 6104,..,2604 | 6104 | 2604
|  | 3 |  | 2BHK | 541.1289 |  | 0 | 838.7498 |  |  |  |  | 13621864.6044 | 6105,..,2605 | 6105 | 2605
|  | 4 |  | 3BHK | 801.2862 |  | 0 | 1241.9935 |  |  |  |  | 0 | 6106,..,2606 | 6106 | 2606
|  | 5 |  | 3BHK | 801.2862 |  | 0 | 1241.9935 |  |  |  |  | 9350375.7204 | 6107,..,2607 | 6107 | 2607
|  | 6 |  | Refuge Area | [8 empty] | 0
|  | 7 |  | 2BHK | 550.0221 |  | 0 | 852.5343 | 20232.076 | SA |  |  | 10419098.8356 | 3101,..,3101 | 3101 | 3101
31st Floor (Part Refuge Area) | [12 empty] | 10419098.8356 | 3102,..,3102 | 3102 | 3102
31st Floor (Part Refuge Area) |  | 1 |  | 2BHK | 612.8882 |  | 0 | 949.9767 |  |  |  |  | 9199191.0348 | 3103,..,3103 | 3103 | 3103
|  | 2 |  | 2BHK | 612.8882 |  | 0 | 949.9767 |  |  |  |  | 14866951.554 | 3104,..,3104 | 3104 | 3104
|  | 3 |  | 2BHK | 541.1289 |  | 0 | 838.7498 |  |  |  |  | 14866951.554 | 3105,..,3105 | 3105 | 3105
|  | 4 |  | 3BHK | 874.5266 |  | 0 | 1355.5162 |  |  |  |  | 0 | 3106,..,3106 | 3106 | 3106
|  | 5 |  | 3BHK | 874.5266 |  | 0 | 1355.5162 |  |  |  |  | 9350375.7204 | 3107,..,3107 | 3107 | 3107
|  | 6 |  | Refuge Area | [8 empty] | 0
|  | 7 |  | 2BHK | 550.0221 |  | 0 | 852.5343 |  |  |  |  | 10419098.8356 | 3201,..,3301 | 3201 | 3301
32nd & 33rd Floor | [12 empty] | 10419098.8356 | 3202,..,3302 | 3202 | 3302
32nd & 33rd Floor |  | 1 |  | 2BHK | 612.8882 |  | 0 | 949.9767 |  |  |  |  | 9199191.0348 | 3203,..,3303 | 3203 | 3303
|  | 2 |  | 2BHK | 612.8882 |  | 0 | 949.9767 |  |  |  |  | 14866951.554 | 3204,..,3304 | 3204 | 3304
|  | 3 |  | 2BHK | 541.1289 |  | 0 | 838.7498 |  |  |  |  | 14866951.554 | 3205,..,3305 | 3205 | 3305
|  | 4 |  | 3BHK | 874.5266 |  | 0 | 1355.5162 |  |  |  |  | 9266375.079 | 3206,..,3306 | 3206 | 3306
|  | 5 |  | 3BHK | 874.5266 |  | 0 | 1355.5162 |  |  |  |  | 9266375.079 | 3207,..,3307 | 3207 | 3307
|  | 6 |  | 2BHK | 545.0809 |  | 0 | 844.8754 |  |  |  |  | 0
|  | 7 |  | 2BHK | 545.0809 |  | 0 | 844.8754 |  |  |  |  | 0
Wing C | [12 empty] | 0
2nd Basement Floor for Parking | [12 empty] | 0
1st Basement Floor for Parking | [12 empty] | 27232951.2156
Ground Floor for Commercial & Parking | [12 empty] | 4191340.14
Ground Floor for Commercial & Parking |  | 1 |  | Shop (Duplex with 1st Podium Floor) | 1601.9383 |  | 0 | 2483.0044 |  |  |  |  | 4904810.352
|  | 2 |  | Shop | 246.5494 |  | 0 | 382.1516 |  |  |  |  | 4886584.7472
|  | 3 |  | Shop | 288.5183 |  | 0 | 447.2033 |  |  |  |  | 4918900.428
|  | 4 |  | Shop | 287.4462 |  | 0 | 445.5416 |  |  |  |  | 2834740.3032
|  | 5 |  | Shop | 289.3471 |  | 0 | 448.488 |  |  |  |  | 18999461.052
|  | 6 |  | Shop | 166.7494 |  | 0 | 258.4616 |  |  |  |  | 4756882.8528
|  | 7 |  | Shop (Duplex with 1st Podium Floor) | 1117.6154 |  | 0 | 1732.3038 |  |  |  |  | 4904810.352
|  | 8 |  | Shop | 279.8166 |  | 0 | 433.7158 |  |  |  |  | 4381720.8552
|  | 9 |  | Shop | 288.5183 |  | 0 | 447.2033 |  |  |  |  | 28245661.704
|  | 10 |  | Shop | 257.7483 |  | 0 | 399.5098 |  |  |  |  | 0
|  | 11 |  | Shop (Duplex with 1st Podium Floor) | 1661.5095 |  | 0 | 2575.3397 |  |  |  |  | 0
1st Podium Floor for Commercial & Parking | [12 empty] | 0
2nd Podium Floor for Amenities | [12 empty] | 10498479.03 | 101,..,101 | 101 | 101
1st Floor for Residential | [12 empty] | 10498479.03 | 102,..,102 | 102 | 102
1st Floor for Residential |  | 1 |  | 2BHK | 617.5576 |  | 0 | 957.2143 |  |  |  |  | 9633696.0408 | 103,..,103 | 103 | 103
|  | 2 |  | 2BHK | 617.5576 |  | 0 | 957.2143 |  |  |  |  | 10502376.6744 | 104,..,104 | 104 | 104
|  | 3 |  | 2BHK | 566.688 |  | 0 | 878.3664 |  |  |  |  | 10502376.6744 | 105,..,105 | 105 | 105
|  | 4 |  | 2BHK | 617.7869 |  | 0 | 957.5696 |  |  |  |  | 9723067.38 | 106,..,106 | 106 | 106
|  | 5 |  | 2BHK | 617.7869 |  | 0 | 957.5696 |  |  |  |  | 9723067.38 | 107,..,107 | 107 | 107
|  | 6 |  | 2BHK | 571.9451 |  | 0 | 886.515 |  |  |  |  | 0
|  | 7 |  | 2BHK | 571.9451 |  | 0 | 886.515 | 16678.6064 | MB |  |  | 10498479.03 | 25701,..,3001 | 25701 | 3001
2nd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th Floor | [12 empty] | 10498479.03 | 25702,..,3002 | 25702 | 3002
2nd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th Floor |  | 1 |  | 2BHK | 617.5576 |  | 0 | 957.2143 |  |  |  |  | 9633696.0408 | 25703,..,3003 | 25703 | 3003
|  | 2 |  | 2BHK | 617.5576 |  | 0 | 957.2143 |  |  |  |  | 10502376.6744 | 25704,..,3004 | 25704 | 3004
|  | 3 |  | 2BHK | 566.688 |  | 0 | 878.3664 |  |  |  |  | 10502376.6744 | 25705,..,3005 | 25705 | 3005
|  | 4 |  | 2BHK | 617.7869 |  | 0 | 957.5696 |  |  |  |  | 9723067.38 | 25706,..,3006 | 25706 | 3006
|  | 5 |  | 2BHK | 617.7869 |  | 0 | 957.5696 |  |  |  |  | 9723067.38 | 25707,..,3007 | 25707 | 3007
|  | 6 |  | 2BHK | 571.9451 |  | 0 | 886.515 |  |  |  |  | 0
|  | 7 |  | 2BHK | 571.9451 |  | 0 | 886.515 |  |  |  |  | 10498479.03 | 6101,..,2601 | 6101 | 2601
6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area) | [12 empty] | 10498479.03 | 6102,..,2602 | 6102 | 2602
6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 617.5576 |  | 0 | 957.2143 |  |  |  |  | 9633696.0408 | 6103,..,2603 | 6103 | 2603
|  | 2 |  | 2BHK | 617.5576 |  | 0 | 957.2143 |  |  |  |  | 10502376.6744 | 6104,..,2604 | 6104 | 2604
|  | 3 |  | 2BHK | 566.688 |  | 0 | 878.3664 |  |  |  |  | 10502376.6744 | 6105,..,2605 | 6105 | 2605
|  | 4 |  | 2BHK | 617.7869 |  | 0 | 957.5696 |  |  |  |  | 0 | 6106,..,2606 | 6106 | 2606
|  | 5 |  | 2BHK | 617.7869 |  | 0 | 957.5696 |  |  |  |  | 9723067.38 | 6107,..,2607 | 6107 | 2607
|  | 6 |  | Refuge Area | [8 empty] | 0
|  | 7 |  | 2BHK | 571.9451 |  | 0 | 886.515 |  |  |  |  | 12125132.5572 | 3101,..,3101 | 3101 | 3101
31st Floor (Part Refuge Area) | [12 empty] | 12125132.5572 | 3102,..,3102 | 3102 | 3102
31st Floor (Part Refuge Area) |  | 1 |  | 2BHK | 713.2431 |  | 0 | 1105.5268 |  |  |  |  | 9633696.0408 | 3103,..,3103 | 3103 | 3103
|  | 2 |  | 2BHK | 713.2431 |  | 0 | 1105.5268 |  |  |  |  | 10502376.6744 | 3104,..,3104 | 3104 | 3104
|  | 3 |  | 2BHK | 566.688 |  | 0 | 878.3664 |  |  |  |  | 10502376.6744 | 3105,..,3105 | 3105 | 3105
|  | 4 |  | 2BHK | 617.7869 |  | 0 | 957.5696 |  |  |  |  | 0 | 3106,..,3106 | 3106 | 3106
|  | 5 |  | 2BHK | 617.7869 |  | 0 | 957.5696 |  |  |  |  | 9723067.38 | 3107,..,3107 | 3107 | 3107
|  | 6 |  | Refuge Area | [8 empty] | 0
|  | 7 |  | 2BHK | 571.9451 |  | 0 | 886.515 |  |  |  |  | 12125132.5572 | 3201,..,3301 | 3201 | 3301
32nd & 33rd Floor | [12 empty] | 12125132.5572 | 3202,..,3302 | 3202 | 3302
32nd & 33rd Floor |  | 1 |  | 2BHK | 713.2431 |  | 0 | 1105.5268 |  |  |  |  | 9633696.0408 | 3203,..,3303 | 3203 | 3303
|  | 2 |  | 2BHK | 713.2431 |  | 0 | 1105.5268 |  |  |  |  | 10502376.6744 | 3204,..,3304 | 3204 | 3304
|  | 3 |  | 2BHK | 566.688 |  | 0 | 878.3664 |  |  |  |  | 10502376.6744 | 3205,..,3305 | 3205 | 3305
|  | 4 |  | 2BHK | 617.7869 |  | 0 | 957.5696 |  |  |  |  | 9723067.38 | 3206,..,3306 | 3206 | 3306
|  | 5 |  | 2BHK | 617.7869 |  | 0 | 957.5696 |  |  |  |  | 9723067.38 | 3207,..,3307 | 3207 | 3307
|  | 6 |  | 2BHK | 571.9451 |  | 0 | 886.515 |  |  |  |  | 0
|  | 7 |  | 2BHK | 571.9451 |  | 0 | 886.515 | Utility & Balcony added while updating |  |  |  | 0
Wing G | [12 empty] | 0
2nd & 1st Basement Floor for Parking | [12 empty] | 0
Ground Floor for Meter Room, Entrance Lobby & Parking | [12 empty] | 0 | 101,..,101 | 101 | 101
1st Podium Floor For Part Residential & Parking | [12 empty] | 0 | 102,..,102 | 102 | 102
1st Podium Floor For Part Residential & Parking |  | 1 |  | Parking | [5 empty] | hyanche flat no |  |  | 7108791.0192 | 103,..,103 | 103 | 103
|  | 2 | [7 empty] | 10.764 |  |  | 7108791.0192 | 104,..,104 | 104 | 104
|  | 3 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 7108791.0192 | 105,..,105 | 105 | 105
|  | 4 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 0 | 106,..,106 | 106 | 106
|  | 5 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 0 | 107,..,107 | 107 | 107
|  | 6 |  | Entrance Lobby below | [8 empty] | 0 | 108,..,108 | 108 | 108
|  | 7 | [10 empty] | 0 | 109,..,109 | 109 | 109
|  | 8 | [10 empty] | 0
|  | 9 | [10 empty] | 0
2nd Podium Floor For Part Amenities (Enclosed Lounge, Gymnasium, Yoga Room & Society Office) & Stilt Parking | [12 empty] | 10539138.9636 | 101,..,101 | 101 | 101
1st Floor for Residential | [12 empty] | 12086393.9976 | 102,..,102 | 102 | 102
1st Floor for Residential |  | 1 |  | 2BHK | 619.9494 |  | 0 | 960.9215 |  |  |  |  | 7108791.0192 | 103,..,103 | 103 | 103
|  | 2 |  | 2BHK | 710.9644 |  | 0 | 1101.9947 |  |  |  |  | 7108791.0192 | 104,..,104 | 104 | 104
|  | 3 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 7108791.0192 | 105,..,105 | 105 | 105
|  | 4 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 12086393.9976 | 106,..,106 | 106 | 106
|  | 5 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 10539138.9636 | 107,..,107 | 107 | 107
|  | 6 |  | 2BHK | 710.9644 |  | 0 | 1101.9947 |  |  |  |  | 11624440.7916 | 108,..,108 | 108 | 108
|  | 7 |  | 2BHK | 619.9494 |  | 0 | 960.9215 |  |  |  |  | 11624440.7916 | 109,..,109 | 109 | 109
|  | 8 |  | 2BHK | 683.7906 |  | 0 | 1059.8755 |  |  |  |  | 0
|  | 9 |  | 2BHK | 683.7906 |  | 0 | 1059.8755 |  |  |  |  | 10539138.9636 | 25701,..,2801 | 25701 | 2801
2nd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th & 28th Floor | [12 empty] | 12086393.9976 | 25702,..,2802 | 25702 | 2802
2nd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th & 28th Floor |  | 1 |  | 2BHK | 619.9494 |  | 0 | 960.9215 |  |  |  |  | 7108791.0192 | 25703,..,2803 | 25703 | 2803
|  | 2 |  | 2BHK | 710.9644 |  | 0 | 1101.9947 |  |  |  |  | 7108791.0192 | 25704,..,2804 | 25704 | 2804
|  | 3 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 7108791.0192 | 25705,..,2805 | 25705 | 2805
|  | 4 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 12086393.9976 | 25706,..,2806 | 25706 | 2806
|  | 5 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 10539138.9636 | 25707,..,2807 | 25707 | 2807
|  | 6 |  | 2BHK | 710.9644 |  | 0 | 1101.9947 |  |  |  |  | 11624440.7916 | 25708,..,2808 | 25708 | 2808
|  | 7 |  | 2BHK | 619.9494 |  | 0 | 960.9215 |  |  |  |  | 11624440.7916 | 25709,..,2809 | 25709 | 2809
|  | 8 |  | 2BHK | 683.7906 |  | 0 | 1059.8755 |  |  |  |  | 0
|  | 9 |  | 2BHK | 683.7906 |  | 0 | 1059.8755 |  |  |  |  | 10539138.9636 | 6101,..,2601 | 6101 | 2601
6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area) | [12 empty] | 12086393.9976 | 6102,..,2602 | 6102 | 2602
6th, 11th, 16th, 21st & 26th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 619.9494 |  | 0 | 960.9215 |  |  |  |  | 7108791.0192 | 6103,..,2603 | 6103 | 2603
|  | 2 |  | 2BHK | 710.9644 |  | 0 | 1101.9947 |  |  |  |  | 7108791.0192 | 6104,..,2604 | 6104 | 2604
|  | 3 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 7108791.0192 | 6105,..,2605 | 6105 | 2605
|  | 4 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 12086393.9976 | 6106,..,2606 | 6106 | 2606
|  | 5 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 10539138.9636 | 6107,..,2607 | 6107 | 2607
|  | 6 |  | 2BHK | 710.9644 |  | 0 | 1101.9947 |  |  |  |  | 11624440.7916 | 6108,..,2608 | 6108 | 2608
|  | 7 |  | 2BHK | 619.9494 |  | 0 | 960.9215 |  |  |  |  | 0 | 6109,..,2609 | 6109 | 2609
|  | 8 |  | 2BHK | 683.7906 |  | 0 | 1059.8755 |  |  |  |  | 0
|  | 9 |  | Refuge Area | [8 empty] | 10539138.9636 | 29301,..,3301 | 29301 | 3301
29th, 30th, 32nd & 33th Floor | [12 empty] | 12086393.9976 | 29302,..,3302 | 29302 | 3302
29th, 30th, 32nd & 33th Floor |  | 1 |  | 2BHK | 619.9494 |  | 0 | 960.9215 |  |  |  |  | 7108791.0192 | 29303,..,3303 | 29303 | 3303
|  | 2 |  | 2BHK | 710.9644 |  | 0 | 1101.9947 |  |  |  |  | 7108791.0192 | 29304,..,3304 | 29304 | 3304
|  | 3 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 7108791.0192 | 29305,..,3305 | 29305 | 3305
|  | 4 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 12086393.9976 | 29306,..,3306 | 29306 | 3306
|  | 5 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 10539138.9636 | 29307,..,3307 | 29307 | 3307
|  | 6 |  | 2BHK | 710.9644 |  | 0 | 1101.9947 |  |  |  |  | 24908399.7552 | 29308,..,3308 | 29308 | 3308
|  | 7 |  | 2BHK | 619.9494 |  | 0 | 960.9215 |  |  |  |  | 0
|  | 8 |  | 4BHK | 1465.2 |  | 0 | 2271.06 |  |  |  |  | 0 | 3101,..,3101 | 3101 | 3101
31st Floor (Part Refuge Area) | [12 empty] | 12086393.9976 | 3102,..,3102 | 3102 | 3102
31st Floor (Part Refuge Area) |  | 1 |  | Refuge Area | [8 empty] | 7108791.0192 | 3103,..,3103 | 3103 | 3103
|  | 2 |  | 2BHK | 710.9644 |  | 0 | 1101.9947 |  |  |  |  | 7108791.0192 | 3104,..,3104 | 3104 | 3104
|  | 3 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 7108791.0192 | 3105,..,3105 | 3105 | 3105
|  | 4 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 12086393.9976 | 3106,..,3106 | 3106 | 3106
|  | 5 |  | 1BHK | 418.1642 |  | 0 | 648.1545 |  |  |  |  | 10539138.9636 | 3107,..,3107 | 3107 | 3107
|  | 6 |  | 2BHK | 710.9644 |  | 0 | 1101.9947 |  |  |  |  | 24908399.7552 | 3108,..,3108 | 3108 | 3108
|  | 7 |  | 2BHK | 619.9494 |  | 0 | 960.9215 |  |  |  |  | 0
|  | 8 |  | 4BHK | 1465.2 |  | 0 | 2271.06 |  |  |  |  | 0
Wing H | [8 empty] | AP NOT Added |  |  |  | 0
2nd & 1st Basement Floor for Parking | [12 empty] | 0
Ground Floor for Meter Room, Entrance Lobby, Drivers Room & Parking | [12 empty] | 0 | 101,..,101 | 101 | 101
1st Podium Floor For Part Residential & Parking | [12 empty] | 0 | 102,..,102 | 102 | 102
1st Podium Floor For Part Residential & Parking |  | 1 |  | Parking | [5 empty] | hyanche flat no |  |  | 0 | 103,..,103 | 103 | 103
|  | 2 | [7 empty] | 10.764 |  |  | 6373380.546 | 104,..,104 | 104 | 104
|  | 3 | [10 empty] | 6373380.546 | 105,..,105 | 105 | 105
|  | 4 |  | 1BHK | 374.9047 |  | 0 | 581.1023 |  |  |  |  | 6373380.546 | 106,..,106 | 106 | 106
|  | 5 |  | 1BHK | 374.9047 |  | 0 | 581.1023 |  |  |  |  | 0 | 107,..,107 | 107 | 107
|  | 6 |  | 1BHK | 374.9047 |  | 0 | 581.1023 |  |  |  |  | 0 | 108,..,108 | 108 | 108
|  | 7 |  | Entrance Lobby Below | [8 empty] | 0 | 109,..,109 | 109 | 109
|  | 8 | [10 empty] | 0 | 110,..,110 | 110 | 110
|  | 9 | [10 empty] | 0 | 111,..,111 | 111 | 111
|  | 10 | [10 empty] | 0
|  | 11 | [10 empty] | 0
2nd Podium Floor For Games Room, Kids Play Room, Music Room & Study Room | [12 empty] | 6373380.546 | 101,..,101 | 101 | 101
1st Floor for Residential | [12 empty] | 6711469.1748 | 102,..,102 | 102 | 102
1st Floor for Residential |  | 1 |  | 1BHK | 374.9047 |  | 0 | 581.1023 |  |  |  |  | 6711469.1748 | 103,..,103 | 103 | 103
|  | 2 |  | 1BHK | 394.7923 |  | 0 | 611.9281 |  |  |  |  | 6107133.006 | 104,..,104 | 104 | 104
|  | 3 |  | 1BHK | 394.7923 |  | 0 | 611.9281 |  |  |  |  | 6107133.006 | 105,..,105 | 105 | 105
|  | 4 |  | 1BHK | 359.2431 |  | 0 | 556.8268 |  |  |  |  | 6107133.006 | 106,..,106 | 106 | 106
|  | 5 |  | 1BHK | 359.2431 |  | 0 | 556.8268 |  |  |  |  | 6711469.1748 | 107,..,107 | 107 | 107
|  | 6 |  | 1BHK | 359.2431 |  | 0 | 556.8268 |  |  |  |  | 6711469.1748 | 108,..,108 | 108 | 108
|  | 7 |  | 1BHK | 394.7923 |  | 0 | 611.9281 |  |  |  |  | 6107133.006 | 109,..,109 | 109 | 109
|  | 8 |  | 1BHK | 394.7923 |  | 0 | 611.9281 |  |  |  |  | 9305836.4412 | 110,..,110 | 110 | 110
|  | 9 |  | 1BHK | 359.2431 |  | 0 | 556.8268 |  |  |  |  | 9305836.4412 | 111,..,111 | 111 | 111
|  | 10 |  | 2BHK | 547.4021 |  | 0 | 848.4733 |  |  |  |  | 0
|  | 11 |  | 2BHK | 547.4021 |  | 0 | 848.4733 |  |  |  |  | 6373380.546 | 201,..,701 | 201 | 701
2nd to 5th, 7th Floor | [12 empty] | 6711469.1748 | 202,..,702 | 202 | 702
2nd to 5th, 7th Floor |  | 1 |  | 1BHK | 374.9047 |  | 0 | 581.1023 |  |  |  |  | 6711469.1748 | 203,..,703 | 203 | 703
|  | 2 |  | 1BHK | 394.7923 |  | 0 | 611.9281 |  |  |  |  | 6107133.006 | 204,..,704 | 204 | 704
|  | 3 |  | 1BHK | 394.7923 |  | 0 | 611.9281 |  |  |  |  | 6107133.006 | 205,..,705 | 205 | 705
|  | 4 |  | 1BHK | 359.2431 |  | 0 | 556.8268 |  |  |  |  | 6107133.006 | 206,..,706 | 206 | 706
|  | 5 |  | 1BHK | 359.2431 |  | 0 | 556.8268 |  |  |  |  | 6711469.1748 | 207,..,707 | 207 | 707
|  | 6 |  | 1BHK | 359.2431 |  | 0 | 556.8268 |  |  |  |  | 6711469.1748 | 208,..,708 | 208 | 708
|  | 7 |  | 1BHK | 394.7923 |  | 0 | 611.9281 |  |  |  |  | 6107133.006 | 209,..,709 | 209 | 709
|  | 8 |  | 1BHK | 394.7923 |  | 0 | 611.9281 |  |  |  |  | 9305836.4412 | 210,..,710 | 210 | 710
|  | 9 |  | 1BHK | 359.2431 |  | 0 | 556.8268 |  |  |  |  | 9305836.4412 | 211,..,711 | 211 | 711
|  | 10 |  | 2BHK | 547.4021 |  | 0 | 848.4733 |  |  |  |  | 0
|  | 11 |  | 2BHK | 547.4021 |  | 0 | 848.4733 |  |  |  |  | 6373380.546 | 801,..,1201 | 801 | 1201
8th to 10th, 12th Floor | [12 empty] | 6711469.1748 | 802,..,1202 | 802 | 1202
8th to 10th, 12th Floor |  | 1 |  | 1BHK | 374.9047 |  | 0 | 581.1023 |  |  |  |  | 6711469.1748 | 803,..,1203 | 803 | 1203
|  | 2 |  | 1BHK | 394.7923 |  | 0 | 611.9281 |  |  |  |  | 6107133.006 | 804,..,1204 | 804 | 1204
|  | 3 |  | 1BHK | 394.7923 |  | 0 | 611.9281 |  |  |  |  | 6107133.006 | 805,..,1205 | 805 | 1205
|  | 4 |  | 1BHK | 359.2431 |  | 0 | 556.8268 |  |  |  |  | 6107133.006 | 806,..,1206 | 806 | 1206
|  | 5 |  | 1BHK | 359.2431 |  | 0 | 556.8268 |  |  |  |  | 6711469.1748 | 807,..,1207 | 807 | 1207
|  | 6 |  | 1BHK | 359.2431 |  | 0 | 556.8268 |  |  |  |  | 6711469.1748 | 808,..,1208 | 808 | 1208
|  | 7 |  | 1BHK | 394.7923 |  | 0 | 611.9281 |  |  |  |  | 6107133.006 | 809,..,1209 | 809 | 1209
|  | 8 |  | 1BHK | 394.7923 |  | 0 | 611.9281 |  |  |  |  | 9305836.4412 | 810,..,1210 | 810 | 1210
|  | 9 |  | 1BHK | 359.2431 |  | 0 | 556.8268 |  |  |  |  | 9305836.4412 | 811,..,1211 | 811 | 1211
|  | 10 |  | 2BHK | 547.4021 |  | 0 | 848.4733 |  |  |  |  | 0
|  | 11 |  | 2BHK | 547.4021 |  | 0 | 848.4733 |  |  |  |  | 0
Wing J | [12 empty] | 0
2nd & 1st Basement Floor for Parking | [12 empty] | #VALUE! | #REF! | #REF! | #REF!
Ground Floor for Commercial & Parking | [12 empty] | 7844713.8588 | #REF! | #REF! | #REF!
Ground Floor for Commercial & Parking |  | 1 |  | Restaurant | [8 empty] | 7788884.22 | #REF! | #REF! | #REF!
|  | 2 |  | Shop | 461.4538 | 390.4114 | 0 | 715.2533 |  |  |  |  | 9825595.5564 | #REF! | #REF! | #REF!
|  | 3 |  | Shop | 458.1697 | 387.1273 | 0 | 710.163 |  |  |  |  | 0 | #REF! | #REF! | #REF!
|  | 4 |  | Shop | 577.9762 | 506.9338 | 0 | 895.8631 |  |  |  |  | 8305678.9296 | #REF! | #REF! | #REF!
|  | 5 |  | Restaurant | [8 empty] | 0
|  | 6 |  | Shop | 488.5693 | 432.9787 | 0 | 757.2825 |  |  |  |  | 27228285.0216 | 101,..,101 | 101 | 101
1st Podium Floor for Commercial & Amenity (Children Play Area, Creche, Library etc) | [12 empty] | 6586927.542 | 102,..,102 | 102 | 102
1st Podium Floor for Commercial & Amenity (Children Play Area, Creche, Library etc) |  | - |  | Office | 1601.6638 | 1601.6638 | 0 | 2482.5789 |  |  |  |  | 6581163.42 | 103,..,103 | 103 | 103
|  | 1 |  | Office | 387.4663 | 387.4663 | 0 | 600.5728 |  |  |  |  | 8550297.288 | 104,..,104 | 104 | 104
|  | 2 |  | Office | 387.1273 | 387.1273 | 0 | 600.0473 |  |  |  |  | 9286329.9204 | 105,..,105 | 105 | 105
|  | 3 |  | Office | 502.9587 | 502.9587 | 0 | 779.5859 |  |  |  |  | 3728618.3844 | 106,..,106 | 106 | 106
|  | 4 |  | Office | 546.2547 | 546.2547 | 0 | 846.6948 |  |  |  |  | 0
|  | 5 |  | Office | 219.3305 | 219.3305 | 0 | 339.9623 | 1 |  |  |  | 0
2nd Podium Floor For Gym, Kids Play Room, Indoor Games Room, Yoga Room & Lounge | [12 empty] | 19638180.666 | 1,..,1 | 1 | 1
1st Floor for Residential | [12 empty] | 19638180.666 | 2,..,2 | 2 | 2
1st Floor for Residential |  | 1 |  | 3BHK | 1155.1871 | 1165.9511 | 0 | 1790.54 |  |  |  |  | 29599644.8124 | 3,..,3 | 3 | 3
|  | 2 |  | 3BHK | 1155.1871 | 1165.9511 | 0 | 1790.54 |  |  |  |  | 19444487.868 | 2,..,2 | 2 | 2
|  | 3 |  | 4BHK | 1741.1556 | 1741.1556 | 0 | 2698.7911 |  |  |  |  | 19444487.868 | 3,..,3 | 3 | 3
|  | 4 |  | 3BHK | 1143.7934 | 1143.7934 | 0 | 1772.8798 | 28 |  |  |  | 0
|  | 5 |  | 3BHK | 1143.7934 | 1143.7934 | 0 | 1772.8798 |  |  |  |  | 19638180.666 | 107,..,107 | 107 | 107
2nd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th, 32nd to 36th Floor | [12 empty] | 19638180.666 | 108,..,108 | 108 | 108
2nd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th, 32nd to 36th Floor |  | 1 |  | 3BHK | 1155.1871 | 1165.9511 | 0 | 1790.54 |  |  |  |  | 29599644.8124 | 109,..,109 | 109 | 109
|  | 2 |  | 3BHK | 1155.1871 | 1165.9511 | 0 | 1790.54 |  |  |  |  | 19444487.868 | 108,..,108 | 108 | 108
|  | 3 |  | 4BHK | 1741.1556 | 1741.1556 | 0 | 2698.7911 |  |  |  |  | 19444487.868 | 109,..,109 | 109 | 109
|  | 4 |  | 3BHK | 1143.7934 | 1143.7934 | 0 | 1772.8798 | 6 |  |  |  | 0
|  | 5 |  | 3BHK | 1143.7934 | 1143.7934 | 0 | 1772.8798 |  |  |  |  | 19638180.666 | 3,..,3 | 3 | 3
6th, 11th, 16th, 21st, 26th & 31st Floor (Part Refuge Floor) | [12 empty] | 19638180.666 | 4,..,4 | 4 | 4
6th, 11th, 16th, 21st, 26th & 31st Floor (Part Refuge Floor) |  | 1 |  | 3BHK | 1155.1871 | 1165.9511 | 0 | 1790.54 |  |  |  |  | 29599644.8124 | 5,..,5 | 5 | 5
|  | 2 |  | 3BHK | 1155.1871 | 1165.9511 | 0 | 1790.54 |  |  |  |  | 19444487.868 | 4,..,4 | 4 | 4
|  | 3 |  | 4BHK | 1741.1556 | 1741.1556 | 0 | 2698.7911 |  |  |  |  | 0 | 5,..,5 | 5 | 5
|  | 4 |  | 3BHK | 1143.7934 | 1143.7934 | 0 | 1772.8798 |  |  |  |  | 0
|  | 5 |  | Refuge Area | [8 empty] | 0
Wing K | [12 empty] | 0
2nd & 1st Basement Floor for Parking | [12 empty] | 0
Ground Floor for Entrance Lobby, Meter Room, Letter Room & Parking | [12 empty] | 0 | 1,..,1 | 1 | 1
1st Podium Floor for Part Residential & Part Parking | [12 empty] | 15687799.1244 | 2,..,2 | 2 | 2
1st Podium Floor for Part Residential & Part Parking |  | 1 |  | Meter Room | [8 empty] | 10779347.3112 | 3,..,3 | 3 | 3
|  | 2 |  | 3BHK | 922.8117 | 921.5846 | 0 | 1430.3582 |  |  |  |  | 15687799.1244 | 2,..,2 | 2 | 2
|  | 3 |  | 2BHK | 634.0793 | 633.8155 | 0 | 982.8228 |  |  |  |  | 0 | 3,..,3 | 3 | 3
|  | 4 |  | 3BHK | 922.8117 | 921.5846 | 0 | 1430.3582 |  |  |  |  | 0
|  | 5 |  | Entrance Lobby Below | [8 empty] | 0
2nd Podium Floor For Gym, Kids Play Room, Indoor Games Room, Yoga Room & Lounge | [12 empty] | 11081167.7184 | 1,..,1 | 1 | 1
1st Floor for Residential | [12 empty] | 15687799.1244 | 2,..,2 | 2 | 2
1st Floor for Residential |  | 1 |  | 2BHK | 651.8334 | 651.8334 | 0 | 1010.3418 |  |  |  |  | 10779347.3112 | 3,..,3 | 3 | 3
|  | 2 |  | 3BHK | 922.8117 | 921.5846 | 0 | 1430.3582 |  |  |  |  | 15687799.1244 | 2,..,2 | 2 | 2
|  | 3 |  | 2BHK | 634.0793 | 633.8155 | 0 | 982.8228 |  |  |  |  | 11081167.7184 | 3,..,3 | 3 | 3
|  | 4 |  | 3BHK | 922.8117 | 921.5846 | 0 | 1430.3582 |  |  |  |  | 12059128.7856 | 4,..,4 | 4 | 4
|  | 5 |  | 2BHK | 651.8334 | 651.8334 | 0 | 1010.3418 |  |  |  |  | 12059128.7856 | 3,..,3 | 3 | 3
|  | 6 |  | 2BHK | 709.3605 | 689.2318 | 0 | 1099.5088 |  |  |  |  | 0
|  | 7 |  | 2BHK | 709.3605 | 689.2318 | 0 | 1099.5088 |  |  |  |  | 11081167.7184 | #REF! | #REF! | #REF!
2nd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th Floor | [12 empty] | 15687799.1244 | #REF! | #REF! | #REF!
2nd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th Floor |  | 1 |  | 2BHK | 651.8334 | 651.8334 | 0 | 1010.3418 |  |  |  |  | 10779347.3112 | #REF! | #REF! | #REF!
|  | 2 |  | 3BHK | 922.8117 | 921.5846 | 0 | 1430.3582 |  |  |  |  | 15687799.1244 | #REF! | #REF! | #REF!
|  | 3 |  | 2BHK | 634.0793 | 633.8155 | 0 | 982.8228 |  |  |  |  | 11081167.7184 | #REF! | #REF! | #REF!
|  | 4 |  | 3BHK | 922.8117 | 921.5846 | 0 | 1430.3582 |  |  |  |  | 12059128.7856 | #REF! | #REF! | #REF!
|  | 5 |  | 2BHK | 651.8334 | 651.8334 | 0 | 1010.3418 |  |  |  |  | 12059128.7856 | #REF! | #REF! | #REF!
|  | 6 |  | 2BHK | 709.3605 | 689.2318 | 0 | 1099.5088 |  |  |  |  | 0
|  | 7 |  | 2BHK | 709.3605 | 689.2318 | 0 | 1099.5088 |  |  |  |  | 11081167.7184 | #REF! | #REF! | #REF!
6th, 11th, 16th, 21st, 26th Floor (Part Refuge Floor) | [12 empty] | 15687799.1244 | #REF! | #REF! | #REF!
6th, 11th, 16th, 21st, 26th Floor (Part Refuge Floor) |  | 1 |  | 2BHK | 651.8334 | 651.8334 | 0 | 1010.3418 |  |  |  |  | 10779347.3112 | #REF! | #REF! | #REF!
|  | 2 |  | 3BHK | 922.8117 | 921.5846 | 0 | 1430.3582 |  |  |  |  | 15687799.1244 | #REF! | #REF! | #REF!
|  | 3 |  | 2BHK | 634.0793 | 633.8155 | 0 | 982.8228 |  |  |  |  | 0 | #REF! | #REF! | #REF!
|  | 4 |  | 3BHK | 922.8117 | 921.5846 | 0 | 1430.3582 |  |  |  |  | 12059128.7856 | #REF! | #REF! | #REF!
|  | 5 |  | Refuge Area | [8 empty] | 12059128.7856 | #REF! | #REF! | #REF!
|  | 6 |  | 2BHK | 709.3605 | 689.2318 | 0 | 1099.5088 |  |  |  |  | 0
|  | 7 |  | 2BHK | 709.3605 | 689.2318 | 0 | 1099.5088 |  |  |  |  | 12743906.4792 | #REF! | #REF! | #REF!
31st Floor (Part Refuge Floor) | [12 empty] | 16984378.8972 | #REF! | #REF! | #REF!
31st Floor (Part Refuge Floor) |  | 1 |  | 2BHK | 749.6416 | 749.6416 | 0 | 1161.9444 |  |  |  |  | 10779347.3112 | #REF! | #REF! | #REF!
|  | 2 |  | 3BHK | 999.0811 | 999.0811 | 0 | 1548.5757 |  |  |  |  | 15687799.1244 | #REF! | #REF! | #REF!
|  | 3 |  | 2BHK | 634.0793 | 634.0793 | 0 | 982.8228 |  |  |  |  | 0 | #REF! | #REF! | #REF!
|  | 4 |  | 3BHK | 922.8117 | 922.8117 | 0 | 1430.3582 |  |  |  |  | 25947497.1132 | #REF! | #REF! | #REF!
|  | 5 |  | Refuge Area | [8 empty] | 0
|  | 6 |  | 4.5BHK | 1526.3234 | 1526.3234 | 0 | 2365.8012 |  |  |  |  | 12743906.4792 | #REF! | #REF! | #REF!
32nd to 36th Floor | [12 empty] | 16984378.8972 | #REF! | #REF! | #REF!
32nd to 36th Floor |  | 1 |  | 2BHK | 749.6416 | 749.6416 | 0 | 1161.9444 |  |  |  |  | 10779347.3112 | #REF! | #REF! | #REF!
|  | 2 |  | 3BHK | 999.0811 | 999.0811 | 0 | 1548.5757 |  |  |  |  | 15687799.1244 | #REF! | #REF! | #REF!
|  | 3 |  | 2BHK | 634.0793 | 634.0793 | 0 | 982.8228 |  |  |  |  | 11081167.7184 | #REF! | #REF! | #REF!
|  | 4 |  | 3BHK | 922.8117 | 922.8117 | 0 | 1430.3582 |  |  |  |  | 25947497.1132 | #REF! | #REF! | #REF!
|  | 5 |  | 2BHK | 651.8334 | 651.8334 | 0 | 1010.3418 |  |  |  |  | 0
|  | 6 |  | 4.5BHK | 1526.3234 | 1526.3234 | 0 | 2365.8012 |  |  |  |  | 0
Wing L | [12 empty] | 0
2nd & 1st Basement Floor for Parking | [12 empty] | 0
Ground Floor for Entrance Lobby, Meter Room, Letter Room & Parking | [12 empty] | 0 | #REF! | #REF! | #REF!
1st Podium Floor for Part Residential & Part Parking | [12 empty] | 15687799.1244 | #REF! | #REF! | #REF!
1st Podium Floor for Part Residential & Part Parking |  | 1 |  | Meter Room | [8 empty] | 10813108.5972 | #REF! | #REF! | #REF!
|  | 2 |  | 3BHK | 922.8117 | 922.8117 | 0 | 1430.3582 |  |  |  |  | 15687799.1244 | #REF! | #REF! | #REF!
|  | 3 |  | 2BHK | 636.0652 | 636.0652 | 0 | 985.9011 |  |  |  |  | 0 | #REF! | #REF! | #REF!
|  | 4 |  | 3BHK | 922.8117 | 922.8117 | 0 | 1430.3582 |  |  |  |  | 0
|  | 5 |  | Entrance Lobby Below | [8 empty] | 0
2nd Podium Floor For Gym, Kids Play Room, Indoor Games Room, Yoga Room & Lounge | [12 empty] | 11081167.7184 | #REF! | #REF! | #REF!
1st Floor for Residential | [12 empty] | 15687799.1244 | #REF! | #REF! | #REF!
1st Floor for Residential |  | 1 |  | 2BHK | 651.8334 |  | 0 | 1010.3418 |  |  |  |  | 10779347.3112 | #REF! | #REF! | #REF!
|  | 2 |  | 3BHK | 922.8117 |  | 0 | 1430.3582 |  |  |  |  | 15687799.1244 | #REF! | #REF! | #REF!
|  | 3 |  | 2BHK | 634.0793 |  | 0 | 982.8228 |  |  |  |  | 11081167.7184 | #REF! | #REF! | #REF!
|  | 4 |  | 3BHK | 922.8117 |  | 0 | 1430.3582 |  |  |  |  | 12059128.7856 | #REF! | #REF! | #REF!
|  | 5 |  | 2BHK | 651.8334 |  | 0 | 1010.3418 |  |  |  |  | 12059128.7856 | #REF! | #REF! | #REF!
|  | 6 |  | 2BHK | 709.3605 | 689.2318 | 0 | 1099.5088 |  |  |  |  | 0
|  | 7 |  | 2BHK | 709.3605 | 689.2318 | 0 | 1099.5088 |  |  |  |  | 11081167.7184 | #REF! | #REF! | #REF!
2nd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th Floor | [12 empty] | 15687799.1244 | #REF! | #REF! | #REF!
2nd to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th Floor |  | 1 |  | 2BHK | 651.8334 | 651.8334 | 0 | 1010.3418 |  |  |  |  | 10779347.3112 | #REF! | #REF! | #REF!
|  | 2 |  | 3BHK | 922.8117 | 922.8117 | 0 | 1430.3582 |  |  |  |  | 15687799.1244 | #REF! | #REF! | #REF!
|  | 3 |  | 2BHK | 634.0793 | 634.0793 | 0 | 982.8228 |  |  |  |  | 11081167.7184 | #REF! | #REF! | #REF!
|  | 4 |  | 3BHK | 922.8117 | 922.8117 | 0 | 1430.3582 |  |  |  |  | 12059128.7856 | #REF! | #REF! | #REF!
|  | 5 |  | 2BHK | 651.8334 | 651.8334 | 0 | 1010.3418 |  |  |  |  | 12059128.7856 | #REF! | #REF! | #REF!
|  | 6 |  | 2BHK | 709.3605 | 689.2318 | 0 | 1099.5088 |  |  |  |  | 0
|  | 7 |  | 2BHK | 709.3605 | 689.2318 | 0 | 1099.5088 |  |  |  |  | 11081167.7184 | #REF! | #REF! | #REF!
6th, 11th, 16th, 21st, 26th Floor (Part Refuge Floor) | [12 empty] | 15687799.1244 | #REF! | #REF! | #REF!
6th, 11th, 16th, 21st, 26th Floor (Part Refuge Floor) |  | 1 |  | 2BHK | 651.8334 | 651.8334 | 0 | 1010.3418 |  |  |  |  | 10779347.3112 | #REF! | #REF! | #REF!
|  | 2 |  | 3BHK | 922.8117 | 922.8117 | 0 | 1430.3582 |  |  |  |  | 15687799.1244 | #REF! | #REF! | #REF!
|  | 3 |  | 2BHK | 634.0793 | 634.0793 | 0 | 982.8228 |  |  |  |  | 0 | #REF! | #REF! | #REF!
|  | 4 |  | 3BHK | 922.8117 | 922.8117 | 0 | 1430.3582 |  |  |  |  | 12059128.7856 | #REF! | #REF! | #REF!
|  | 5 |  | Refuge Area | [8 empty] | 12059128.7856 | #REF! | #REF! | #REF!
|  | 6 |  | 2BHK | 709.3605 | 689.2318 | 0 | 1099.5088 |  |  |  |  | 0
|  | 7 |  | 2BHK | 709.3605 | 689.2318 | 0 | 1099.5088 |  |  |  |  | 11081167.7184 | #REF! | #REF! | #REF!
31st Floor (Part Refuge Floor) | [12 empty] | 15687799.1244 | #REF! | #REF! | #REF!
31st Floor (Part Refuge Floor) |  | 1 |  | 2BHK | 651.8334 | 651.8334 | 0 | 1010.3418 |  |  |  |  | 10779347.3112 | #REF! | #REF! | #REF!
|  | 2 |  | 3BHK | 922.8117 | 922.8117 | 0 | 1430.3582 |  |  |  |  | 15687799.1244 | #REF! | #REF! | #REF!
|  | 3 |  | 2BHK | 634.0793 | 634.0793 | 0 | 982.8228 |  |  |  |  | 0 | #REF! | #REF! | #REF!
|  | 4 |  | 3BHK | 922.8117 | 922.8117 | 0 | 1430.3582 |  |  |  |  | 25947497.1132 | #REF! | #REF! | #REF!
|  | 5 |  | Refuge Area | [8 empty] | 0
|  | 6 |  | 4.5BHK | 1526.3234 | 1526.3234 | 0 | 2365.8012 |  |  |  |  | 11081167.7184 | 107,..,107 | 107 | 107
32nd to 36th Floor | [12 empty] | 15687799.1244 | 108,..,108 | 108 | 108
32nd to 36th Floor |  | 1 |  | 2BHK | 651.8334 | 651.8334 | 0 | 1010.3418 |  |  |  |  | 10779347.3112 | 109,..,109 | 109 | 109
|  | 2 |  | 3BHK | 922.8117 | 922.8117 | 0 | 1430.3582 |  |  |  |  | 15687799.1244 | 108,..,108 | 108 | 108
|  | 3 |  | 2BHK | 634.0793 | 634.0793 | 0 | 982.8228 |  |  |  |  | 11081167.7184 | 109,..,109 | 109 | 109
|  | 4 |  | 3BHK | 922.8117 | 922.8117 | 0 | 1430.3582 |  |  |  |  | 25947497.1132 | 110,..,110 | 110 | 110
|  | 5 |  | 2BHK | 651.8334 | 651.8334 | 0 | 1010.3418
|  | 6 |  | 4.5BHK | 1526.3234 | 1526.3234 | 0 | 2365.8012
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Construction work is in process at the time of Visit. (Internal Photo was not allowed.) 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Balcony + Utility. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. On Site, we meet Mr. Sidhharth Sharma - 9820255521. 8. We have updated approved layout plan, floor plan & CC for wing G & H (on 29/11/2023). 9. Please provide approved floor plan of 6th, 11th, 13th to 33rd floor (Sheet No. 29) of Wing H. 10.We have added Wing J, K & L (On 25/04/2025) 11. We have update EC (on 24/04/2025). 12.We have referred approved Ground Floor, 2nd Podium Floor & 1st to 30th Floor Plans For Wing K, Layout Plan & CC for Wing JKL from RERA site (On 25/04/2025). 13.As per approved 1st podium Floor Plan in Wing J, Office number is not mentioned. 14.Recommended Rates of the Property have been revised as per market inquiry on 25/04/2025 | [10 empty] | Wing A Wing B Wing C Wing G Wing H Wing J, K, L
Site & Building/Tower Photographs
Name of the Project |  |  | : | Kalpataru Srushti
Project Site Address |  |  | : | Sector 1, Srishti Complex, Mira Road, Mira Bhayandar, Maharashtra 401107
Site Visit Date & Time |  |  | : | 03/07/2025 @05:50PM
Layout Plan
Remark No.13
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Suraj Mali | Authorized Signatory Name & Signature | :
Note on H7: Rushil Sanghvi or Fahad
Note on E10: Initiation Address
Note on E11: Plan Address
Note on E12: Map Address
Note on H18: From Rera
Note on H21: From RERA
Note on H210: Ready Recknor
Proposed Site
Proposed Site
N
A
D
C
B
H
G
F
E
I
J
K
A
B
C
D
C
K
J
G
L
L
Office 1
Not Metioned Office Number
Office 2
Office 3
Office 4
Office 5
A Wing
B Wing
B Wing
C Wing
D Wing
E Wing
F Wing
G Wing
H Wing