## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  | Kalpataru Sector 5 Phase 3 Starlight (Wing A, C, G, H, J, K) Eternia (Wing B) & Expansia (Wing D, E, F) |  | Date & Time of Site Visit |  | 04/07/2025 @11:15 AM
Name of the person met at site & Contact No. |  | NA |  | Date of Report Release |  | 05/07/2025
Data from APF Request Form
Branch Name/ID |  | Godrej One, Vikhroli East, Mumbai |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | Kalpataru Group |  | Developer Name |  | Agile Real Estate Pvt. Ltd.
Developer Office Address |  | Kalpataru Ltd.101, Kalpataru Synergy, Opp. Grand Hyatt, Santacruz (E), Mumbai, India 400 055.
Project Address | As per ARF | Expansia at Parkcity, Kalpataru Parkcity, Kolshet Rd, Thane West, Thane, Maharashtra 400607
| As per Legal Documents | Kalpataru Sector 5 Phase 3 (Wing A to H, J & K), Survey No..79/1A, 3, 5, 7, 8, 9, S No. 80/1(Pt), S No. 83/1, 2A, 2B/1(Pt),5, S No. 89/1, 2/B, 3, 4, 5, S No. 90/3E, 5, 7, 8, 9, 10A, 10B, 12, 13 and others, near NaMo Grand Central, Dosti West County Road, Balkum, Kolshet Industrial Area, Thane West, Thane, Thane - 400607.
| As per Actual at site | Kalpataru Sector 5 Phase 3 (Wing A to H, J & K), Survey No..79/1A, 3, 5, 7, 8, 9, S No. 80/1(Pt), S No. 83/1, 2A, 2B/1(Pt),5, S No. 89/1, 2/B, 3, 4, 5, S No. 90/3E, 5, 7, 8, 9, 10A, 10B, 12, 13 and others, near NaMo Grand Central, Dosti West County Road, Balkum, Kolshet Industrial Area, Thane West, Thane, Thane - 400607.
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC, RERA certificate.
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Thane Municipal Corporation (TMC)
RERA Registration No. | : | Wing A = P51700020201 Wing B = P51700020237 Wing C = P51700020196 Wing D, E, F = P51700016308 Wing G & H = P51700020175 Wing J & K = P51700020264 |  | RERA Registration Validity | : | Wing A, B, C, G, H, J & K = 30/12/2027 Wing D, E & F = 30/12/2027
Project Launch Date | : | Wing A, B, C, G, H, J & K = 29/03/2019 Wing D, E & F = 03/05/2018 |  | Construction Start Date | : | 2019-03-01
Proposed Date of Completion (As per RERA) | : | Wing A, B, C, G, H, J & K = 30/12/2027 Wing D, E & F = 30/12/2027 |  | Developer Bank Name (As per RERA) | : | NA
Project Type (Mixed, Residential, Comm.) | : | Residential |  | Plot Area (In Sq.Mt) | : | 348900
FSI/FAR Permissible | : | 1 |  | Net Plot Area (In Sq.Mt) | : | 241721.5
Permissible Built up Area (In Sq.Mt) | : | 265893.65 |  | Proposed Built up Area (In Sq.Mt) | : | 326681.44 |  |  | A | B | C | D | E | F | G | H | J | K
Total Number of Units Approved | : | Flats = 1698 |  | Total Number of Units Planned | : | As per RERA Site Flats = 2174 |  | 2174 | 310 | 310 | 213 | 143 | 143 | 174 | 264 | 232 | 236 | 149
Latitude, Longitude | : | 19.230994,72.991312 |  | Landmark | : | NaMo Grand Central
Location Link | : | https://maps.app.goo.gl/QDGpeayCRBUhvFBX7
Extra Amenities available | : | Clubhouse, Gym, Garden, Swimming Pool, SPA, Meditation Area & Yoga Area, Squash Court, Kids Play Area, Banquet Hall, Multipurpose Activity Room, Solar Heating System, etc.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  | Width of the Road | : | 24M
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 0.70KM from Bayer Main Gate Bus Stop
Distance from the nearest School (Km) | : | About 0.75KM from Blossom English High school |  | Distance from Hospital (Km) | : | About 1.10KM form Navjeevan Hospital
Distance from the Main Market (Km) | : | 1. Approx. 1.60KM from Lodha Amara Shopping Complex. 2. Approx. 2.00KM from R Mall Thane. |  | Distance from Railway Station (Km) | : | 6.40KM from Thane Railway Station 8.30KM from Kalva Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | Yes
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | A: North; C: South; D: East; F: West
East |  | 30.00 M. Wide Road |  |  | Dosti West County Road
West |  | Sector 4 Phase 2 |  |  | Kalpataru Immensia
North |  | Nala/Other Plot |  |  | Nala/Lodha Amara
South |  | 24.00 M. Wide Road |  |  | Kalpataru Sunrise Road/Namo Central Park
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Approved
Wing A |  | Sale | B + LG + UG + 3P + 1st to 15th Floor |  |  |  |  | changed
Wing B |  | Sale | B + LG + UG + 3P + 1st to 47th Floor |  |  |  |  | changed
Wing C |  | Sale | B + LG + UG + 3P + 1st to 45th Floor
Wing D |  | Sale | 2B + LG + UG + 3P + 1st to 32nd Floor
Wing E |  | Sale | 2B + LG + UG + 3P + 1st to 32nd Floor
Wing F |  | Sale | 2B + LG + UG + 3P + 1st to 32nd Floor
Wing G |  | Sale | 2B + LG + UG + 3P + 1st to 40th Floor
Wing H |  | Sale | 2B + LG + UG + 3P + 1st to 32nd Floor
Wing J |  | Sale | 2B + LG + UG + 3P + 1st Floor |  |  |  |  | changed
Wing K |  | Sale | 2B + LG + UG + 3P + 1st Floor |  |  |  |  | changed
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed
Wing A |  | Sale | 2B + LG + UG + 3P + 1st to 47th Floor
Wing B |  | Sale | 2B + LG + UG + 3P + 1st to 47th Floor
Wing C |  | Sale | 2B + LG + UG + 3P + 1st 45th Floor
Wing D |  | Sale | 2B + LG + UG + 3P + 1st to 32nd Floor
Wing E |  | Sale | 2B + LG + UG + 3P + 1st to 32nd Floor
Wing F |  | Sale | 2B + LG + UG + 3P + 1st to 32nd Floor
Wing G |  | Sale | 2B + LG + UG + 3P + 1st to 40th Floor
Wing H |  | Sale | 2B + LG + UG + 3P + 1st to 32nd Floor
Wing J |  | Sale | 2B + LG + UG + 3P + 1st to 32nd Floor
Wing K |  | Sale | 2B + LG + UG + 3P + 1st to 32nd Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | S05/0093/15/TMC/TD-DP/TPS/3815/21 |  |  |  | Date: | 2021-12-20
LOI/IOD Details | : | S05/0093/15/4/TMC/TD-DP/TPS/3815/21 |  |  |  | Date: | 2025-03-29 | latest plan
Approved Plan Details (Wing D to H) | : | S05/0093/15/TMC/TD-DP/TPS/3815/21 |  |  |  | Date: | 2021-12-20
Approved Plan Details (Wing A, B, C, J & K) | : | S05/0093/15/4/TMC/TD-DP/TPS/3815/21 |  |  |  | Date: | 2025-03-29 | latest plan
CC Details Valid Up to: |  | V.P. No. 86/122A/(New No. S05/0093/15)TMC/ TDD/3815/21 |  |  |  | Date: | 2021-12-20
|  | Wing A = 2B + LG + UG + 3 Podium + 1st Floor, Wing B = 2B + LG + UG + 3 Podium + 1st Floor, Wing C = 2B + LG + UG + 3 Podium + 1st Floor, Wing G = 2B + LG + UG + 3 Podium + 1st Floor, Wing H = 2B + LG + UG + 3 Podium + 1st Floor, Wing J = 2B + LG + UG + 3 Podium + 1st Floor, Wing K = 2B + LG + UG + 3 Podium + 1st Floor, Wing D = 2B + LG + UG + 3 Podium + 1st to 17th Floor, Wing E = 2B + LG + UG + 3 Podium + 1st to 17th Floor, Wing F = 2B + LG + UG + 3 Podium + 1st to 17th Floor. | [6 empty] | C: A,B,C,D,E,F,G,H,J,K
CC Details Valid Up to: |  | V.P. No. 86/122A/(New No. S05/0093/15)TMC/ TDD/3980/22 |  |  |  | Date: | 2022-02-22
Wing G = 2nd to 20th Floor
CC Details Valid Up to: |  | V.P. No. 86/122A/(New No. S05/0093/15)TMCB/ TDD/0029/(P/C)/2023/AutoDCR |  |  |  | Date: | 2023-11-24
Wing B = 2nd to 14th Floor Wing C = 2nd to 14th Floor Wing D = 18th to 24th Floor Wing E = 18th to 26th Floor Wing F = 18th to 28th Floor Wing G = 21st to 30th Floor Wing H = 2nd to 14th Floor
CC Details Valid Up to: |  | V.P. No. 86/122A/(New No. S05/0093/15)TMCB/ TDD/0120/(P/C)/2024/AutoDCR |  |  |  | Date: | 2024-04-24
Wing D = 25th to 30th Floor + 31st & 32nd (Part) Floor Wing E = 27th to 30th Floor + 31st & 32nd (Part) Floor Wing F = 29th & 30th Floor + 31st & 32nd (Part) Floor Wing G = 31st to 40th Floor Wing H = 15th to 25th Floor
CC Details Valid Up to: |  | TMCB/TDD/0009/[P/C]/2025/AutoDCR |  |  |  | Date: | 2025-03-29 | Latest CC
|  | Wing A = B + LG + UG + 1st to 3rd Podium + 1st to 15th Floor Wing B = B + LG + UG + 1st to 3rd Podium + 1st to 47th Floor Wing C = B + LG + UG + 1st to 3rd Podium + 1st to 45th Floor Wing J = 2B + LG + UG + 1st to 3rd Podium + 1st Floor Wing K = 2B + LG + UG + 1st to 3rd Podium + 1st Floor | [5 empty] | Latest CC
Fire Noc & Plans For Tower A, B, C, E, F, G, H, J, K | : | TMC/CFO/M/123/123 Valid Upto : Wing A, B = 1B + LG + UG + 3P + 1st to 47th Floor (Height 164.95 mtrs) Wing C = 1B + LG + UG + 3P + 1st 45th Floor (Height 166.35 mtrs) Wing G = 2B + LG + UG + 3P + 1st to 40th Floor (Height 140.30 Mtrs) Wing H, J & K = 2B + LG + UG + 3P + 1st to 32nd Floor (Height 116.30 Mtrs) |  |  |  | Date: | 2021-12-07
Environmental Clearance Details | : | F.No. 21-45/2017-IA-III Total plot area = 2,43,787.42 sqm. Proposed FSI area = 6,36,007.91 sqm Total proposed construction area = 14,85,927.16 sqm. The project will comprise of 44 towers. Maximum height of the building, among the 44 no. of towers is 150.50 m. |  |  |  | Date: | 2017-10-10
Change of User/Zone Certificate Details | : |  |  |  |  | Date: |  | Wing A = 2B + LG + UG + 3P + 1st to 47th Floor.
Airport Authority Clearance Details | : |  |  |  |  | Date:
Other NOC Details | : |  |  |  |  | Date:
Construction Status
Wing A = 2B + LG + UG + 3P + 1st to 47th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work in process
|  |  | 2 | 2 |  | 3 | 47 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | A: 11.75
Excavation |  | 23.5 | 50% | 5% |  | Excavation work in process |  | Excavation in process | A: 23.5
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | A: 47
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | A: 11.75
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | A: 23.5
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | A: 35.25
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | A: 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | A: 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | A: 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | A: 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | A: 47
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Wing B = 2B + LG + UG + 3P + 1st to 47th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 20 Slab, Brickwork upto 15 Floor, Internal Plaster upto 12 Floor, External Plaster upto 12 Floor, External Plumbing, Elevation and Waterproofing upto 6 Floor Completed
|  |  | 2 | 2 |  | 3 | 47 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | A: 11.75
Excavation |  | 47 | 100% | 38.13% |  | Excavation work Completed. Plinth work completed, RCC upto 20 Slab, Brickwork upto 15 Floor, Internal Plaster upto 12 Floor, External Plaster upto 12 Floor, External Plumbing, Elevation and Waterproofing upto 6 Floor Completed |  | Excavation in process | A: 23.5
Plinth |  | 47 | 100% |  |  |  |  | Excavation Completed | A: 47
RCC (Including podiums) |  | 20 | 38.46% |  |  |  |  | Footing in Process | A: 11.75
Brickwork |  | 15 | 31.91% |  |  |  |  | Footing Completed | A: 23.5
Internal Plaster |  | 12 | 25.53% |  |  |  |  | Basement 1 | A: 35.25
External Plaster |  | 12 | 25.53% |  |  |  |  | Basement 2 | A: 0
External Plumbing, Elevation and Waterproofing |  | 6 | 12.77% |  |  |  |  | Basement 3 | A: 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | A: 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | A: 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | A: 47
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Wing C = 2B + LG + UG + 3P + 1st 45th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 24 Slab, Brickwork upto 19 Floor, Internal Plaster upto 17 Floor, External Plaster upto 17 Floor, External Plumbing, Elevation and Waterproofing upto 7 Floor Completed
|  |  | 2 | 2 |  | 3 | 45 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | A: 11.25
Excavation |  | 45 | 100% | 41.78% |  | Excavation work Completed. Plinth work completed, RCC upto 24 Slab, Brickwork upto 19 Floor, Internal Plaster upto 17 Floor, External Plaster upto 17 Floor, External Plumbing, Elevation and Waterproofing upto 7 Floor Completed |  | Excavation in process | A: 22.5
Plinth |  | 45 | 100% |  |  |  |  | Excavation Completed | A: 45
RCC (Including podiums) |  | 24 | 48% |  |  |  |  | Footing in Process | A: 11.25
Brickwork |  | 19 | 42.22% |  |  |  |  | Footing Completed | A: 22.5
Internal Plaster |  | 17 | 37.78% |  |  |  |  | Basement 1 | A: 33.75
External Plaster |  | 17 | 37.78% |  |  |  |  | Basement 2 | A: 0
External Plumbing, Elevation and Waterproofing |  | 7 | 15.56% |  |  |  |  | Basement 3 | A: 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | A: 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | A: 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | A: 45
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Wing D = 2B + LG + UG + 3P + 1st to 32nd Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 20 Floor, Flooring & Fitting upto 10 Floor, Wooden Work upto 5 Floor Completed
|  |  | 2 | 2 |  | 3 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | A: 8
Excavation |  | 32 | 100% | 66.64% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 20 Floor, Flooring & Fitting upto 10 Floor, Wooden Work upto 5 Floor Completed |  | Excavation in process | A: 16
Plinth |  | 32 | 100% |  |  |  |  | Excavation Completed | A: 32
RCC (Including podiums) |  | 37 | 100% |  |  |  |  | Footing in Process | A: 8
Brickwork |  | 32 | 100% |  |  |  |  | Footing Completed | A: 16
Internal Plaster |  | 32 | 100% |  |  |  |  | Basement 1 | A: 24
External Plaster |  | 32 | 100% |  |  |  |  | Basement 2 | A: 0
External Plumbing, Elevation and Waterproofing |  | 20 | 62.5% |  |  |  |  | Basement 3 | A: 0
Flooring & Fitting |  | 10 | 31.25% |  |  |  |  | Basement 4 | A: 0
Wooden Work |  | 5 | 15.62% |  |  |  |  | Plinth in process | A: 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | A: 32
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Wing E = 2B + LG + UG + 3P + 1st to 32nd Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 20 Floor, Flooring & Fitting upto 12 Floor, Wooden Work upto 6 Floor Completed
|  |  | 2 | 2 |  | 3 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | A: 8
Excavation |  | 32 | 100% | 67.34% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 20 Floor, Flooring & Fitting upto 12 Floor, Wooden Work upto 6 Floor Completed |  | Excavation in process | A: 16
Plinth |  | 32 | 100% |  |  |  |  | Excavation Completed | A: 32
RCC (Including podiums) |  | 37 | 100% |  |  |  |  | Footing in Process | A: 8
Brickwork |  | 32 | 100% |  |  |  |  | Footing Completed | A: 16
Internal Plaster |  | 32 | 100% |  |  |  |  | Basement 1 | A: 24
External Plaster |  | 32 | 100% |  |  |  |  | Basement 2 | A: 0
External Plumbing, Elevation and Waterproofing |  | 20 | 62.5% |  |  |  |  | Basement 3 | A: 0
Flooring & Fitting |  | 12 | 37.5% |  |  |  |  | Basement 4 | A: 0
Wooden Work |  | 6 | 18.75% |  |  |  |  | Plinth in process | A: 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | A: 32
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Wing F = 2B + LG + UG + 3P + 1st to 32nd Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 20 Floor, Flooring & Fitting upto 13 Floor, Wooden Work upto 7 Floor Completed
|  |  | 2 | 2 |  | 3 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | A: 8
Excavation |  | 32 | 100% | 67.73% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 20 Floor, Flooring & Fitting upto 13 Floor, Wooden Work upto 7 Floor Completed |  | Excavation in process | A: 16
Plinth |  | 32 | 100% |  |  |  |  | Excavation Completed | A: 32
RCC (Including podiums) |  | 37 | 100% |  |  |  |  | Footing in Process | A: 8
Brickwork |  | 32 | 100% |  |  |  |  | Footing Completed | A: 16
Internal Plaster |  | 32 | 100% |  |  |  |  | Basement 1 | A: 24
External Plaster |  | 32 | 100% |  |  |  |  | Basement 2 | A: 0
External Plumbing, Elevation and Waterproofing |  | 20 | 62.5% |  |  |  |  | Basement 3 | A: 0
Flooring & Fitting |  | 13 | 40.62% |  |  |  |  | Basement 4 | A: 0
Wooden Work |  | 7 | 21.88% |  |  |  |  | Plinth in process | A: 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | A: 32
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Wing G = 2B + LG + UG + 3P + 1st to 40th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 25 Floor, Flooring & Fitting upto 16 Floor, Wooden Work upto 4 Floor Completed
|  |  | 2 | 2 |  | 3 | 40 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | A: 10
Excavation |  | 40 | 100% | 67.38% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 25 Floor, Flooring & Fitting upto 16 Floor, Wooden Work upto 4 Floor Completed |  | Excavation in process | A: 20
Plinth |  | 40 | 100% |  |  |  |  | Excavation Completed | A: 40
RCC (Including podiums) |  | 45 | 100% |  |  |  |  | Footing in Process | A: 10
Brickwork |  | 40 | 100% |  |  |  |  | Footing Completed | A: 20
Internal Plaster |  | 40 | 100% |  |  |  |  | Basement 1 | A: 30
External Plaster |  | 40 | 100% |  |  |  |  | Basement 2 | A: 0
External Plumbing, Elevation and Waterproofing |  | 25 | 62.5% |  |  |  |  | Basement 3 | A: 0
Flooring & Fitting |  | 16 | 40% |  |  |  |  | Basement 4 | A: 0
Wooden Work |  | 4 | 10% |  |  |  |  | Plinth in process | A: 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | A: 40
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Wing H = 2B + LG + UG + 3P + 1st to 32nd Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 34 Slab, Brickwork upto 29 Floor, Internal Plaster upto 27 Floor, External Plaster upto 27 Floor, External Plumbing, Elevation and Waterproofing upto 10 Floor Completed
|  |  | 2 | 2 |  | 3 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | A: 8
Excavation |  | 32 | 100% | 58.29% |  | Excavation work Completed. Plinth work completed, RCC upto 34 Slab, Brickwork upto 29 Floor, Internal Plaster upto 27 Floor, External Plaster upto 27 Floor, External Plumbing, Elevation and Waterproofing upto 10 Floor Completed |  | Excavation in process | A: 16
Plinth |  | 32 | 100% |  |  |  |  | Excavation Completed | A: 32
RCC (Including podiums) |  | 34 | 91.89% |  |  |  |  | Footing in Process | A: 8
Brickwork |  | 29 | 90.62% |  |  |  |  | Footing Completed | A: 16
Internal Plaster |  | 27 | 84.38% |  |  |  |  | Basement 1 | A: 24
External Plaster |  | 27 | 84.38% |  |  |  |  | Basement 2 | A: 0
External Plumbing, Elevation and Waterproofing |  | 10 | 31.25% |  |  |  |  | Basement 3 | A: 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | A: 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | A: 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | A: 32
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Wing J = 2B + LG + UG + 3P + 1st to 32nd Floor. |  |  | Basement | Ground |  | Podium | Floors | Work not yet Started.
|  |  | 2 | 2 |  | 3 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | A: 8
Excavation |  | 0 | 0% | 0% |  | Work not yet Started. |  | Excavation in process | A: 16
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | A: 32
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | A: 8
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | A: 16
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | A: 24
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | A: 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | A: 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | A: 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | A: 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | A: 32
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Wing K = 2B + LG + UG + 3P + 1st to 32nd Floor. |  |  | Basement | Ground |  | Podium | Floors | Work not yet Started.
|  |  | 2 | 2 |  | 3 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | A: 8
Excavation |  | 0 | 0% | 0% |  | Work not yet Started. |  | Excavation in process | A: 16
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | A: 32
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | A: 8
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | A: 16
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | A: 24
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | A: 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | A: 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | A: 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | A: 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | A: 32
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 37.48%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 18000 to 19000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA |  | RATE FROM RBL
Car Parking Charges |  | 500000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 1718.6919
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 8788.5544
Distress Value (Rs. Per sqft) |  |  |  |  | : | 1374.9535
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Wing A | Wing A | Sale |  | 8 |  | 15297.7358
Wing B | Wing B
Wing C | Wing C
Wing J | Wing J
Total |  | - |  | 0 |  | 0 | 0
Unit Details, Nomenclature and Area Details (Flats)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Wing A | Wing A | Sale |  | 102 |  | 102172.8568
Wing B | Wing B | Sale |  | 317 |  | 225524.3679
Wing C | Wing C | Sale |  | 233 |  | 274554.657
Wing D | Wing D | Sale |  | 153 |  | 103367.9393
Wing E | Wing E | Sale |  | 153 |  | 103367.9393
Wing F | Wing F | Sale |  | 186 |  | 108299.432
Wing G | Wing G | Sale |  | 276 |  | 182288.4057 |  | In RBL Area of balcony/Utility Mistake
Wing H | Wing H | Sale |  | 248 |  | 132141.0895
Wing J | Wing J | Sale |  | 18 |  | 12184.7856
Wing K | Wing K | Sale |  | 12 |  | 23123.6898
Grand Total |  | - |  | 1698 |  | 1267025.1627
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony Area+ Utility | Attached Terrace area | Gross Carpet area
Wing A
1st & 2nd Basement Floor For Parking
Lower Ground Floor For Commercial, Entrance Lobby & Parking
1A |  | Sale | Shop (Duplex With UG Floor) | 2703.5636 | 0 | 0 | 2703.5636 | bar: C
2A |  | Sale | Shop (Duplex With UG Floor) | 1919.7236 | 0 | 0 | 1919.7236
3A |  | Sale | Shop (Duplex With UG Floor) | 1968.9229 | 0 | 0 | 1968.9229
4A |  | Sale | Shop (Duplex With UG Floor) | 1100.2245 | 0 | 0 | 1100.2245
5A |  | Sale | Shop (Duplex With UG Floor) | 1162.2849 | 0 | 0 | 1162.2849
6A |  | Sale | Shop (Duplex With UG Floor) | 2929.2644 | 0 | 0 | 2929.2644
7A |  | Sale | Shop | 858.0279 | 0 | 0 | 858.0279
Upper Ground Floor For Commercial, Meter Room & Parking
18 |  | - | Shop (Duplex With LG Floor) | bar: C
2B |  | - | Shop (Duplex With LG Floor)
3B |  | - | Shop (Duplex With LG Floor)
4B |  | - | Shop (Duplex With LG Floor)
5B |  | - | Shop (Duplex With LG Floor)
6B |  | - | Shop (Duplex With LG Floor)
16 |  | Sale | Shop | 2655.724 | 0 | 0 | 2655.724
1st Podium Floor For Commercial, & Parking
25 |  | Sale | Shop | 857.0226 | 0 | 0 | 857.0226
26 |  | Sale | Shop | 1153.5241 | 0 | 0 | 1153.5241
2nd Podium Floor For Fitness Centre & Parking
3rd Podium Floor For Parking
1st, 2nd, 4th to 7th, 9th to 12th, 14th, 15th Floor For Residential | [7 empty] | 12
1 |  | Sale | 2BHK | 737.8722 | 47.5769 | 0 | 785.4491 | 69.0076 | A: 3.6905; C: 10.764
2 |  | Sale | 2BHK | 737.8722 | 47.5769 | 0 | 785.4491
3 |  | Sale | 2BHK | 625.6037 | 47.5769 | 0 | 673.1806
4 |  | Sale | 2BHK | 737.8722 | 47.5769 | 0 | 785.4491
5 |  | Sale | 3BHK | 1241.3045 | 155.1092 | 0 | 1396.4137
6 |  | Sale | 3BHK | 1092.2231 | 87.7266 | 0 | 1179.9497
7 |  | Sale | 3BHK | 1216.1167 | 146.6057 | 0 | 1362.7224
3rd, 8th, 13th Floor (Part Refuge Area) | [7 empty] | 3
1 |  | Sale | 2BHK | 737.8722 | 47.5769 | 0 | 785.4491
2 |  | Sale | 2BHK | 737.8722 | 47.5769 | 0 | 785.4491
3 |  | Sale | 2BHK | 625.6037 | 47.5769 | 0 | 673.1806
4 |  | Refuge Area
5 |  | Sale | 3BHK | 1241.3045 | 155.1092 | 0 | 1396.4137
6 |  | Sale | 3BHK | 1092.2231 | 87.7266 | 0 | 1179.9497
7 |  | Sale | 3BHK | 1216.1167 | 146.6057 | 0 | 1362.7224
Wing B
1st & 2nd Basement Floor For Parking
Lower Ground Floor For Commercial, Entrance Lobby & Parking
8A |  | Sale | Shop | 1194.7287 | 0 | 0 | 1194.7287 |  | C: 10.764
9 |  | Sale | Shop | 468.7538 | 0 | 0 | 468.7538
10 |  | Sale | Shop | 642.7438 | 0 | 0 | 642.7438
11A |  | Sale | Shop | 502.7671 | 0 | 0 | 502.7671
Upper Ground Floor For Commercial, Meter Room & Parking
9 |  | Sale | Shop Below
10 |  | Sale | Shop Below
11A |  | Sale | Shop Below
17 |  | Sale | Shop | 421.0244 | 0 | 0 | 421.0244
18A |  | Sale | Shop (Duplex With 1st Podium Floor) | 770.2153 | 0 | 0 | 770.2153
1st Podium Floor For Commercial, & Parking
2nd Podium Floor For Fitness Centre & Parking
3rd Podium Floor For Parking
1st, 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th, 40th Floor | [7 empty] | 32
1 |  | Sale | 2BHK | 589.8672 | 34.1219 | 0 | 623.9891 | 535.9988 | C: 10.764
2 |  | Sale | 2BHK | 575.874 | 35.3059 | 0 | 611.1799 | 520.892
3 |  | Sale | 2BHK | 573.3983 | 35.3059 | 0 | 608.7042 | 520.892
4 |  | Sale | 2BHK | 592.2353 | 34.1219 | 0 | 626.3572 | 535.9988
5 |  | Sale | 3BHK | 855.4151 | 44.4553 | 0 | 899.8704 | 770.6173
6 |  | Sale | 2BHK | 626.8954 | 40.0421 | 0 | 666.9374 | 590.06
7 |  | Sale | 3BHK | 863.1652 | 44.4553 | 0 | 907.6205 | 770.6173
3rd, 8th, 13th, 23rd, 28th, 33rd Floor (Part Refuge Area) | [7 empty] | 6
1 |  | Sale | 2BHK | 589.8672 | 34.1219 | 0 | 623.9891
2 |  | Sale | 2BHK | 575.874 | 35.3059 | 0 | 611.1799
3 |  | Refuge Area
4 |  | Sale | 2.5BHK | 671.0278 | 34.1219 | 0 | 705.1496
5 |  | Sale | 3BHK | 855.4151 | 44.4553 | 0 | 899.8704
6 |  | Sale | 2BHK | 626.8954 | 40.0421 | 0 | 666.9374
7 |  | Sale | 3BHK | 863.1652 | 44.4553 | 0 | 907.6205
43rd Floor (Part Refuge Area) | [7 empty] | 1
1 |  | Sale | 2BHK | 592.5582 | 56.0266 | 0 | 648.5848
2 |  | Sale | 2BHK | 575.874 | 35.3059 | 0 | 611.1799
3 |  | Refuge Area
4 |  | Sale | 2.5BHK | 671.0278 | 34.1219 | 0 | 705.1496
5 |  | Sale | 3BHK | 855.4151 | 44.4553 | 0 | 899.8704
6 |  | Sale | 2BHK | 626.8954 | 40.0421 | 0 | 666.9374
7 |  | Sale | 3BHK | 863.1652 | 44.4553 | 0 | 907.6205
18th, 38th Floor (Part Refuge, Booster Pump Area) | [7 empty] | 2
1 |  | Sale | 2BHK | 589.8672 | 34.1219 | 0 | 623.9891
2 |  | Booster Pump Area
3 |  | Refuge Area
4 |  | Sale | 2.5BHK | 671.0278 | 34.1219 | 0 | 705.1496
5 |  | Sale | 3BHK | 855.4151 | 44.4553 | 0 | 899.8704
6 |  | Sale | 2BHK | 626.8954 | 40.0421 | 0 | 666.9374
7 |  | Sale | 3BHK | 863.1652 | 44.4553 | 0 | 907.6205
41st, 42nd, 44th to 46th Floor | [7 empty] | 5
1 |  | Sale | 2BHK | 589.8672 | 34.1219 | 0 | 623.9891 | bar: C
2 |  | Sale | 2BHK | 575.874 | 35.3059 | 0 | 611.1799
3 |  | Sale | 2BHK | 573.3983 | 35.3059 | 0 | 608.7042
4 |  | Sale | 2BHK | 592.2353 | 34.1219 | 0 | 626.3572
5 |  | Sale | 3BHK | 855.4151 | 44.4553 | 0 | 899.8704
6 |  | Sale | 2BHK | 626.8954 | 40.0421 | 0 | 666.9374
7 |  | Sale | 3BHK | 863.1652 | 44.4553 | 0 | 907.6205
47th Floor (Part Terrace Area) | [7 empty] | 1
1 |  | Sale | 2BHK | 589.8672 | 34.1219 | 0 | 623.9891 | bar: C
2 |  | Sale | 2BHK | 575.874 | 35.3059 | 0 | 611.1799
3 |  | Sale | 2BHK | 573.3983 | 35.3059 | 0 | 608.7042
4 |  | Sale | 2BHK | 592.2353 | 34.1219 | 0 | 626.3572
5 |  | Sale | 3BHK | 855.4151 | 44.4553 | 0 | 899.8704
6 |  | Sale | 2BHK | 626.8954 | 40.0421 | 0 | 666.9374
7 |  | Terrace Area
Wing C
1st & 2nd Basement Floor For Parking
Lower Ground Floor For Commercial, Entrance Lobby & Parking
Upper Ground Floor For Commercial, Meter Room & Parking
1st & 2nd Podium Floor For Commercial & Parking
3rd Podium Floor For Parking
1st, 5th, 9th, 11th, 15th, 21st, 25th, 29th, 31st & 35th Floor For Residential | [7 empty] | 10
1 |  | Sale | 3BHK | 937.652 | 54.5735 | 0 | 992.2255 |  | C: 10.764
2 |  | Sale | 2BHK | 777.1608 | 57.8027 | 0 | 834.9635
3 |  | Sale | 3BHK | 1023.5488 | 64.0458 | 0 | 1087.5946
4 |  | Sale | 3BHK | 1209.9812 | 109.0393 | 0 | 1319.0206
5 |  | Sale | 3BHK (Duplex with Upper Floor) | 1638.0655 | 96.5531 | 0 | 1734.6186
6 |  | Sale | 3BHK | 1075.9694 | 54.0353 | 0 | 1130.0047
2nd, 6th, 10th, 12th, 16th, 22nd, 26th, 30th, 32nd, 36th Floor | [7 empty] | 10
1 |  | Sale | 3BHK | 942.3882 | 54.5735 | 0 | 996.9617 | bar: C
2 |  | Sale | 2BHK | 777.1608 | 57.8027 | 0 | 834.9635
3 |  | Sale | 3BHK | 1023.5488 | 64.0458 | 0 | 1087.5946
4 |  | Sale | 3BHK | 1209.9812 | 109.0393 | 0 | 1319.0206
5 |  | Flat Duplex with Lower Floor
6 |  | Sale | 3BHK | 1075.9694 | 54.0353 | 0 | 1130.0047
3rd, 13th, 23rd, 33rd Floor (Part Refuge Area) | [7 empty] | 4
1 |  | Sale | 4BHK | 1198.3561 | 54.5735 | 0 | 1252.9296 | bar: C
2 |  | Refuge Area
3 |  | Sale | 3BHK | 1023.5488 | 64.0458 | 0 | 1087.5946
4 |  | Sale | 3BHK | 1209.9812 | 109.0393 | 0 | 1319.0206
5 |  | Sale | 3BHK (Duplex with Lower Floor) | 1638.0655 | 96.5531 | 0 | 1734.6186
6 |  | Sale | 3BHK | 1075.9694 | 54.0353 | 0 | 1130.0047
4th, 14th, 24th, 34th Floor | [7 empty] | 4
1 |  | Sale | 4BHK | 1198.3561 | 54.5735 | 0 | 1252.9296 | bar: C
2 |  | Sale | 2BHK | 777.1608 | 57.8027 | 0 | 834.9635
3 |  | Sale | 3BHK | 1023.5488 | 64.0458 | 0 | 1087.5946
4 |  | Sale | 3BHK | 1209.9812 | 109.0393 | 0 | 1319.0206
5 |  | Flat Duplex with Lower Floor
6 |  | Sale | 3BHK | 1075.9694 | 54.0353 | 0 | 1130.0047
7th, 17th, 27th, 37th Floor For Residential | [7 empty] | 4
1 |  | Sale | 3BHK | 937.652 | 54.5735 | 0 | 992.2255 |  | C: 10.764
2 |  | Sale | 2BHK | 777.1608 | 57.8027 | 0 | 834.9635
3 |  | Sale | 3BHK | 1023.5488 | 64.0458 | 0 | 1087.5946
4 |  | Sale | 3BHK | 1209.9812 | 109.0393 | 0 | 1319.0206
5 |  | Sale | 3BHK (Duplex with Upper Floor) | 1638.0655 | 96.5531 | 0 | 1734.6186
6 |  | Sale | 3BHK | 1075.9694 | 54.0353 | 0 | 1130.0047
8th, 18th, 28th, 38th Floor (Part Refuge Area) | [7 empty] | 4
1 |  | Sale | 3BHK | 1198.3561 | 54.5735 | 0 | 1252.9296 | bar: C
2 |  | Refuge Area
3 |  | Sale | 3BHK | 1023.5488 | 64.0458 | 0 | 1087.5946
4 |  | Sale | 3BHK | 1209.9812 | 109.0393 | 0 | 1319.0206
5 |  | Flat Duplex with Lower Floor
6 |  | Sale | 3BHK | 1075.9694 | 54.0353 | 0 | 1130.0047
19th Floor (Part Pressure Break Tank Area) | [7 empty] | 1
1 |  | Sale | 3BHK | 937.652 | 54.5735 | 0 | 992.2255 |  | C: 10.764
2 |  | Pressure Break Tank Area
3 |  | Sale | 3BHK | 1023.5488 | 64.0458 | 0 | 1087.5946
4 |  | Sale | 3BHK | 1209.9812 | 109.0393 | 0 | 1319.0206
5 |  | Sale | 3BHK (Duplex with Upper Floor) | 1638.0655 | 96.5531 | 0 | 1734.6186
6 |  | Sale | 3BHK | 1075.9694 | 54.0353 | 0 | 1130.0047
20th Floor | [7 empty] | 1
1 |  | Sale | 3BHK | 937.652 | 54.5735 | 0 | 992.2255 |  | C: 10.764
2 |  | Sale | 2BHK | 777.1608 | 57.8027 | 0 | 834.9635
3 |  | Sale | 3BHK | 1023.5488 | 64.0458 | 0 | 1087.5946
4 |  | Sale | 3BHK | 1209.9812 | 109.0393 | 0 | 1319.0206
5 |  | Flat Duplex with Lower Floor
6 |  | Sale | 3BHK | 1075.9694 | 54.0353 | 0 | 1130.0047
39th Floor (Part Break Pressure Tank Area) | [7 empty] | 1
1 |  | Sale | 3BHK | 937.652 | 54.5735 | 0 | 992.2255 |  | C: 10.764
2 |  | Break Pressure Tank Area
3 |  | Sale | 3BHK | 1023.5488 | 64.0458 | 0 | 1087.5946
4 |  | Sale | 3BHK | 1209.9812 | 109.0393 | 0 | 1319.0206
5 |  | Sale | 3BHK (Duplex with Upper Floor) | 1638.0655 | 96.5531 | 0 | 1734.6186
6 |  | Sale | 3BHK | 1075.9694 | 54.0353 | 0 | 1130.0047
40th Floor | [7 empty] | 1
1 |  | Sale | 3BHK | 937.652 | 54.5735 | 0 | 992.2255 |  | C: 10.764
2 |  | Sale | 2BHK | 777.1608 | 57.8027 | 0 | 834.9635
3 |  | Sale | 3BHK | 1023.5488 | 64.0458 | 0 | 1087.5946
4 |  | Sale | 3BHK | 1209.9812 | 109.0393 | 0 | 1319.0206
5 |  | Flat Duplex with Lower Floor
6 |  | Sale | 3BHK | 1075.9694 | 54.0353 | 0 | 1130.0047
41st Floor | [7 empty] | 1
1 |  | Sale | 3BHK | 942.3882 | 54.5735 | 0 | 996.9617 |  | C: 10.764
2 |  | Sale | 2BHK | 777.1608 | 57.8027 | 0 | 834.9635
3 |  | Sale | 3BHK | 1023.5488 | 64.0458 | 0 | 1087.5946
4 |  | Sale | 4BHK (Duplex with Upper Floor) | 2519.8524 | 256.3985 | 0 | 2776.2509
5 |  | Sale | 3BHK (Duplex with Upper Floor) | 1638.0655 | 96.5531 | 0 | 1734.6186
6 |  | Sale | 3BHK | 1075.9694 | 54.0353 | 0 | 1130.0047
42nd Floor | [7 empty] | 1
1 |  | Sale | 3BHK | 942.3882 | 54.5735 | 0 | 996.9617 |  | C: 10.764
2 |  | Sale | 2BHK | 777.1608 | 57.8027 | 0 | 834.9635
3 |  | Sale | 3BHK | 1023.5488 | 64.0458 | 0 | 1087.5946
4 |  | Flat Duplex with Lower Floor
5 |  | Flat Duplex with Lower Floor
6 |  | Sale | 3BHK | 1075.9694 | 54.0353 | 0 | 1130.0047
43rd Floor (Part Refuge Area) | [7 empty] | 1
1 |  | Sale | 4BHK | 1226.0196 | 54.6811 | 0 | 1280.7007 | bar: C
2 |  | Refuge Area
3 |  | Sale | 3BHK | 1023.5488 | 64.0458 | 0 | 1087.5946
5 |  | Sale | 4BHK | 2110.1746 | 358.6565 | 0 | 2468.831
6 |  | Sale | 3BHK | 1075.9694 | 54.0353 | 0 | 1130.0047
44th Floor | [7 empty] | 1
1 |  | Sale | 3BHK | 942.3882 | 54.5735 | 0 | 996.9617 |  | C: 10.764
2 |  | Sale | 2BHK | 777.1608 | 57.8027 | 0 | 834.9635
3 |  | Sale | 3BHK | 1023.5488 | 64.0458 | 0 | 1087.5946
5 |  | Sale | 4BHK | 2110.1746 | 358.6565 | 0 | 2468.831
6 |  | Sale | 3BHK | 1075.9694 | 54.0353 | 0 | 1130.0047
45th Floor (Part Terrace Area) | [7 empty] | 1
1 |  | Sale | 3BHK | 942.3882 | 54.5735 | 0 | 996.9617 |  | C: 10.764
2 |  | Sale | 2BHK | 777.1608 | 57.8027 | 0 | 834.9635
3 |  | Sale | 3BHK | 1023.5488 | 64.0458 | 0 | 1087.5946
5 |  | Sale | 4BHK | 2110.1746 | 358.6565 | 0 | 2468.831
Wing D
1st & 2nd Basement Floor For Parking
Lower Ground Floor For Entrance Lobby & Parking
Upper Ground Floor For Meter Room & Parking
1st Podium Floor For Parking
2nd Podium Floor For Society Office & Parking
3rd Podium Floor For Residential & Parking | [7 empty] | 1
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 301,..,301 | 301 | 301
2 |  | Sale | 1BHK | 439.116 | 0 | 0 | 439.116 | [11 empty] | 302,..,302 | 302 | 302
3 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 303,..,303 | 303 | 303
4 |  | Parking | [16 empty] | 304,..,304 | 304 | 304
5 | [18 empty] | 305,..,305 | 305 | 305
1st, 2nd, 4th to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th & 28th to 30th Floor | [7 empty] | 24
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 12401,..,3001 | 12401 | 3001
2 |  | Sale | 1BHK | 439.116 | 0 | 0 | 439.116 | [11 empty] | 12402,..,3002 | 12402 | 3002
3 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 12403,..,3003 | 12403 | 3003
4 |  | Sale | 3BHK | 971.011 | 25.1474 | 0 | 996.1584 | [11 empty] | 12404,..,3004 | 12404 | 3004
5 |  | Sale | 3BHK | 971.011 | 25.1474 | 0 | 996.1584 | [11 empty] | 12405,..,3005 | 12405 | 3005
3rd, 12th & 27th Floor (Part Refuge Area) | [7 empty] | 3
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 301,..,2701 | 301 | 2701
2 |  | Sale | 1BHK | 439.116 | 0 | 0 | 439.116 | [11 empty] | 302,..,2702 | 302 | 2702
3 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 303,..,2703 | 303 | 2703
4 |  | Refuge Area | [16 empty] | 304,..,2704 | 304 | 2704
5 |  | Sale | 3BHK | 971.011 | 25.1474 | 0 | 996.1584 | [11 empty] | 305,..,2705 | 305 | 2705
7th & 22nd Floor (Part Refuge Area) | [7 empty] | 2
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 701,..,2201 | 701 | 2201
2 |  | Sale | 1BHK | 439.116 | 0 | 0 | 439.116 | [11 empty] | 702,..,2202 | 702 | 2202
3 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 703,..,2203 | 703 | 2203
4 |  | Sale | 3BHK | 971.011 | 25.1474 | 0 | 996.1584 | [11 empty] | 704,..,2204 | 704 | 2204
5 |  | Refuge Area | [16 empty] | 705,..,2205 | 705 | 2205
17th Floor (Part Refuge Area) | [7 empty] | 1
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 101,..,1701 | 101 | 1701
2 |  | Sale | 1BHK | 439.116 | 0 | 0 | 439.116 | [11 empty] | 102,..,1702 | 102 | 1702
3 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 103,..,1703 | 103 | 1703
4 |  | Refuge Area | [16 empty] | 104,..,1704 | 104 | 1704
5 |  | Sale | 3BHK | 971.011 | 25.1474 | 0 | 996.1584 | [11 empty] | 105,..,1705 | 105 | 1705
31st Floor (Part Terrace Area) | [7 empty] | 1
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 3101,..,3101 | 3101 | 3101
2 |  | Sale | 1BHK | 439.116 | 0 | 0 | 439.116 | [11 empty] | 3102,..,3102 | 3102 | 3102
3 |  | Terrace Area | [16 empty] | 3103,..,3103 | 3103 | 3103
4 |  | Sale | 3BHK | 971.011 | 25.1474 | 0 | 996.1584 | [11 empty] | 3104,..,3104 | 3104 | 3104
5 |  | Terrace Area | [16 empty] | 3105,..,3105 | 3105 | 3105
32nd Floor | [7 empty] | 1
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 3201,..,3201 | 3201 | 3201
2 |  | Sale | 1BHK | 439.116 | 0 | 0 | 439.116 | [11 empty] | 3202,..,3202 | 3202 | 3202
3 |  | Terrace Area Below @ 31st Floor | [16 empty] | 3203,..,3203 | 3203 | 3203
4 |  | Sale | 3BHK | 971.011 | 25.1474 | 0 | 996.1584 | [11 empty] | 3204,..,3204 | 3204 | 3204
5 |  | Terrace Area Below @ 31st Floor | [16 empty] | 3205,..,3205 | 3205 | 3205
Wing E
1st & 2nd Basement Floor For Parking
Lower Ground Floor For Entrance Lobby & Parking
Upper Ground Floor For Meter Room & Parking
1st Podium Floor For Parking
2nd Podium Floor For Society Office & Parking
3rd Podium Floor For Residential & Parking | [7 empty] | 1
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 301,..,301 | 301 | 301
2 |  | Sale | 1BHK | 439.116 | 0 | 0 | 439.116 | [11 empty] | 302,..,302 | 302 | 302
3 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 303,..,303 | 303 | 303
4 |  | Parking | [16 empty] | 304,..,304 | 304 | 304
5 | [18 empty] | 305,..,305 | 305 | 305
1st, 2nd, 4th to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th & 28th to 30th Floor | [7 empty] | 24
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 12401,..,3001 | 12401 | 3001
2 |  | Sale | 1BHK | 439.116 | 0 | 0 | 439.116 | [11 empty] | 12402,..,3002 | 12402 | 3002
3 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 12403,..,3003 | 12403 | 3003
4 |  | Sale | 3BHK | 971.011 | 25.1474 | 0 | 996.1584 | [11 empty] | 12404,..,3004 | 12404 | 3004
5 |  | Sale | 3BHK | 971.011 | 25.1474 | 0 | 996.1584 | [11 empty] | 12405,..,3005 | 12405 | 3005
3rd, 12th & 27th Floor (Part Refuge Area) | [7 empty] | 3
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 301,..,2701 | 301 | 2701
2 |  | Sale | 1BHK | 439.116 | 0 | 0 | 439.116 | [11 empty] | 302,..,2702 | 302 | 2702
3 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 303,..,2703 | 303 | 2703
4 |  | Refuge Area | [16 empty] | 304,..,2704 | 304 | 2704
5 |  | Sale | 3BHK | 971.011 | 25.1474 | 0 | 996.1584 | [11 empty] | 305,..,2705 | 305 | 2705
7th & 22nd Floor (Part Refuge Area) | [7 empty] | 2
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 701,..,2201 | 701 | 2201
2 |  | Sale | 1BHK | 439.116 | 0 | 0 | 439.116 | [11 empty] | 702,..,2202 | 702 | 2202
3 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 703,..,2203 | 703 | 2203
4 |  | Sale | 3BHK | 971.011 | 25.1474 | 0 | 996.1584 | [11 empty] | 704,..,2204 | 704 | 2204
5 |  | Refuge Area | [16 empty] | 705,..,2205 | 705 | 2205
17th Floor (Part Refuge Area) | [7 empty] | 1
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 101,..,1701 | 101 | 1701
2 |  | Sale | 1BHK | 439.116 | 0 | 0 | 439.116 | [11 empty] | 102,..,1702 | 102 | 1702
3 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 103,..,1703 | 103 | 1703
4 |  | Refuge Area | [16 empty] | 104,..,1704 | 104 | 1704
5 |  | Sale | 3BHK | 971.011 | 25.1474 | 0 | 996.1584 | [11 empty] | 105,..,1705 | 105 | 1705
31st Floor (Part Terrace Area) | [7 empty] | 1
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 3101,..,3101 | 3101 | 3101
2 |  | Sale | 1BHK | 439.116 | 0 | 0 | 439.116 | [11 empty] | 3102,..,3102 | 3102 | 3102
3 |  | Terrace Area | [16 empty] | 3103,..,3103 | 3103 | 3103
4 |  | Sale | 3BHK | 971.011 | 25.1474 | 0 | 996.1584 | [11 empty] | 3104,..,3104 | 3104 | 3104
5 |  | Terrace Area | [16 empty] | 3105,..,3105 | 3105 | 3105
32nd Floor | [7 empty] | 1
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 3201,..,3201 | 3201 | 3201
2 |  | Sale | 1BHK | 439.116 | 0 | 0 | 439.116 | [11 empty] | 3202,..,3202 | 3202 | 3202
3 |  | Terrace Area Below @ 31st Floor | [16 empty] | 3203,..,3203 | 3203 | 3203
4 |  | Sale | 3BHK | 971.011 | 25.1474 | 0 | 996.1584 | [11 empty] | 3204,..,3204 | 3204 | 3204
5 |  | Terrace Area Below @ 31st Floor | [16 empty] | 3205,..,3205 | 3205 | 3205
Wing F
1st & 2nd Basement Floor For Parking
Lower Ground Floor For Amenities, Entrance Lobby & Parking
Upper Ground Floor For Meter Room & Parking
1st & 2nd Podium Floor Parking
3rd Podium Floor For Residential, Fitness Centre & Parking
1 |  | Fitness Centre | [16 empty] | 301,..,301 | 301 | 301
2 |  | Sale | 1BHK | 433.4709 | 0 | 0 | 433.4709 | [11 empty] | 302,..,302 | 302 | 302
3 |  | Sale | 3BHK | 883.951 | 0 | 0 | 883.951 | [11 empty] | 303,..,303 | 303 | 303
4 |  | Parking | [16 empty] | 304,..,304 | 304 | 304
5 | [18 empty] | 305,..,305 | 305 | 305
6 | [18 empty] | 306,..,306 | 306 | 306
1st, 2nd, 4th to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th & 28th to 30th Floor | [7 empty] | 24
1 |  | Sale | 2BHK | 616.4018 | 10.764 | 0 | 627.1658 | [11 empty] | 12401,..,3001 | 12401 | 3001
2 |  | Sale | 1BHK | 436.9094 | 0 | 0 | 436.9094 | [11 empty] | 12402,..,3002 | 12402 | 3002
3 |  | Sale | 3BHK | 853.5965 | 30.3545 | 0 | 883.951 | [11 empty] | 12403,..,3003 | 12403 | 3003
4 |  | Sale | 1.5BHK | 499.3864 | 0 | 0 | 499.3864 | [11 empty] | 12404,..,3004 | 12404 | 3004
5 |  | Sale | 1BHK | 426.1454 | 0 | 0 | 426.1454 | [11 empty] | 12405,..,3005 | 12405 | 3005
6 |  | Sale | 2BHK | 628.3095 | 0 | 0 | 628.3095 | [11 empty] | 12406,..,3006 | 12406 | 3006
3rd Floor (Part Refuge Area)
1 |  | Sale | 2BHK | 616.4018 | 10.764 | 0 | 627.1658 | [11 empty] | 301,..,301 | 301 | 301
2 |  | Sale | 1BHK | 436.9094 | 0 | 0 | 436.9094 | [11 empty] | 302,..,302 | 302 | 302
3 |  | Sale | 3BHK | 853.5965 | 30.3545 | 0 | 883.951 | [11 empty] | 303,..,303 | 303 | 303
4 |  | Sale | 1.5BHK | 499.3864 | 0 | 0 | 499.3864 | [11 empty] | 304,..,304 | 304 | 304
5 |  | Refuge Area | [16 empty] | 305,..,305 | 305 | 305
6 |  | Sale | 2BHK | 628.3095 | 0 | 0 | 628.3095 | [11 empty] | 306,..,306 | 306 | 306
7th & 17th Floor (Part Refuge Area) | [7 empty] | 2
1 |  | Sale | 2BHK | 616.4018 | 10.764 | 0 | 627.1658 | [11 empty] | 701,..,1701 | 701 | 1701
2 |  | Sale | 1BHK | 436.9094 | 0 | 0 | 436.9094 | [11 empty] | 702,..,1702 | 702 | 1702
3 |  | Sale | 3BHK | 853.5965 | 30.3545 | 0 | 883.951 | [11 empty] | 703,..,1703 | 703 | 1703
4 |  | Refuge Area | [16 empty] | 704,..,1704 | 704 | 1704
5 |  | Sale | 1BHK | 426.1454 | 0 | 0 | 426.1454 | [11 empty] | 705,..,1705 | 705 | 1705
6 |  | Sale | 2BHK | 628.3095 | 0 | 0 | 628.3095 | [11 empty] | 706,..,1706 | 706 | 1706
12th & 22nd Floor (Part Refuge Area) | [7 empty] | 2
1 |  | Sale | 2BHK | 616.4018 | 10.764 | 0 | 627.1658 | [11 empty] | 1201,..,2201 | 1201 | 2201
2 |  | Sale | 1BHK | 436.9094 | 0 | 0 | 436.9094 | [11 empty] | 1202,..,2202 | 1202 | 2202
3 |  | Sale | 3BHK | 853.5965 | 30.3545 | 0 | 883.951 | [11 empty] | 1203,..,2203 | 1203 | 2203
4 |  | Sale | 1.5BHK | 499.3864 | 0 | 0 | 499.3864 | [11 empty] | 1204,..,2204 | 1204 | 2204
5 |  | Sale | 1BHK | 426.1454 | 0 | 0 | 426.1454 | [11 empty] | 1205,..,2205 | 1205 | 2205
6 |  | Refuge Area | [16 empty] | 1206,..,2206 | 1206 | 2206
27th Floor (Part Refuge Area)
1 |  | Sale | 2BHK | 616.4018 | 10.764 | 0 | 627.1658 | [11 empty] | 201,..,2701 | 201 | 2701
2 |  | Sale | 1BHK | 436.9094 | 0 | 0 | 436.9094 | [11 empty] | 202,..,2702 | 202 | 2702
3 |  | Sale | 3BHK | 853.5965 | 30.3545 | 0 | 883.951 | [11 empty] | 203,..,2703 | 203 | 2703
4 |  | Sale | 1.5BHK | 499.3864 | 0 | 0 | 499.3864 | [11 empty] | 204,..,2704 | 204 | 2704
5 |  | Sale | 1BHK | 426.1454 | 0 | 0 | 426.1454 | [11 empty] | 205,..,2705 | 205 | 2705
6 |  | Refuge Area | [16 empty] | 206,..,2706 | 206 | 2706
31st Floor (Part Terrace Area)
1 |  | Sale | 2BHK | 616.4018 | 10.764 | 0 | 627.1658 | [11 empty] | 3101,..,3101 | 3101 | 3101
2 |  | Sale | 1BHK | 436.9094 | 0 | 0 | 436.9094 | [11 empty] | 3102,..,3102 | 3102 | 3102
3 |  | Terrace Area | [16 empty] | 3103,..,3103 | 3103 | 3103
4 |  | Sale | 1.5BHK | 499.3864 | 0 | 0 | 499.3864 | [11 empty] | 3104,..,3104 | 3104 | 3104
5 |  | Sale | 1BHK | 426.1454 | 0 | 0 | 426.1454 | [11 empty] | 3105,..,3105 | 3105 | 3105
6 |  | Sale | 2BHK | 628.3095 | 0 | 0 | 628.3095 | [11 empty] | 3106,..,3106 | 3106 | 3106
32nd Floor
1 |  | Sale | 2BHK | 616.4018 | 10.764 | 0 | 627.1658 | [11 empty] | 3201,..,3201 | 3201 | 3201
2 |  | Sale | 1BHK | 436.9094 | 0 | 0 | 436.9094 |  | A: 10.764 | 3202,..,3202 | 3202 | 3202
3 |  | Terrace Area Below @ 31st Floor | [16 empty] | 3203,..,3203 | 3203 | 3203
4 |  | Sale | 1.5BHK | 499.3864 | 0 | 0 | 499.3864 | [11 empty] | 3204,..,3204 | 3204 | 3204
5 |  | Sale | 1BHK | 426.1454 | 0 | 0 | 426.1454 | [11 empty] | 3205,..,3205 | 3205 | 3205
6 |  | Sale | 2BHK | 628.3095 | 0 | 0 | 628.3095 | [11 empty] | 3206,..,3206 | 3206 | 3206
Wing G
1st & 2nd Basement Floor For Parking
Lower Ground Floor For Entrance Lobby & Parking
Upper Ground Floor For Residential & Parking | [7 empty] | 1
1 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | #REF! | #REF! | #NUM!
2 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | #REF! | #REF! | #NUM!
3 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | #REF! | #REF! | #NUM!
4 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | #REF! | #REF! | #NUM!
5 |  | Parking | [16 empty] | #REF! | #REF! | #NUM!
6 | [18 empty] | #REF! | #REF! | #NUM!
7 | [18 empty] | #REF! | #REF! | #NUM!
8 | [18 empty] | #REF! | #REF! | #NUM!
1st Podium Floor For Residential & Parking | [7 empty] | 1
1 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 101,..,101 | 101 | 101
2 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 102,..,102 | 102 | 102
3 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 103,..,103 | 103 | 103
4 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 104,..,104 | 104 | 104
5 |  | Parking | [16 empty] | 105,..,105 | 105 | 105
6 | [18 empty] | 106,..,106 | 106 | 106
7 | [18 empty] | 107,..,107 | 107 | 107
8 | [18 empty] | 108,..,108 | 108 | 108
2nd Podium Floor For Residential & Parking | [7 empty] | 1
1 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 201,..,201 | 201 | 201
2 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 202,..,202 | 202 | 202
3 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 203,..,203 | 203 | 203
4 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 204,..,204 | 204 | 204
5 |  | Parking | [16 empty] | 205,..,205 | 205 | 205
6 | [18 empty] | 206,..,206 | 206 | 206
7 | [18 empty] | 207,..,207 | 207 | 207
8 | [18 empty] | 208,..,208 | 208 | 208
3rd Podium Floor For Residential & Parking | [7 empty] | 1
1 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 301,..,301 | 301 | 301
2 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 302,..,302 | 302 | 302
3 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 303,..,303 | 303 | 303
4 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 304,..,304 | 304 | 304
5 |  | Parking | [16 empty] | 305,..,305 | 305 | 305
6 | [18 empty] | 306,..,306 | 306 | 306
7 | [18 empty] | 307,..,307 | 307 | 307
8 | [18 empty] | 308,..,308 | 308 | 308
1st, 5th, 9th, 11th, 13th, 15th, 19th, 21st, 23rd, 25th, 29th, 31st, 33rd & 35th Floor For Residential | [7 empty] | 14
1 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 1591101,..,3501 | 1591101 | 3501
2 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 1591102,..,3502 | 1591102 | 3502
3 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 1591103,..,3503 | 1591103 | 3503
4 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 1591104,..,3504 | 1591104 | 3504
5 |  | Sale | 2BHK(Duplex With Upper Floor) | 1123.0568 | 127.7332 | 0 | 1250.79 | Area of balcony/Utility Mistake in RBL | C: 10.764 | 1591105,..,3505 | 1591105 | 3505
6 |  | Sale | 2BHK | 668.0354 | 100.8888 | 0 | 768.9242 | [11 empty] | 1591106,..,3506 | 1591106 | 3506
7 |  | Sale | 2BHK | 668.0354 | 100.8888 | 0 | 768.9242 | [11 empty] | 1591107,..,3507 | 1591107 | 3507
8 |  | Sale | 2BHK(Duplex With Upper Floor) | 1123.0568 | 127.7332 | 0 | 1250.79 | [11 empty] | 1591108,..,3508 | 1591108 | 3508
2nd, 4th, 6th, 8th, 10th, 14th, 16th, 18th, 20th, 24th, 26th, 28th, 30th, 34th, 36th, 38th Floor | [7 empty] | 16
1 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 246801,..,3801 | 246801 | 3801
2 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 246802,..,3802 | 246802 | 3802
3 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 246803,..,3803 | 246803 | 3803
4 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 246804,..,3804 | 246804 | 3804
5 |  | 2BHK(Duplex With Lower Floor) | [6 empty] | C: 10.764 | 246805,..,3805 | 246805 | 3805
6 |  | Sale | 2BHK | 668.0354 | 100.8888 | 0 | 768.9242 | [11 empty] | 246806,..,3806 | 246806 | 3806
7 |  | Sale | 2BHK | 668.0354 | 100.8888 | 0 | 768.9242 | [11 empty] | 246807,..,3807 | 246807 | 3807
8 |  | 2BHK(Duplex With Lower Floor) | [16 empty] | 246808,..,3808 | 246808 | 3808
3rd, 17th, & 37th Floor (Part Refuge Area) | [7 empty] | 3
1 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 301,..,3701 | 301 | 3701
2 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 302,..,3702 | 302 | 3702
3 |  | Refuge Area | [16 empty] | 303,..,3703 | 303 | 3703
4 | [18 empty] | 304,..,3704 | 304 | 3704
5 |  | Sale | 2BHK(Duplex With Upper Floor) | 1123.0568 | 127.7332 | 0 | 1250.79 | [11 empty] | 305,..,3705 | 305 | 3705 | bar: C
6 |  | Sale | 2BHK | 668.0354 | 100.8888 | 0 | 768.9242 | [11 empty] | 306,..,3706 | 306 | 3706
7 |  | Sale | 2BHK | 668.0354 | 100.8888 | 0 | 768.9242 | [11 empty] | 307,..,3707 | 307 | 3707
8 |  | Sale | 2BHK(Duplex With Upper Floor) | 1123.0568 | 127.7332 | 0 | 1250.79 | [11 empty] | 308,..,3708 | 308 | 3708
12th & 22nd Floor (Part Refuge Area) | [7 empty] | 2
1 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 1201,..,2201 | 1201 | 2201
2 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 1202,..,2202 | 1202 | 2202
3 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 1203,..,2203 | 1203 | 2203
4 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 1204,..,2204 | 1204 | 2204
5 |  | 2BHK(Duplex With Lower Floor) | [6 empty] | C: 10.764 | 1205,..,2205 | 1205 | 2205
6 |  | Refuge Area | [16 empty] | 1206,..,2206 | 1206 | 2206
7 | [18 empty] | 1207,..,2207 | 1207 | 2207
8 |  | 2BHK(Duplex With Lower Floor) | [16 empty] | 1208,..,2208 | 1208 | 2208
7th & 27th Floor (Part Refuge Area) | [7 empty] | 2
1 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 701,..,2701 | 701 | 2701
2 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 702,..,2702 | 702 | 2702
3 |  | Refuge Area | [16 empty] | 703,..,2703 | 703 | 2703
4 | [18 empty] | 704,..,2704 | 704 | 2704
5 |  | Sale | 2BHK(Duplex With Upper Floor) | 1123.0568 | 127.7332 | 0 | 1250.79 | [11 empty] | 705,..,2705 | 705 | 2705 | bar: C
6 |  | Sale | 2BHK | 668.0354 | 100.8888 | 0 | 768.9242 | [11 empty] | 706,..,2706 | 706 | 2706
7 |  | Sale | 2BHK | 668.0354 | 100.8888 | 0 | 768.9242 | [11 empty] | 707,..,2707 | 707 | 2707
8 |  | Sale | 2BHK(Duplex With Upper Floor) | 1123.0568 | 127.7332 | 0 | 1250.79 | [11 empty] | 708,..,2708 | 708 | 2708
32nd Floor
1 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 3201,..,3201 | 3201 | 3201
2 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 3202,..,3202 | 3202 | 3202
3 |  | Refuge Area | [16 empty] | 3203,..,3203 | 3203 | 3203
4 | [18 empty] | 3204,..,3204 | 3204 | 3204
5 |  | 2BHK(Duplex With Lower Floor) | [16 empty] | 3205,..,3205 | 3205 | 3205 | bar: C
6 |  | Sale | 2BHK | 668.0354 | 100.8888 | 0 | 768.9242 | [11 empty] | 3206,..,3206 | 3206 | 3206
7 |  | Sale | 2BHK | 668.0354 | 100.8888 | 0 | 768.9242 | [11 empty] | 3207,..,3207 | 3207 | 3207
8 |  | 2BHK(Duplex With Lower Floor) | [16 empty] | 3208,..,3208 | 3208 | 3208
39th Floor (Part Terrace Area)
1 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 301,..,3901 | 301 | 3901
2 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 302,..,3902 | 302 | 3902
3 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 303,..,3903 | 303 | 3903
4 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 304,..,3904 | 304 | 3904
5 |  | Terrace Area | [16 empty] | 305,..,3905 | 305 | 3905 | bar: C
6 |  | Sale | 2BHK | 668.0354 | 100.8888 | 0 | 768.9242 | [11 empty] | 306,..,3906 | 306 | 3906
7 |  | Sale | 2BHK | 668.0354 | 100.8888 | 0 | 768.9242 | [11 empty] | 307,..,3907 | 307 | 3907
8 |  | Terrace Area | [16 empty] | 308,..,3908 | 308 | 3908
40th Floor (Part Terrace Area)
1 |  | Terrace Area | [16 empty] | 401,..,4001 | 401 | 4001
2 | [18 empty] | 402,..,4002 | 402 | 4002
3 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 403,..,4003 | 403 | 4003
4 |  | Sale | 2BHK | 460.6979 | 10.4142 | 0 | 471.112 | [11 empty] | 404,..,4004 | 404 | 4004
5 |  | Terrace Area Below @ 40th Floor | [16 empty] | 405,..,4005 | 405 | 4005 | bar: C
6 |  | Sale | 2BHK | 668.0354 | 100.8888 | 0 | 768.9242 | [11 empty] | 406,..,4006 | 406 | 4006
7 |  | Sale | 2BHK | 668.0354 | 100.8888 | 0 | 768.9242 | [11 empty] | 407,..,4007 | 407 | 4007
8 |  | Terrace Area Below @ 40th Floor | [16 empty] | 408,..,4008 | 408 | 4008
Wing H
1st & 2nd Basement Floor For Parking
Lower Ground Floor For Entrance Lobby & Parking
Upper Ground Floor For Residential & Parking | [7 empty] | 1
1 |  | Parking | [16 empty] | #REF! | #REF! | #NUM!
2 | [18 empty] | #REF! | #REF! | #NUM!
3 | [18 empty] | #REF! | #REF! | #NUM!
4 | [18 empty] | #REF! | #REF! | #NUM!
5 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | #REF! | #REF! | #NUM!
6 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | #REF! | #REF! | #NUM!
7 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | #REF! | #REF! | #NUM!
8 |  | Parking | [16 empty] | #REF! | #REF! | #NUM!
1st Podium Floor For Residential & Parking | [7 empty] | 1
1 |  | Parking | [16 empty] | 101,..,101 | 101 | 101
2 | [18 empty] | 102,..,102 | 102 | 102
3 | [18 empty] | 103,..,103 | 103 | 103
4 | [18 empty] | 104,..,104 | 104 | 104
5 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 105,..,105 | 105 | 105
6 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 106,..,106 | 106 | 106
7 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 107,..,107 | 107 | 107
8 |  | Parking | [16 empty] | 108,..,108 | 108 | 108
2nd Podium Floor For Residential, Society Office & Parking | [7 empty] | 1
1 |  | Parking | [16 empty] | 201,..,201 | 201 | 201
2 | [18 empty] | 202,..,202 | 202 | 202
3 | [18 empty] | 203,..,203 | 203 | 203
4 | [18 empty] | 204,..,204 | 204 | 204
5 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 205,..,205 | 205 | 205
6 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 206,..,206 | 206 | 206
7 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 207,..,207 | 207 | 207
8 |  | Society Office | [16 empty] | 208,..,208 | 208 | 208
3rd Podium Floor For Residential & Parking | [7 empty] | 1
1 |  | Parking | [16 empty] | 301,..,301 | 301 | 301
2 | [18 empty] | 302,..,302 | 302 | 302
3 | [18 empty] | 303,..,303 | 303 | 303
4 | [18 empty] | 304,..,304 | 304 | 304
5 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 305,..,305 | 305 | 305
6 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 306,..,306 | 306 | 306
7 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 307,..,307 | 307 | 307
8 |  | Parking | [16 empty] | 308,..,308 | 308 | 308
1st, 2nd, 4th, 5th, 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th and 28th to 30th Floor For Residential | [7 empty] | 24
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 124501,..,3001 | 124501 | 3001
2 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 124502,..,3002 | 124502 | 3002
3 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 124503,..,3003 | 124503 | 3003
4 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 124504,..,3004 | 124504 | 3004
5 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 124505,..,3005 | 124505 | 3005
6 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 124506,..,3006 | 124506 | 3006
7 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 124507,..,3007 | 124507 | 3007
8 |  | Sale | 2BHK | 623.6742 | 23.6808 | 0 | 647.355 | [11 empty] | 124508,..,3008 | 124508 | 3008
3rd, 7th & 22nd Floor (Part Refuge Area) | [7 empty] | 3
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 301,..,2201 | 301 | 2201
2 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 302,..,2202 | 302 | 2202
3 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 303,..,2203 | 303 | 2203
4 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 304,..,2204 | 304 | 2204
5 |  | Refuge Area | [16 empty] | 305,..,2205 | 305 | 2205
6 | [18 empty] | 306,..,2206 | 306 | 2206
7 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 307,..,2207 | 307 | 2207
8 |  | Sale | 2BHK | 623.6742 | 23.6808 | 0 | 647.355 | [11 empty] | 308,..,2208 | 308 | 2208
17th Floor (Part Refuge Area) | [7 empty] | 1
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 101,..,1701 | 101 | 1701
2 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 102,..,1702 | 102 | 1702
3 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 103,..,1703 | 103 | 1703
4 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 104,..,1704 | 104 | 1704
5 |  | Refuge Area | [16 empty] | 105,..,1705 | 105 | 1705
6 | [18 empty] | 106,..,1706 | 106 | 1706
7 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 107,..,1707 | 107 | 1707
8 |  | Sale | 2BHK | 623.6742 | 23.6808 | 0 | 647.355 | [11 empty] | 108,..,1708 | 108 | 1708
12th & 27th Floor (Part Refuge Area) | [7 empty] | 2
1 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 1201,..,2701 | 1201 | 2701
2 |  | Refuge Area | [16 empty] | 1202,..,2702 | 1202 | 2702
3 | [18 empty] | 1203,..,2703 | 1203 | 2703
4 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 1204,..,2704 | 1204 | 2704
5 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 1205,..,2705 | 1205 | 2705
6 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 1206,..,2706 | 1206 | 2706
7 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 1207,..,2707 | 1207 | 2707
8 |  | Sale | 2BHK | 623.6742 | 23.6808 | 0 | 647.355 | [11 empty] | 1208,..,2708 | 1208 | 2708
31st Floor (Part Terrace Area) | [7 empty] | 1
1 |  | Terrace Area | [16 empty] | 3101,..,3101 | 3101 | 3101
2 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 3102,..,3102 | 3102 | 3102
3 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 3103,..,3103 | 3103 | 3103
4 |  | Terrace Area | [16 empty] | 3104,..,3104 | 3104 | 3104
5 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 3105,..,3105 | 3105 | 3105
6 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 3106,..,3106 | 3106 | 3106
7 |  | Terrace Area | [16 empty] | 3107,..,3107 | 3107 | 3107
8 | [18 empty] | 3108,..,3108 | 3108 | 3108
32nd Floor | [7 empty] | 1
1 |  | Terrace Area Below @ 31st Floor | [16 empty] | 3201,..,3201 | 3201 | 3201
2 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 3202,..,3202 | 3202 | 3202
3 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 3203,..,3203 | 3203 | 3203
4 |  | Terrace Area Below @ 31st Floor | [16 empty] | 3204,..,3204 | 3204 | 3204
5 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 3205,..,3205 | 3205 | 3205
6 |  | Sale | 1.5BHK | 517.0662 | 0 | 0 | 517.0662 | [11 empty] | 3206,..,3206 | 3206 | 3206
7 |  | Terrace Area Below @ 31st Floor | [16 empty] | 3207,..,3207 | 3207 | 3207
8 | [18 empty] | 3208,..,3208 | 3208 | 3208
Wing J
1st & 2nd Basement Floor For Parking
Lower Ground Floor For Entrance Lobby & Parking
Upper Ground Floor For Residential & Parking
1 |  | Sale | 2BHK | 620.9752 | 39.9344 | 0 | 660.9096 | [11 empty] | #REF! | #REF! | #NUM!
2 |  | Sale | 2BHK | 621.5134 | 39.9344 | 0 | 661.4478 | [11 empty] | #REF! | #REF! | #NUM!
3 |  | Sale | 2BHK | 627.9718 | 39.9344 | 0 | 667.9062 | [11 empty] | #REF! | #REF! | #NUM!
4 |  | Parking | [16 empty] | #REF! | #REF! | #NUM!
5 | [18 empty] | #REF! | #REF! | #NUM!
6 | [18 empty] | #REF! | #REF! | #NUM!
1st Podium Floor For Residential & Parking
1 |  | Sale | 2BHK | 620.9752 | 39.9344 | 0 | 660.9096 | [11 empty] | 101,..,101 | 101 | 101
2 |  | Sale | 2BHK | 621.5134 | 39.9344 | 0 | 661.4478 | [11 empty] | 102,..,102 | 102 | 102
3 |  | Sale | 2BHK | 627.9718 | 39.9344 | 0 | 667.9062 | [11 empty] | 103,..,103 | 103 | 103
4 |  | Parking | [16 empty] | 104,..,104 | 104 | 104
5 | [18 empty] | 105,..,105 | 105 | 105
6 | [18 empty] | 106,..,106 | 106 | 106
2nd Podium Floor For Residential, & Parking
1 |  | Sale | 2BHK | 620.9752 | 39.9344 | 0 | 660.9096 | [11 empty] | 201,..,201 | 201 | 201
2 |  | Sale | 2BHK | 621.5134 | 39.9344 | 0 | 661.4478 | [11 empty] | 202,..,202 | 202 | 202
3 |  | Sale | 2BHK | 627.9718 | 39.9344 | 0 | 667.9062 | [11 empty] | 203,..,203 | 203 | 203
4 |  | Parking | [16 empty] | 204,..,204 | 204 | 204
5 | [18 empty] | 205,..,205 | 205 | 205
6 | [18 empty] | 206,..,206 | 206 | 206
3rd Podium Floor For Residential & Parking
1 |  | Sale | 2BHK | 620.9752 | 39.9344 | 0 | 660.9096 | [11 empty] | 301,..,301 | 301 | 301
2 |  | Sale | 2BHK | 621.5134 | 39.9344 | 0 | 661.4478 | [11 empty] | 302,..,302 | 302 | 302
3 |  | Sale | 2BHK | 627.9718 | 39.9344 | 0 | 667.9062 | [11 empty] | 303,..,303 | 303 | 303
4 |  | Parking | [16 empty] | 304,..,304 | 304 | 304
5 | [18 empty] | 305,..,305 | 305 | 305
6 | [18 empty] | 306,..,306 | 306 | 306
1st Floor For Residential | [7 empty] | 24
1 |  | Sale | 2BHK | 620.9752 | 39.9344 | 0 | 660.9096 | [11 empty] | 101,..,101 | 101 | 101
2 |  | Sale | 2BHK | 621.5134 | 39.9344 | 0 | 661.4478 | [11 empty] | 102,..,102 | 102 | 102
3 |  | Sale | 2BHK | 627.9718 | 39.9344 | 0 | 667.9062 | [11 empty] | 103,..,103 | 103 | 103
4 |  | Sale | 2BHK | 635.6088 | 39.7245 | 0 | 675.3334 | [11 empty] | 104,..,104 | 104 | 104
5 |  | Sale | 2BHK | 635.6088 | 39.7245 | 0 | 675.3334 | [11 empty] | 105,..,105 | 105 | 105
6 |  | Sale | 3BHK | 842.4251 | 40.3758 | 0 | 882.8008 | [11 empty] | 106,..,106 | 106 | 106
Wing K
1st & 2nd Basement Floor For Parking
Lower Ground Floor For Commercial, Entrance Lobby & Parking
12A |  |  | Shop | 1143.0216 | 0 | 0 | 1143.0216 |  | C: 10.764
13 |  |  | Shop | 1290.128 | 0 | 0 | 1290.128
14 |  |  | Shop | 525.0873 | 0 | 0 | 525.0873
15 |  |  | Shop | 516.5826 | 0 | 0 | 516.5826
Upper Ground Floor For Residential & Parking
1 |  | Sale | 3BHK | 889.1064 | 43.5942 | 0 | 932.7006 | [11 empty] | #REF! | #REF! | #NUM!
2 |  | Sale | 3BHK | 889.1064 | 43.5942 | 0 | 932.7006 | [11 empty] | #REF! | #REF! | #NUM!
3 |  | Parking & Meter Room | [16 empty] | #REF! | #REF! | #NUM!
4 | [18 empty] | #REF! | #REF! | #NUM!
2nd Podium Floor For Residential & Parking
1 |  | Sale | 3BHK | 889.1064 | 39.7192 | 0 | 928.8256 | [11 empty] | 201,..,201 | 201 | 201
2 |  | Sale | 3BHK | 889.1064 | 39.7192 | 0 | 928.8256 | [11 empty] | 202,..,202 | 202 | 202
3 |  | Parking & Meter Room | [16 empty] | 203,..,203 | 203 | 203
4 | [18 empty] | 204,..,204 | 204 | 204
3rd Podium Floor For Residential & Parking
1 |  | Sale | 3BHK | 889.1064 | 43.5942 | 0 | 932.7006 | [11 empty] | 301,..,301 | 301 | 301
2 |  | Sale | 3BHK | 889.1064 | 43.5942 | 0 | 932.7006 | [11 empty] | 302,..,302 | 302 | 302
3 |  | Parking & Meter Room | [16 empty] | 303,..,303 | 303 | 303
4 | [18 empty] | 304,..,304 | 304 | 304
Upper Ground Floor For Residential & Parking
1 |  | Sale | 3BHK | 889.1064 | 43.5942 | 0 | 932.7006 | [11 empty] | #REF! | #REF! | #NUM!
2 |  | Sale | 3BHK | 889.1064 | 43.5942 | 0 | 932.7006 | [11 empty] | #REF! | #REF! | #NUM!
3 |  | Parking & Meter Room | [16 empty] | #REF! | #REF! | #NUM!
4 | [18 empty] | #REF! | #REF! | #NUM!
1st Floor For Residential
1 |  | Sale | 3BHK | 889.1064 | 43.5942 | 0 | 932.7006 | [11 empty] | 101,..,101 | 101 | 101
2 |  | Sale | 3BHK | 889.1064 | 43.5942 | 0 | 932.7006 | [11 empty] | 102,..,102 | 102 | 102
3 |  | Sale | 3BHK | 976.918 | 49.1107 | 0 | 1026.0288 | [11 empty] | 103,..,103 | 103 | 103
4 |  | Sale | 3BHK | 976.918 | 49.1107 | 0 | 1026.0288 | [11 empty] | 104,..,104 | 104 | 104
Project Specific Remarks & Observation
* | Wing A, B, C, D, E, F, G & H = Construction work is in process at the time of Visit. (Internal visit not allowed). Wing J & K = Work is not started.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony Area+ Utility.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | Nala located on North side of the project.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Commercial carpet area table & Floor plan commercial Unit count does not match. Hence we have not drafted commercial area of Wing A, B, C J & K. | [6 empty] | Provided Podium floor plans does not consist measurements of Commercial units.
* | We have updated approved plan and CC For Wing A, B, C, J & K (On 05/04/2025).
* | As per the provided approved plans and CC dated 29/03/2025, we have observed that in Project Kalpataru Sector 5 Phase 3 Wing A, J & K the approved number of floors is reduced therefore area is updated as per it.
* | Please provide revised CC for H Wing.
Site & Building/Tower Photographs
Name of the Project |  |  | Kalpataru Sector 5 Phase 3 Starlight (Wing A, C, G, H, J, K) Eternia (Wing B) & Expansia (Wing D, E, F)
Project Site Address |  |  | Expansia at Parkcity, Kalpataru Parkcity, Kolshet Rd, Thane West, Thane, Maharashtra 400607
Site Visit Date & Time |  |  | 04/07/2025 @11:15 AM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr. Ajay Songare |  | Authorized Signatory Name & Signature
Nala
Sector 5
Phase 3
Wing A
Wing B
Wing C
Wing D
Wing E
Wing F
Wing G
Wing H
Wing J
Wing K
Sector 5
Phase 3
Wing C
Wing B
Wing A
Wing K
Wing J
Wing C
Wing B
Wing F
Wing E
Wing H
Note on C9: SACHIN: As per initiation Mail
Note on C17: Maybe same as RERA Registration Validity or different
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G254: Ready Recknor
Note on F690: VSJ: Area of balcony/Utility Mistake in RBL

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0