## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  |  | : | Godrej Vistas |  | Date & Time of Site Visit |  | 07/07/2025 @03:12 PM
Name of the person met at site & Contact No. |  |  | : | Mr. Mahesh 9702498159 |  | Date of Report Release |  | 07/07/2025
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | Godrej and Boyce Mfg. Co. Ltd. | Developer Name | : | Godrej and Boyce Mfg. Co. Ltd.
Developer Office Address |  |  | : | Pirojshanagar, Vikhroli, Mumbai-400079
Project Address | : | As per ARF | : | Godrej Vistas, Vikhroli, Pirojshanagar, Vikhroli, Mumbai, Maharashtra
| : | As per Legal Documents | : | Godrej Vistas, CTS No.8A/1/1, 8A/1/2, 8A/2, 8A/3, 8A/4(Pt), 8A/5, 8A/6, 8A/7, 8A/9, 56(Pt), 92(Pt) & 205(Pt), Pirojshanagar, Vikroli, Kurla, Mumbai - 400079
| : | As per Actual at site | : | Godrej Vistas, Pirojshanagar, Vikhroli, Mumbai, Maharashtra 400079
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate.
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Municipal Corporation of Greater Mumbai (MCGM)
RERA Registration No. | : | P51800055142 |  |  | RERA Registration Validity | : | 2029-12-31
Project Launch Date | : | 2024-03-04 |  |  | Construction Start Date | : | 2024-03-01
Proposed Date of Completion (As per RERA) | : | 2029-12-31 |  |  | Developer Bank Name (As per RERA) | : | ICICI Bank Limited IFSC Code = ICIC0001196
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  |  | Plot Area (In Sq.Mt) | : | 60667.16
FSI/FAR Permissible | : | 1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 104952.04
Permissible Built up Area (In Sq.Mt) | : | 105656.08 |  |  | Total Number of Units Planned | : | As per RERA Site Flats = 375 & Shop = 7
Total Number of Units Approved | : | Flats = 375 |  |  | If Mixed, No. of Commercial Units | : | Shop = 7
Latitude, Longitude | : | 19.1031202,72.929218 |  |  | Landmark | : | Godrej Platinum Building
Location Link | : | https://maps.app.goo.gl/gF9ugAYqu6Aw4yoP7
Extra Amenities available | : | Kids Play Area, Gym, Landscape Garden, Jogging Track, Swimming Pool, Clubhouse, Multipurpose Court, Multipurpose Hall, Yoga Zone, Indoor games, etc.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 27.45 M
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 3.7 KM from Munciple Colony Bus Stop
Distance from the nearest School (Km) | : | About 180M from Udayachal High School |  |  | Distance from Hospital (Km) | : | About 230 M form Godrej Memorial Hospital
Distance from the Main Market (Km) | : | 1.Approx. 3.7 KM from R City Mall 2. Approx.4 KM from Munciple Market |  |  | Distance from Railway Station (Km) | : | 1.7 KM from Vikroli Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Road | Road | 27.45 M W Road |  | Plot I-B-IV
As per Site / Actual |  |  | : | Bhula Bhai Deasai Marg | Godrej Road | Eastern Express Highway |  | Lal Matti Ground
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Tower C1 |  | Sale |  | 4B + G + P + S + 1st to 32nd Floor |  |  | 4B + G + P + S + 1st to 32nd Floor
Tower C2 |  | Sale |  | 4B + G + P + S + 1st to 32nd Floor |  |  | 4B + G + P + S + 1st to 32nd Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | CHE/ES/4409/S/337(NEW)/IOD/1/Amend Date: 08/12/2023
CC Details | : | CHE/ES/4409/S/337(NEW)/FCC/1/New Date: 10/02/2025 Valid Up to: 02/03/2026 Further C.C. up to 22nd upper only as per the approved amended plans dated 08.12.2023 (restricting the further C.C. of 23rd to 32nd (part) upper floor for non-handing over of Road Set backs & reservation of ROS 1.5) |  |  | Approved Plan Details | : | CHE/ES/4409/S/337(NEW)/IOD/1/Amend Date: 08/12/2023
Environmental Clearance Details | : | Date: |  |  | Airport Authority Clearance Details | : | Date:
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
Construction Status
Tower C1= 4B + G + P + S + 1st to 32nd Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed
|  |  |  | 4 | 1 |  | 2 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8
Excavation |  | 32 |  | 100% | 25.71% |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed |  | Excavation in process | 16
Plinth |  | 32 |  | 100% |  |  |  |  | Excavation Completed | 32
RCC (Including podiums) |  | 1 |  | 2.857% |  |  |  |  | Footing in Process | 5.3333
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 10.6667
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 16
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 21.3333
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 26.6667
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 32
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower C2= 4B + G + P + S + 1st to 32nd Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed
|  |  |  | 4 | 1 |  | 2 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8
Excavation |  | 32 |  | 100% | 25.71% |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed |  | Excavation in process | 16
Plinth |  | 32 |  | 100% |  |  |  |  | Excavation Completed | 32
RCC (Including podiums) |  | 1 |  | 2.857% |  |  |  |  | Footing in Process | 5.3333
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 10.6667
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 16
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 21.3333
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 26.6667
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 32
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 25.71%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 42000 | Floor Rise Per Sq. Ft. (on Carpet area) | : | 150/- from 2nd Floor |  |  |  | rate 42000 req by vaibhav 25/09/2024
Car Parking Charges |  |  | : | 1200000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 7921.7763
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 17422.8911
Distress Value (Rs. Per sqft) | [5 empty] | : | 6337.421
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Gross Carpet Area
Shops |  | Sale |  | Shops | 7 |  | 9939.7951
Tower C1 |  | Sale |  | Flats | 172 |  | 170462.423
Tower C2 |  | Sale |  | Flats | 203 |  | 186840.3387
Total |  | 0 |  | 0 | 382 |  | 367242.5568 | 0
Details of Flats in Building
Flat/Shop No. |  | Description |  | Carpet area | Deck Area |  | Attached Terrace area | Gross Carpet area
Tower C1 + C2
1st, 2nd, 3rd & 4th Floor Basement For Parking
Ground Floor For Commercials, Meter Room, Fire Control Room & Lobby | [10 empty] | 10.764
1 |  | Shop |  | 1477.359 | 0 |  | 0 | 1477.359
2 |  | Shop |  | 1990.129 | 0 |  | 0 | 1990.129
3 |  | Shop |  | 2423.5953 | 0 |  | 0 | 2423.5953
4 |  | Shop |  | 1272.3048 | 0 |  | 0 | 1272.3048
5 |  | Shop |  | 1323.084 | 0 |  | 0 | 1323.084
6 |  | Shop |  | 1390.5473 | 0 |  | 0 | 1390.5473
7 |  | Shop |  | 62.7756 | 0 |  | 0 | 62.7756
Service Floor For Swimming Pool & Servant Room
Podium Floor For Fitness Centre, Swimming Pool, Society Office & Garden Area
Tower C1
1st Floor For Residential
1 |  | 3BHK |  | 1268.3759 | 76.7473 | 0 | 0 | 1345.1233
2 |  | 2BHK |  | 766.6175 | 39.6115 | 0 | 0 | 806.229
3 |  | 2BHK |  | 766.6175 | 39.6115 | 0 | 0 | 806.229
4 |  | 3BHK |  | 1100.6459 | 38.5082 | 0 | 0 | 1139.1541
5 |  | 2BHK |  | 766.6175 | 37.1358 | 0 | 0 | 803.7533
6 |  | 2BHK |  | 768.0706 | 37.1358 | 0 | 0 | 805.2064
2nd to 5th, 7th to 12th, 14th to 19th, 21st to 26th Floor For Residential
1 |  | 3BHK |  | 1268.3759 | 76.7473 | 0 | 0 | 1345.1233 |  |  |  | 2501,..,2601 | 2501 | 2601
2 |  | 2BHK |  | 766.6175 | 39.6115 | 0 | 0 | 806.229 |  |  |  | 2502,..,2602 | 2502 | 2602
3 |  | 2BHK |  | 766.6175 | 39.6115 | 0 | 0 | 806.229 |  |  |  | 2503,..,2603 | 2503 | 2603
4 |  | 3BHK |  | 1100.6459 | 38.5082 | 0 | 0 | 1139.1541 |  |  |  | 2504,..,2604 | 2504 | 2604
5 |  | 2BHK |  | 766.6175 | 37.1358 | 0 | 0 | 803.7533 |  |  |  | 2505,..,2605 | 2505 | 2605
6 |  | 2BHK |  | 768.0706 | 37.1358 | 0 | 0 | 805.2064 |  |  |  | 2506,..,2606 | 2506 | 2606
6th, 13th & 20th Floor For Residential (Part Refuge Area)
1 |  | 3BHK |  | 1268.3759 | 76.7473 | 0 | 0 | 1345.1233 |  |  |  | 601,..,2001 | 601 | 2001
2 |  | Refuge Area | [9 empty] | 602,..,2002 | 602 | 2002
3 | [11 empty] | 603,..,2003 | 603 | 2003
4 |  | 3BHK |  | 1100.6459 | 38.5082 | 0 | 0 | 1139.1541 |  |  |  | 604,..,2004 | 604 | 2004
5 |  | 2BHK |  | 766.6175 | 37.1358 | 0 | 0 | 803.7533 |  |  |  | 605,..,2005 | 605 | 2005
6 |  | 2BHK |  | 768.0706 | 37.1358 | 0 | 0 | 805.2064 |  |  |  | 606,..,2006 | 606 | 2006
27th Floor For Residential (Part Refuge Area)
1 |  | 3BHK |  | 1268.3759 | 76.7473 | 0 | 0 | 1345.1233
2 |  | Refuge Area
3
4 |  | 3BHK |  | 1100.6459 | 38.5082 | 0 | 0 | 1139.1541
5 |  | 4BHK |  | 1739.7907 | 104.1417 | 0 | 0 | 1843.9324
6 |  | - |  | - |  |  |  | 0
28th to 30th Floor
1 |  | 3BHK |  | 1268.3759 | 76.7473 | 0 | 0 | 1345.1233 |  |  |  | 2801 to 3001 | 2801 | 3001
2 |  | 2BHK |  | 766.6175 | 39.6115 | 0 | 0 | 806.229 |  |  |  | 2802 to 3002 | 2802 | 3002
3 |  | 2BHK |  | 766.6175 | 39.6115 | 0 | 0 | 806.229 |  |  |  | 2803 to 3003 | 2803 | 3003
4 |  | 3BHK |  | 1100.6459 | 38.5082 | 0 | 0 | 1139.1541 |  |  |  | 2804 to 3004 | 2804 | 3004
5 |  | 4BHK |  | 1739.7907 | 104.1417 | 0 | 0 | 1843.9324 |  |  |  | 2805 to 3005 | 2805 | 3005
31st Floor For Residential & Fitness Centre
3101 |  | 3BHK |  | 1268.3759 | 76.7473 | 0 | 0 | 1345.1233
3102 |  | 2BHK |  | 766.6175 | 39.6115 | 0 | 0 | 806.229
3103 |  | 2BHK |  | 766.6175 | 39.6115 | 0 | 0 | 806.229
3104 |  | Fitness Centre
3105 |  | 4BHK |  | 1739.7907 | 104.1417 | 0 | 0 | 1843.9324
32nd Floor For Fitness Centre, Garden Area & Terrace Area
Tower C2
1st Floor For Residential
101 |  | 3BHK |  | 1100.6459 | 38.5082 | 0 | 0 | 1139.1541
102 |  | 2BHK |  | 766.6175 | 39.6115 | 0 | 0 | 806.229
103 |  | 2BHK |  | 783.8722 | 36.5169 | 0 | 0 | 820.389
104 |  | 2.5BHK |  | 933.89 | 0 | 0 | 0 | 933.89
105 |  | 2.5BHK |  | 933.89 | 0 | 0 | 0 | 933.89
106 |  | 2BHK |  | 767.2202 | 37.1358 | 0 | 0 | 804.356
107 |  | 2BHK |  | 768.0706 | 37.1358 | 0 | 0 | 805.2064
2nd to 5th, 7th to 12th, 14th to 19th, 21st to 26th Floor For Residential
201,..,2601 |  | 3BHK |  | 1100.6459 | 38.5082 | 0 | 0 | 1139.1541 |  |  |  | 201,..,2601 | 201 | 2601
202,..,2602 |  | 2BHK |  | 766.6175 | 39.6115 | 0 | 0 | 806.229 |  |  |  | 202,..,2602 | 202 | 2602
203,..,2603 |  | 2BHK |  | 783.8722 | 36.5169 | 0 | 0 | 820.389 |  |  |  | 203,..,2603 | 203 | 2603
204,..,2604 |  | 2.5BHK |  | 933.89 | 0 | 0 | 0 | 933.89 |  |  |  | 204,..,2604 | 204 | 2604
205,..,2605 |  | 2.5BHK |  | 933.89 | 0 | 0 | 0 | 933.89 |  |  |  | 205,..,2605 | 205 | 2605
206,..,2606 |  | 2BHK |  | 767.2202 | 37.1358 | 0 | 0 | 804.356 |  |  |  | 206,..,2606 | 206 | 2606
207,..,2607 |  | 2BHK |  | 768.0706 | 37.1358 | 0 | 0 | 805.2064 |  |  |  | 207,..,2607 | 207 | 2607
6th, 13th to 20th Floor For Residential (Part Refuge Area)
601,..,2001 |  | 3BHK |  | 1100.6459 | 38.5082 | 0 | 0 | 1139.1541 |  |  |  | 601,..,2001 | 601 | 2001
602,..,2002 |  | Refuge Area | [9 empty] | 602,..,2002 | 602 | 2002
603,..,2003 | [11 empty] | 603,..,2003 | 603 | 2003
604,..,2004 |  | 2.5BHK |  | 933.89 | 0 | 0 | 0 | 933.89 |  |  |  | 604,..,2004 | 604 | 2004
605,..,2005 |  | 2.5BHK |  | 933.89 | 0 | 0 | 0 | 933.89 |  |  |  | 605,..,2005 | 605 | 2005
606,..,2006 |  | 2BHK |  | 767.2202 | 37.1358 | 0 | 0 | 804.356 |  |  |  | 606,..,2006 | 606 | 2006
607,..,2007 |  | 2BHK |  | 768.0706 | 37.1358 | 0 |  | 805.2064 |  |  |  | 607,..,2007 | 607 | 2007
27th Floor For Residential (Part Refuge Area)
2701 |  | 3BHK |  | 1100.6459 | 38.5082 | 0 | 0 | 1139.1541
2702 |  | Refuge Area
2703
2704 |  | 2.5BHK |  | 933.89 | 0 | 0 | 0 | 933.89
2705 |  | 2.5BHK |  | 933.89 | 0 | 0 | 0 | 933.89
2706 |  | 4BHK |  | 1719.6028 | 79.842 | 0 | 0 | 1799.4448
28th to 30th Floor For Residential | [11 empty] | 2801 to 3001 | 2801 | 3001
2801 to 3001 |  | 3BHK |  | 1100.6459 | 38.5082 | 0 | 0 | 1139.1541 |  |  |  | 2802 to 3002 | 2802 | 3002
2802 to 3002 |  | 2BHK |  | 766.6175 | 39.6115 | 0 | 0 | 806.229 |  |  |  | 2803 to 3003 | 2803 | 3003
2803 to 3003 |  | 2BHK |  | 783.8722 | 36.5169 | 0 | 0 | 820.389 |  |  |  | 2804 to 3004 | 2804 | 3004
2804 to 3004 |  | 2.5BHK |  | 933.89 | 0 | 0 | 0 | 933.89 |  |  |  | 2805 to 3005 | 2805 | 3005
2805 to 3005 |  | 2.5BHK |  | 933.89 | 0 | 0 | 0 | 933.89 |  |  |  | 2806 to 3006 | 2806 | 3006
2806 to 3006 |  | 4BHK |  | 1719.6028 | 79.842 | 0 | 0 | 1799.4448 |  |  |  | 2807 to 3007 | 2807 | 3007
31st Floor For Residential & Fitness Centre
3101 |  | Fitness Centre
3102 |  | 2BHK |  | 766.6175 | 39.6115 | 0 | 0 | 806.229
3103 |  | 2BHK |  | 783.8722 | 36.5169 | 0 | 0 | 820.389
3104 |  | 2.5BHK |  | 933.89 | 0 | 0 | 0 | 933.89
3105 |  | 2.5BHK |  | 933.89 | 0 | 0 | 0 | 933.89
3106 |  | 4BHK |  | 1719.6028 | 79.842 | 0 | 0 | 1799.4448
32nd Floor For Fitness Centre, Garden Area & Terrace Area
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Construction work is in process at the time of Visit. Internal visit was not allowed. 2. We considered Gross carpet area = Net carpet + Deck Area. 3. We considered Carpet area as per Approved Plan. 4. Car parking is subjected to authentic documentation. 5. We have considered rate by verifying it from market inquire. 6. High Tension Line Passing Near By Project Godrej Vistas (Document Attach Below). 7. We have updated CC from MCGM site on 07/07/2025.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Godrej Vistas
Project Site Address |  |  | : | Godrej Vistas, Vikhroli, Pirojshanagar, Vikhroli, Mumbai, Maharashtra
Site Visit Date & Time |  |  | : | 07/07/2025 @03:12 PM
Layout
Tata NOC ( High Voltage Line) (Remark No.7)
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Nainesh Tambe | Authorized Signatory Name & Signature | :
Site
Site
High Tension Line
High Tension Line
Site
High Tension Line
High Tension Line
C1
C2
Note on E9: Initiation Address
Note on E10: Plan Address
Note on E11: Plan Address
Note on C17: Maybe same as RERA Registration Validity or different
Note on H17: From Rera
Note on H20: From RERA
Note on A39: As per Layout
Note on H95: Ready Recknor