## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  |  | : | Montana Phase 4 Building No.10 ( Blissberg ) |  | Date & Time of Site Visit |  | 07/07/2025 @ 10.57 AM | 2025-04-26 | 2025-07-07
Provided Contact Details ( Name & Contact No.) |  |  | : | Mr. Avinash CRM 8879975804 |  | Date of Report Release |  | 07/07/2025 |  | 72
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Singh
Builder Group Name |  |  | : | Lohitka Properties LLP | Developer Name | : | Ashwin Sheth group
Developer Office Address |  |  | : | Ground & 3rd floor, Prius Infinity. Behind Garware house Subhash Rd, Vile Parle East, Mumbai, Maharashtra 400057
Project Address | : | As per ARF | : | Montana Phase 4, Vasant Oscar, Mulund West, Mumbai, Maharashtra 400082
| : | As per Legal Documents | : | Montana Phase 4, Proposed Bldg. No.-7&10 On Plot Bearing C.T.S. No. 514 A, 514 B And 514 C Of Village Nahur At L.B.S. Marg, Mulund(w), Mumbai 400082.
| : | As per Actual at site | : | Montana Phase 4, Vasant Oscar, Marathon Ave Road, Mulund West, Mumbai, Maharashtra 400082
Documents Provided by GHF |  |  | : | RERA certificate
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Municipal Corporation of Greater Mumbai
RERA Registration No. | : | P51800026393 |  |  | RERA Registration Validity | : | 2026-12-31
Project Launch Date | : | 2020-09-17 |  |  | Construction Start Date | : | 2020-09-17
Proposed Date of Completion (As per RERA) | : | 2026-12-31
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 57838.66
FSI/FAR Permissible | : | 1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 161939.02
Permissible Built up Area (In Sq.Mt) | : | 161939.02 |  |  | Total Number of Units Planned | : | Flats = 374 |  | 279
Total Number of Units Approved | : | Flats = 374 |  |  | If Mixed, No. of Commercial Units | : | Shop = 0
Latitude | : | 19.1717 |  |  | Longitude | : | 72.9371
Location Link | : | https://maps.app.goo.gl/wZQmnAsLUydg4zGfA
Extra Amenities available | : | Swimming Pool, Spa, Jogging Track, Kids play area, Yoga oom, Banquet Hall, Party Lawn, Fitness Centre, Games Room, etc. | [7 empty] | https://www.shethmontana-mulund.com/index.html?utm_source=google&utm_medium=cpc_pin&utm_campaign=184_sheth_montana_exact&utm_term=montana%20mulund&utm_content=Search&gclid=CjwKCAiA1MCrBhAoEiwAC2d64b1T-KRVGA5mkMztPSlOiQPTH1PXz23rfZFrr40id11eRw_-aBEQMxoC1PIQAvD_BwE#amenities
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developed |  |  | Class of Locality | : | Upper Class
Type of Road | : | Bitumen |  |  | Width of the Road | : | 18.30M
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 0.55KM from Ralli Wolf Bus Stop
Distance from the nearest School (Km) | : | About 0.50KM from Friends Academy |  |  | Distance from Hospital (Km) | : | About 1.5KM form Fortis Hospital
Distance from the Main Market (Km) | : | 1. Approx. 1.20KM from D mart. 2. Approx. 2.60 KM from R Mall |  |  | Distance from Railway Station (Km) | : | 2.8KM from Mulund Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | CTS NO. 547 | 18.30 M. Wide Road | LBS Marg |  | Tansa Pipe Line
As per Site / Actual |  |  | : | Slum | Marathon Ave | LBS Marg |  | Pipe Line
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Building No.10 Blissberg (Wing C1) |  | Sale |  | Gr/Stilt + 1st to 5th Podium + 6th Podium / EDeck Floor + 1st to 43rd Floor |  |  | Gr/Stilt + 1st to 5th Podium + 6th Podium / E-Deck Floor + 1st to 43rd Floor
Building No.10 Blissberg (Wing C2) |  | Sale |  | Gr/Stilt + 1st to 5th Podium + 6th Podium / EDeck Floor + 1st to 43rd Floor |  |  | Gr/Stilt + 1st to 5th Podium + 6th Podium / E-Deck Floor + 1st to 43rd Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | CHE/ES/2036/T/337( NEW) Date: 20/03/2023
CC Details | : | CHE/ES/2036/T/337(NEW)/FCC/4/Amend Date: 21/10/2024 Valid Upto Date : 14/10/2025 Valid Upto : Full C.C. for wing ‘C’ of building No. 10 is granted as per amended approved plan dated 20.03.2023 subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution. |  |  | Approved Plan Details | : | CHE/ES/2036/T/337( NEW) Date: 20/03/2023
Environmental Clearance Details | : |  |  |  | Airport Authority Clearance Details | : | NA
Change of User/Zone Certificate Details | : | - |  |  | Fire NOC Details | : | CHE/ES/2119/T/337(NEW)-CFO. Date: 25/07/2022 Valis Up to: Basement + 1st to 43rd Floor (Height of 158.95 Mtr)
Construction Status
Building No.10 Blissberg (Wing C1) = Gr/Stilt + 1st to 5th Podium + 6th Podium / EDeck Floor + 1st to 43rd Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 44 Slab, Brickwork upto 37 Floor, Internal Plaster upto 29.6 Floor, External Plaster upto 29.6 Floor, External Plumbing, Elevation and Waterproofing upto 18 Floor, Flooring & Fitting upto 12 Floor, Wooden Work upto 5 Floor, Electrical & Sanitary fittings upto 8 Floor Completed
|  |  |  | 0 | 1 |  | 6 | 43 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 10.75
Excavation |  | 43 |  | 100% | 60.38% |  | Excavation work Completed. Plinth work completed, RCC upto 44 Slab, Brickwork upto 37 Floor, Internal Plaster upto 29.6 Floor, External Plaster upto 29.6 Floor, External Plumbing, Elevation and Waterproofing upto 18 Floor, Flooring & Fitting upto 12 Floor, Wooden Work upto 5 Floor, Electrical & Sanitary fittings upto 8 Floor Completed |  | Excavation in process | 21.5
Plinth |  | 43 |  | 100% |  |  |  |  | Excavation Completed | 43
RCC (Including podiums) |  | 44 |  | 88% |  |  |  |  | Footing in Process | 10.75
Brickwork |  | 37 |  | 86.05% |  |  |  |  | Footing Completed | 21.5
Internal Plaster |  | 29.6 |  | 68.84% |  |  |  |  | Basement 1 | 0
External Plaster |  | 29.6 |  | 68.84% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 18 |  | 41.86% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 12 |  | 27.91% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 5 |  | 11.63% |  |  |  |  | Plinth in process | 32.25
Electrical & Sanitary fittings |  | 8 |  | 18.6% |  |  |  |  | Plinth completed | 43 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building No.10 Blissberg (Wing C2) = Gr/Stilt + 1st to 5th Podium + 6th Podium / EDeck Floor + 1st to 43rd Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 44 Slab, Brickwork upto 37 Floor, Internal Plaster upto 29.6 Floor, External Plaster upto 29.6 Floor, External Plumbing, Elevation and Waterproofing upto 16 Floor, Flooring & Fitting upto 10 Floor, Wooden Work upto 5 Floor, Electrical & Sanitary fittings upto 8 Floor Completed
|  |  |  | 0 | 1 |  | 6 | 43 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 10.75
Excavation |  | 43 |  | 100% | 59.69% |  | Excavation work Completed. Plinth work completed, RCC upto 44 Slab, Brickwork upto 37 Floor, Internal Plaster upto 29.6 Floor, External Plaster upto 29.6 Floor, External Plumbing, Elevation and Waterproofing upto 16 Floor, Flooring & Fitting upto 10 Floor, Wooden Work upto 5 Floor, Electrical & Sanitary fittings upto 8 Floor Completed |  | Excavation in process | 21.5
Plinth |  | 43 |  | 100% |  |  |  |  | Excavation Completed | 43
RCC (Including podiums) |  | 44 |  | 88% |  |  |  |  | Footing in Process | 10.75
Brickwork |  | 37 |  | 86.05% |  |  |  |  | Footing Completed | 21.5
Internal Plaster |  | 29.6 |  | 68.84% |  |  |  |  | Basement 1 | 0
External Plaster |  | 29.6 |  | 68.84% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 16 |  | 37.21% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 10 |  | 23.26% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 5 |  | 11.63% |  |  |  |  | Plinth in process | 32.25
Electrical & Sanitary fittings |  | 8 |  | 18.6% |  |  |  |  | Plinth completed | 43 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 60.03%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 24000 to 25000
Car Parking Charges |  |  | : | 800000 | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 4905.2397
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 9791.8989
Distress Value (Rs. Per sqft) | [5 empty] | : | 3924.1918
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area
Building No.10 Wing C1 |  | Sale |  | Flats | 202 |  | 187615.8742
Building No.10 Wing C2 |  | Sale |  | Flats | 172 |  | 113019.2014
Total |  | 0 |  | 0 | 374 |  | 300635.0755
Details of Flats in Building
Flat/Shop No. |  | Description |  | Net carpet | Fungible Area |  | Attached Terrace area | Gross Carpet area Loading :
Building No.10 ( Blissberg )
Wing C1
Ground Floor for Parking, Society Office & Domestic water tank
1st to 5th Floor for Podium for Parking
6th Floor for Podium / E-Deck
1st, 8th, 15th, 22nd & 29th Floor for Residential (Part Refuge Area)
1 |  | 2BHK |  | 640.7809 | 17.8682 |  | 0 | 658.6492 | 202
2 |  | 3.5BHK |  | 1301.6905 | 51.3443 |  | 0 | 1353.0348
3 |  | Refuge Area
4
5 |  | 2BHK |  | 612.4716 | 14.639 |  | 0 | 627.1106 | 53.5295 | 1.52
2nd to 7th, 9th to 14th, 16th to 21st, 23rd to 28th, 30th to 35th & 37th to 43rd Floor | [8 empty] | 37
1 |  | 2BHK | 2BHK | 640.7809 | 17.8682 |  | 0 | 658.6492 | 25051.2731 |  |  | 27901,..,4301 | 27901 | 4301
2 |  | 3.5BHK | 3.5BHK | 1301.6905 | 51.3443 |  | 0 | 1353.0348 |  |  |  | 27902,..,4302 | 27902 | 4302
3 |  | 2.5BHK | 2.5BHK | 858.2137 | 45.6394 |  | 0 | 903.8531 | 24672.1514 |  |  | 27903,..,4303 | 27903 | 4303
4 |  | 3BHK | 3BHK | 1074.893 | 42.1949 |  | 0 | 1117.0879 |  |  |  | 27904,..,4304 | 27904 | 4304
5 |  | 2BHK | 2BHK | 612.4716 | 14.639 |  | 0 | 627.1106 | 25513.8392 |  |  | 27905,..,4305 | 27905 | 4305
36th Floor (Part Refuge Area)
1 |  | 2BHK | 2BHK | 640.7809 | 17.8682 |  | 0 | 658.6492 |  |  |  | 301,..,3601 | 301 | 3601
2 |  | 3.5BHK | 3.5BHK | 1301.6905 | 51.3443 |  | 0 | 1353.0348 |  |  |  | 302,..,3602 | 302 | 3602
3 |  | Refuge Area | [9 empty] | 303,..,3603 | 303 | 3603
4 | [11 empty] | 304,..,3604 | 304 | 3604
5 | [11 empty] | 305,..,3605 | 305 | 3605
Wing C2
Ground Floor for Parking, Society Office & Domestic water tank
1st to 5th Floor for Podium for Parking
6th Floor for Podium / E-Deck
1st, 8th, 15th, 22nd & 29th Floor for Residential (Refuge Area At Wing C1)
1 |  | 1.5BHK | 1.5BHK | 586.4227 | 14.1008 |  | 0 | 600.5236 |  |  |  | #VALUE! | 1 | #VALUE!
2 |  | 1.5BHK | 1.5BHK | 586.4227 | 14.1008 |  | 0 | 600.5236 |  |  |  | #VALUE! | 2 | #VALUE!
3 |  | 2BHK | 2BHK | 677.9167 | 35.7365 |  | 0 | 713.6532 |  |  |  | #VALUE! | 3 | #VALUE!
4 |  | 2BHK | 2BHK | 677.9167 | 35.7365 |  | 0 | 713.6532 |  |  |  | #VALUE! | 4 | #VALUE!
2nd to 7th, 9th to 14th, 16th to 21st, 23rd to 28th, 30th to 35th & 37th to 43rd Floor
1 |  | 1.5BHK | 1.5BHK | 586.4227 | 14.1008 |  | 0 | 600.5236 |  |  |  | #VALUE! | 5 | #VALUE!
2 |  | 1.5BHK | 1.5BHK | 586.4227 | 14.1008 |  | 0 | 600.5236 |  |  |  | #VALUE! | 6 | #VALUE!
3 |  | 2BHK | 2BHK | 677.9167 | 35.7365 |  | 0 | 713.6532 |  |  |  | #VALUE! | 7 | #VALUE!
4 |  | 2BHK | 2BHK | 677.9167 | 35.7365 |  | 0 | 713.6532 |  |  |  | #VALUE! | 8 | #VALUE!
36th Floor (Refuge Area At Wing C1)
1 |  | 1.5BHK | 1.5BHK | 586.4227 | 14.1008 |  | 0 | 600.5236 |  |  |  | #VALUE! | 3601 | #VALUE!
2 |  | 1.5BHK | 1.5BHK | 586.4227 | 14.1008 |  | 0 | 600.5236 |  |  |  | #VALUE! | 3602 | #VALUE!
3 |  | 2BHK | 2BHK | 677.9167 | 35.7365 |  | 0 | 713.6532 |  |  |  | #VALUE! | 3603 | #VALUE!
4 |  | 2BHK | 2BHK | 677.9167 | 35.7365 |  | 0 | 713.6532 |  |  |  | #VALUE! | 3604 | #VALUE!
Project Specific Remarks & Observation
| : | 1. Construction work is in process at the time of Visit. Internal visit not allowed. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Dry Balcony + Deck. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. On Site, we meet Mr Avinash (8879975804). 8. We have refered approved plans, CC, & Fire Noc from MCGM site. 10. We have updated approved CC from MCGM Site (on 16/11/2024). 9. We have updated the revised construction table on dated 16/11/2024, which is shared with us by the Godrej officials. 9. Validity of CC is expired on 14/10/2023. Please provide latest CC.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Montana Phase 4 Building No.10 ( Blissberg )
Project Site Address |  |  | : | Montana Phase 4, Vasant Oscar, Mulund West, Mumbai, Maharashtra 400082
Site Visit Date & Time |  |  | : | 07/07/2025 @ 10.57 AM
Location Plan
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Nainesh Tambe | Authorized Signatory Name & Signature | :
Building No 10
Wing C1 & C2
Building No 10
Building No. 7
C2
C1
C2
C1