## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  | Mahindra Alcove (Wing A to E) |  | Date & Time of Site Visit |  | 04/07/2025 @ 01:56 PM
Name of the person met at site & Contact No. |  | Ms. Gauri 8692011409 |  | Date of Report Release |  | 05/07/2025
Data from APF Request Form
Branch Name/ID |  | Godrej One, Vikhroli East, Mumbai |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | Mahindra Lifespace Developers limited |  | Developer Name |  | Mahindra Lifespace Developers limited
Developer Office Address |  | Mahindra Lifespace Developers limited, 5th Floor, Mahindra Towers, Dr. G.M Bhosale, Near Doordarshan, Worli, Mumbai City -400018
Project Address | As per ARF | (Building name, CTS No., Plot No., Survey No., Road., Locality/Village., Near by Landmark., City., District., Taluka., Pin Code -)
| As per Legal Documents | Mahindra Alcove, CTS No.95, 95/1 to 5, near J. B. Metal Compound, Saki Vihar Road, Saki, Ghatkopar, Kurla, Mumbai - 400072
| As per Actual at site | Mahindra Alcove, Saki Vihar Complex, Saki Vihar Complex Rd, Ansa Industrial Estate, Chandivali, Powai, Mumbai, Maharashtra 400072
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC, RERA certificate, NOC
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | MCGM
RERA Registration No. | : | Wing B = P51800031699 Wing A & C = P51800033573 Wing D & E = P51800028352 |  | RERA Registration Validity | : | 2026-06-30
Project Launch Date | : |  |  | Construction Start Date | :
Proposed Date of Completion (As per RERA) | : | 2026-06-30 |  | Developer Bank Name (As per RERA) | : | AXIS BANK
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  | Plot Area (In Sq.Mt) | :
FSI/FAR Permissible | : |  |  | Net Plot Area (In Sq.Mt) | :
Permissible Built up Area (In Sq.Mt) | : |  |  | Proposed Built up Area (In Sq.Mt) | :
Total Number of Units Approved | : | Flats = & Shop = |  | Total Number of Units Planned | : | As per RERA Site Flats = & Shop =
Latitude, Longitude | : | 19.107742,72.8901317 |  | Landmark | : | Gundecha Onclave
Location Link | : | https://maps.app.goo.gl/ENojD8GgvEmt5QUc6
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developed |  | Class of Locality | : | Upper
Type of Road | : | Bitumen |  | Width of the Road | : | 9m
Distance from Train stand (Km) | : | 4Km from Ghatkopar Railway Station |  | Distance from Bus stand (Km) | : | 0.5 KM from Marva Road Junction Bus Stop
Distance from the nearest School (Km) | : | About 4KM from School |  | Distance from Hospital (Km) | : | About 4K form Hospital
Distance from the Main Market (Km) | : | 1. Approx. 2KM from Village Market. 2. Approx. 10KM from Panvel Main Market. |  | Distance from Railway Station (Km) | : | 5.4KM from Somatne Railway Station 10.5KM from Panvel Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North | South | East | West
East |  | NA |  |  | Ansa Industrial Estate
West |  | NA |  |  | Saki Vihar Road
North |  | NA |  |  | Slum
South |  | NA |  |  | Gundecha Onclave
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  | No. of Floors Approved
Wing A |  | Sale | Bs + 1st & 2nd Prk Floor + St + 1st to 16th Floor |  | Bs + 1st & 2nd Prk Floor + St + 1st to 16th Floor
Wing B |  | Sale | Bs + 1st & 2nd Prk Floor + St + 1st to 16th Floor |  | Bs + 1st & 2nd Prk Floor + St + 1st to 16th Floor
Wing C |  | Sale | Bs + 1st & 2nd Prk Floor + St + 1st to 16th Floor |  | Bs + 1st & 2nd Prk Floor + St + 1st to 16th Floor
Wing D |  | Sale | Bs + 1st & 2nd Prk Floor + St + 1st to 16th Floor |  | Bs + 1st & 2nd Prk Floor + St + 1st to 16th Floor
Wing E |  | Sale | Bs + 1st & 2nd Prk Floor + St + 1st to 16th Floor |  | Bs + 1st & 2nd Prk Floor + St + 1st to 16th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : |  |  |  |  | Date:
Approved Plan Details | : |  |  |  |  | Date:
CC Details Valid Up to: |  | CHE/ES/2226/L/337(NEW)/FCC/5/Amend |  |  |  | Date: | 2023-07-03
|  | "Full C.C. to Wing ‘C’, ‘D’ & ‘E’ and Further C.C. up to top of 8th floor only for Wing ‘A’ & ‘B’ as per approved amended plans dated 12.08.2022 excluding 9th to 16th floors for Wing ‘A’ & ‘B’ (restricted for non-handing over of setback area) |  |  |  | Valid Upto Date | 2024-07-02
CC Details Valid Up to: |  | CHE/ES/2226/L/337(NEW)/FCC/6/Amend |  |  |  | Date: | 2023-11-21
|  | Further C.C. up to top of 11th floor only for Wing ‘A’ & ‘B’ as per approved amended plans dated 12.08.2022 excluding 12th to 16th floors for Wing ‘A’ & ‘B’ (restricted for non-handing over of setback area)" |  |  |  | Valid Upto Date | 2024-05-07
Construction Status
Wing A & B = B + 1st & 2nd Prk Floor + St + 1st to 16th Floor |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 12 Slab, Brickwork upto 11 Floor, Internal Plaster upto 8.8 Floor, External Plaster upto 8.8 Floor, External Plumbing, Elevation and Waterproofing upto 1 Floor, Flooring & Fitting upto 4 Floor Completed
|  |  | 2 | 1 |  | 1 | 16 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4
Excavation |  | 16 | 100% | 50.67% |  | Excavation work Completed. Plinth work completed, RCC upto 12 Slab, Brickwork upto 11 Floor, Internal Plaster upto 8.8 Floor, External Plaster upto 8.8 Floor, External Plumbing, Elevation and Waterproofing upto 1 Floor, Flooring & Fitting upto 4 Floor Completed |  | Excavation in process | 8
Plinth |  | 16 | 100% |  |  |  |  | Excavation Completed | 16
RCC (Including podiums) |  | 12 | 66.67% |  |  |  |  | Footing in Process | 4
Brickwork |  | 11 | 68.75% |  |  |  |  | Footing Completed | 8
Internal Plaster |  | 8.8 | 55% |  |  |  |  | Basement 1 | 12
External Plaster |  | 8.8 | 55% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 1 | 6.25% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 4 | 25% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 16
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Wing C, D & E = B + 1st & 2nd Prk Floor + St + 1st to 16th Floor |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing, Flooring & Fitting, Wooden Work, Electrical & Sanitary fittings, Finishing upto 11 Floor Completed
|  |  | 2 | 1 |  | 1 | 16 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4
Excavation |  | 16 | 100% | 86.88% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing, Flooring & Fitting, Wooden Work, Electrical & Sanitary fittings, Finishing upto 11 Floor Completed |  | Excavation in process | 8
Plinth |  | 16 | 100% |  |  |  |  | Excavation Completed | 16
RCC (Including podiums) |  | 18 | 100% |  |  |  |  | Footing in Process | 4
Brickwork |  | 16 | 100% |  |  |  |  | Footing Completed | 8
Internal Plaster |  | 16 | 100% |  |  |  |  | Basement 1 | 12
External Plaster |  | 16 | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 16 | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 16 | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 16 | 100% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 16 | 100% |  |  |  |  | Plinth completed | 16
Building Common Amenities |  | 11 | 68.75%
Possession |  | 0 | 0%
Construction Status
Wing D & E = B + 1st & 2nd Prk Floor + St + 1st to 16th Floor |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 15 Floor, Flooring & Fitting, Wooden Work upto 15 Floor, Electrical & Sanitary fittings upto 2 Floor Completed
|  |  | 3 | 1 |  | 1 | 16 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4
Excavation |  | 16 | 100% | 77.34% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 15 Floor, Flooring & Fitting, Wooden Work upto 15 Floor, Electrical & Sanitary fittings upto 2 Floor Completed |  | Excavation in process | 8
Plinth |  | 16 | 100% |  |  |  |  | Excavation Completed | 16
RCC (Including podiums) |  | 18 | 100% |  |  |  |  | Footing in Process | 3.2
Brickwork |  | 16 | 100% |  |  |  |  | Footing Completed | 6.4
Internal Plaster |  | 16 | 100% |  |  |  |  | Basement 1 | 9.6
External Plaster |  | 16 | 100% |  |  |  |  | Basement 2 | 12.8
External Plumbing, Elevation and Waterproofing |  | 15 | 93.75% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 16 | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 15 | 93.75% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 2 | 12.5% |  |  |  |  | Plinth completed | 16
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 72.39%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 27000 to 28000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 1000000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft)
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | :
Distress Value (Rs. Per sqft) |  |  |  |  | : | 0
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Total |  | - |  | 0 |  | 0 | 0
Unit Details, Nomenclature and Area Details (Flats)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Total |  | - |  | 0 |  | 0 | 0
Grand Total |  | - |  | 0 |  | 0
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
1st Floor
101 |  |  |  | 0 | 0 | 0 | 0
102 | [6 empty] | 0
103 | [6 empty] | 0
104 | [6 empty] | 0
105 | [6 empty] | 0
106 | [6 empty] | 0
107 | [6 empty] | 0
108 | [6 empty] | 0
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor
201,..,901 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 201,..,901 | 201 | 901
202,..,902 | [6 empty] | 0 | [5 empty] | 202,..,902 | 202 | 902
203,..,903 | [6 empty] | 0 | [5 empty] | 203,..,903 | 203 | 903
204,..,904 | [6 empty] | 0 | [5 empty] | 204,..,904 | 204 | 904
205,..,905 | [6 empty] | 0 | [5 empty] | 205,..,905 | 205 | 905
206,..,906 | [6 empty] | 0 | [5 empty] | 206,..,906 | 206 | 906
207,..,907 | [6 empty] | 0 | [5 empty] | 207,..,907 | 207 | 907
208,..,908 | [6 empty] | 0 | [5 empty] | 208,..,908 | 208 | 908
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 201 to 501 | 201 | 501
202 to 502 | [6 empty] | 0 | [5 empty] | 202 to 502 | 202 | 502
203 to 503 | [6 empty] | 0 | [5 empty] | 203 to 503 | 203 | 503
204 to 504 | [6 empty] | 0 | [5 empty] | 204 to 504 | 204 | 504
205 to 505 | [6 empty] | 0 | [5 empty] | 205 to 505 | 205 | 505
206 to 506 | [6 empty] | 0 | [5 empty] | 206 to 506 | 206 | 506
207 to 507 | [6 empty] | 0 | [5 empty] | 207 to 507 | 207 | 507
208 to 508 | [6 empty] | 0 | [5 empty] | 208 to 508 | 208 | 508
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 201 & 501 | 201 | 501
202 & 502 | [6 empty] | 0 | [5 empty] | 202 & 502 | 202 | 502
203 & 503 | [6 empty] | 0 | [5 empty] | 203 & 503 | 203 | 503
204 & 504 | [6 empty] | 0 | [5 empty] | 204 & 504 | 204 | 504
205 & 505 | [6 empty] | 0 | [5 empty] | 205 & 505 | 205 | 505
206 & 506 | [6 empty] | 0 | [5 empty] | 206 & 506 | 206 | 506
207 & 507 | [6 empty] | 0 | [5 empty] | 207 & 507 | 207 | 507
208 & 508 | [6 empty] | 0 | [5 empty] | 208 & 508 | 208 | 508
Project Specific Remarks & Observation
* | Wing A & B = Construction work is same as last visit dtd. 30/09/2024 Wing C, D & E = Finishing work is in process at the time of Visit. Internal visit was not allowed.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | We are releasing stage updation report
* | Please provide revised CC for A & B Wing.
* | Remark for NOCs
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
Site & Building/Tower Photographs
Name of the Project |  |  | Mahindra Alcove (Wing A to E)
Project Site Address |  |  | Mahindra Alcove, CTS No.95, 95/1 to 5, near J. B. Metal Compound, Saki Vihar Road, Saki, Ghatkopar, Kurla, Mumbai - 400072
Site Visit Date & Time |  |  | 04/07/2025 @ 01:56 PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr. Ganesh Wadkar |  | Authorized Signatory Name & Signature
A Wing
B Wing
C Wing
D Wing
E Wing
Wing A
Wing A
Wing B
Wing C,D & E
Wing B
Wing A
Wing E
Wing D
Wing C
Note on C9: SACHIN: As per initiation Mail
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G113: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%