## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02 | 2025-01-13
Project Name |  |  | : | Runwal Forest Tower 8, 9, 10 & 11 |  | Date of Site Visit |  | 03/07/2025 @ 12.18 PM |  | 2025-04-04 | 2025-07-03
Name of the person met at site & Contact No. |  |  | : | Mr.Rajeev Malhotra 9167582129 |  | Date of Report Release |  | 10/07/2025 |  |  | 90
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr.Suraj Khare
Builder Group Name |  |  | : | Wheelabrator Alloy Castings Limited | Developer Name | : | Wheelabrator Alloy Castings Limited
Developer Office Address |  |  | : | Runwal & Omkar Esquare,5th Floor, Eastern Express Highway,Sion (East),Mumbai - 400022
Project Address | : | As per ARF | : | Lal Bahadur Shastri Rd, near Mangatram Petrol Pump, Ambedkar Nagar, Kanjurmarg West, Bhandup West, Mumbai, Maharashtra 400078
| : | As per Legal Documents | : | Proposed building on plot bearing CTS No. 596, 596/1-6, 597, 597/1-7,598, 598/1-3, 599A, 599A/1-81, 601, 602, 602/1-9, 603, 604, 605, 605/1-17, 606, 606/1-83, 607/1-31, 607A, 607D of village Kanjur, At LBS Marg, Kanjur(W), Mumbai
| : | As per Actual at site | : | Runwal Forest Tower 8, 10 & 11, Near. St Xavier's High School & Junior College, Road. Lal Bahadur Shastri Road, Village. Kanjur West, Mumbai, 400078
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate.
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Municipal Corporation Of Greater Mumbai (MCGM)
RERA Registration No. | : | Tower 8 = P51800001838 Tower 9, 10 & 11 = P51800001137 |  |  | RERA Registration Validity | : | Tower 8 = Completed Tower 9, 10 & 11 = 30/06/2026
Project Launch Date | : | 2015-01-07 |  |  | Construction Start Date | : | 2017-07-29
Proposed Date of Completion (As per RERA) | : | Tower 8 = Completed Tower 9, 10 & 11 = 30/06/2026 |  |  | Developer Bank Name (As per RERA) | : | HDFC Bank IFSC Code :HDFC0000163
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 62558.2
FSI/FAR Permissible | : | 1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 168129.99 |  |  | Tower 9, 10 & 11 | 56852.28
Permissible Built up Area (In Sq.Mt) | : | 47427.55 |  |  | Total Number of Units Planned | : | Flats = 1115
Total Number of Units Approved | : | Flats = 1152 |  |  | If Mixed, No. of Commercial Units | : | -
Latitude, Longitude | : | 19.13686,72.932314 |  |  | Landmark |  | Gundecha Altura
Location Link | : | https://goo.gl/maps/Spdk4i8KNYYqhQyu5
Extra Amenities available | : | Jogging Track, Pet Zone, Mini theatre, Senior Citizen's Area, Kids Play Area, Clubhouse, Cafe, Open Air Gym, Basketball/ Badminton Court, Tennis Court, Baby Creche, Steam/ Massage Room, Bakery Outlet, Music & Art Room, Zen Garden, Putting Green, Skating Rink, Yoga Room, Landscape Area, Convenience Room, Squash Court, Indoor games.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Upper
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | About 300 M from Ciba Company Bus Stop
Distance from the nearest School (Km) | : | About 1KM from B.P.E.S. High School. |  |  | Distance from Hospital (Km) | : | About 300 M form Central Hospital
Distance from the Main Market (Km) | : | 1. Approx. 750 M from Kanjurmarg Market. 2. Approx. 950 M from D Mart. |  |  | Distance from Railway Station (Km) | : | 1.5 KM from Kanjur Marg Railway Station 1.4 KM from Bhandup Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Road | Drive Way | Road |  | Tower 5 & 6
As per Site / Actual |  |  | : | Jaihind Oil Mill Company | Gundecha Altura | Railway Track |  | Tower 5 & 6
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Tower 8 |  | Sale |  | 3B + G + 1P +1st to 48th Floor |  |  | 3B + G + 1P +1st to 48th Floor
Tower 9 |  | Sale |  | 3B + G + 1P +1st to 48th Floor |  |  | 3B + G + 1P +1st to 48th Floor
Tower 10 |  | Sale |  | 3B + G + 1P +1st to 54th Floor |  |  | 3B + G + 1P +1st to 50th Floor
Tower 11 |  | Sale |  | 3B + G + 1P +1st to 50th Floor |  |  | 3B + G + 1P +1st to 47th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | CHE/ES/1458/S/337(NEW)/337/25/Amend Date: 19/11/2024
Approved Plan Details (Tower 8 to 11) | : | CHE/ES/1458/S/337(NEW)/337/25/Amend Date: 19/11/2024
CC Details | : | CHE/ES/1458/S/337(NEW)/FCC/10/Amend Date: 22/10/2024 Valid Upto Date: 21/10/2025 Full C.C. is granted for Tower no. 9 & Tower no. 10 and further C.C. is granted for Tower no. 11 upto 40th floor and C.C. is re-endorsed for Fitness Centre as per approved amended plans dated 05.03.2024 by restricting C.C. of tower 11 fro m 41st floor to 48th floor for installment facility and temporary site office subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution.
CC Details | : | CHE/ES/1458/S/337(NEW)/FCC/11/Amend Date: 26/11/2024 Valid Upto Date: 25/11/2025 Full C.C. is granted for Tower no. 10 and C.C. is re-endorsed for Tower no. 9 & Tower no. 11 as per approved amended plans dated 19/11/2024 by restricting C.C. of 41st to 47th floor of Tower 11 for installment facility subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution.
CC Details | : | CHE/ES/1458/S/337(NEW)/FCC/12/Amend Date: 25/03/2025 Valid Upto Date: 08/01/2026 Full C.C. of Tower no. 10 & C.C. upto 48th floor of Tower no. 11 is granted as per approved amended plans dated 17/02/2025 by restricting C.C. from 49th to 54th floor of Tower no 11 for installment facility, subject to timely renewal of B.G., SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction along with precautionary measures for air pollution.
Part OC Details Tower no. 8 | : | CHE/ES/1458/S/337(NEW)/OCC/4/New |  |  | Dated |  | 2022-06-28
Approved Floor : Part Occupation for the proposed Residential Tower no. 8 consisting of 3 level Basement (Pt) + Ground + P1 Level + 1st to 45th floors
OC Details Tower no. 8 | : | CHE/ES/1458/S/337(NEW)/OCC/5/New |  |  | Dated |  | 2023-01-23
Approved Floor : part Occupation i.e. Full Occupation of Tower no. 8 consisting of 46th to 48th floor including OHT & Lift Machine room in continuation with earlier occupation certificate issued on 28.06.2022 for Tower no. 8 consisting of 3 level Basement (Pt) + Ground + P1 Level + 1st to 48th floors.
Part OC Details Tower no. 9 | : | CHE/ES/1458/S/337(NEW)/OCC/7/New |  |  | Dated |  | 2025-04-07
Tower No. 9 Consisting Of 3 Level Basement (Pt) + Ground + P1 Level + 1st To 45th Upper Floors (Excluding 46th To 48th Floor) Along with Built Up Amenity As Per Reg. 14(b) Of DCPR 2034.
Railway NOC Details | : | BB.W.6561.NOC.KJRD.1077.DB |  |  | Airport Authority Clearance Details | : | SNCR/WEST/B/070921/559456
Forest NOC Details | : | Format1.0/CAC-CELL/UAN No.0000084171/CO2003001084 |  |  | Other NOC Details | : | -
Construction Status
Tower 8 = 3B + G + 1P +1st to 48th Floor |  |  | : | Basement | Ground |  | Podium | Floors | All work completed. Please provide OC.
|  |  |  | 3 | 1 |  | 1 | 48 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 12
Excavation |  | 48 |  | 100% | 100% |  | All work Completed. OC Received. |  | Excavation in process | 24
Plinth |  | 48 |  | 100% |  |  |  |  | Excavation Completed | 48
RCC (Including podiums) |  | 50 |  | 100% |  |  |  |  | Footing in Process | 9.6
Brickwork |  | 48 |  | 100% |  |  |  |  | Footing Completed | 19.2
Door & Window Frames |  | 48 |  | 100% |  |  |  |  | Basement 1 | 28.8
Internal Plaster |  | 48 |  | 100% |  |  |  |  | Basement 2 | 38.4
Ext.Plaster |  | 48 |  | 100% |  |  |  |  | Basement 3 | 0
Plumb.& Electri. |  | 48 |  | 100% |  |  |  |  | Basement 4 | 0
Flooring & Fitting |  | 48 |  | 100% |  |  |  |  | Plinth in process | 0
Painting |  | 48 |  | 100% |  |  |  |  | Plinth completed | 48
Building Common Amenities |  | 48 |  | 100%
Possession |  | 48 |  | 100%
Construction Status
Tower 9 = 3B + G + 1P + 1st to 48th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Plinth, RCC, Brick, Plaster, Flooring, Wooden, Plumbing, Electrification, etc., work Completed. Finishing work is in process.
|  |  |  | 3 | 1 |  | 1 | 48 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 12
Excavation |  | 48 |  | 100% | 98.59% |  | Plinth, RCC, Brick, Plaster, Flooring, Wooden, Plumbing, Electrification, etc., work Completed. Finishing work is in process. |  | Excavation in process | 24
Plinth |  | 48 |  | 100% |  |  |  |  | Excavation Completed | 48
RCC (Including podiums) |  | 50 |  | 100% |  |  |  |  | Footing in Process | 9.6
Brickwork |  | 48 |  | 100% |  |  |  |  | Footing Completed | 19.2
Internal Plaster |  | 48 |  | 100% |  |  |  |  | Basement 1 | 28.8
External Plaster |  | 48 |  | 100% |  |  |  |  | Basement 2 | 38.4
External Plumbing, Elevation and Waterproofing |  | 48 |  | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 48 |  | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 48 |  | 100% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 45 |  | 93.75% |  |  |  |  | Plinth completed | 48 |  | #VALUE!
Building Common Amenities |  | 45 |  | 93.75%
Possession |  | 45 |  | 93.75%
Construction Status
Tower 10 = 3B + G + 1P + 1st to 54th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 52 Slab, Brickwork upto 49 Floor, Internal Plaster upto 49 Floor, External Plaster upto 47 Floor, External Plumbing, Elevation and Waterproofing upto 40 Floor, Flooring & Fitting upto 29 Floor, Wooden Work upto 18 Floor, Electrical & Sanitary fittings upto 15 Floor Completed
|  |  |  | 3 | 1 |  | 1 | 54 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.5
Excavation |  | 54 |  | 100% | 67.8% |  | Excavation work Completed. Plinth work completed, RCC upto 52 Slab, Brickwork upto 49 Floor, Internal Plaster upto 49 Floor, External Plaster upto 47 Floor, External Plumbing, Elevation and Waterproofing upto 40 Floor, Flooring & Fitting upto 29 Floor, Wooden Work upto 18 Floor, Electrical & Sanitary fittings upto 15 Floor Completed |  | Excavation in process | 27
Plinth |  | 54 |  | 100% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 52 |  | 92.86% |  |  |  |  | Footing in Process | 10.8 | As per letter
Brickwork |  | 49 |  | 90.74% |  |  |  |  | Footing Completed | 21.6
Internal Plaster |  | 49 |  | 90.74% |  |  |  |  | Basement 1 | 32.4
External Plaster |  | 47 |  | 87.04% |  |  |  |  | Basement 2 | 43.2
External Plumbing, Elevation and Waterproofing |  | 40 |  | 74.07% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 29 |  | 53.7% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 18 |  | 33.33% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 15 |  | 27.78% |  |  |  |  | Plinth completed | 54 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower 11 = 3B + G + 1P + 1st to 50th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 49 Slab, Brickwork upto 39 Floor, Internal Plaster upto 35 Floor, External Plaster upto 35 Floor, External Plumbing, Elevation and Waterproofing upto 36 Floor, Flooring & Fitting upto 17 Floor, Wooden Work upto 14 Floor, Electrical & Sanitary fittings upto 4 Floor Completed
|  |  |  | 3 | 1 |  | 1 | 50 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 12.5
Excavation |  | 50 |  | 100% | 63.86% |  | Excavation work Completed. Plinth work completed, RCC upto 49 Slab, Brickwork upto 39 Floor, Internal Plaster upto 35 Floor, External Plaster upto 35 Floor, External Plumbing, Elevation and Waterproofing upto 36 Floor, Flooring & Fitting upto 17 Floor, Wooden Work upto 14 Floor, Electrical & Sanitary fittings upto 4 Floor Completed |  | Excavation in process | 25
Plinth |  | 50 |  | 100% |  |  |  |  | Excavation Completed | 50
RCC (Including podiums) |  | 49 |  | 94.23% |  |  |  |  | Footing in Process | 10
Brickwork |  | 39 |  | 78% |  |  |  |  | Footing Completed | 20
Internal Plaster |  | 35 |  | 70% |  |  |  |  | Basement 1 | 30
External Plaster |  | 35 |  | 70% |  |  |  |  | Basement 2 | 40
External Plumbing, Elevation and Waterproofing |  | 36 |  | 72% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 17 |  | 34% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 14 |  | 28% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 4 |  | 8% |  |  |  |  | Plinth completed | 50 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 82.56%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 22000 | Floor Rise Per Sq. Ft. (on Carpet area) | : | 100/- from 2nd Floor
Car Parking Charges |  |  | : | 7,00,000/- | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 6017.2798
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 12191.5645
Distress Value (Rs. Per sqft) | [5 empty] | : | 4813.8239
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Tower 8 |  | Sale |  | Flats | 191 |  | 203436.909 | 325499.0544
Tower 9 |  | Sale |  | Flats | 191 |  | 203436.909 | 325499.0544
Tower 10 |  | Sale |  | Flats | 396 |  | 225759.3998 | 361215.0397
Tower 11 |  | Sale |  | Flats | 374 |  | 209032.6928 | 334452.3085
Total |  | - |  | - | 1152 |  | 841665.9106 | 1346665.457
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
60%
Tower 8 - Magnolia
3rd to 1st Basement Floor For Parking
Ground Floor
Ground Floor |  | 1 |  | 3BHK | 1075.6465 |  | 0 | 1721.0344
|  | 2 |  | Amenities
|  | 3 |  | Double Height
|  | 4 |  | 3BHK | 1104.1711 |  | 0 | 1766.6738
1st Podium Level Floor
1st Podium Level Floor |  | 1 |  | 3BHK | 1137.8624 |  | 0 | 1820.5799
|  | 2 |  | 3BHK | 986.5206 |  | 0 | 1578.433
|  | 3 |  | Double Height |  |  |  | 0
|  | 4 |  | 3BHK | 1249.7004 |  | 0 | 1999.5206
1st to 5th, 7th to 12th, 14th to 19th, 20th to 26th, 28th to 33rd, 35th to 40th, 42nd to 48th Floor
1st to 5th, 7th to 12th, 14th to 19th, 20th to 26th, 28th to 33rd, 35th to 40th, 42nd to 48th Floor |  | 1 |  | 3BHK | 1137.8624 |  | 0 | 1820.5799 |  |  |  |  | 15701,..,4801 | 15701 | 4801
|  | 2 |  | 3BHK | 986.5206 |  | 0 | 1578.433 |  |  |  |  | 15702,..,4802 | 15702 | 4802
|  | 3 |  | 3BHK | 986.5206 |  | 0 | 1578.433 |  |  |  |  | 15703,..,4803 | 15703 | 4803
|  | 4 |  | 3BHK | 1137.8624 |  | 0 | 1820.5799 |  |  |  |  | 15704,..,4804 | 15704 | 4804
6th, 13th, 20th, 27th & 34th Floor (Part Refuge Area)
6th, 13th, 20th, 27th & 34th Floor (Part Refuge Area) |  | 1 |  | 3BHK | 1137.8624 |  | 0 | 1820.5799 | 14995.2221 | 23992.3554 |  |  | 6101,..,3401 | 6101 | 3401
|  | 2 |  | Refuge Area | [8 empty] | 6102,..,3402 | 6102 | 3402
|  | 3 |  | 3BHK | 986.5206 |  | 0 | 1578.433 | 15014.8917 | 24023.8268 |  |  | 6103,..,3403 | 6103 | 3403
|  | 4 |  | 3BHK | 1137.8624 |  | 0 | 1820.5799 |  |  |  |  | 6104,..,3404 | 6104 | 3404
41st Floor (Part Refuge Area)
41st Floor (Part Refuge Area) |  | 1 |  | 2BHK | 999.2221 |  | 0 | 1598.7554 |  |  |  |  | 401,..,4101 | 401 | 4101
|  | 2 |  | Refuge Area | [8 empty] | 402,..,4102 | 402 | 4102
|  | 3 |  | 3BHK | 986.5206 |  | 0 | 1578.433 |  |  |  |  | 403,..,4103 | 403 | 4103
|  | 4 |  | 3BHK | 1137.8624 |  | 0 | 1820.5799 |  |  |  |  | 404,..,4104 | 404 | 4104
Tower 9 - Lily
3rd to 1st Basement Floor For Parking
Ground Floor For Part Residential
Ground Floor For Part Residential |  | 1 |  | 3BHK | 1075.6465 |  | 0 | 1721.0344
|  | 2 |  | Meter Room
|  | 3 |  | Double Height Entrance
|  | 4 |  | 3BHK | 1104.1711 |  | 0 | 1766.6738
1st Podium Level Floor
1st Podium Level Floor |  | 1 |  | 3BHK | 1137.8624 |  | 0 | 1820.5799
|  | 2 |  | 3BHK | 986.5206 |  | 0 | 1578.433
|  | 3 |  | Double Height |  |  |  | 0
|  | 4 |  | 3BHK | 1249.7004 |  | 0 | 1999.5206
1st to 5th & 7th to 12th & 14th to 19th & 21st to 26th, 28th to 33rd & 35th to 40th, 42nd to 48th Floor
1st to 5th & 7th to 12th & 14th to 19th & 21st to 26th, 28th to 33rd & 35th to 40th, 42nd to 48th Floor |  | 1 |  | 3BHK | 1137.8624 |  | 0 | 1820.5799 |  |  |  |  | 15701,..,4801 | 15701 | 4801
|  | 2 |  | 3BHK | 986.5206 |  | 0 | 1578.433 |  |  |  |  | 15702,..,4802 | 15702 | 4802
|  | 3 |  | 3BHK | 986.5206 |  | 0 | 1578.433 |  |  |  |  | 15703,..,4803 | 15703 | 4803
|  | 4 |  | 3BHK | 1137.8624 |  | 0 | 1820.5799 |  |  |  |  | 15704,..,4804 | 15704 | 4804
Fire Check Floor Inbetween 18th & 19th Floor
6th, 13th, 20th, 27th & 34th Floor (Part Refuge Area)
6th, 13th, 20th, 27th & 34th Floor (Part Refuge Area) |  | 1 |  | 3BHK | 1137.8624 |  | 0 | 1820.5799 | 14995.2221 | 23992.3554 |  |  | 6101,..,3401 | 6101 | 3401
|  | 2 |  | Refuge Area | [8 empty] | 6102,..,3402 | 6102 | 3402
|  | 3 |  | 3BHK | 986.5206 |  | 0 | 1578.433 | 15014.8917 | 24023.8268 |  |  | 6103,..,3403 | 6103 | 3403
|  | 4 |  | 3BHK | 1137.8624 |  | 0 | 1820.5799 |  |  |  |  | 6104,..,3404 | 6104 | 3404
41st Floor (Part Refuge Area)
41st Floor (Part Refuge Area) |  | 1 |  | 2BHK | 999.2221 |  | 0 | 1598.7554 |  |  |  |  | 401,..,4101 | 401 | 4101
|  | 2 |  | Refuge Area | [8 empty] | 402,..,4102 | 402 | 4102
|  | 3 |  | 3BHK | 986.5206 |  | 0 | 1578.433 |  |  |  |  | 403,..,4103 | 403 | 4103
|  | 4 |  | 3BHK | 1137.8624 |  | 0 | 1820.5799 |  | 94.5802 |  |  | 404,..,4104 | 404 | 4104
Tower 10 - Tulip | [9 empty] | 4.392
3rd to 1st Basement Floor For Parking
Ground Floor For Part Residential
Ground Floor For Part Residential |  | 1 |  | Double Height Entrance
2
|  | 3 |  | Society Office | 535.9396 |  | 0 | 857.5033
|  | 4 |  | 2BHK | 591.1589 |  | 0 | 945.8542
|  | 5 |  | 2BHK | 644.9789 |  | 0 | 1031.9662 | 14272.8128
|  | 6 |  | 2BHK | 644.9789 |  | 0 | 1031.9662
|  | 7 |  | 2BHK | 591.1589 |  | 0 | 945.8542
|  | 8 |  | Meter Room | 535.9396 |  | 0 | 857.5033
1st Podium Level Floor
1st Podium Level Floor |  | 1 |  | Double Height
2
|  | 3 |  | 2BHK | 535.9396 |  | 0 | 857.5033
|  | 4 |  | 2BHK | 591.1589 |  | 0 | 945.8542
|  | 5 |  | 2BHK | 671.566 |  | 0 | 1074.5055
|  | 6 |  | 2BHK | 671.566 |  | 0 | 1074.5055
|  | 7 |  | 2BHK | 591.1589 |  | 0 | 945.8542
|  | 8 |  | 2BHK | 535.9396 |  | 0 | 857.5033
1st to 6th, 8th to 13th, 15th to 20th, 22nd to 27th, 29th & 30th Floor
1st to 6th, 8th to 13th, 15th to 20th, 22nd to 27th, 29th & 30th Floor |  | 1 |  | 1.5BHK | 466.1888 |  | 0 | 745.9021 | 17160.428 | 27456.6847
|  | 2 |  | 1.5BHK | 466.1888 |  | 0 | 745.9021
|  | 3 |  | 2BHK | 535.9396 |  | 0 | 857.5033
|  | 4 |  | 2BHK | 591.1589 |  | 0 | 945.8542
|  | 5 |  | 2BHK | 671.566 |  | 0 | 1074.5055
|  | 6 |  | 2BHK | 671.566 |  | 0 | 1074.5055
|  | 7 |  | 2BHK | 591.1589 |  | 0 | 945.8542
|  | 8 |  | 2BHK | 535.9396 |  | 0 | 857.5033
Service Floor Inbetween 30th & 31st Floor
7th, 14th, 21st & 28th Floor (Part Refuge Area)
7th, 14th, 21st & 28th Floor (Part Refuge Area) |  | 1 |  | 1.5BHK | 466.1888 |  | 0 | 745.9021
|  | 2 |  | 1.5BHK | 466.1888 |  | 0 | 745.9021
|  | 3 |  | 2BHK | 535.9396 |  | 0 | 857.5033
|  | 4 |  | 2BHK | 591.1589 |  | 0 | 945.8542
|  | 5 |  | 2BHK | 671.566 |  | 0 | 1074.5055
|  | 6 |  | 2BHK | 671.566 |  | 0 | 1074.5055
|  | 7 |  | Refuge Area | [8 empty] | 1,..,1 | 1 | 1
|  | 8 | [10 empty] | 2,..,2 | 2 | 2
31st to 34th & 36th To 41st, 43rd to 48th & 50th Floor
31st to 34th & 36th To 41st, 43rd to 48th & 50th Floor |  | 1 |  | 1.5BHK | 470.3868 |  | 0 | 752.6189 | 17007.28 | 27211.6479
|  | 2 |  | 1.5BHK | 470.3868 |  | 0 | 752.6189
|  | 3 |  | 2BHK | 542.2903 |  | 0 | 867.6645
|  | 4 |  | 2BHK | 599.3395 |  | 0 | 958.9432
|  | 5 |  | 2BHK | 682.6529 |  | 0 | 1092.2446
|  | 6 |  | 2BHK | 682.6529 |  | 0 | 1092.2446
|  | 7 |  | 2BHK | 596.1103 |  | 0 | 953.7765
|  | 8 |  | 2BHK | 542.2903 |  | 0 | 867.6645
35th, 42nd & 49th Floor (Part Refuge Area)
35th, 42nd & 49th Floor (Part Refuge Area) |  | 1 |  | 1.5BHK | 470.3868 |  | 0 | 752.6189
|  | 2 |  | 1.5BHK | 470.3868 |  | 0 | 752.6189
|  | 3 |  | 2BHK | 542.2903 |  | 0 | 867.6645
|  | 4 |  | 2BHK | 599.3395 |  | 0 | 958.9432
|  | 5 |  | 2BHK | 682.6529 |  | 0 | 1092.2446
|  | 6 |  | 2BHK | 682.6529 |  | 0 | 1092.2446
|  | 7 |  | Refuge Area | [8 empty] | 1,..,1 | 1 | 1
|  | 8 | [10 empty] | 2,..,2 | 2 | 2
Tower 11 - Orchid
3rd to 1st Basement Floor For Parking
Ground Floor For Part Residential
Ground Floor For Part Residential |  | 1 |  | Society Office
|  | 2 |  | 2BHK | 665.4305 |  | 0 | 1064.6888
|  | 3 |  | 1.5BHK | 511.3976 |  | 0 | 818.2362
|  | 4 |  | 1.5BHK | 511.3976 |  | 0 | 818.2362
|  | 5 |  | 2BHK | 663.0732 |  | 0 | 1060.9171 |  | 54.3093 | 3.721
|  | 6 |  | Amenities | 644.9789 |  | 0 | 1031.9662 |  | 58.0303
|  | 7 |  | Double Height Entrance
8
1st Podium Level Floor
1st Podium Level Floor |  | 1 |  | 2BHK | 620.437 |  | 0 | 992.6991
|  | 2 |  | 2BHK | 665.4305 |  | 0 | 1064.6888
|  | 3 |  | 1.5BHK | 511.3976 |  | 0 | 818.2362
|  | 4 |  | 1.5BHK | 511.3976 |  | 0 | 818.2362
|  | 5 |  | 2BHK | 666.0763 |  | 0 | 1065.7221
|  | 6 |  | 2BHK | 620.437 |  | 0 | 992.6991
|  | 7 |  | Double Height Entrance
8
1st to 6th, 8th to 13th & 15th Floor
1st to 6th, 8th to 13th & 15th Floor |  | 1 |  | 2BHK | 620.437 |  | 0 | 992.6991
|  | 2 |  | 2BHK | 665.4305 |  | 0 | 1064.6888
|  | 3 |  | 1.5BHK | 511.3976 |  | 0 | 818.2362
|  | 4 |  | 1.5BHK | 511.3976 |  | 0 | 818.2362
|  | 5 |  | 2BHK | 665.861 |  | 0 | 1065.3777
|  | 6 |  | 2BHK | 620.437 |  | 0 | 992.6991
|  | 7 |  | 1BHK | 433.4663 |  | 0 | 693.546 | 21916.353 | 13697.7206
|  | 8 |  | 1BHK | 433.4663 |  | 0 | 693.546
7th & 14th Floor (Part Refuge Area)
7th & 14th Floor (Part Refuge Area) |  | 1 |  | Refuge Area | 466.1888 |  | 0 | 745.9021
|  | 2 |  | 1.5BHK | 466.1888 |  | 0 | 745.9021
|  | 3 |  | 1.5BHK | 511.3976 |  | 0 | 818.2362
|  | 4 |  | 1.5BHK | 511.3976 |  | 0 | 818.2362
|  | 5 |  | 2BHK | 665.861 |  | 0 | 1065.3777
|  | 6 |  | 2BHK | 620.437 |  | 0 | 992.6991
|  | 7 |  | 1BHK | 433.4663 |  | 0 | 693.546
|  | 8 |  | 1BHK | 433.4663 |  | 0 | 693.546
16th to 20th & 22nd to 27th & 29th, & 30th Floor
16th to 20th & 22nd to 27th & 29th, & 30th Floor |  | 1 |  | 2BHK | 620.9752 |  | 0 | 993.5603
|  | 2 |  | 2BHK | 665.9687 |  | 0 | 1065.5499
|  | 3 |  | 1.5BHK | 511.3976 |  | 0 | 818.2362
|  | 4 |  | 1.5BHK | 511.3976 |  | 0 | 818.2362
|  | 5 |  | 2BHK | 666.3992 |  | 0 | 1066.2388
|  | 6 |  | 2BHK | 620.9752 |  | 0 | 993.5603
|  | 7 |  | 1BHK | 433.7892 |  | 0 | 694.0627
|  | 8 |  | 1BHK | 433.7892 |  | 0 | 694.0627
Service Floor Inbetween 30th & 31st Floor
21st & 28th Floor (Part Refuge Area)
21st & 28th Floor (Part Refuge Area) |  | 1 |  | Refuge Area | 466.1888 |  | 0 | 745.9021
|  | 2 |  | 1.5BHK | 466.1888 |  | 0 | 745.9021
|  | 3 |  | 1.5BHK | 511.3976 |  | 0 | 818.2362
|  | 4 |  | 1.5BHK | 511.3976 |  | 0 | 818.2362
|  | 5 |  | 2BHK | 665.861 |  | 0 | 1065.3777 | 25530.8525
|  | 6 |  | 2BHK | 620.9752 |  | 0 | 993.5603
|  | 7 |  | 1BHK | 433.7892 |  | 0 | 694.0627
|  | 8 |  | 1BHK | 433.7892 |  | 0 | 694.0627
31st to 34th & 36th to 40th Floor
31st to 34th & 36th to 40th Floor |  | 1 |  | 2BHK | 627.003 |  | 0 | 1003.2048
|  | 2 |  | 2BHK | 668.875 |  | 0 | 1070.1999
|  | 3 |  | 1.5BHK | 516.7796 |  | 0 | 826.8474
|  | 4 |  | 1.5BHK | 516.7796 |  | 0 | 826.8474
|  | 5 |  | 2BHK | 672.6424 |  | 0 | 1076.2278
|  | 6 |  | 2BHK | 627.003 |  | 0 | 1003.2048
|  | 7 |  | 1BHK | 437.7719 |  | 0 | 700.435
|  | 8 |  | 1BHK | 437.7719 |  | 0 | 700.435
35th Floor (Part Refuge Area)
35th Floor (Part Refuge Area) |  | 1 |  | Refuge Area | 466.1888 |  | 0 | 745.9021
|  | 2 |  | 1.5BHK | 466.1888 |  | 0 | 745.9021
|  | 3 |  | 1.5BHK | 516.7796 |  | 0 | 826.8474
|  | 4 |  | 1.5BHK | 516.7796 |  | 0 | 826.8474
|  | 5 |  | 2BHK | 672.6424 |  | 0 | 1076.2278 | 25273.4603
|  | 6 |  | 2BHK | 627.003 |  | 0 | 1003.2048
|  | 7 |  | 1BHK | 437.7719 |  | 0 | 700.435
|  | 8 |  | 1BHK | 437.7719 |  | 0 | 700.435
41st & 43rd Floor
41st & 43rd Floor |  | 1 |  | 2BHK | 627.003 |  | 0 | 1003.2048
|  | 2 |  | 2BHK | 672.6424 |  | 0 | 1076.2278
|  | 3 |  | 1.5BHK | 516.7796 |  | 0 | 826.8474
|  | 4 |  | 1.5BHK | 516.7796 |  | 0 | 826.8474
|  | 5 |  | 2BHK | 672.6424 |  | 0 | 1076.2278
|  | 6 |  | 2BHK | 627.003 |  | 0 | 1003.2048
|  | 7 |  | 1BHK | 437.7719 |  | 0 | 700.435
|  | 8 |  | 1BHK | 437.7719 |  | 0 | 700.435
42nd Floor (Part Refuge Area)
42nd Floor (Part Refuge Area) |  | 1 |  | Refuge Area | 466.1888 |  | 0 | 745.9021
|  | 2 |  | 1.5BHK | 466.1888 |  | 0 | 745.9021
|  | 3 |  | 1.5BHK | 516.7796 |  | 0 | 826.8474
|  | 4 |  | 1.5BHK | 516.7796 |  | 0 | 826.8474
|  | 5 |  | 2BHK | 672.6424 |  | 0 | 1076.2278 | 25273.4603
|  | 6 |  | 2BHK | 627.003 |  | 0 | 1003.2048
|  | 7 |  | 1BHK | 437.7719 |  | 0 | 700.435
|  | 8 |  | 1BHK | 437.7719 |  | 0 | 700.435
44th to 47th Floor
44th to 47th Floor |  | 1 |  | 2BHK | 627.003 |  | 0 | 1003.2048
|  | 2 |  | 2BHK | 672.6424 |  | 0 | 1076.2278
|  | 3 |  | 1.5BHK | 557.3599 |  | 0 | 891.7759
|  | 4 |  | 1.5BHK | 557.3599 |  | 0 | 891.7759
|  | 5 |  | 2BHK | 672.6424 |  | 0 | 1076.2278
|  | 6 |  | 2BHK | 627.003 |  | 0 | 1003.2048
|  | 7 |  | 1BHK | 437.7719 |  | 0 | 700.435
|  | 8 |  | 1BHK | 437.7719 |  | 0 | 700.435
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Tower 8 - All work Completed. OC Received. Tower 9 - Finishing work is in process at the time of Visit. Part OC received. Tower 10 & 11 - Construction work is in process at the time of Visit. Internal visit was not allowed. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Deck Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We have updated Latest approved floor plan of Tower 8 (on 26/08/2022). 8. We have updated part OC of Tower 8 (on 26/08/2022). 9. We have updated Approved Plans & CC of Tower 9, 10 & 11 (on 28/11/2024). 10. We have updated Approved CC (on 26/03/2025). 11. We have updated Part OC for Tower 9 (On 19/04/2025). 12. Please provide revised approved plans & CC. 11. Validity of CC is expired on 06/01/2024. Please provide revised CC. | [6 empty] | 10. We have updated Approved Plans & CC of Tower 9, 10 & 11 (on 07/03/2024). 9. We have updated Approved Plans & CC of Tower 9, 10 & 11 (on 02/11/2023).
Site & Building/Tower Photographs
Name of the Project |  |  | : | Runwal Forest Tower 8, 9, 10 & 11
Project Site Address |  |  | : | Lal Bahadur Shastri Rd, near Mangatram Petrol Pump, Ambedkar Nagar, Kanjurmarg West, Bhandup West, Mumbai, Maharashtra 400078
Site Visit Date & Time |  |  | : | 03/07/2025 @ 12.18 PM
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Nainesh | Authorized Signatory Name & Signature | :
Tower
9
Tower 8
Tower
10
Tower 11