## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  |  | : | Raunak Bliss (B1 To B6) |  | Date & Time of Site Visit |  | 04/07/2025 @ 12:13 PM
Name of the person met at site & Contact No. |  |  | : | Mr. Sunil |  | Date of Report Release |  | 05/07/2025
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | Unnathi Associates | Developer Name | : | Raunak Group
Developer Office Address |  |  | : | Raunak Group 1st Floor Plot Number 1 Mohan Mill Compound, Ghodbunder Rd, above Ford Showroom, Thane West, Thane, Maharashtra 400607
Project Address | : | As per ARF | : | Raunak Bliss B1 to B6, Road.Hawre City , Village.Owala, Near by Landmark.Purushottam Nayan , City.Thane West, District. Thane, Taluka.Thane, Pin Code - 400615.
| : | As per Legal Documents | : | Raunak Bliss B1 to B6, Survey No.21/1,3,4,5,6,7,8A,8B of Village - Vadavali & Survey No.72/8, 71/1, 66/1,2,4,6,7,8,9,10,11,12,13,14,15,16,17 & 65/1&2 of Village Owala, District.Thane, Taluka.Thane (west) , Pin Code - 400615
| : | As per Actual at site | : | Raunak Bliss B1 to B6, Road.Hawre City , Village.Owala, Near by Landmark.Purushottam Nayan , City.Thane West, District. Thane, Taluka.Thane, Pin Code - 400615.
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate, NOC
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Thane Municipal Corporation (TMC)
RERA Registration No. | : | Raunak Bliss B1 - P51700046534 Raunak Bliss B2 - P51700046565 Raunak Bliss B3 - P51700046564 Raunak Bliss B4 - P51700050829 Raunak Bliss B5 - P51700050828 Raunak Bliss B6 - P51700050827 |  |  | RERA Registration Validity | : | 2029-12-30
Project Launch Date | : | 2022-08-12 |  |  | Construction Start Date | : | 2022-12-01
Proposed Date of Completion (As per RERA) | : | 2029-12-30 |  |  | Developer Bank Name (As per RERA) | : | HDFC BANK IFSC Code - HDFC0000488
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 46829.89
FSI/FAR Permissible | : | 1.6 |  |  | Proposed Built up Area (In Sq.Mt) | : | 152458.75
Permissible Built up Area (In Sq.Mt) | : | 152458.75 |  |  | Total Number of Units Planned | : | Flats = 1638
Total Number of Units Approved | : | Flats = 1638 |  |  | If Mixed, No. of Commercial Units | : | NA
Latitude | : | 19.2622 |  |  | Longitude | : | 72.9587
Location Link | : | https://goo.gl/maps/PcNa7JMbKFZabgTX9
Extra Amenities available | : | Entrance, Open Party, Garden, Jogging Track, Pet Zone, Outdoor Activity Lawn, Kids Play Area, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | .7 KM from Haware City (Borivade Gaon)
Distance from the nearest School (Km) | : | About 300 M from DG International School |  |  | Distance from Hospital (Km) | : | About 1.6 K form Tieten Medicity - Super Speciality Hospital
Distance from the Main Market (Km) | : | 1. Approx. 1.6 KM from Hypercity Market. 2. Approx. 1.3 KM from D Mart. |  |  | Distance from Railway Station (Km) | : | 12.2 KM from Thane Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Open Plot | Road | Road |  | Open Plot
As per Site / Actual |  |  | : | Open Plot | Open Plot | Building A4 |  | Open Plot
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Building B1 & B2 |  | Sale |  | 2P + St + 1st to 17th + Recreation Floor + 18th to 35th + Recreation Floor |  |  | 2P + St + 1st to 17th + Recreation Floor + 18th to 35th + Recreation Floor
Building B3 |  | Sale |  | UG + 2P + St + 1st to 17th + Recreation Floor + 18th to 35th + Recreation Floor |  |  | UG + 2P + St + 1st to 17th + Recreation Floor + 18th to 35th + Recreation Floor
Building B4, B5 & B6 |  | Sale |  | 2P + St + 1st to 17th + Recreation Floor + 18th to 35th + Recreation Floor |  |  | 2P + St + 1st to 17th + Recreation Floor + 18th to 35th + Recreation Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | S06/0201/14TMC/TD-DP/4079/22 Date: 15/06/2022
CC Details | : | S06/0201/14TMC/TDD/4079/22 Date: 15/06/2022 Valid Up to: Building B1 & B2 = 2P + St + 1st to 17th + Recreation Floor + 18th to 35th + Recreation Floor Building B3 = UG + 2P + St + 1st to 17th + Recreation Floor + 18th to 35th + Recreation Floor Building B4, B5 & B6 = 2P + St + 1st to 17th + Recreation Floor + 18th to 30th Floor |  |  | Approved Plan Details | : | S06/0201/14TMC/TD-DP/4079/22 Date: 15/06/2022
Environmental Clearance Details | : | EC22B039MH118000 Date: 25/08/2022 |  |  | Fire NOC Details | : | TMX/CFO/M/HR/75/50 Date: 03/06/2022
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
Construction Status
Building B1 = 2P + St + 1st to 17th + Recreation Floor + 18th to 35th + Recreation Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 20 Slab, Brickwork upto 17 Floor, Internal Plaster upto 13.6 Floor, External Plaster upto 13.6 Floor Completed
|  |  |  | 0 | 1 |  | 2 | 35 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8.75
Excavation |  | 35 |  | 100% | 42.53% |  | Excavation work Completed. Plinth work completed, RCC upto 20 Slab, Brickwork upto 17 Floor, Internal Plaster upto 13.6 Floor, External Plaster upto 13.6 Floor Completed |  | Excavation in process | 17.5
Plinth |  | 35 |  | 100% |  |  |  |  | Excavation Completed | 35
RCC (Including podiums) |  | 20 |  | 52.63% |  |  |  |  | Footing in Process | 8.75
Brickwork |  | 17 |  | 48.57% |  |  |  |  | Footing Completed | 17.5
Internal Plaster |  | 13.6 |  | 38.86% |  |  |  |  | Basement 1 | 0
External Plaster |  | 13.6 |  | 38.86% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 26.25
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 35 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building B2 = 2P + St + 1st to 17th + Recreation Floor + 18th to 35th + Recreation Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 19 Slab, Brickwork upto 16 Floor, Internal Plaster upto 12.8 Floor, External Plaster upto 12.8 Floor Completed
|  |  |  | 0 | 1 |  | 2 | 35 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8.75
Excavation |  | 35 |  | 100% | 41.61% |  | Excavation work Completed. Plinth work completed, RCC upto 19 Slab, Brickwork upto 16 Floor, Internal Plaster upto 12.8 Floor, External Plaster upto 12.8 Floor Completed |  | Excavation in process | 17.5
Plinth |  | 35 |  | 100% |  |  |  |  | Excavation Completed | 35
RCC (Including podiums) |  | 19 |  | 50% |  |  |  |  | Footing in Process | 8.75
Brickwork |  | 16 |  | 45.71% |  |  |  |  | Footing Completed | 17.5
Internal Plaster |  | 12.8 |  | 36.57% |  |  |  |  | Basement 1 | 0
External Plaster |  | 12.8 |  | 36.57% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 26.25
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 35 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building B3 = UG + 2P + St + 1st to 17th + Recreation Floor + 18th to 35th + Recreation Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 36 Slab, Brickwork upto 33 Floor, Internal Plaster upto 26.4 Floor, External Plaster upto 26.4 Floor Completed
|  |  |  | 1 | 1 |  | 2 | 35 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8.75
Excavation |  | 35 |  | 100% | 57.17% |  | Excavation work Completed. Plinth work completed, RCC upto 36 Slab, Brickwork upto 33 Floor, Internal Plaster upto 26.4 Floor, External Plaster upto 26.4 Floor Completed |  | Excavation in process | 17.5
Plinth |  | 35 |  | 100% |  |  |  |  | Excavation Completed | 35
RCC (Including podiums) |  | 36 |  | 94.74% |  |  |  |  | Footing in Process | 8.75
Brickwork |  | 33 |  | 94.29% |  |  |  |  | Footing Completed | 17.5
Internal Plaster |  | 26.4 |  | 75.43% |  |  |  |  | Basement 1 | 0
External Plaster |  | 26.4 |  | 75.43% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 26.25
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 35 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building B4 = 2P + St + 1st to 17th + Recreation Floor + 18th to 35th + Recreation Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 10 Slab, Brickwork upto 7 Floor, Internal Plaster upto 5.6 Floor, External Plaster upto 5.6 Floor Completed
|  |  |  | 0 | 1 |  | 2 | 35 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8.75
Excavation |  | 35 |  | 100% | 33.38% |  | Excavation work Completed. Plinth work completed, RCC upto 10 Slab, Brickwork upto 7 Floor, Internal Plaster upto 5.6 Floor, External Plaster upto 5.6 Floor Completed |  | Excavation in process | 17.5
Plinth |  | 35 |  | 100% |  |  |  |  | Excavation Completed | 35
RCC (Including podiums) |  | 10 |  | 26.32% |  |  |  |  | Footing in Process | 8.75
Brickwork |  | 7 |  | 20% |  |  |  |  | Footing Completed | 17.5
Internal Plaster |  | 5.6 |  | 16% |  |  |  |  | Basement 1 | 0
External Plaster |  | 5.6 |  | 16% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 26.25
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 35 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building B5 = 2P + St + 1st to 17th + Recreation Floor + 18th to 35th + Recreation Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 6 Floor, Internal Plaster upto 4.8 Floor, External Plaster upto 4.8 Floor Completed
|  |  |  | 0 | 1 |  | 2 | 35 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8.75
Excavation |  | 35 |  | 100% | 32.46% |  | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 6 Floor, Internal Plaster upto 4.8 Floor, External Plaster upto 4.8 Floor Completed |  | Excavation in process | 17.5
Plinth |  | 35 |  | 100% |  |  |  |  | Excavation Completed | 35
RCC (Including podiums) |  | 9 |  | 23.68% |  |  |  |  | Footing in Process | 8.75
Brickwork |  | 6 |  | 17.14% |  |  |  |  | Footing Completed | 17.5
Internal Plaster |  | 4.8 |  | 13.71% |  |  |  |  | Basement 1 | 0
External Plaster |  | 4.8 |  | 13.71% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 26.25
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 35 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building B6 = 2P + St + 1st to 17th + Recreation Floor + 18th to 35th + Recreation Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed
|  |  |  | 0 | 1 |  | 2 | 35 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8.75
Excavation |  | 35 |  | 100% | 26.97% |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed |  | Excavation in process | 17.5
Plinth |  | 35 |  | 100% |  |  |  |  | Excavation Completed | 35 |  | Extra stage given in previous report
RCC (Including podiums) |  | 3 |  | 7.895% |  |  |  |  | Footing in Process | 8.75 |  | 2025-07-05
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 17.5
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 26.25
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 35 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 39.02%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area |  | 14080
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 13200 to 14200 | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA |  | 12200 to 13200 change to 13200 to 14200 for unit addtion
Car Parking Charges |  |  | : | 6,00,000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 1505.0167
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 7617.9859
Distress Value (Rs. Per sqft) | [5 empty] | : | 1204.0134
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Building B1 |  | Sale |  | Flats | 273 |  | 154533.4736 | 233164.2245
Building B2 |  | Sale |  | Flats | 273 |  | 154590.8458 | 233250.2827
Building B3 |  | Sale |  | Flats | 273 |  | 117395.9514 | 176093.9271
Building B4 |  | Sale |  | Flats | 273 |  | 117395.9514 | 176093.9271
Building B5 |  | Sale |  | Flats | 273 |  | 154593.752 | 233254.6421
Building B6 |  | Sale |  | Flats | 273 |  | 154551.5572 | 233191.3498
Total |  |  |  |  | 1638 |  | 853061.5314 | 1285048.3534
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
50%
Building B1
1st & 2nd Podium Floor for Parking
Ground / Stilt Floor for Parking, Fitness Center & Drive Way
1st, 3rd, 7th, 9th, 11th, 13th, 17th, 21st, 23rd, 25th, 27th, 31st, 33rd & 35th Floor
1st, 3rd, 7th, 9th, 11th, 13th, 17th, 21st, 23rd, 25th, 27th, 31st, 33rd & 35th Floor |  | 1 |  | 2BHK | 620.7599 |  | 37.8893 | 969.0291 | 54.3625
|  | 2 |  | 2BHK | 620.7599 |  | 37.8893 | 969.0291
|  | 3 |  | 2BHK | 610.2112 |  | 0 | 915.3167 | 51.6585 | 6.7125
|  | 4 |  | 2BHK | 610.2112 |  | 0 | 915.3167 |  | 628.3054
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 8 |  | 2BHK | 610.2112 |  | 0 | 915.3167
2nd, 4th, 6th, 8th, 12th,14th, 16th, 18th, 20th, 22nd, 26th, 28th, 30th & 32nd Floor
2nd, 4th, 6th, 8th, 12th,14th, 16th, 18th, 20th, 22nd, 26th, 28th, 30th & 32nd Floor |  | 1 |  | 2BHK | 615.4855 |  | 0 | 923.2283 | 14622.6023
|  | 2 |  | 2BHK | 615.4855 |  | 0 | 923.2283
|  | 3 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 4 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 8 |  | 2BHK | 610.2112 |  | 0 | 915.3167
5th, 15th, 19th & 29th Floor (Part Refuge Area)
5th, 15th, 19th & 29th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 620.7599 |  | 37.8893 | 969.0291
|  | 2 |  | 2BHK | 620.7599 |  | 37.8893 | 969.0291
|  | 3 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 4 |  | Refuge Area
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 8 |  | 2BHK | 610.2112 |  | 0 | 915.3167
10th, 24th & 34th Floor (Part Refuge Area)
10th, 24th & 34th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 615.4855 |  | 0 | 923.2283
|  | 2 |  | 2BHK | 615.4855 |  | 0 | 923.2283
|  | 3 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 4 |  | Refuge Area | 675.1988 |  | 0 | 1012.7982
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 8 |  | 2BHK | 610.2112 |  | 0 | 915.3167
Building B2
1st & 2nd Podium Floor for Parking
Ground / Stilt Floor for Parking, Fitness Center & Drive Way
1st, 3rd, 7th, 9th, 11th, 13th, 17th, 21st, 23rd, 25th, 27th, 31st, 33rd & 35th Floor
1st, 3rd, 7th, 9th, 11th, 13th, 17th, 21st, 23rd, 25th, 27th, 31st, 33rd & 35th Floor |  | 1 |  | 2BHK | 622.9127 |  | 37.8893 | 972.2583
|  | 2 |  | 2BHK | 622.9127 |  | 37.8893 | 972.2583
|  | 3 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 4 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | 2BHK | 610.2112 |  | 0 | 915.3167 | 13601.8489
|  | 8 |  | 2BHK | 610.2112 |  | 0 | 915.3167
2nd, 4th, 6th, 8th, 12th,14th, 16th, 18th, 20th, 22nd, 26th, 28th, 30th & 32nd Floor
2nd, 4th, 6th, 8th, 12th,14th, 16th, 18th, 20th, 22nd, 26th, 28th, 30th & 32nd Floor |  | 1 |  | 2BHK | 615.4855 |  | 0 | 923.2283
|  | 2 |  | 2BHK | 615.4855 |  | 0 | 923.2283
|  | 3 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 4 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 8 |  | 2BHK | 610.2112 |  | 0 | 915.3167
5th, 15th, 19th & 29th Floor (Part Refuge Area)
5th, 15th, 19th & 29th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 620.7599 |  | 37.8893 | 969.0291
|  | 2 |  | 2BHK | 620.7599 |  | 37.8893 | 969.0291
|  | 3 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 4 |  | Refuge Area
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 8 |  | 2BHK | 610.2112 |  | 0 | 915.3167
10th, 24th & 34th Floor (Part Refuge Area)
10th, 24th & 34th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 615.4855 |  | 0 | 923.2283
|  | 2 |  | 2BHK | 615.4855 |  | 0 | 923.2283
|  | 3 |  | 2BHK | 609.2424 |  | 0 | 913.8636
|  | 4 |  | Refuge Area | 675.1988 |  | 0 | 1012.7982
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 8 |  | 2BHK | 610.2112 |  | 0 | 915.3167
Building B3
Upper Ground Floor for Parking
1st & 2nd Podium Floor for Parking
Ground / Stilt Floor for Parking & Drive Way
1st to 3rd, 5th to 8th, 10th to 13th, 15th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th & 35th Floor
1st to 3rd, 5th to 8th, 10th to 13th, 15th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th & 35th Floor |  | 1 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 2 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 3 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 4 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 8 |  | 1BHK | 430.0218 |  | 0 | 645.0327
7th, 9th, 14th, 18th, 23rd, 28th & 33rd Floor (Part Refuge Area)
7th, 9th, 14th, 18th, 23rd, 28th & 33rd Floor (Part Refuge Area) |  | 1 |  | 1BHK | 430.0218 |  | 0 | 645.0327 |  | 14650.42
|  | 2 |  | 1BHK | 430.0218 |  | 0 | 645.0327 |  | 12790.0492
|  | 3 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 4 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | Refuge Area
|  | 8 |  | 1BHK | 430.0218 |  | 0 | 645.0327
Building B4
1st & 2nd Podium Floor for Parking
Ground / Stilt Floor for Parking, Fitness Center & Drive Way
1st to 4th, 6th to 9th, 11th to 14th, 16th, 17th, 18th, 20th to 23rd, 25th to 28th, 30th to 33rd & 35th Floor
1st to 4th, 6th to 9th, 11th to 14th, 16th, 17th, 18th, 20th to 23rd, 25th to 28th, 30th to 33rd & 35th Floor |  | 1 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 2 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 3 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 4 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | 1BHK | 430.0218 |  | 0 | 645.0327 | 19301.347
|  | 8 |  | 1BHK | 430.0218 |  | 0 | 645.0327
5th, 10th, 15th, 19th, 24th, 29th & 34th Floor (Part Refuge Area)
5th, 10th, 15th, 19th, 24th, 29th & 34th Floor (Part Refuge Area) |  | 1 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 2 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 3 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 4 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | Refuge Area
|  | 8 |  | 1BHK | 430.0218 |  | 0 | 645.0327
Building B5
1st & 2nd Podium Floor for Parking
Ground / Stilt Floor for Parking, Fitness Center & Drive Way
1st, 3rd, 7th, 9th, 11th, 13th, 17th, 21st, 23rd, 25th, 27th, 31st, 33rd & 35th Floor
1st, 3rd, 7th, 9th, 11th, 13th, 17th, 21st, 23rd, 25th, 27th, 31st, 33rd & 35th Floor |  | 1 |  | 2BHK | 622.9127 |  | 37.8893 | 972.2583
|  | 2 |  | 2BHK | 622.9127 |  | 37.8893 | 972.2583
|  | 3 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 4 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | 2BHK | 610.2112 |  | 0 | 915.3167 | 13601.8489
|  | 8 |  | 2BHK | 610.2112 |  | 0 | 915.3167
2nd, 4th, 6th, 8th, 12th, 14th, 16th, 18th, 20th, 22nd, 26th, 28th, 30th & 32nd Floor
2nd, 4th, 6th, 8th, 12th, 14th, 16th, 18th, 20th, 22nd, 26th, 28th, 30th & 32nd Floor |  | 1 |  | 2BHK | 615.4855 |  | 0 | 923.2283
|  | 2 |  | 2BHK | 615.4855 |  | 0 | 923.2283
|  | 3 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 4 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 8 |  | 2BHK | 610.2112 |  | 0 | 915.3167
5th, 15th, 19th & 29th Floor (Part Refuge Area)
5th, 15th, 19th & 29th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 620.7599 |  | 37.8893 | 969.0291
|  | 2 |  | 2BHK | 620.7599 |  | 37.8893 | 969.0291
|  | 3 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 4 |  | Refuge Area
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 8 |  | 2BHK | 610.2112 |  | 0 | 915.3167
10th, 24th & 34th Floor (Part Refuge Area)
10th, 24th & 34th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 615.4855 |  | 0 | 923.2283
|  | 2 |  | 2BHK | 615.4855 |  | 0 | 923.2283
|  | 3 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 4 |  | Refuge Area | 675.1988 |  | 0 | 1012.7982
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 8 |  | 2BHK | 610.2112 |  | 0 | 915.3167
Building B6
1st & 2nd Podium Floor for Parking
Ground / Stilt Floor for Parking, Fitness Center & Drive Way
1st, 3rd, 7th, 9th, 11th, 13th, 17th, 21st, 23rd, 25th, 27th, 31st, 33rd & 35th Floor
1st, 3rd, 7th, 9th, 11th, 13th, 17th, 21st, 23rd, 25th, 27th, 31st, 33rd & 35th Floor |  | 1 |  | 2BHK | 622.9127 |  | 37.8893 | 972.2583
|  | 2 |  | 2BHK | 622.9127 |  | 37.8893 | 972.2583
|  | 3 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 4 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | 2BHK | 610.2112 |  | 0 | 915.3167 | 13601.8489
|  | 8 |  | 2BHK | 610.2112 |  | 0 | 915.3167
2nd, 4th, 6th, 8th, 12th, 14th, 16th, 18th, 20th, 22nd, 26th, 28th, 30th & 32nd Floor
2nd, 4th, 6th, 8th, 12th, 14th, 16th, 18th, 20th, 22nd, 26th, 28th, 30th & 32nd Floor |  | 1 |  | 2BHK | 615.4855 |  | 0 | 923.2283
|  | 2 |  | 2BHK | 615.4855 |  | 0 | 923.2283
|  | 3 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 4 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 8 |  | 2BHK | 610.2112 |  | 0 | 915.3167
5th, 15th, 19th & 29th Floor (Part Refuge Area)
5th, 15th, 19th & 29th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 615.4855 |  | 37.8893 | 961.1176
|  | 2 |  | 2BHK | 615.4855 |  | 37.8893 | 961.1176
|  | 3 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 4 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | Refuge Area |  |  |  |  | 13601.8489
|  | 8 |  | 2BHK | 610.2112 |  | 0 | 915.3167
10th, 24th & 34th Floor (Part Refuge Area)
10th, 24th & 34th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 615.4855 |  | 0 | 923.2283
|  | 2 |  | 2BHK | 615.4855 |  | 0 | 923.2283
|  | 3 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 4 |  | 2BHK | 610.2112 |  | 0 | 915.3167
|  | 5 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 6 |  | 1BHK | 430.0218 |  | 0 | 645.0327
|  | 7 |  | Refuge Area
|  | 8 |  | 2BHK | 610.2112 |  | 0 | 915.3167
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Building B1 to B5 = Construction work is in process at the time of Visit. Internal visit was not allowed. Building B6 = Construction work is in process at the time of Visit. (Slow Speed) 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + C.B Area + A.P Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We have updated revised approved floor plan & C.C for Building B4 to B6 (on 27/07/2023).
Site & Building/Tower Photographs
Name of the Project |  |  | : | Raunak Bliss (B1 To B6)
Project Site Address |  |  | : | Raunak Bliss B1 to B6, Road.Hawre City , Village.Owala, Near by Landmark.Purushottam Nayan , City.Thane West, District. Thane, Taluka.Thane, Pin Code - 400615.
Site Visit Date & Time |  |  | : | 04/07/2025 @ 12:13 PM
Layout Plan
B5
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr.Ajay | Authorized Signatory Name & Signature | :
B1
B2
B3
B6
B5
B4
B3
B2
B1
B3
B1
B2
B6
B5
B4
Note on H6: Rushil Sanghvi or Fahad
Note on E9: Initiation Address
Note on E10: Plan Address
Note on E11: Map Address
Note on H17: From Rera
Note on H20: From RERA
Note on H160: Ready Recknor