## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  |  | : | Rejuve 360 ­ Tower A |  | Date & Time of Site Visit |  | 04/07/2025 at 02:36PM
Name of the person met at site & Contact No. |  |  | : | Ms Vidhi Sharma (project manager) -8225936113 |  | Date of Report Release |  | 07/07/2025
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | L&T Asian Realty Project LLP | Developer Name | : | L&T Asian Realty Project LLP
Developer Office Address |  |  | : | Building Name - L&T House, N. M. Marg, Locality Ballard Estate, Fort, Maharashtra Mumbai City - 400001
Project Address | : | As per ARF | : | Rejuve 360 ­ Tower A, CTS No.710A, 712A, 763A, 762A, 706-B/A, 706-B/B, 706-B/C, 706-B/D, 706-B/E, 706-B/F, 706-B/G, 706-B/H & 706-B/J, Lalbahadur Shastri Road, Village - Nahur, Taluka - Kurla, District: Mumbai - 400080.
| : | As per Legal Documents | : | Rejuve 360 ­ Tower A, CTS No.710A, 712A, 763A, 762A, 706-B/A, 706-B/B, 706-B/C, 706-B/D, 706-B/E, 706-B/F, 706-B/G, 706-B/H & 706-B/J, Village - Nahur, Taluka - Kurla, District : Mumbai - 400080.
| : | As per Actual at site | : | Rejuve 360 ­ Tower A, Near - Marathon Millennium, Lalbahadur Shastri Road, Village - Nahur, Taluka - Kurla, District: Mumbai - 400080.
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Municipal Corporation Of Greater Mumbai (MCGM)
RERA Registration No. | : | P51800023075 |  |  | RERA Registration Validity | : | 2026-12-30
Project Launch Date | : | 2018-08-07 |  |  | Construction Start Date | : | 25/11/2019
Proposed Date of Completion (As per RERA) | : | 2026-12-30 |  |  | Developer Bank Name (As per RERA) |  | HDFC BANK LIMITED IFSC Code - HDFC0000239
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 55602.12
FSI/FAR Permissible | : | 1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 107570.36
Permissible Built up Area (In Sq.Mt) | : | 127464.15 |  |  | Total Number of Units Planned | : | Flats = 538 |  |  |  | 538
Total Number of Units Approved | : | Flats = 538 |  |  | If Mixed, No. of Commercial Units | : | NA
Latitude | : | 19.166842, |  |  | Longitude | : | 72.9406
Location Link | : | https://goo.gl/maps/734ApsgJhp1cNDu59
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developed |  |  | Class of Locality | : | Upper
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 500M from Duncan Company Bus Stop
Distance from the nearest School (Km) | : | About 1.2KM from Holy Angels Marthoma School |  |  | Distance from Hospital (Km) | : | About 1.3K form Fortis Hospital
Distance from the Main Market (Km) | : | 1. Approx. 950 M from Dmart. 2. Approx. 2.9KM from Mulund Market. |  |  | Distance from Railway Station (Km) | : | 2.4KM from Nahur Railway Station 3KM from Mulund Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Road | Tower 2 | Open Plot |  | Wing A1
As per Site / Actual |  |  | : | Road | Tower 2 | Open Plot |  | Building
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Tower 1 (A Wing) |  | Sale |  | 2B + G + 7Podium + 3 Stilt + 1st To 57th Floor |  |  | 2B + G + 7Podium + 3 Stilt + 1st To 57th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | CE/4813/BPES/AT Date: 27/06/2023
CC Details | : | CE/4813/BPES/AT/FCC/3/Amend Date: 05/06/2024 Date Valid Up to: 02.01.2026 Valid Up To: Further C.C. is granted for wing ‘A’ comprising of 2 level basements + stilt + 1st to 7th podium + 1st to 3rd upper stilt and 1st to 57th upper floors as per amended approved plan dated 27.06.2023 subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution. |  |  | Approved Plan Details | : | CE/4813/BPES/AT Date: 27/06/2023
Environmental Clearance Details | : |  |  |  | Airport Authority Clearance Details | :
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
Construction Status
Tower 1 (A Wing) = 2B + G + 7Podium + 3 Stilt + 1st To 57th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 51 Floor, External Plaster upto 51 Floor, External Plumbing, Elevation and Waterproofing upto 43 Floor, Flooring & Fitting upto 22 Floor, Wooden Work upto 14 Floor Completed
|  |  |  | 2 | 4 |  | 7 | 57 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 14.25
Excavation |  | 57 |  | 100% | 67.72% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 51 Floor, External Plaster upto 51 Floor, External Plumbing, Elevation and Waterproofing upto 43 Floor, Flooring & Fitting upto 22 Floor, Wooden Work upto 14 Floor Completed |  | Excavation in process | 28.5
Plinth |  | 57 |  | 100% |  |  |  |  | Excavation Completed | 57
RCC (Including podiums) |  | 68 |  | 100% |  |  |  |  | Footing in Process | 14.25
Brickwork |  | 57 |  | 100% |  |  |  |  | Footing Completed | 28.5
Internal Plaster |  | 51 |  | 89.47% |  |  |  |  | Basement 1 | 42.75
External Plaster |  | 51 |  | 89.47% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 43 |  | 75.44% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 22 |  | 38.6% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 14 |  | 24.56% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 57 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 25000 to 26000
Car Parking Charges |  |  | : | 800000 | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 5968.0416
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 12326.2728
Distress Value (Rs. Per sqft) | [5 empty] | : | 4774.4333
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Tower A |  | Sale |  | Flats | 538 |  | 451046.0448 | 721673.6717
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
60%
Building No. 3 (Wing A)
1st & 2nd Basement Floor is For Parking
Ground Floor is For Parking
1st To 3rd Podium Floor is For Parking
4th Podium Floor is For Parking & Residential
4th Podium Floor is For Parking & Residential |  | 1 |  | 3BHK | 1047.1219 |  | 0 | 1675.3951
|  | 2 |  | 2BHK | 749.3897 |  | 0 | 1199.0235
|  | 3 |  | 2BHK | 749.3897 |  | 0 | 1199.0235
|  | 4 |  | 3BHK | 975.7566 |  | 0 | 1561.2106
|  | 5 |  | Parking Area
|  | 6 |  | 2.5BHK | 931.9471 |  | 0 | 1491.1154
|  | 7 |  | 2BHK | 611.7181 |  | 0 | 978.749
5th Podium Floor is For Parking & Residential
5th Podium Floor is For Parking & Residential |  | 1 |  | 3BHK | 1047.1219 |  | 0 | 1675.3951
|  | 2 |  | 2BHK | 749.3897 |  | 0 | 1199.0235
|  | 3 |  | 2BHK | 749.3897 |  | 0 | 1199.0235
|  | 4 |  | 3BHK | 975.7566 |  | 0 | 1561.2106
|  | 5 |  | Parking Area
|  | 6 |  | 2.5BHK | 931.9471 |  | 0 | 1491.1154
|  | 7 |  | 2BHK | 611.7181 |  | 0 | 978.749 |  | 26155.8379
6th Podium Floor is For Parking & Residential
6th Podium Floor is For Parking & Residential |  | 1 |  | 3BHK | 1047.1219 |  | 0 | 1675.3951
|  | 2 |  | 2BHK | 749.3897 |  | 0 | 1199.0235
|  | 3 |  | 2BHK | 749.3897 |  | 0 | 1199.0235
|  | 4 |  | 3BHK | 975.7566 |  | 0 | 1561.2106
|  | 5 |  | Parking Area
|  | 6 |  | 2.5BHK | 931.9471 |  | 0 | 1491.1154
|  | 7 |  | 2BHK | 611.7181 |  | 0 | 978.749
7th Podium Floor is For Parking & Residential (Part Refuge Area)
7th Podium Floor is For Parking & Residential (Part Refuge Area) |  | 1 |  | 3BHK | 1047.1219 |  | 0 | 1675.3951
|  | 2 |  | Refuge Area
3
|  | 4 |  | 3BHK | 975.7566 |  | 0 | 1561.2106
|  | 5 |  | Parking Area
|  | 6 |  | 2.5BHK | 931.9471 |  | 0 | 1491.1154
|  | 7 |  | 2BHK | 611.7181 |  | 0 | 978.749
1st Stilt Floor
1st Stilt Floor |  | 1 |  | 3BHK | 1047.1219 |  | 0 | 1675.3951
|  | 2 |  | 2BHK | 749.3897 |  | 0 | 1199.0235
|  | 3 |  | 2BHK | 749.3897 |  | 0 | 1199.0235
|  | 4 |  | 3BHK | 975.7566 |  | 0 | 1561.2106
|  | 5 |  | Amenities Area
|  | 6 |  | 2.5BHK | 931.9471 |  | 0 | 1491.1154
|  | 7 |  | 2BHK | 611.7181 |  | 0 | 978.749
2nd Stilt Floor
2nd Stilt Floor |  | 1 |  | 3BHK | 1047.1219 |  | 0 | 1675.3951
|  | 2 |  | 2BHK | 749.3897 |  | 0 | 1199.0235
|  | 3 |  | 2BHK | 749.3897 |  | 0 | 1199.0235
|  | 4 |  | 3BHK | 975.7566 |  | 0 | 1561.2106
|  | 5 |  | Amenities Area
6
7
|  | 8 |  | 2.5BHK | 931.9471 |  | 0 | 1491.1154
|  | 9 |  | 2BHK | 611.7181 |  | 0 | 978.749
3rd Stilt Floor
3rd Stilt Floor |  | 1 |  | 3BHK | 1047.1219 |  | 0 | 1675.3951
|  | 2 |  | 2BHK | 749.3897 |  | 0 | 1199.0235
|  | 3 |  | 2BHK | 749.3897 |  | 0 | 1199.0235
|  | 4 |  | 3BHK | 975.7566 |  | 0 | 1561.2106
|  | 5 |  | 3BHK | 875.0056 |  | 0 | 1400.0089
|  | 6 |  | Terrace for Club House
7
|  | 8 |  | 2.5BHK | 931.9471 |  | 0 | 1491.1154
|  | 9 |  | 2BHK | 611.7181 |  | 0 | 978.749
1st to 3rd, 5th to 10th & 19th to 24th Floor
1st to 3rd, 5th to 10th & 19th to 24th Floor |  | 1 |  | 3BHK | 1047.1219 |  | 0 | 1675.3951 |  |  |  |  | 101,..,2401 | 101 | 2401
|  | 2 |  | 2BHK | 750.3584 |  | 0 | 1200.5735 |  |  |  |  | 102,..,2402 | 102 | 2402
|  | 3 |  | 2BHK | 750.3584 |  | 0 | 1200.5735 |  |  |  |  | 103,..,2403 | 103 | 2403
|  | 4 |  | 3BHK | 976.4024 |  | 0 | 1562.2439 |  |  |  |  | 104,..,2404 | 104 | 2404
|  | 5 |  | 2.5BHK | 875.0056 |  | 0 | 1400.0089 |  |  |  |  | 105,..,2405 | 105 | 2405
|  | 6 |  | 2BHK | 611.9334 |  | 0 | 979.0934 |  |  |  |  | 106,..,2406 | 106 | 2406
|  | 7 |  | 2BHK | 611.9334 |  | 0 | 979.0934 |  |  |  |  | 107,..,2407 | 107 | 2407
|  | 8 |  | 3.5BHK | 1261.7561 |  | 0 | 2018.8097 |  |  |  |  | 108,..,2408 | 108 | 2408
|  | 9 |  | 2BHK | 611.7181 |  | 0 | 978.749 |  |  |  |  | 109,..,2409 | 109 | 2409
4th, 11th, 18th, 25th & 32nd Floor (Part Refuge Area)
4th, 11th, 18th, 25th & 32nd Floor (Part Refuge Area) |  | 1 |  | 3BHK | 1047.1219 |  | 0 | 1675.3951 |  |  |  |  | 4101,..,3201 | 4101 | 3201
|  | 2 |  | Refuge Area |  |  |  | 0 |  |  |  |  | 4102,..,3202 | 4102 | 3202
|  | 3 |  | 2BHK |  |  |  | 0 |  |  |  |  | 4103,..,3203 | 4103 | 3203
|  | 4 |  | 3BHK | 976.4024 |  | 0 | 1562.2439 |  |  |  |  | 4104,..,3204 | 4104 | 3204
|  | 5 |  | 2.5BHK | 875.0056 |  | 0 | 1400.0089 |  |  |  |  | 4105,..,3205 | 4105 | 3205
|  | 6 |  | 2BHK | 611.9334 |  | 0 | 979.0934 |  |  |  |  | 4106,..,3206 | 4106 | 3206
|  | 7 |  | 2BHK | 611.9334 |  | 0 | 979.0934 |  |  |  |  | 4107,..,3207 | 4107 | 3207
|  | 8 |  | 3.5BHK | 1261.7561 |  | 0 | 2018.8097 |  |  |  |  | 4108,..,3208 | 4108 | 3208
|  | 9 |  | 2BHK | 611.7181 |  | 0 | 978.749 |  |  |  |  | 4109,..,3209 | 4109 | 3209
12th to 17th & 26th to 31st Floor
12th to 17th & 26th to 31st Floor |  | 1 |  | 3BHK | 1047.1219 |  | 0 | 1675.3951 |  |  |  |  | 1201,..,3101 | 1201 | 3101
|  | 2 |  | 2BHK | 756.8168 |  | 0 | 1210.9069 |  |  |  |  | 1202,..,3102 | 1202 | 3102
|  | 3 |  | 2BHK | 756.8168 |  | 0 | 1210.9069 |  |  |  |  | 1203,..,3103 | 1203 | 3103
|  | 4 |  | 3BHK | 976.4024 |  | 0 | 1562.2439 |  |  |  |  | 1204,..,3104 | 1204 | 3104
|  | 5 |  | 2.5BHK | 875.0056 |  | 0 | 1400.0089 |  |  |  |  | 1205,..,3105 | 1205 | 3105
|  | 6 |  | 2BHK | 611.9334 |  | 0 | 979.0934 |  |  |  |  | 1206,..,3106 | 1206 | 3106
|  | 7 |  | 2BHK | 611.9334 |  | 0 | 979.0934 |  |  |  |  | 1207,..,3107 | 1207 | 3107
|  | 8 |  | 3.5BHK | 1261.7561 |  | 0 | 2018.8097 |  |  |  |  | 1208,..,3108 | 1208 | 3108
|  | 9 |  | 2BHK | 611.7181 |  | 0 | 978.749 |  |  |  |  | 1209,..,3109 | 1209 | 3109
33rd to 38th, 47th to 52nd & 54th to 57th Floor
33rd to 38th, 47th to 52nd & 54th to 57th Floor |  | 1 |  | 3BHK | 1056.379 |  | 0 | 1690.2063 |  |  |  |  | 3301,..,5701 | 3301 | 5701
|  | 2 |  | 2BHK | 754.1258 |  | 0 | 1206.6013 |  |  |  |  | 3302,..,5702 | 3302 | 5702
|  | 3 |  | 2BHK | 754.1258 |  | 0 | 1206.6013 |  |  |  |  | 3303,..,5703 | 3303 | 5703
|  | 4 |  | 3BHK | 971.5586 |  | 0 | 1554.4938 |  |  |  |  | 3304,..,5704 | 3304 | 5704
|  | 5 |  | 2.5BHK | 882.648 |  | 0 | 1412.2368 |  |  |  |  | 3305,..,5705 | 3305 | 5705
|  | 6 |  | 2BHK | 612.2563 |  | 0 | 979.6101 |  |  |  |  | 3306,..,5706 | 3306 | 5706
|  | 7 |  | 2BHK | 612.2563 |  | 0 | 979.6101 |  |  |  |  | 3307,..,5707 | 3307 | 5707
|  | 8 |  | 3.5BHK | 1272.7354 |  | 0 | 2036.3766 |  |  |  |  | 3308,..,5708 | 3308 | 5708
|  | 9 |  | 2BHK | 611.7181 |  | 0 | 978.749 |  |  |  |  | 3309,..,5709 | 3309 | 5709
40th to 45th Floor
40th to 45th Floor |  | 1 |  | 3BHK | 1056.379 |  | 0 | 1690.2063 |  |  |  |  | 401,..,4501 | 401 | 4501
|  | 2 |  | 2BHK | 754.1258 |  | 0 | 1206.6013 |  |  |  |  | 402,..,4502 | 402 | 4502
|  | 3 |  | 2BHK | 754.1258 |  | 0 | 1206.6013 |  |  |  |  | 403,..,4503 | 403 | 4503
|  | 4 |  | 3BHK | 971.5586 |  | 0 | 1554.4938 |  |  |  |  | 404,..,4504 | 404 | 4504
|  | 5 |  | 2.5BHK | 882.648 |  | 0 | 1412.2368 |  |  |  |  | 405,..,4505 | 405 | 4505
|  | 6 |  | 2BHK | 612.2563 |  | 0 | 979.6101 |  |  |  |  | 406,..,4506 | 406 | 4506
|  | 7 |  | 2BHK | 612.2563 |  | 0 | 979.6101 |  |  |  |  | 407,..,4507 | 407 | 4507
|  | 8 |  | 3.5BHK | 1272.7354 |  | 0 | 2036.3766 |  |  |  |  | 408,..,4508 | 408 | 4508
|  | 9 |  | 2BHK | 611.7181 |  | 0 | 978.749 |  |  |  |  | 409,..,4509 | 409 | 4509
39th & 46th Floor (Part Refuge Area)
39th & 46th Floor (Part Refuge Area) |  | 1 |  | 3BHK | 1056.379 |  | 0 | 1690.2063 |  |  |  |  | 301,..,4601 | 301 | 4601
|  | 2 |  | Refuge Area |  |  |  | 0 |  |  |  |  | 302,..,4602 | 302 | 4602
|  | 3 |  | 2BHK |  |  |  | 0 |  |  |  |  | 303,..,4603 | 303 | 4603
|  | 4 |  | 3BHK | 971.5586 |  | 0 | 1554.4938 |  |  |  |  | 304,..,4604 | 304 | 4604
|  | 5 |  | 2.5BHK | 882.648 |  | 0 | 1412.2368 |  |  |  |  | 305,..,4605 | 305 | 4605
|  | 6 |  | 2BHK | 612.2563 |  | 0 | 979.6101 |  |  |  |  | 306,..,4606 | 306 | 4606
|  | 7 |  | 2BHK | 612.2563 |  | 0 | 979.6101 |  |  |  |  | 307,..,4607 | 307 | 4607
|  | 8 |  | 3.5BHK | 1272.7354 |  | 0 | 2036.3766 |  |  |  |  | 308,..,4608 | 308 | 4608
|  | 9 |  | 2BHK | 611.7181 |  | 0 | 978.749 |  |  |  |  | 309,..,4609 | 309 | 4609
53rd Floor (Part Refuge Area)
53rd Floor (Part Refuge Area) |  | 1 |  | 3BHK | 1056.379 |  | 0 | 1690.2063 |  |  |  |  | 501,..,5301 | 501 | 5301
|  | 2 |  | Refuge Area |  |  |  | 0 |  |  |  |  | 502,..,5302 | 502 | 5302
|  | 3 |  | 2BHK |  |  |  | 0 |  |  |  |  | 503,..,5303 | 503 | 5303
|  | 4 |  | 3BHK | 971.5586 |  | 0 | 1554.4938 |  |  |  |  | 504,..,5304 | 504 | 5304
|  | 5 |  | 2.5BHK | 882.648 |  | 0 | 1412.2368 |  |  |  |  | 505,..,5305 | 505 | 5305
|  | 6 |  | 2BHK | 612.2563 |  | 0 | 979.6101 |  |  |  |  | 506,..,5306 | 506 | 5306
|  | 7 |  | 2BHK | 612.2563 |  | 0 | 979.6101 |  |  |  |  | 507,..,5307 | 507 | 5307
|  | 8 |  | 3.5BHK | 1272.7354 |  | 0 | 2036.3766 |  |  |  |  | 508,..,5308 | 508 | 5308
|  | 9 |  | 2BHK | 611.7181 |  | 0 | 978.749 |  |  |  |  | 509,..,5309 | 509 | 5309
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Construction work is in process at the time of Visit. Internal Visit was not allowed. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area. 7. Validity of CC is expired on 02/01/2025. Please provide revised CC.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Rejuve 360 ­ Tower A
Project Site Address |  |  | : | Rejuve 360 ­ Tower A, CTS No.710A, 712A, 763A, 762A, 706-B/A, 706-B/B, 706-B/C, 706-B/D, 706-B/E, 706-B/F, 706-B/G, 706-B/H & 706-B/J, Lalbahadur Shastri Road, Village - Nahur, Taluka - Kurla, District: Mumbai - 400080.
Site Visit Date & Time |  |  | : | 04/07/2025 at 02:36PM
Layout Plan:
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Nainesh Tambe | Authorized Signatory Name & Signature | :
Tower A
Tower A