## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  |  | : | Raunak Centrum |  | Date & Time of Site Visit |  | 04/07/2025 at 03:46 PM
Name of the person met at site & Contact No. |  |  | : | Mr.Sunil (Sales) 9769963390 |  | Date of Report Release |  | 04/07/2025
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | Raunak Jigna Associates | Developer Name | : | Raunak Group
Developer Office Address |  |  | : | Raunak Group 1st Floor Plot Number 1 Mohan Mill Compound, Ghodbunder Rd, above Ford Showroom, Thane West, Thane, Maharashtra 400607
Project Address | : | As per ARF | : | Raunak Centrum 12, Rahul Nagar, Everard Nagar, Chembur, Mumbai, Maharashtra 400024
| : | As per Legal Documents | : | Raunak Centrum, CTS No. 126(PT), Near Vasantdada Patil Pratishthan's College of Engineering, Eastern Express Highway, Chembur, Chunabhatti East, Kurla, Mumbai 400022
| : | As per Actual at site | : | Raunak Centrum, CTS No. 126(PT), Near Vasantdada Patil Pratishthan's College of Engineering, Eastern Express Highway, Chembur, Chunabhatti East, Kurla, Mumbai 400022
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate, EC.
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Slum Rehabilitation Authority (SRA)
RERA Registration No. | : | Raunak Centrum = P51800006705 Raunak Centrum A = P51800033269 |  |  | RERA Registration Validity | : | Raunak Centrum = 30/12/2027 Raunak Centrum A = 31/12/2028
Project Launch Date | : | Raunak Centrum = 16/08/2017 Raunak Centrum A = 10/02/2022 |  |  | Construction Start Date | : | Raunak Centrum = 16/08/2017 Raunak Centrum A = 10/02/2022
Proposed Date of Completion (As per RERA) | : | Raunak Centrum = 30/12/2027 Raunak Centrum A = 31/12/2028 |  |  | Developer Bank Name (As per RERA) | : | ICICI BANK LIMITED IFSC Code = ICIC0000035
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  |  | Plot Area (In Sq.Mt) | : | 12420.2
Net Plot Area (In Sq.Mt) | : | 11396.87 |  |  | Proposed Built up Area (In Sq.Mt) | : | 54194.86
FSI/FAR Permissible | : | 4.36 |  |  | Proposed Built up Area For Sale (In Sq.Mt) | : | 29953.93
Permissible Built up Area (In Sq.Mt) | : | 49690.3532 |  |  | Total Number of Units Planned | : | As per RERA Site Flats = 547 & Office = 16 |  |  |  | Raunak Centrum | Raunak Centrum A
Total Number of Units Approved | : | Flats = 548 |  |  | If Mixed, No. of Commercial Units | : | Shop = 07, Office = 18 |  |  | Flats | 209 | 338 | 547
Latitude, Longitude | : | 19.051386,72.878980 |  |  | Landmark | : | Vasantdada Patil Pratishthan's College of Engineering |  |  | Office | 4 | 12 | 16
Location Link | : | https://maps.app.goo.gl/y4Hp7SWLQfAUt7h29
Extra Amenities available | : | Pleasant Open Spaces, Central Landscape, Jogging Track, Garden, Outdoor Kids Play Area, Life-Size Game Plaza, Aerial Seating Area, High-End Gym, Steam & Sauna, Aerobics And Zumba Studio, Dance And Music Studio, Creche, Mini Theatre, Banquet, Rooftop Sky-Lounge, Star Gazing Deck, Open-Air Theatre
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9M
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 350M from Everard Colony Bus Stop
Distance from the nearest School (Km) | : | About 1KM from ORCHIDS The International School |  |  | Distance from Hospital (Km) | : | About 1KM form K.J. Somaiya Hospital
Distance from the Main Market (Km) | : | 1. Approx. 2.90KM from East Point Mall. 2. Approx. 3KM from East Point Mall |  |  | Distance from Railway Station (Km) | : | 2.20KM from Chunnabhatti Railway Station 2.60KM from Kurla Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Eastern Express Highway | Other Plot | Other Plot |  | Other Plot
As per Site / Actual |  |  | : | Eastern Express Highway | Slum | Open Plot |  | Vasantdada Patil Pratishthan's College
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Wing D |  | Sale |  | 3B + G + 1st to 30th Floor |  |  | 3B + G + 1st to 29th Floor
Wing E |  | Sale |  | 3B + G + 1st to 30th Floor |  |  | 3B + G + 1st to 30th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | SRA/ENG/2655/L/STGL/AP Date: 22/12/2023
CC Details | : | SRA/ENG/2655/L/STGL/AP Date: 22/12/2023 Valid Up to: This C.C. is re-endorsed for composite building (3 level basement, Rehab wing A, B & C from Ground to 21st (pt) upper floor, Sale wing 'D' from Ground to 29th upper floor, plinth C.C. for sale wing 'E') as per approved amended plan dated 22/12/2023. |  |  | Approved Plan Details | : | SRA/ENG/2655/L/STGL/AP Date: 22/12/2023
Environmental Clearance Details | : | SIA/MH/MIS/266431/2022 Date: 10/08/2022 Valid For : Plot Area = 12420.20 Sqm Proposed BUA = 124603.76 Sqm |  |  | Airport Authority Clearance Details | : | Date:
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
Construction Status
Wing D = 3B + G + 1st to 30th Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 14 Floor, Flooring & Fitting upto 12 Floor, Wooden Work upto 14 Floor Completed
|  |  |  | 3 | 1 |  | 0 | 30 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 7.5
Excavation |  | 30 |  | 100% | 67.5% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 14 Floor, Flooring & Fitting upto 12 Floor, Wooden Work upto 14 Floor Completed |  | Excavation in process | 15
Plinth |  | 30 |  | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 31 |  | 100% |  |  |  |  | Footing in Process | 6
Brickwork |  | 30 |  | 100% |  |  |  |  | Footing Completed | 12
Internal Plaster |  | 30 |  | 100% |  |  |  |  | Basement 1 | 18
External Plaster |  | 30 |  | 100% |  |  |  |  | Basement 2 | 24
External Plumbing, Elevation and Waterproofing |  | 14 |  | 46.67% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 12 |  | 40% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 14 |  | 46.67% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 30
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Wing E = 3B + G + 1st to 30th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 5 Slab Completed
|  |  |  | 3 | 1 |  | 0 | 30 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 7.5
Excavation |  | 30 |  | 100% | 29.03% |  | Excavation work Completed. Plinth work completed, RCC upto 5 Slab Completed |  | Excavation in process | 15
Plinth |  | 30 |  | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 5 |  | 16.13% |  |  |  |  | Footing in Process | 6
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 12
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 18
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 24
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 30
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Part II Wing E = 3B + G + 1st to 30th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed
|  |  |  | 3 | 1 |  | 0 | 30 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 7.5
Excavation |  | 30 |  | 100% | 22.58% |  | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed |  | Excavation in process | 15
Plinth |  | 30 |  | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 2 |  | 6.452% |  |  |  |  | Footing in Process | 6
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 12
Door & Window Frames |  | 0 |  | 0% |  |  |  |  | Basement 1 | 18
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 24
Ext.Plaster |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Plumb.& Electri. |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Painting |  | 0 |  | 0% |  |  |  |  | Plinth completed | 30
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Average of Part I & Part II Wing E |  |  |  | Progress % |  |  | 25.81% |  | Excavation in process | 0
Project Completion % | [6 empty] | 48.27%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 28000 to 29000 | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  |  | : | 900000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 4495.5407
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 12048.495
Distress Value (Rs. Per sqft) | [5 empty] | : | 3596.4326
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Gross Carpet Area
Wing D |  | Sale |  | Shops | 2 |  | 7532.9701
Wing D |  | Sale |  | Flats | 210 |  | 110862.311
Wing E |  | Sale |  | Flats | 338 |  | 230803.195
Total |  | 0 |  | 0 | 548 |  | 341665.506 | 0
Details of Flats in Building
Flat/Shop No. |  | Description |  | Carpet area | Deck Area |  | Attached Terrace area | Gross Carpet area
Sale Wing D (As per Approved Plan) = Sale Wing B (As per Builder letter & Index II)
1st to 3rd Basement Floor For Parking
Ground Floor Commercial, Entrance Lobby, Substation, Meter Room, Fire Control Room.
1 |  | Shop (Duplex With 1st Floor) |  | 3483.338 | 0 |  | 0 | 3483.338 | 105.7172 | 203.0955
2 |  | Shop (Duplex With 1st Floor) |  | 4049.6321 | 0 |  | 0 | 4049.6321
1st Floor (Shop Duplex With Ground Floor) | [8 empty] | 1
2nd Floor for Amenities | [8 empty] | 1
3rd Floor For Residential | [8 empty] | 1
1 |  | 1BHK |  | 371.2504 | 0 |  | 0 | 371.2504 |  | 10.764 | 10.764
2 |  | 2BHK |  | 567.5857 | 0 |  | 0 | 567.5857
3 |  | 2BHK |  | 586.8533 | 62.0814 |  | 0 | 648.9347
4 |  | 2BHK |  | 586.8533 | 62.0814 |  | 0 | 648.9347
5 |  | 2BHK |  | 586.8533 | 62.0814 |  | 0 | 648.9347
6 |  | 2BHK |  | 586.8533 | 62.0814 |  | 0 | 648.9347
7 |  | 2BHK |  | 567.5857 | 0 |  | 0 | 567.5857
8 |  | 1BHK |  | 371.2504 | 0 |  | 0 | 371.2504
4th to 6th, 8th to 13th, 15th to 20th, 22nd to 29th Floor | [8 empty] | 23
1 |  | 1BHK |  | 371.2504 | 0 |  | 0 | 371.2504
2 |  | 2BHK |  | 567.5857 | 0 |  | 0 | 567.5857
3 |  | 2BHK |  | 586.8533 | 0 |  | 0 | 586.8533
4 |  | 2BHK |  | 586.8533 | 0 |  | 0 | 586.8533
5 |  | 2BHK |  | 586.8533 | 0 |  | 0 | 586.8533
6 |  | 2BHK |  | 586.8533 | 0 |  | 0 | 586.8533
7 |  | 2BHK |  | 567.5857 | 0 |  | 0 | 567.5857
8 |  | 1BHK |  | 371.2504 | 0 |  | 0 | 371.2504
7th & 14th Floor ( Part Refuge Area) | [8 empty] | 2
1 |  | 1BHK |  | 371.2504 | 0 |  | 0 | 371.2504
2 |  | Refuge Area
3
4 |  | 2BHK |  | 586.8533 | 0 |  | 0 | 586.8533
5 |  | 2BHK |  | 586.8533 | 0 |  | 0 | 586.8533
6 |  | 2BHK |  | 586.8533 | 0 |  | 0 | 586.8533
7 |  | 2BHK |  | 567.5857 | 0 |  | 0 | 567.5857
8 |  | 1BHK |  | 371.2504 | 0 |  | 0 | 371.2504
21st Floor ( Part Refuge Area) | [8 empty] | 1
1 |  | 1BHK |  | 371.2504 | 0 |  | 0 | 371.2504
2 |  | Refuge Area
3
4 |  | 2BHK |  | 586.8533 | 0 |  | 0 | 586.8533
5 |  | 2BHK |  | 586.8533 | 0 |  | 0 | 586.8533
6 |  | 2BHK |  | 586.8533 | 0 |  | 0 | 586.8533
7 |  | 2BHK |  | 567.5857 | 0 |  | 0 | 567.5857
8 |  | 1BHK |  | 371.2504 | 0 |  | 0 | 371.2504
Sale Wing E (As per Approved Plan) = Sale Wing A (As per Builder letter & Index II)
1st & 2nd Basement Floor For Parking
Ground Floor Commercial, Entrance Lobby, College Area, Society Office & Meter Room.
1st Floor For Commercial (Shop & Office) & College Area | [8 empty] | 1
2nd Floor For Commercial (Shop & Office), College Area, Multipurpose Hall, Fitness Centre, Game Room, Reading Lounge. | [8 empty] | 1
3rd & 4th Floor For Residential, Commercial & College Area | [8 empty] | 2
1 |  | Commercial & College Area | [11 empty] | 301,..,401 | 301 | 401
2 | [13 empty] | 302,..,402 | 302 | 402
3 |  | 2BHK |  | 611.5028 | 0 |  | 0 | 611.5028 |  | 10.764 | 10.764 |  |  | 303,..,403 | 303 | 403
4 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 304,..,404 | 304 | 404
5 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 305,..,405 | 305 | 405
6 |  | 2BHK |  | 611.5028 | 0 |  | 0 | 611.5028 | [5 empty] | 306,..,406 | 306 | 406
7 |  | 2BHK |  | 611.5028 | 0 |  | 0 | 611.5028 | [5 empty] | 307,..,407 | 307 | 407
8 |  | 2BHK |  | 593.8499 | 0 |  | 0 | 593.8499 | [5 empty] | 308,..,408 | 308 | 408
9 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 309,..,409 | 309 | 409
10 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 310,..,410 | 310 | 410
11 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 311,..,411 | 311 | 411
12 |  | Commercial & College Area | [11 empty] | 312,..,412 | 312 | 412
12A | [13 empty] | 313,..,413 | 313 | 413
5th Floor For Residential ( Terrace Area as Refuge Floor) | [8 empty] | 1
1 |  | Terrace Area as Refuge Floor | [11 empty] | #REF! | #REF! | 501
2 | [13 empty] | #REF! | #REF! | 502
3 |  | 2BHK |  | 611.5028 | 0 |  | 0 | 611.5028 | [5 empty] | #REF! | #REF! | 503
4 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | #REF! | #REF! | 504
5 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | #REF! | #REF! | 505
6 |  | 2BHK |  | 611.5028 | 0 |  | 0 | 611.5028 | [5 empty] | #REF! | #REF! | 506
7 |  | 2BHK |  | 611.5028 | 0 |  | 0 | 611.5028 | [5 empty] | #REF! | #REF! | 507
8 |  | 2BHK |  | 593.8499 | 0 |  | 0 | 593.8499 | [5 empty] | #REF! | #REF! | 508
9 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | #REF! | #REF! | 509
10 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | #REF! | #REF! | 510
11 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | #REF! | #REF! | 511
12 |  | Terrace Area as Refuge Floor | [11 empty] | #REF! | #REF! | 512
12A | [13 empty] | #REF! | #REF! | 513
6th, 8th to 13th, 15th to 20th, 22nd to 27th, 29th & 30th Floor | [8 empty] | 21
1 |  | 3BHK |  | 991.1491 | 0 |  | 0 | 991.1491 | [5 empty] | 6801,..,3001 | 6801 | 3001
2 |  | 3BHK |  | 991.1491 | 0 |  | 0 | 991.1491 | [5 empty] | 6802,..,3002 | 6802 | 3002
3 |  | 2BHK |  | 611.5028 | 0 |  | 0 | 611.5028 | [5 empty] | 6803,..,3003 | 6803 | 3003
4 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 6804,..,3004 | 6804 | 3004
5 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 6805,..,3005 | 6805 | 3005
6 |  | 2BHK |  | 611.5028 | 0 |  | 0 | 611.5028 | [5 empty] | 6806,..,3006 | 6806 | 3006
7 |  | 2BHK |  | 611.5028 | 0 |  | 0 | 611.5028 | [5 empty] | 6807,..,3007 | 6807 | 3007
8 |  | 2BHK |  | 593.8499 | 0 |  | 0 | 593.8499 | [5 empty] | 6808,..,3008 | 6808 | 3008
9 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 6809,..,3009 | 6809 | 3009
10 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 6810,..,3010 | 6810 | 3010
11 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 6811,..,3011 | 6811 | 3011
12 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 6812,..,3012 | 6812 | 3012
12A |  | 3BHK |  | 935.284 | 0 |  | 0 | 935.284 | [5 empty] | 6813,..,3013 | 6813 | 3013
7th, 14th & 21st Floor ( Part Refuge Area) | [8 empty] | 3
1 |  | 3BHK |  | 991.1491 | 0 |  | 0 | 991.1491 | [5 empty] | 701,..,2101 | 701 | 2101
2 |  | 3BHK |  | 991.1491 | 0 |  | 0 | 991.1491 | [5 empty] | 702,..,2102 | 702 | 2102
3 |  | Refuge Area | [11 empty] | 703,..,2103 | 703 | 2103
4 | [13 empty] | 704,..,2104 | 704 | 2104
5 | [13 empty] | 705,..,2105 | 705 | 2105
6 | [13 empty] | 706,..,2106 | 706 | 2106
7 |  | 2BHK |  | 611.5028 | 0 |  | 0 | 611.5028 | [5 empty] | 707,..,2107 | 707 | 2107
8 |  | 2BHK |  | 593.8499 | 0 |  | 0 | 593.8499 | [5 empty] | 708,..,2108 | 708 | 2108
9 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 709,..,2109 | 709 | 2109
10 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 710,..,2110 | 710 | 2110
11 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 711,..,2111 | 711 | 2111
12 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 712,..,2112 | 712 | 2112
12A |  | 3BHK |  | 935.284 | 0 |  | 0 | 935.284 | [5 empty] | 713,..,2113 | 713 | 2113
28th Floor (Part Refuge Area) | [8 empty] | 1
1 |  | 3BHK |  | 991.1491 | 0 |  | 0 | 991.1491 | [5 empty] | 201,..,2801 | 201 | 2801
2 |  | 3BHK |  | 991.1491 | 0 |  | 0 | 991.1491 | [5 empty] | 202,..,2802 | 202 | 2802
3 |  | 2BHK |  | 611.5028 | 0 |  | 0 | 611.5028 | [5 empty] | 203,..,2803 | 203 | 2803
4 |  | Refuge Area | [11 empty] | 204,..,2804 | 204 | 2804
5 | [13 empty] | 205,..,2805 | 205 | 2805
6 |  | 2BHK |  | 611.5028 | 0 |  | 0 | 611.5028 | [5 empty] | 206,..,2806 | 206 | 2806
7 |  | 2BHK |  | 611.5028 | 0 |  | 0 | 611.5028 | [5 empty] | 207,..,2807 | 207 | 2807
8 |  | 2BHK |  | 593.8499 | 0 |  | 0 | 593.8499 | [5 empty] | 208,..,2808 | 208 | 2808
9 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 209,..,2809 | 209 | 2809
10 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 210,..,2810 | 210 | 2810
11 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 211,..,2811 | 211 | 2811
12 |  | 2BHK |  | 595.7874 | 0 |  | 0 | 595.7874 | [5 empty] | 212,..,2812 | 212 | 2812
12A |  | 3BHK |  | 935.284 | 0 |  | 0 | 935.284 | [5 empty] | 213,..,2813 | 213 | 2813
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Wing D (Wing B) = Construction work is in process at the time of Visit. Internal visit not allowed. Wing E (Wing A) = Construction work is in process at the time of Visit. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Deck. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We have not drafted Commercial area of Wing E (Ground to 4th Floor Consist of Commercial(Offices & Shops) Beceause shop/office Numbering was not mentioned on it. 8. Nomenclature for Project Sale Wing D (As per Approved Plan) = Sale Wing B (As per Builder letter & Index II) Sale Wing E (As per Approved Plan) = Sale Wing A (As per Builder letter & Index II) 9. High Tension lines are passing between Wing D & Wing E 10. Flat No. 1, 2 & 12A consist of seperate servent room. 11. Please Provide latest approved plan & CC For Sale Wing D = Sale Wing B | [6 empty] | All work completed. OC received.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Raunak Centrum
Project Site Address |  |  | : | Raunak Centrum 12, Rahul Nagar, Everard Nagar, Chembur, Mumbai, Maharashtra 400024
Site Visit Date & Time |  |  | : | 04/07/2025 at 03:46 PM
jkcgn
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Akash Kadam | Authorized Signatory Name & Signature | :
Wing D
Wing E
WING E
Rehab Wing A, B & C
WING D
High Tension Line
High
Tension Line
This Picture is attached to show high tension lines only. This picture should not be considered for stage construction as picture is of visit dtd 13/03/2024.
Part 1
Part 2
Wing A
HT LINES
Wing B
Wing A
Wing B
Wing A
HT LINES
HT LINES
Wing E
Wing D
Note on E9: Initiation Address
Note on E10: Plan Address
Note on E11: Plan Address
Note on C17: Maybe same as RERA Registration Validity or different
Note on H17: From Rera
Note on H21: From RERA
Note on A40: As per Layout
Note on H113: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%