## report
APF Report Format
Name of Valuation Agency |  |  | : | V.S.JADON & CO VALUERS LLP |  | Date of Technical Initiation |  | 2025-07-02 |  | 2025-04-10 | 2025-07-04 | 85
Project Name |  |  | : | Runwal Gardens Phase IV (T31 to T37) |  | Date & Time of Site Visit |  | 04/07/2025 at 10:05 AM
Name of the person met at site & Contact No. |  |  | : | Mr. Ankit 9137940152 |  | Date of Report Release |  | 07/07/2025 |  | 83 | Miss. Sarikha Mhatre 8591953567
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | M/s.Runwal Residency Private Limited | Developer Name | : | M/s.Runwal Residency Private Limited
|  |  | : | Runwal & Omkar Esquare, 5th Floor, Eastern Express Highway, Sion (East), Mumbai – 400022
Project Address | : | As per ARF | : | Runwal Gardens, Kalyan-Shilphata Road, Village Usarghar, Gharvali & Sagaon, Dombivli East, Thane, Maharashtra- 421204
| : | As per Legal Documents | : | Runwal Gardens Phase 4, Survey No.67/1 of village Sagaon 4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 4/7, 4/7, 4/8, 4/9, 4/10, 4/11, 5/1, 5/2, 5/3, 5/4, 5/5, 5/6, 6/1, 6/2, 6/3, 7/1, 7/2/A, 7/2/B, 7/2/C, 7/3/A, 7/3/B, 8/1, 8/2, 8/3, 8/4, 8/5, 8/6, 8/7, 8/8, 9/1, 9/2, 9/3, 9/4, 9/5, 9/6, 9/7, 9/8, 10, 11, 12/1, 12/2, 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9, 12/10, 12/11, 12/12, 12/13, 12/14, 13, 14/1, 12/2A, 14/2B, 14/3, 14/4, 14/5, 15, 16/1, 16/2, 17/1, 17/2, 17/3, 17/4, 17/5, 17/6, 17/7, 17/8, 17/9, 17/10, 17/11, 18, 19, 20/1, 20/2, 21/1, 21/2, 21/3, 21/4, 22, 23/1, 23/2, 23/3, 23/10, 37/1, 37/2B, 37/2C, 37/2D, 37/3, 37/4, 37/21, 38/1, 38/2, 39/1, 39/2, 39/3, 40, 41/1A, 41/1B, 41/2, 41/3, 41/4, 44/1, 44/4, 44/5A, 44/5B, 44/6A, 44/6B, 44/7, 44/8, 44/9, 44/10, 44/11, 44/12, 44/13, 44/14, 44/15, 44/16, 44/17, 44/18, 44/19, 44/20, 49, 50/1, 50/2, 50/3, 51/1, 51/2, 56/1, 56/2 of Village Gharivali 44/1, 44/2, 44/3, 44/4, 44/5, 44/6, 44/7, 44/8, 44/9, 44/10, 44/11, 44/12, 45/1, 45/2, 45/3, 45/4, 15/5/A, 45/5/B, 45/6, 46/1, 46/2A, 46/2B, 46/3, 47, 49, 50, 51, 52/1, 52/2, 53/1/A, 53/1/B, 53/2/A, 53/2/B, 53/3/A, 53/3/B, 94 Village Usarghar, Kalyan Shilphata Road, Dombivli, Dombivli, Kalyan, Thane.
| : | As per Actual at site | : | Runwal Gardens Phase 4, Village Usarghar, Kalyan Shilphata Road, Dombivli, Kalyan, Thane.
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate
General Details
Status of Holding |  |  | : | Freehold | Name of Municipal Corporation/Authority | : | MMRDA
RERA Registration No. |  |  | : | Phase 4 - Building No. 31 & 32 = P51700029155 Building No. 33 & 34 = P51700030533 Building No. 35 & 36 = P51700031319 Building No 37 = P51700033206 | RERA Registration Validity | : | 31/12/2025.
Project Launch Date |  |  | : | 29/04/2021. | Construction Start Date | : | June 2021.
Proposed Date of Completion (As per RERA) |  |  | : | 31/12/2025. | Developer Bank Name (As per RERA) | : | HDFC Bank IFSC Code : HDFC0000163
Project Type (Mixed, Residential, Comm.) |  |  | : | Residential | Plot Area (In Sq.Mt) 115Acres (Site A) | : | 464428
Permissible Built up Area (In Sq.Mt) |  |  | : | 783025.61 | Proposed Built up Area (In Sq.Mt) | : | 199781.44
Free/ Fungible FSI Additional FSI |  |  | : | 1 0.7 | Total Number of Units Planned | : | Flats - 2038
Total Number of Units Approved |  |  | : | Flats - 1906 | If Mixed, No. of Commercial Units | : | -
Latitude |  |  | : | 19.1849 | Longitude | : | 73.0866
Location Link |  |  | : | https://maps.app.goo.gl/RsZH7xuB7bamkxvr5
Extra Amenities available |  |  | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area |  |  | : | Developing | Class of Locality | : | Middle
Type of Road |  |  | : | Bitumen | Width of the Road in ft. | : | 9ft
Electrification/Electric poles observed |  |  | : | Yes | Distance from Bus stand (Km) | : | 400m Premier Company Bus Stop
Distance from the nearest School (Km) |  |  | : | 600m from Pawar Public School | Distance from Hospital (Km) | : | 650m from Shree Gajanan Hospital
Distance from the Main Market (Km) |  |  | : | 600m Paradise Mall | Distance from nearest Railway/Metro/Airport (Km) | : | 4.7Km from Nilaje Railway Station
Water Supply |  |  | : | Being Provisioned | Electricity Supply | : | Being Provisioned
Drainage Connection |  |  | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Road | Open Plot | Road |  | Road
As per Site / Actual |  |  | : | Open Plot | Open Plot | Road |  | Building U/C
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure (As per Commencement Certificate)
Building/Tower Name/No. |  |  | Type (Sale/Rehab) |  | No. of Floors Planned |  | No. of Floors Approved
Phase III
Blg No.31 |  |  | Sale |  | Bs + Stilt + 1st to 32nd Floor |  | Bs + Stilt + 1st to 32nd Floor
Blg No.32 |  |  | Sale |  | Bs + Stilt + 1st to 32nd Floor |  | Bs + Stilt + 1st to 32nd Floor
Blg No.33 |  |  | Sale |  | Bs + Stilt + 1st to 32nd Floor |  | Bs + Stilt + 1st to 32nd Floor
Blg No.34 |  |  | Sale |  | Bs + Stilt + 1st to 32nd Floor |  | Bs + Stilt + 1st to 32nd Floor
Blg No.35 |  |  | Sale |  | Bs + Stilt + 1st to 32nd Floor |  | Bs + Stilt + 1st to 32nd Floor
Blg No.36 |  |  | Sale |  | Bs + Stilt + 1st to 32nd Floor |  | Bs + Stilt + 1st to 32nd Floor
Blg No.37 |  |  | Sale |  | Bs + Stilt + 1st to 32nd Floor |  | Bs + Stilt + 1st to 17th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Under Construction |  |  | LOI/IOD Details | : | SROT/Growth Center/2401/BP/ITP-Usarghar-Gharivali-Sagaon-01/Site-A/Vol.XVI/782/2020 Date - 14/10/2020. SROT/Growth Center/2401/BP/ITP-Usarghar-Gharivali-Sagaon-01/Site-A/Vol.31/720/2021 Date - 05/08/2021.
CC Details | : | Tower No. 31 to 36 - SROT/Growth Center/2401/BP/ITP-Usarghar-Gharivali-Sagaon-01/Site-A/Vol.33/1319/2021 Date - 15/12/2021 CC Valid upto : Valid Up to: Building No.31 to 36 = Bs + Stilt + 1st to 32nd Floor. Building No.37 = Bs + Stilt + 1st to 17th Floor. |  |  | Approved Plan Details | : | Tower No.31 & 32 - SROT/Growth Center/2401/BP/ITP-Usarghar-Gharivali-Sagaon-01/Site-A/Vol.XXVI/383/2021 Date - 12/04/2021. Tower No.33, 34 & 37 - SROT/Growth Center/2401/BP/ITP-Usarghar-Gharivali-Sagaon-01/Site-A/Vol.31/720/2021 Date - 05/08/2021. Tower No - 35 & 36 SROT/Growth Center/2401/BP/ITP-Usarghar-Gharivali-Sagaon-01/Site-A/Vol.33/1319/2021 Date - 15/12/2021.
Environmental Clearance Details | : | SEIAA-MINUTES-0000002667 Date:02/11/2019. |  |  | Forest NOC Details | : | KS-1/20/JAMIN/3902/2018-2019 Date : 02/10/2018.
Irrigaton NOC Details | : | TMID/PB-3/379/2018 Date:30/11/2018. |  |  | Tribal NOC Details | : | MHASUL/T-2/JAMINBB-1/KV-68/18 Date:14/12/2018. MHASUL/T-2/JAMINBB-1/KV-40/18 Date:05/02/2019.
Construction Status
Building No. 31 & 32 = Bs + Stilt + 1st to 32nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 22 Floor, Flooring & Fitting upto 12 Floor, Electrical & Sanitary fittings upto 10 Floor Completed
|  |  |  | 1 | 1 |  | 0 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8
Excavation |  | 32 |  | 100% | 67.97% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 22 Floor, Flooring & Fitting upto 12 Floor, Electrical & Sanitary fittings upto 10 Floor Completed |  | Excavation in process | 16
Plinth |  | 32 |  | 100% |  |  |  |  | Excavation Completed | 32
RCC (Including podiums) |  | 33 |  | 100% |  |  |  |  | Footing in Process | 8
Brickwork |  | 32 |  | 100% |  |  |  |  | Footing Completed | 16
Internal Plaster |  | 32 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 32 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 22 |  | 68.75% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 12 |  | 37.5% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 24
Electrical & Sanitary fittings |  | 10 |  | 31.25% |  |  |  |  | Plinth completed | 32 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building No. 33 = Bs + Stilt + 1st to 32nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 25 Floor, Flooring & Fitting upto 15 Floor, Electrical & Sanitary fittings upto 15 Floor Completed
|  |  |  | 1 | 1 |  | 0 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8
Excavation |  | 32 |  | 100% | 69.77% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 25 Floor, Flooring & Fitting upto 15 Floor, Electrical & Sanitary fittings upto 15 Floor Completed |  | Excavation in process | 16
Plinth |  | 32 |  | 100% |  |  |  |  | Excavation Completed | 32
RCC (Including podiums) |  | 33 |  | 100% |  |  |  |  | Footing in Process | 8
Brickwork |  | 32 |  | 100% |  |  |  |  | Footing Completed | 16
Internal Plaster |  | 32 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 32 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 25 |  | 78.12% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 15 |  | 46.88% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 24
Electrical & Sanitary fittings |  | 15 |  | 46.88% |  |  |  |  | Plinth completed | 32 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building No. 34 = Bs + Stilt + 1st to 32nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 23 Slab, Brickwork upto 22 Floor, Internal Plaster upto 22 Floor, External Plaster upto 22 Floor, External Plumbing, Elevation and Waterproofing upto 13 Floor, Flooring & Fitting upto 5 Floor, Electrical & Sanitary fittings upto 8 Floor Completed
|  |  |  | 1 | 1 |  | 0 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8
Excavation |  | 32 |  | 100% | 53.52% |  | Excavation work Completed. Plinth work completed, RCC upto 23 Slab, Brickwork upto 22 Floor, Internal Plaster upto 22 Floor, External Plaster upto 22 Floor, External Plumbing, Elevation and Waterproofing upto 13 Floor, Flooring & Fitting upto 5 Floor, Electrical & Sanitary fittings upto 8 Floor Completed |  | Excavation in process | 16
Plinth |  | 32 |  | 100% |  |  |  |  | Excavation Completed | 32
RCC (Including podiums) |  | 23 |  | 69.7% |  |  |  |  | Footing in Process | 8
Brickwork |  | 22 |  | 68.75% |  |  |  |  | Footing Completed | 16
Internal Plaster |  | 22 |  | 68.75% |  |  |  |  | Basement 1 | 0
External Plaster |  | 22 |  | 68.75% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 13 |  | 40.62% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 5 |  | 15.62% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 24
Electrical & Sanitary fittings |  | 8 |  | 25% |  |  |  |  | Plinth completed | 32 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building No. 35 = Bs + Stilt + 1st to 32nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 23 Slab, Brickwork upto 22 Floor, Internal Plaster upto 21 Floor, External Plaster upto 21 Floor, External Plumbing, Elevation and Waterproofing upto 8 Floor, Flooring & Fitting upto 5 Floor, Electrical & Sanitary fittings upto 5 Floor Completed
|  |  |  | 1 | 1 |  | 0 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8
Excavation |  | 32 |  | 100% | 52.35% |  | Excavation work Completed. Plinth work completed, RCC upto 23 Slab, Brickwork upto 22 Floor, Internal Plaster upto 21 Floor, External Plaster upto 21 Floor, External Plumbing, Elevation and Waterproofing upto 8 Floor, Flooring & Fitting upto 5 Floor, Electrical & Sanitary fittings upto 5 Floor Completed |  | Excavation in process | 16
Plinth |  | 32 |  | 100% |  |  |  |  | Excavation Completed | 32
RCC (Including podiums) |  | 23 |  | 69.7% |  |  |  |  | Footing in Process | 8
Brickwork |  | 22 |  | 68.75% |  |  |  |  | Footing Completed | 16
Internal Plaster |  | 21 |  | 65.62% |  |  |  |  | Basement 1 | 0
External Plaster |  | 21 |  | 65.62% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 8 |  | 25% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 5 |  | 15.62% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 24
Electrical & Sanitary fittings |  | 5 |  | 15.62% |  |  |  |  | Plinth completed | 32 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building No. 36 = Bs + Stilt + 1st to 32nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 26 Slab, Brickwork upto 25 Floor, Internal Plaster upto 25 Floor, External Plaster upto 25 Floor, External Plumbing, Elevation and Waterproofing upto 7 Floor, Flooring & Fitting upto 4 Floor, Electrical & Sanitary fittings upto 4 Floor Completed
|  |  |  | 1 | 1 |  | 0 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8
Excavation |  | 32 |  | 100% | 55.17% |  | Excavation work Completed. Plinth work completed, RCC upto 26 Slab, Brickwork upto 25 Floor, Internal Plaster upto 25 Floor, External Plaster upto 25 Floor, External Plumbing, Elevation and Waterproofing upto 7 Floor, Flooring & Fitting upto 4 Floor, Electrical & Sanitary fittings upto 4 Floor Completed |  | Excavation in process | 16
Plinth |  | 32 |  | 100% |  |  |  |  | Excavation Completed | 32
RCC (Including podiums) |  | 26 |  | 78.79% |  |  |  |  | Footing in Process | 8
Brickwork |  | 25 |  | 78.12% |  |  |  |  | Footing Completed | 16
Internal Plaster |  | 25 |  | 78.12% |  |  |  |  | Basement 1 | 0
External Plaster |  | 25 |  | 78.12% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 7 |  | 21.88% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 4 |  | 12.5% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 24
Electrical & Sanitary fittings |  | 4 |  | 12.5% |  |  |  |  | Plinth completed | 32 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building No. 37 = Bs + Stilt + 1st to 32nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 14 Slab, Brickwork upto 13 Floor, Internal Plaster upto 9.75 Floor, External Plaster upto 9.75 Floor, External Plumbing, Elevation and Waterproofing upto 3 Floor Completed
|  |  |  | 1 | 1 |  | 0 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8
Excavation |  | 32 |  | 100% | 39.63% |  | Excavation work Completed. Plinth work completed, RCC upto 14 Slab, Brickwork upto 13 Floor, Internal Plaster upto 9.75 Floor, External Plaster upto 9.75 Floor, External Plumbing, Elevation and Waterproofing upto 3 Floor Completed |  | Excavation in process | 16
Plinth |  | 32 |  | 100% |  |  |  |  | Excavation Completed | 32
RCC (Including podiums) |  | 14 |  | 42.42% |  |  |  |  | Footing in Process | 8 |  |  | 34.35.36
Brickwork |  | 13 |  | 40.62% |  |  |  |  | Footing Completed | 16
Internal Plaster |  | 9.75 |  | 30.47% |  |  |  |  | Basement 1 | 0
External Plaster |  | 9.75 |  | 30.47% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 3 |  | 9.375% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 24
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 32 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 58.05%
Market Value
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq.ft | Type of Saleable Area (CA/BUA/SBA/Plot Area) | : | SBA
Rate Per Sq. Ft. (on Saleable area) |  |  | : | 6800/-Sq.ft | Floor Rise Details Per Sq.Ft. (on Saleable area) Any Floor | : | NA
Car Parking Charges |  |  | : | 300000/- | Other Charges | : | As per documentation
Guideline Values & Distress Value
Government Guideline/ Circle rate for Land (Rs per sqft) - Gharivali | [5 empty] | : | 696.767
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) - Gharivali | [5 empty] | : | 3428.0936
Government Guideline/ Circle rate for Land (Rs per sqft) - Usarghar | [5 empty] | : | 575.9941
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) - Usarghar | [5 empty] | : | 3808.9929
Distress Value (Rs. Per sqft) | [5 empty] | : | 3047.1944
Unit Details, Nomenclature and Area Details
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  |  | Total Saleable Area
Building No.31 |  | 314 |  | 161329.4327 |  |  | 241994.149
Building No.32 |  | 314 |  | 155372.7427 |  |  | 233059.1141
Building No.33 |  | 282 |  | 171144.6937 |  |  | 256717.0406
Building No.34 |  | 282 |  | 171731.1164 |  |  | 257596.6747
Building No.35 |  | 282 |  | 174578.9479 |  |  | 261868.4219
Building No.36 |  | 282 |  | 174578.9479 |  |  | 261868.4219
Building No.37 |  | 150 |  | 90638.3696 |  |  | 135957.5545
Total |  | 1906 |  | 1099374.251 |  |  | 1649061.3766
Building details Floor Wise
Details of Flats in Building
Building/Tower & Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area (50% Loading)
Building No.31
Basement Floor for Parking
Ground Floor for Parking
1st Floor
1st Floor |  | 101 |  | 1BHK | 418.7196 |  | 0 | 628.0794
|  | 102 |  | 1BHK | 369.4205 |  | 0 | 554.1307
|  | 103 |  | 1BHK | 369.4205 |  | 0 | 554.1307
|  | 104 |  | 2BHK | 484.2724 |  | 0 | 726.4085
|  | 105 |  | Double Height
|  | 106 |  | 2BHK | 533.5715 |  | 0 | 800.3572
|  | 107 |  | 1BHK | 427.869 |  | 0 | 641.8035
|  | 108 |  | 3BHK | 794.1679 |  | 0 | 1191.2519
|  | 109 |  | 2BHK | 619.7911 |  | 0 | 929.6867
|  | 110 |  | 1BHK | 418.7196 |  | 0 | 628.0794
2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor |  | 201,..,3201 |  | 1BHK | 418.7196 |  | 0 | 628.0794
|  | 202,..,3202 |  | 2BHK | 505.1545 |  | 0 | 757.7318
|  | 203,..,3203 |  | 2BHK | 505.1545 |  | 0 | 757.7318
|  | 204,..,3204 |  | 2BHK | 484.2724 |  | 0 | 726.4085
|  | 205,..,3205 |  | 1BHK | 421.1953 |  | 0 | 631.793
|  | 206,..,3206 |  | 2BHK | 533.5715 |  | 0 | 800.3572
|  | 207,..,3207 |  | 1BHK | 427.869 |  | 0 | 641.8035
|  | 208,..,3208 |  | 3BHK | 794.1679 |  | 0 | 1191.2519
|  | 209,..,3209 |  | 2BHK | 619.7911 |  | 0 | 929.6867
|  | 210,..,3210 |  | 1BHK | 418.7196 |  | 0 | 628.0794
8th, 14th, 19th, 24th & 29th Floor
8th, 14th, 19th, 24th & 29th Floor |  | 801,..,2901 |  | 1BHK | 418.7196 |  | 0 | 628.0794
|  | 802,..,2902 |  | 2BHK | 505.1545 |  | 0 | 757.7318
|  | 803,..,2903 |  | 2BHK | 505.1545 |  | 0 | 757.7318
|  | 804,..,2904 |  | 2BHK | 484.2724 |  | 0 | 726.4085
|  | 805,..,2905 |  | 1BHK | 421.1953 |  | 0 | 631.793
|  | 806,..,2906 |  | 2BHK | 533.5715 |  | 0 | 800.3572
|  | 807,..,2907 |  | 1BHK | 427.869 |  | 0 | 641.8035
|  | 808,..,2908 |  | 3BHK | 794.1679 |  | 0 | 1191.2519
|  | 809,..,2909 |  | 2BHK | 619.7911 |  | 0 | 929.6867
|  | 810,..,2910 |  | Refuge Area
Building No.32
Basement Floor for Parking
Ground Floor for Parking
1st Floor
1st Floor |  | 101 |  | 1BHK | 424.5322 |  | 0 | 636.7982
|  | 102 |  | 1BHK | 373.9414 |  | 0 | 560.912
|  | 103 |  | 1BHK | 373.9414 |  | 0 | 560.912
|  | 104 |  | 2BHK | 484.2724 |  | 0 | 726.4085
|  | 105 |  | 2BHK | 530.2346 |  | 0 | 795.352
|  | 106 |  | 1BHK | 421.1953 |  | 0 | 631.793
|  | 107 |  | 1BHK | 421.1953 |  | 0 | 631.793
|  | 108 |  | 2BHK | 469.5257 |  | 0 | 704.2885
|  | 109 |  | 2BHK | 469.5257 |  | 0 | 704.2885
|  | 110 |  | Double Height
2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor |  | 201,..,3201 |  | 1BHK | 424.5322 |  | 0 | 636.7982
|  | 202,..,3202 |  | 2BHK | 506.8768 |  | 0 | 760.3151
|  | 203,..,3203 |  | 2BHK | 506.8768 |  | 0 | 760.3151
|  | 204,..,3204 |  | 2BHK | 484.2724 |  | 0 | 726.4085
|  | 205,..,3205 |  | 2BHK | 530.2346 |  | 0 | 795.352
|  | 206,..,3206 |  | 1BHK | 421.1953 |  | 0 | 631.793
|  | 207,..,3207 |  | 1BHK | 421.1953 |  | 0 | 631.793
|  | 208,..,3208 |  | 2BHK | 621.621 |  | 0 | 932.4315
|  | 209,..,3209 |  | 2BHK | 621.621 |  | 0 | 932.4315
|  | 210,..,3210 |  | 1BHK | 412.0459 |  | 0 | 618.0689
8th, 14th, 19th, 24th & 29th Floor
8th, 14th, 19th, 24th & 29th Floor |  | 801,..,2901 |  | 1BHK | 424.5322 |  | 0 | 636.7982
|  | 802,..,2902 |  | 2BHK | 506.8768 |  | 0 | 760.3151
|  | 803,..,2903 |  | 2BHK | 506.8768 |  | 0 | 760.3151
|  | 804,..,2904 |  | 2BHK | 484.2724 |  | 0 | 726.4085
|  | 805,..,2905 |  | 2BHK | 530.2346 |  | 0 | 795.352
|  | 806,..,2906 |  | 1BHK | 421.1953 |  | 0 | 631.793
|  | 807,..,2907 |  | 1BHK | 421.1953 |  | 0 | 631.793
|  | 808,..,2908 |  | 2BHK | 621.621 |  | 0 | 932.4315
|  | 809,..,2909 |  | 2BHK | 621.621 |  | 0 | 932.4315
|  | 810,..,2910 |  | Refuge Area
Building No.33
Basement Floor for Parking
Ground Floor for Parking
1st Floor
1st Floor |  | 101 |  | 2BHK | 523.3457 |  | 0 | 785.0185
|  | 102 |  | 1BHK | 441.0011 |  | 0 | 661.5016
|  | 103 |  | 1BHK | 441.0011 |  | 0 | 661.5016
|  | 104 |  | Double Height
|  | 105 |  | 3BHK | 732.2749 |  | 0 | 1098.4124
|  | 106 |  | 2.5BHK | 663.493 |  | 0 | 995.2394
|  | 107 |  | 2BHK | 619.1453 |  | 0 | 928.7179
|  | 108 |  | 2BHK | 619.1453 |  | 0 | 928.7179
|  | 109 |  | 1.5BHK | 488.6856 |  | 0 | 733.0284
2nd to 7th, 9th to 13th, 15th Floor
2nd to 7th, 9th to 13th, 15th Floor |  | 201,..,1501 |  | 2BHK | 523.3457 |  | 0 | 785.0185
|  | 202,..,1502 |  | 2BHK | 587.4991 |  | 0 | 881.2487
|  | 203,..,1503 |  | 2BHK | 587.4991 |  | 0 | 881.2487
|  | 204,..,1504 |  | 2.5BHK | 646.2706 |  |  | 969.4058
|  | 205,..,1505 |  | 3BHK | 732.2749 |  | 0 | 1098.4124
|  | 206,..,1506 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686
|  | 207,..,1507 |  | 2BHK | 619.6835 |  | 0 | 929.5252
|  | 208,..,1508 |  | 2BHK | 619.6835 |  | 0 | 929.5252
|  | 209,..,1509 |  | 1.5BHK | 488.6856 |  | 0 | 733.0284
8th & 14th Floor (Part Refuge Area)
8th & 14th Floor (Part Refuge Area) |  | 801 & 1401 |  | 2BHK | 523.3457 |  | 0 | 785.0185
|  | 802 & 1402 |  | 2BHK | 587.4991 |  | 0 | 881.2487
|  | 803 & 1403 |  | 2BHK | 587.4991 |  | 0 | 881.2487
|  | 804 & 1404 |  | 2.5BHK | 646.2706 |  |  | 969.4058
|  | 805 & 1405 |  | Refuge Area
|  | 806 & 1406 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686
|  | 807 & 1407 |  | 2BHK | 619.6835 |  | 0 | 929.5252
|  | 808 & 1408 |  | 2BHK | 619.6835 |  | 0 | 929.5252
|  | 809 & 1409 |  | 1.5BHK | 488.6856 |  | 0 | 733.0284
16th to 18th, 20th to 23rd, 25th to 28th & 30th to 32nd Floor
16th to 18th, 20th to 23rd, 25th to 28th & 30th to 32nd Floor |  | 1601,..,3201 |  | 2BHK | 525.6061 |  | 0 | 788.4092
|  | 1602,..,3202 |  | 2BHK | 589.5443 |  | 0 | 884.3164
|  | 1603,..,3203 |  | 2BHK | 589.5443 |  | 0 | 884.3164
|  | 1604,..,3204 |  | 2.5BHK | 649.3921 |  |  | 974.0882
|  | 1605,..,3205 |  | 3BHK | 740.2403 |  |  | 1110.3604
|  | 1606,..,3206 |  | 2.5BHK | 668.7673 |  | 0 | 1003.151
|  | 1607,..,3207 |  | 2BHK | 629.4787 |  | 0 | 944.2181
|  | 1608,..,3208 |  | 2BHK | 629.4787 |  | 0 | 944.2181
|  | 1609,..,3209 |  | 1.5BHK | 490.5155 |  | 0 | 735.7732
19th, 24th & 29th Floor (Part Refuge Area)
19th, 24th & 29th Floor (Part Refuge Area) |  | 1901,..,2901 |  | 2BHK | 525.6061 |  | 0 | 788.4092
|  | 1902,..,2902 |  | 2BHK | 589.5443 |  | 0 | 884.3164
|  | 1903,..,2903 |  | 2BHK | 589.5443 |  | 0 | 884.3164
|  | 1904,..,2904 |  | 2.5BHK | 649.3921 |  |  | 974.0882
|  | 1905,..,2905 |  | Refuge Area
|  | 1906,..,2906 |  | 2.5BHK | 668.7673 |  | 0 | 1003.151
|  | 1907,..,2907 |  | 2BHK | 629.4787 |  | 0 | 944.2181
|  | 1908,..,2908 |  | 2BHK | 629.4787 |  | 0 | 944.2181
|  | 1909,..,2909 |  | 1.5BHK | 490.5155 |  | 0 | 735.7732
Building No.34
Basement Floor for Parking
Ground Floor for Parking
1st Floor
1st Floor |  | 101 |  | 2BHK | 540.4604 |  | 0 | 810.6907
|  | 102 |  | 1BHK | 441.0011 |  | 0 | 661.5016
|  | 103 |  | 1BHK | 441.0011 |  | 0 | 661.5016
|  | 104 |  | Double Height
|  | 105 |  | 3BHK | 733.8895 |  | 0 | 1100.8343
|  | 106 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686
|  | 107 |  | 2BHK | 619.6835 |  | 0 | 929.5252
|  | 108 |  | 2BHK | 619.6835 |  | 0 | 929.5252
|  | 109 |  | 1.5BHK | 488.6856 |  | 0 | 733.0284
2nd to 7th, 9th to 13th & 15th Floor
2nd to 7th, 9th to 13th & 15th Floor |  | 201,..,1501 |  | 2BHK | 540.4604 |  | 0 | 810.6907
|  | 202,..,1502 |  | 1BHK | 587.4991 |  | 0 | 881.2487
|  | 203,..,1503 |  | 1BHK | 587.4991 |  | 0 | 881.2487
|  | 204,..,1504 |  | 2.5BHK | 646.2706 |  | 0 | 969.4058
|  | 205,..,1505 |  | 3BHK | 733.8895 |  | 0 | 1100.8343
|  | 206,..,1506 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686
|  | 207,..,1507 |  | 2BHK | 619.6835 |  | 0 | 929.5252
|  | 208,..,1508 |  | 2BHK | 619.6835 |  | 0 | 929.5252
|  | 209,..,1509 |  | 1.5BHK | 488.6856 |  | 0 | 733.0284
8th & 14th Floor (Part Refuge Area)
8th & 14th Floor (Part Refuge Area) |  | 801 & 1401 |  | 2BHK | 540.4604 |  | 0 | 810.6907
|  | 802 & 1402 |  | 2BHK | 587.4991 |  | 0 | 881.2487
|  | 803 & 1403 |  | 2BHK | 587.4991 |  | 0 | 881.2487
|  | 804 & 1404 |  | 2.5BHK | 646.2706 |  | 0 | 969.4058 |  | 10880
|  | 805 & 1405 |  | Refuge Area
|  | 806 & 1406 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686
|  | 807 & 1407 |  | 2BHK | 619.6835 |  | 0 | 929.5252
|  | 808 & 1408 |  | 2BHK | 619.6835 |  | 0 | 929.5252
|  | 809 & 1409 |  | 1.5BHK | 488.6856 |  | 0 | 733.0284
16th to 18th, 20th to 23rd, 25th to 28th & 30th to 32nd Floor
16th to 18th, 20th to 23rd, 25th to 28th & 30th to 32nd Floor |  | 1601,..,3201 |  | 2BHK | 542.7209 |  | 0 | 814.0813
|  | 1602,..,3202 |  | 2BHK | 589.5443 |  | 0 | 884.3164
|  | 1603,..,3203 |  | 2BHK | 589.5443 |  | 0 | 884.3164
|  | 1604,..,3204 |  | 2.5BHK | 649.3921 |  | 0 | 974.0882
|  | 1605,..,3205 |  | 3BHK | 740.8861 |  | 0 | 1111.3292
|  | 1606,..,3206 |  | 2.5BHK | 668.7673 |  | 0 | 1003.151
|  | 1607,..,3207 |  | 2BHK | 629.5864 |  | 0 | 944.3795
|  | 1608,..,3208 |  | 2BHK | 629.5864 |  | 0 | 944.3795
|  | 1609,..,3209 |  | 1.5BHK | 490.6231 |  | 0 | 735.9347
19th, 24th & 29th Floor (Part Refuge Area)
19th, 24th & 29th Floor (Part Refuge Area) |  | 1901,..,2901 |  | 2BHK | 542.7209 |  | 0 | 814.0813
|  | 1902,..,2902 |  | 2BHK | 589.5443 |  | 0 | 884.3164
|  | 1903,..,2903 |  | 2BHK | 589.5443 |  | 0 | 884.3164
|  | 1904,..,2904 |  | 2.5BHK | 649.3921 |  | 0 | 974.0882
|  | 1905,..,2905 |  | Refuge Area
|  | 1906,..,2906 |  | 2.5BHK | 668.7673 |  | 0 | 1003.151
|  | 1907,..,2907 |  | 2BHK | 629.5864 |  | 0 | 944.3795
|  | 1908,..,2908 |  | 2BHK | 629.5864 |  | 0 | 944.3795
|  | 1909,..,2909 |  | 1.5BHK | 490.6231 |  | 0 | 735.9347
Building No.35
Basement Floor for Parking
Ground Floor for Parking
1st Floor
1st Floor |  | 101 |  | 2BHK | 561.7732 |  | 0 | 842.6597
|  | 102 |  | 1BHK | 441.0011 |  | 0 | 661.5016 | 40.647
|  | 103 |  | 1BHK | 441.0011 |  | 0 | 661.5016
|  | 104 |  | Double Height
|  | 105 |  | 3BHK | 752.1883 |  | 0 | 1128.2825
|  | 106 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686
|  | 107 |  | 2BHK | 636.3677 |  | 0 | 954.5515
|  | 108 |  | 2BHK | 636.3677 |  | 0 | 954.5515
|  | 109 |  | 1.5BHK | 488.6856 |  | 0 | 733.0284
2nd to 7th, 9th to 13th & 15th Floor
2nd to 7th, 9th to 13th & 15th Floor |  | 201,..,1501 |  | 2BHK | 561.7732 |  | 0 | 842.6597
|  | 202,..,1502 |  | 2BHK | 587.4991 |  | 0 | 881.2487
|  | 203,..,1503 |  | 2BHK | 587.4991 |  | 0 | 881.2487
|  | 204,..,1504 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686
|  | 205,..,1505 |  | 3BHK | 752.1883 |  | 0 | 1128.2825
|  | 206,..,1506 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686
|  | 207,..,1507 |  | 2BHK | 636.3677 |  | 0 | 954.5515
|  | 208,..,1508 |  | 2BHK | 636.3677 |  | 0 | 954.5515
|  | 209,..,1509 |  | 1.5BHK | 488.6856 |  | 0 | 733.0284
8th & 14th Floor (Part Refuge Area)
8th & 14th Floor (Part Refuge Area) |  | 801 & 1401 |  | 2BHK | 561.7732 |  | 0 | 842.6597
|  | 802 & 1402 |  | 2BHK | 587.4991 |  | 0 | 881.2487
|  | 803 & 1403 |  | 2BHK | 587.4991 |  | 0 | 881.2487
|  | 804 & 1404 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686
|  | 805 & 1405 |  | Refuge Area
|  | 806 & 1406 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686
|  | 807 & 1407 |  | 2BHK | 636.3677 |  | 0 | 954.5515
|  | 808 & 1408 |  | 2BHK | 636.3677 |  | 0 | 954.5515
|  | 809 & 1409 |  | 1.5BHK | 488.6856 |  | 0 | 733.0284
16th to 18th, 20th to 23rd, 25th to 28th & 30th to 32nd Floor
16th to 18th, 20th to 23rd, 25th to 28th & 30th to 32nd Floor |  | 1601,..,3201 |  | 2BHK | 564.1412 |  | 0 | 846.2119
|  | 1602,..,3202 |  | 2BHK | 589.5443 |  | 0 | 884.3164
|  | 1603,..,3203 |  | 2BHK | 589.5443 |  | 0 | 884.3164
|  | 1604,..,3204 |  | 2.5BHK | 668.7673 |  | 0 | 1003.151
|  | 1605,..,3205 |  | 3BHK | 759.2926 |  | 0 | 1138.9388
|  | 1606,..,3206 |  | 2.5BHK | 668.7673 |  | 0 | 1003.151
|  | 1607,..,3207 |  | 2BHK | 646.2706 |  | 0 | 969.4058
|  | 1608,..,3208 |  | 2BHK | 646.2706 |  | 0 | 969.4058
|  | 1609,..,3209 |  | 1.5BHK | 490.6231 |  | 0 | 735.9347
19th, 24th & 29th Floor (Part Refuge Area)
19th, 24th & 29th Floor (Part Refuge Area) |  | 1901,..,2901 |  | 2BHK | 564.1412 |  | 0 | 846.2119
|  | 1902,..,2902 |  | 2BHK | 589.5443 |  | 0 | 884.3164
|  | 1903,..,2903 |  | 2BHK | 589.5443 |  | 0 | 884.3164
|  | 1904,..,2904 |  | 2.5BHK | 668.7673 |  | 0 | 1003.151
|  | 1905,..,2905 |  | Refuge Area
|  | 1906,..,2906 |  | 2.5BHK | 668.7673 |  | 0 | 1003.151
|  | 1907,..,2907 |  | 2BHK | 646.2706 |  | 0 | 969.4058
|  | 1908,..,2908 |  | 2BHK | 646.2706 |  | 0 | 969.4058
|  | 1909,..,2909 |  | 1.5BHK | 490.6231 |  | 0 | 735.9347
Building No.36
Basement Floor for Parking
Ground Floor for Parking
1st Floor
1st Floor |  | 101 |  | 2BHK | 561.7732 |  | 0 | 842.6597
|  | 102 |  | 1BHK | 441.0011 |  | 0 | 661.5016 | 40.647
|  | 103 |  | 1BHK | 441.0011 |  | 0 | 661.5016
|  | 104 |  | Double Height
|  | 105 |  | 3BHK | 752.1883 |  | 0 | 1128.2825
|  | 106 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686
|  | 107 |  | 2BHK | 636.3677 |  | 0 | 954.5515
|  | 108 |  | 2BHK | 636.3677 |  | 0 | 954.5515
|  | 109 |  | 1.5BHK | 488.6856 |  | 0 | 733.0284
2nd to 7th, 9th to 13th & 15th Floor
2nd to 7th, 9th to 13th & 15th Floor |  | 201,..,1501 |  | 2BHK | 561.7732 |  | 0 | 842.6597
|  | 202,..,1502 |  | 2BHK | 587.4991 |  | 0 | 881.2487
|  | 203,..,1503 |  | 2BHK | 587.4991 |  | 0 | 881.2487
|  | 204,..,1504 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686
|  | 205,..,1505 |  | 3BHK | 752.1883 |  | 0 | 1128.2825
|  | 206,..,1506 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686
|  | 207,..,1507 |  | 2BHK | 636.3677 |  | 0 | 954.5515
|  | 208,..,1508 |  | 2BHK | 636.3677 |  | 0 | 954.5515
|  | 209,..,1509 |  | 1.5BHK | 488.6856 |  | 0 | 733.0284
8th & 14th Floor (Part Refuge Area)
8th & 14th Floor (Part Refuge Area) |  | 801 & 1401 |  | 2BHK | 561.7732 |  | 0 | 842.6597
|  | 802 & 1402 |  | 2BHK | 587.4991 |  | 0 | 881.2487
|  | 803 & 1403 |  | 2BHK | 587.4991 |  | 0 | 881.2487
|  | 804 & 1404 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686
|  | 805 & 1405 |  | Refuge Area
|  | 806 & 1406 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686
|  | 807 & 1407 |  | 2BHK | 636.3677 |  | 0 | 954.5515
|  | 808 & 1408 |  | 2BHK | 636.3677 |  | 0 | 954.5515
|  | 809 & 1409 |  | 1.5BHK | 488.6856 |  | 0 | 733.0284
16th to 18th, 20th to 23rd, 25th to 28th & 30th to 32nd Floor
16th to 18th, 20th to 23rd, 25th to 28th & 30th to 32nd Floor |  | 1601,..,3201 |  | 2BHK | 564.1412 |  | 0 | 846.2119
|  | 1602,..,3202 |  | 2BHK | 589.5443 |  | 0 | 884.3164
|  | 1603,..,3203 |  | 2BHK | 589.5443 |  | 0 | 884.3164
|  | 1604,..,3204 |  | 2.5BHK | 668.7673 |  | 0 | 1003.151
|  | 1605,..,3205 |  | 3BHK | 759.2926 |  | 0 | 1138.9388
|  | 1606,..,3206 |  | 2.5BHK | 668.7673 |  | 0 | 1003.151
|  | 1607,..,3207 |  | 2BHK | 646.2706 |  | 0 | 969.4058
|  | 1608,..,3208 |  | 2BHK | 646.2706 |  | 0 | 969.4058
|  | 1609,..,3209 |  | 1.5BHK | 490.6231 |  | 0 | 735.9347
19th, 24th & 29th Floor (Part Refuge Area)
19th, 24th & 29th Floor (Part Refuge Area) |  | 1901,..,2901 |  | 2BHK | 564.1412 |  | 0 | 846.2119
|  | 1902,..,2902 |  | 2BHK | 589.5443 |  | 0 | 884.3164
|  | 1903,..,2903 |  | 2BHK | 589.5443 |  | 0 | 884.3164
|  | 1904,..,2904 |  | 2.5BHK | 668.7673 |  | 0 | 1003.151
|  | 1905,..,2905 |  | Refuge Area
|  | 1906,..,2906 |  | 2.5BHK | 668.7673 |  | 0 | 1003.151
|  | 1907,..,2907 |  | 2BHK | 646.2706 |  | 0 | 969.4058
|  | 1908,..,2908 |  | 2BHK | 646.2706 |  | 0 | 969.4058
|  | 1909,..,2909 |  | 1.5BHK | 490.6231 |  | 0 | 735.9347
Building No.37
Basement Floor for Parking
Ground Floor for Parking
1st Floor
1st Floor |  | 1 |  | 2BHK | 523.3457 |  | 0 | 785.0185
1st Floor |  | 2 |  | 1BHK | 441.0011 |  | 0 | 661.5016
1st Floor |  | 3 |  | 1BHK | 441.0011 |  | 0 | 661.5016
1st Floor |  | 4 |  | Society Office
1st Floor |  | 5 |  | 2BHK | 624.6349 |  | 0 | 936.9524
1st Floor |  | 6 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686
1st Floor |  | 7 |  | 2BHK | 643.4719 |  | 0 | 965.2079
1st Floor |  | 8 |  | 2BHK | 643.4719 |  | 0 | 965.2079
1st Floor |  | 9 |  | 1.5BHK | 488.6856 |  | 0 | 733.0284
2nd to 7th, 9th to 13th & 15th Floor
2nd to 7th, 9th to 13th & 15th Floor |  | 1 |  | 2BHK | 523.3457 |  | 0 | 785.0185 | [5 empty] | 201,..,1501 | 201 | 1501
2nd to 7th, 9th to 13th & 15th Floor |  | 2 |  | 2BHK | 587.4991 |  | 0 | 881.2487 | [5 empty] | 202,..,1502 | 202 | 1502
2nd to 7th, 9th to 13th & 15th Floor |  | 3 |  | 2BHK | 587.4991 |  | 0 | 881.2487 | [5 empty] | 203,..,1503 | 203 | 1503
2nd to 7th, 9th to 13th & 15th Floor |  | 4 |  | 2.5BHK | 646.2706 |  | 0 | 969.4058 | [5 empty] | 204,..,1504 | 204 | 1504
2nd to 7th, 9th to 13th & 15th Floor |  | 5 |  | 3BHK | 732.2749 |  | 0 | 1098.4124 | [5 empty] | 205,..,1505 | 205 | 1505
2nd to 7th, 9th to 13th & 15th Floor |  | 6 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686 | [5 empty] | 206,..,1506 | 206 | 1506
2nd to 7th, 9th to 13th & 15th Floor |  | 7 |  | 2BHK | 643.4719 |  | 0 | 965.2079 | [5 empty] | 207,..,1507 | 207 | 1507
2nd to 7th, 9th to 13th & 15th Floor |  | 8 |  | 2BHK | 643.4719 |  | 0 | 965.2079 | [5 empty] | 208,..,1508 | 208 | 1508
2nd to 7th, 9th to 13th & 15th Floor |  | 9 |  | 1.5BHK | 435.4038 |  | 0 | 653.1057 | [5 empty] | 209,..,1509 | 209 | 1509
8th & 14th Floor (Part Refuge Area)
8th & 14th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 523.3457 |  | 0 | 785.0185 | [5 empty] | 801,..,1401 | 801 | 1401
8th & 14th Floor (Part Refuge Area) |  | 2 |  | 2BHK | 587.4991 |  | 0 | 881.2487 | [5 empty] | 802,..,1402 | 802 | 1402
8th & 14th Floor (Part Refuge Area) |  | 3 |  | 2BHK | 587.4991 |  | 0 | 881.2487 | [5 empty] | 803,..,1403 | 803 | 1403
8th & 14th Floor (Part Refuge Area) |  | 4 |  | 2.5BHK | 646.2706 |  | 0 | 969.4058 | [5 empty] | 804,..,1404 | 804 | 1404
8th & 14th Floor (Part Refuge Area) |  | 5 |  | Refuge Area | [9 empty] | 805,..,1405 | 805 | 1405
8th & 14th Floor (Part Refuge Area) |  | 6 |  | 2.5BHK | 665.6458 |  | 0 | 998.4686 | [5 empty] | 806,..,1406 | 806 | 1406
8th & 14th Floor (Part Refuge Area) |  | 7 |  | 2BHK | 643.4719 |  | 0 | 965.2079 | [5 empty] | 807,..,1407 | 807 | 1407
8th & 14th Floor (Part Refuge Area) |  | 8 |  | 2BHK | 643.4719 |  | 0 | 965.2079 | [5 empty] | 808,..,1408 | 808 | 1408
8th & 14th Floor (Part Refuge Area) |  | 9 |  | 1.5BHK | 435.4038 |  | 0 | 653.1057 | [5 empty] | 809,..,1409 | 809 | 1409
16th & 17th Floor
16th & 17th Floor |  | 1 |  | 2BHK | 525.6061 |  | 0 | 788.4092 | [5 empty] | 1601,..,1701 | 1601 | 1701
16th & 17th Floor |  | 2 |  | 2BHK | 589.5443 |  | 0 | 884.3164 | [5 empty] | 1602,..,1702 | 1602 | 1702
16th & 17th Floor |  | 3 |  | 2BHK | 589.5443 |  | 0 | 884.3164 | [5 empty] | 1603,..,1703 | 1603 | 1703
16th & 17th Floor |  | 4 |  | 2.5BHK | 649.3921 |  | 0 | 974.0882 | [5 empty] | 1604,..,1704 | 1604 | 1704
16th & 17th Floor |  | 5 |  | 3BHK | 740.2403 |  | 0 | 1110.3604 | [5 empty] | 1605,..,1705 | 1605 | 1705
16th & 17th Floor |  | 6 |  | 2.5BHK | 668.7673 |  | 0 | 1003.151 | [5 empty] | 1606,..,1706 | 1606 | 1706
16th & 17th Floor |  | 7 |  | 2BHK | 654.0206 |  | 0 | 981.031 | [5 empty] | 1607,..,1707 | 1607 | 1707
16th & 17th Floor |  | 8 |  | 2BHK | 654.0206 |  | 0 | 981.031 | [5 empty] | 1608,..,1708 | 1608 | 1708
16th & 17th Floor |  | 9 |  | 1.5BHK | 490.5155 |  | 0 | 735.7732 | [5 empty] | 1609,..,1709 | 1609 | 1709
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Tower 31 to 33 = Construction work is in process at the time of Visit. Internal visit was not allowed Tower 34 to 37 = Construction work is the same as last visit (dtd.10/04/2025), but work is in process at the time of the visit. (Slow Speed). 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet. 5. We have considered rate by verifying it from market inquiry. 6. Car parking is subjected to authentic documentation. 7. Tower No.33 & 34 - We have updated approved floor plan & CC(on 27/09/2021). 8. Tower No.35 & 36 - We have updated approved floor plan & CC(on 30/12/2021). 9. Tower No.37 - We have updated approved floor plan & CC(on 28/03/2022). 10. Please provide latest layout plan.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Runwal Gardens Phase IV (T31 to T37)
Project Site Address |  |  | : | Runwal Gardens Phase 4, Village Usarghar, Kalyan Shilphata Road, Dombivli, Kalyan, Thane.
Site Visit Date & Time |  |  | : | 04/07/2025 at 10:05 AM
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Gangaram parshuram Lambore | Authorized Signatory Name & Signature | :

## Sheet1
Building/Tower & Floor | Flat/Shop No. | Description | Gross Carpet area | Attached Terrace area | Saleable area (50% Loading)
Residential Area Details :
Building & Wing | No. of Units | Total Carpet Area |  | Total Saleable Area
Building No.31 | 314 | 161329.4327 |  | 241994.149
Building No.32 | 314 | 155372.7427 |  | 233059.1141
Total | 628 | 316702.1754 |  | 475053.2631
Building details Floor Wise
Details of Flats in Building
Building/Tower & Floor | Flat/Shop No. | Description | Gross Carpet area | Attached Terrace area | Saleable area (50% Loading)
Building No.31
Ground Floor for Parking
1st Floor
1st Floor | 101 | 1BHK | 418.7196 | 0 | 628.0794
1st Floor | 102 | 1BHK | 369.4205 | 0 | 554.1307
1st Floor | 103 | 1BHK | 369.4205 | 0 | 554.1307
1st Floor | 104 | 2BHK | 484.2724 | 0 | 726.4085
1st Floor | 105 | Double Height
1st Floor | 106 | 2BHK | 533.5715 | 0 | 800.3572
1st Floor | 107 | 1BHK | 427.869 | 0 | 641.8035
1st Floor | 108 | 3BHK | 794.1679 | 0 | 1191.2519
1st Floor | 109 | 2BHK | 619.7911 | 0 | 929.6867
1st Floor | 110 | 1BHK | 418.7196 | 0 | 628.0794
2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor | 201,..,3201 | 1BHK | 418.7196 | 0 | 628.0794
| 202,..,3202 | 2BHK | 505.1545 | 0 | 757.7318
| 203,..,3203 | 2BHK | 505.1545 | 0 | 757.7318
| 204,..,3204 | 2BHK | 484.2724 | 0 | 726.4085
| 205,..,3205 | 1BHK | 421.1953 | 0 | 631.793
| 206,..,3206 | 2BHK | 533.5715 | 0 | 800.3572
| 207,..,3207 | 1BHK | 427.869 | 0 | 641.8035
| 208,..,3208 | 3BHK | 794.1679 | 0 | 1191.2519
| 209,..,3209 | 2BHK | 619.7911 | 0 | 929.6867
| 210,..,3210 | 1BHK | 418.7196 | 0 | 628.0794
8th, 14th, 19th, 24th & 29th Floor
8th, 14th, 19th, 24th & 29th Floor | 801,..,2901 | 1BHK | 418.7196 | 0 | 628.0794
| 802,..,2902 | 2BHK | 505.1545 | 0 | 757.7318
| 803,..,2903 | 2BHK | 505.1545 | 0 | 757.7318
| 804,..,2904 | 2BHK | 484.2724 | 0 | 726.4085
| 805,..,2905 | 1BHK | 421.1953 | 0 | 631.793
| 806,..,2906 | 2BHK | 533.5715 | 0 | 800.3572
| 807,..,2907 | 1BHK | 427.869 | 0 | 641.8035
| 808,..,2908 | 3BHK | 794.1679 | 0 | 1191.2519
| 809,..,2909 | 2BHK | 619.7911 | 0 | 929.6867
| 810,..,2910 | Refuge Area
Building No.32
Ground Floor for Parking
1st Floor
1st Floor | 101 | 1BHK | 424.5322 | 0 | 636.7982
1st Floor | 102 | 1BHK | 373.9414 | 0 | 560.912
1st Floor | 103 | 1BHK | 373.9414 | 0 | 560.912
1st Floor | 104 | 2BHK | 484.2724 | 0 | 726.4085
1st Floor | 105 | 2BHK | 530.2346 | 0 | 795.352
1st Floor | 106 | 1BHK | 421.1953 | 0 | 631.793
1st Floor | 107 | 1BHK | 421.1953 | 0 | 631.793
1st Floor | 108 | 2BHK | 469.5257 | 0 | 704.2885
1st Floor | 109 | 2BHK | 469.5257 | 0 | 704.2885
1st Floor | 110 | Double Height
2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor | 201,..,3201 | 1BHK | 424.5322 | 0 | 636.7982
| 202,..,3202 | 2BHK | 506.8768 | 0 | 760.3151
| 203,..,3203 | 2BHK | 506.8768 | 0 | 760.3151
| 204,..,3204 | 2BHK | 484.2724 | 0 | 726.4085
| 205,..,3205 | 2BHK | 530.2346 | 0 | 795.352
| 206,..,3206 | 1BHK | 421.1953 | 0 | 631.793
| 207,..,3207 | 1BHK | 421.1953 | 0 | 631.793
| 208,..,3208 | 2BHK | 621.621 | 0 | 932.4315
| 209,..,3209 | 2BHK | 621.621 | 0 | 932.4315
| 210,..,3210 | 1BHK | 412.0459 | 0 | 618.0689
8th, 14th, 19th, 24th & 29th Floor
8th, 14th, 19th, 24th & 29th Floor | 801,..,2901 | 1BHK | 424.5322 | 0 | 636.7982
| 802,..,2902 | 2BHK | 506.8768 | 0 | 760.3151
| 803,..,2903 | 2BHK | 506.8768 | 0 | 760.3151
| 804,..,2904 | 2BHK | 484.2724 | 0 | 726.4085
| 805,..,2905 | 2BHK | 530.2346 | 0 | 795.352
| 806,..,2906 | 1BHK | 421.1953 | 0 | 631.793
| 807,..,2907 | 1BHK | 421.1953 | 0 | 631.793
| 808,..,2908 | 2BHK | 621.621 | 0 | 932.4315
| 809,..,2909 | 2BHK | 621.621 | 0 | 932.4315
| 810,..,2910 | Refuge Area

## 31
Particulars | totaL floor | 32
| total | completed
plinth | 10 | 1 |  | 10
slab | total slab | completed slab |  | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 33 | 0 |  | 0 | Progress |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | 0 | Recommended |  |  | 21 | 0 | 0 | 0 | 0 | 0 | 0
| 32 | 0 |  | 0
plaster | Total Floor | completed Floor |  | 0
| 32 | 0 |  | 0
Flooring | Total Floor | completed Floor
| 32 | 0 |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 1 | 21
| 32 | 0 |  |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 32 | 0 |  |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 1% | 21%
Excavation in process |  | 1% | 2%
Excavation Completed |  | 2% | 4%
Footing in Process |  | 4% | 8%
Footing Completed |  | 5% | 15%
Plinth in process |  | 7% | 20%
Plinth completed |  | 10% | 30%

## 32
Particulars | totaL floor | 32
| total | completed
plinth | 10 | 0 |  | 0
slab | total slab | completed slab |  | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 33 | 0 |  | 0 | Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | 0 | Recommended |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
| 32 | 0 |  | 0
plaster | Total Floor | completed Floor |  | 0
| 32 | 0 |  | 0
Flooring | Total Floor | completed Floor
| 32 | 0 |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 0 | 20
| 32 | 0 |  |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 32 | 0 |  |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 0% | 20%
Excavation in process |  | 1% | 2%
Excavation Completed |  | 2% | 4%
Footing in Process |  | 4% | 8%
Footing Completed |  | 5% | 15%
Plinth in process |  | 7% | 20%
Plinth completed |  | 10% | 30%

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing.c |  |  |  |  | #DIV/0!
housing.c |  |  |  |  | #DIV/0!
housing.c |  |  |  |  | #DIV/0!
housing.c |  |  |  |  | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted