## report
APF Report Format | [11 empty] | Old Int date
Name of Valuation Agency |  |  | : | V.S.JADON & CO VALUERS LLP |  | Date of Technical Initiation |  | 2025-07-02 |  | 2025-07-22 |  | 2025-04-23
Project Name |  |  | : | The Highlands at Godrej City, Panvel (Tower 4 & 5) |  | Date of Site Visit |  | 04/07/2025 at 10:51AM | 70 | > 90
Name of the person met at site & Contact No. |  |  | : | NA |  | Date of Report Release |  | 05/07/2025 | Mr.Shantanu - 7262030139
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | Godrej Group | Developer Name | : | Caroa Properties LLP
Developer Office Address |  |  | : | Office at Godrej One, 5th floor, Pirojshanagar, Eastern Express Highway, Vikhroli (East), Mumbai 400 079
Project Address | : | As per ARF | : | Integrated Township Project (ITP) on land bearing S.No.38/0, 74/0, 36/1, 73/0, 30/1, 75/0, 42/4, 42/1, 42/3, 32/2, 39/0, 43/0, 44/4, 70/1, 70/2, 72/0, 76/1, 76/2, 68/0, 81/2A, 81/2B, 40/0, 47/2, 50/12, 50/13, 69/0, 41/1, 41/2, 44/3, 47/1, 71/0, 36/2, 37/1, 37/2, 78/0 of village -Khanavale, Taluka-Panvel, Dist -Raigad, And S.No.6/1, 6/5, 7/1, 6/6, 7/2, 7/3A, 7/4, 5/2B, 9/2, 4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 7/3B, 7/B/1, 7/B/2, 7B/3, 7B/4, 7B/5, 7B/6, 7B/7, 7C/1, 7C/2, 7C/3, 7C/4, 7C/5, 7C/6, 7C/7, 7C/8, 8/3A/1, 8/3A/2, 8/3A/3, 8/3A/4, 8/3A/5, 8/3A/6, 8/3A/7, 8/3A/8, 8/3A/9, 8/3A/10, 8/D/1, 8/D/2, 8/D/3, 8/D/4, 8/D/5, 8/D/6, 8/D/7, 8/D/8, 8/B/1, 8/B/2, 8/B/3, 8/B/4, 8/B/5, 8/D/6, 8/D/7, 8/D/8, 8/B/1, 8/B/2, 8/B/3, 8/B/4, 8/B/5, 8/B/6, 8/C/1, 8/C/2, 8/1A/1, 8/1A/2, 8/1A/3, 8/1A/4, 8/1A/5, 8/1A/6, 9/B/1, 9/B/2, 9/B/3, 9/B/4, 9/B/5, 9/B/6, 9/B/7, 9/B/8, 9/D/1, 9/D/2, 9/D/3, 9/D/4, 9/D/5, 9/D/6, 9/D/7, 9/D/8, 9/C/1, 9/C/2, 9/C/3, 9/C/4, 9/C/5, 9/C/5, 9/C/6, 9/C/7, 9/C/8, 9/C/9, 7/C/9, 7/C/10 of village Talegaon, Taluka-Khalapur, Dist-Raigad - 410221
| : | As per Legal Documents | : | S. Nos.4/1,4/2,4/3pt,4/4pt,4/5pt,4/6,5pt,6/6pt at Village- Talegaon, Taluka- Khalapur, Dist- Raigad - 410221
| : | As per Actual at site | : | The Highlands at Godrej City situated at Village- Talegaon, Taluka- Khalapur, Dist- Raigad - 410221
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans
General Details
Status of Holding |  |  | : | Freehold | Name of Municipal Corporation/Authority | : | Maharashtra State Road Development Corporation. (MSRDC)
RERA Registration No. |  |  | : | Tower 4 = P52000030367 Tower 5 = P52000049669 | RERA Registration Validity | : | Tower 4 = 31/12/2026 Tower 5 = 31/05/2029
Project Launch Date |  |  | : | Tower 4 = June 2021 Tower 5 = January 2023 | Construction Start Date | : | Tower 4 = 17/08/2021 Tower 5 = 22/02/2023
Proposed Date of Completion (As per RERA) |  |  | : | Tower 4 = 31/12/2026 Tower 5 = 31/05/2029 | Developer Bank Name (As per RERA) | : | Axis Bank IFSC Code - UTIB0000004
Project Type (Mixed, Residential, Comm.) |  |  | : | Residential | Plot Area (In Sq.Mt) | : | 431675.64
Permissible Built up Area (In Sq.Mt) |  |  | : | 333155 | Proposed Built up Area (In Sq.Mt) | : | 174228.302
Free/ Fungible FSI |  |  | : | 0.6 | Total Number of Units Planned | : | 591 |  | 292+299
Total Number of Units Approved |  |  | : | 587 | If Mixed, No. of Commercial Units | : | -
Latitude, Longitude |  |  | : | 18.927472,73.183503
Location Link |  |  | : | https://goo.gl/maps/A7kCtSnFsg7HVfhp8?coh=178572&entry=tt
Extra Amenities available |  |  | : | Kids Pool, Gymnasium, Kids Play Area, Badminton Court, Barbeque Counter, Basketball Court, Board Games, Cafe Style Sitting Area, Community Stitting Area, Creche, Cricket Box, Indoor Games Room, Jogging-walking Track, Library, Skating, Squash Court, Multipurpose Court
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area |  |  | : | Developing | Class of Locality | : | Middle class
Type of Road |  |  | : | Bitumen | Width of the Road in ft. | : | 9ft
Electrification/Electric poles observed |  |  | : | Yes | Distance from Bus stand (Km) | : | About 6.6KM from Rasayani Bus Depot
Distance from the nearest School (Km) |  |  | : | About 3.7 KM from St. Wilfred's School, Panvel | Distance from Hospital (Km) | : | About 5 km form Mangal Murti Clinic Dr Raut.
Distance from the Main Market (Km) |  |  | : | 1. Approx. 2KM from Village Market. 2. Approx. 10KM from Panvel Main Market. | Distance from nearest Railway/Metro/Airport (Km) | : | 5.4KM from Somatne Railway Station 10.5KM from Panvel Railway Station
Water Supply |  |  | : | Being Provisioned | Electricity Supply | : | Being Provisioned
Drainage Connection |  |  | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Building | Road | Tower 3 |  | Tower 5
As per Site / Actual |  |  | : | Open Plot | Open Plot | Road |  | Open Plot
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  |  | Type (Sale/Rehab) |  | No. of Floors Planned |  | No. of Floors Approved
Tower No.4 (Type B) |  |  | Sale |  | B0/P0 + B1/P1 to B2/P2 + G + 1st to 38th Floor |  | B0/P0 + B1/P1 to B2/P2 + G + 1st to 38th Floor
Tower No.5 (Type C & A) |  |  | Sale |  | G + 1st to 41st Floor |  | G + 1st to 41st Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans |  |  | : | Under Construction | LOI/IOD Details | : | MSRDC/SPA/ITP-3/CC/2020/502 Dated: 06/10/2020.
CC Details |  |  | : | MSRDC/SPA/ITP-3/RZ-5/Amended CC/2023/1178 Dated: 07/07/2023. Valid Up to: Tower No.4 = B + B1 to B2 + Gr + 1st to 38th Floor Tower No.5 = Gr + 1st to 41st Floor | Approved Plan Details | : | MSRDC/SPA/ITP-3/CC/2020/502 Dated: 06/10/2020.
Environmental Clearance Details |  |  | : | SEIAA-EC-0000002285 Dated : 25/06/2020. | Airport Authority Clearance Details | : | NOC for Height Clearance NAVI/West/B/02820/450961 Dated : 12/03/2020. Valid upto : 10/03/2028.
Tree NOC details |  |  | : | JVK No. B/20/JMIN/970/2019-20 Dated : 03/12/2019. | Other NOC Details | : | Fire NOC Dated : 29/08/2020. (By MFS)
Construction Status
Tower No.4 = B0/P0 + B1/P1 & B2/P2 + G + 1st to 38th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 31 Slab, Brickwork upto 29 Floor, Internal Plaster upto 23.2 Floor, External Plaster upto 23.2 Floor Completed
|  |  |  | 3 | 1 |  | 0 | 38 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.5
Excavation |  | 38 |  | 100% | 51.74% |  | Excavation work Completed. Plinth work completed, RCC upto 31 Slab, Brickwork upto 29 Floor, Internal Plaster upto 23.2 Floor, External Plaster upto 23.2 Floor Completed |  | Excavation in process | 19
Plinth |  | 38 |  | 100% |  |  |  |  | Excavation Completed | 38
RCC (Including podiums) |  | 31 |  | 79.49% |  |  |  |  | Footing in Process | 7.6
Brickwork |  | 29 |  | 76.32% |  |  |  |  | Footing Completed | 15.2
Internal Plaster |  | 23.2 |  | 61.05% |  |  |  |  | Basement 1 | 22.8
External Plaster |  | 23.2 |  | 61.05% |  |  |  |  | Basement 2 | 30.4
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 38 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower No. 5 = Gr + 1st to 41st Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 10 Slab, Brickwork upto 9 Floor, Internal Plaster upto 7.2 Floor, External Plaster upto 7.2 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 41 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 10.25
Excavation |  | 41 |  | 100% | 32.93% |  | Excavation work Completed. Plinth work completed, RCC upto 10 Slab, Brickwork upto 9 Floor, Internal Plaster upto 7.2 Floor, External Plaster upto 7.2 Floor Completed |  | Excavation in process | 20.5
Plinth |  | 41 |  | 100% |  |  |  |  | Excavation Completed | 41
RCC (Including podiums) |  | 10 |  | 23.81% |  |  |  |  | Footing in Process | 10.25
Brickwork |  | 9 |  | 21.95% |  |  |  |  | Footing Completed | 20.5
Internal Plaster |  | 7.2 |  | 17.56% |  |  |  |  | Basement 1 | 0
External Plaster |  | 7.2 |  | 17.56% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 30.75
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 41 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Overall Project Completion % | [6 empty] | 42.33%
Market Value
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA/PlotArea) | : | CA |  |  | Rate matched with Tower 6 on 08/01/2025 by gaurav
Rate Per Sq. Ft. (on Carpet area) |  |  | : | 12000/- to 13700/- | Floor Rise Details Per Sq. Ft. (on Carpet area) | : | 60/- from 2nd Floor |  |  | 11000 to 12000 | Rushil | 2023-01-02 | verbal
Car Parking Charges |  |  | : | 500000/- | Other Charges | : | As applicable and documented.
Guideline Values & Distress Value
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 410.63
Government Guideline/ Circle rate for Flat Built up(Rs per sqft) | [5 empty] | : | 4580.08
Distress Value (Rs. Per sqft) | [5 empty] | : | 6400
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Tower 4 |  | Sale |  | Flats | 292 |  | 252219.7639 | 403551.6222
Tower 5 |  | Sale |  | Flats | 295 |  | 169115.4752 | 270584.7603 |  |  |  |  | 40
Total |  | - |  | - | 587 |  | 421335.2391 | 674136.3825
Details of Flats in Building | [14 empty] | 40
Building/Tower & Floor |  | Flat/Shop No. as per approved plan |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area (60% Loading)
RZ-5
Tower No.4
Basement 0 + Parking Floor 0 (Level 0.6 M)
Basement 1 + Parking Floor 1 (Level 3.75 M)
Basement 2 + Parking Floor 2 (Level 6.9 M)
Ground Floor + Parking Floor 3 (Level 10.050 M)
1st Floor + Parking Floor 4 + Amenities(Level 13.200 M)
1st Floor + Parking Floor 4 + Amenities(Level 13.200 M) |  | 1 |  | 3BHK | 1025.7656 |  | 0 | 1641.225
2nd Floor + Parking Floor 5 + Amenities(Level 16.35 M)
2nd Floor + Parking Floor 5 + Amenities(Level 16.35 M) |  | 1 |  | 3BHK | 1025.7656 |  | 0 | 1641.225
|  | 2 |  | 2BHK | 707.2093 |  | 0 | 1131.5349
|  | 3 |  | 2BHK | 707.2093 |  | 0 | 1131.5349
3rd Floor + Parking Floor 6 (Level 19.675 M)
3rd Floor + Parking Floor 6 (Level 19.675 M) |  | 1 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
|  | 2 |  | 2BHK | 707.2093 |  | 0 | 1131.5349
|  | 3 |  | 2BHK | 707.2093 |  | 0 | 1131.5349
|  | 4 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
|  | 5 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
|  | 6 |  | 2BHK | 653.053 |  | 0 | 1044.8847 |  | 292
|  | 7 |  | 2BHK | 653.053 |  | 0 | 1044.8847
|  | 8 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214 |  |  |  | 25 |  | 287
4th Floor (Level 22.825 M)
4th Floor (Level 22.825 M) |  | 1 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
|  | 2 |  | 2BHK | 707.2093 |  | 0 | 1131.5349
|  | 3 |  | 2BHK | 707.2093 |  | 0 | 1131.5349
|  | 4 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
|  | 5 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
|  | 6 |  | 2BHK | 653.053 |  | 0 | 1044.8847
|  | 7 |  | 2BHK | 653.053 |  | 0 | 1044.8847
|  | 8 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
5th Floor (Level 25.775 M)
5th Floor (Level 25.775 M) |  | 1 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
|  | 2 |  | 2BHK | 707.2093 |  | 0 | 1131.5349
|  | 3 |  | 2BHK | 707.2093 |  | 0 | 1131.5349
|  | 4 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
|  | 5 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
|  | 6 |  | 2BHK | 653.053 |  | 0 | 1044.8847
|  | 7 |  | 2BHK | 653.053 |  | 0 | 1044.8847
|  | 8 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
6th to 10th, 12th, 14th, 16th, 18th, 20th, 22nd, 24th, 26th, 28th, 30th, 32nd, 34th, 36th & 38th Floor
6th to 10th, 12th, 14th, 16th, 18th, 20th, 22nd, 24th, 26th, 28th, 30th, 32nd, 34th, 36th & 38th Floor |  | 1 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
|  | 2 |  | 2BHK | 707.2093 |  | 0 | 1131.5349
|  | 3 |  | 2BHK | 707.2093 |  | 0 | 1131.5349
|  | 4 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
|  | 5 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
|  | 6 |  | 2BHK | 653.053 |  | 0 | 1044.8847
|  | 7 |  | 2BHK | 653.053 |  | 0 | 1044.8847
|  | 8 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
11th, 13th, 15th, 17th, 19th, 21st, 23rd, 25th, 27th, 29th, 31st, 33rd, 35th & 37th Floor ( Part Refuge Area)
11th, 13th, 15th, 17th, 19th, 21st, 23rd, 25th, 27th, 29th, 31st, 33rd, 35th & 37th Floor ( Part Refuge Area) |  | 1 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
|  | 2 |  | 2BHK | 707.2093 |  | 0 | 1131.5349
|  | 3 |  | 2BHK | 707.2093 |  | 0 | 1131.5349
|  | 4 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
|  | 5 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
|  | 6 |  | 2BHK | 653.053 |  | 0 | 1044.8847
|  | 7 |  | 2BHK | 653.053 |  | 0 | 1044.8847
|  | 8 |  | 3BHK | 1047.3259 |  | 0 | 1675.7214
Tower No. 5 (Type C & A) | [8 empty] | FROM G TO 6TH = TYPE C
Ground Floor + Parking Floor 0 For Parking, Doubled Heighted Lobby, Amenity Room, Meter Room & Garbage Room | [8 empty] | ABOVE 7 = TYPE A
1st Floor + Parking Floor 1 For Parking, Doubled Heighted Lobby, Amenity Room, Letter Room & Residential
As per sale plan - 4 |  | 1 |  | 2BHK | 649.0843 |  | 0 | 1038.5348 |  |  |  | 10.764
2nd Floor + Parking Floor 2 For Parking, Drivers Room & Residential
As per sale plan - 4 |  | 1 |  | 2BHK | 649.0843 |  | 0 | 1038.5348
5 |  | 2 |  | 1BHK | 441.0194 |  | 0 | 705.631 |  |  |  |  | 29
6 |  | 3 |  | 1BHK | 442.9838 |  | 0 | 708.7741
7 |  | 4 |  | 2BHK | 709.1754 |  | 0 | 1134.6806
1 |  | 5 |  | Drivers Room
3rd Floor + Parking Floor 3 For Parking, Drivers Room & Residential
As per sale plan - 4 |  | 1 |  | 2BHK | 649.0843 |  | 0 | 1038.5348
5 |  | 2 |  | 1BHK | 441.0194 |  | 0 | 705.631
6 |  | 3 |  | 1BHK | 442.9838 |  | 0 | 708.7741
7 |  | 4 |  | 2BHK | 709.1754 |  | 0 | 1134.6806
1 |  | 5 |  | Drivers Room
4th Floor + Parking Floor 4 For Parking, Drivers Room & Residential
4 |  | 1 |  | 2BHK | 649.0843 |  | 0 | 1038.5348
5 |  | 2 |  | 1BHK | 441.0194 |  | 0 | 705.631
6 |  | 3 |  | 1BHK | 442.9838 |  | 0 | 708.7741
7 |  | 4 |  | 2BHK | 709.1754 |  | 0 | 1134.6806
1 |  | 5 |  | Drivers Room
5th Floor + Parking Floor 5 For Parking, Servant Toilet & Residential
4 |  | 1 |  | 2BHK | 649.0843 |  | 0 | 1038.5348
5 |  | 2 |  | 1BHK | 441.0194 |  | 0 | 705.631
6 |  | 3 |  | 1BHK | 442.9838 |  | 0 | 708.7741
7 |  | 4 |  | 2BHK | 709.1754 |  | 0 | 1134.6806
1 |  | 5 |  | Servant Toilet
6th Floor + Parking Floor 6 For Parking & Residential
3 |  | 1 |  | 2BHK | 664.7082 |  | 0 | 1063.5331
4 |  | 2 |  | 2BHK | 664.7082 |  | 0 | 1063.5331
5 |  | 3 |  | 1BHK | 454.8 |  | 0 | 727.68
6 |  | 4 |  | 1BHK | 454.8 |  | 0 | 727.68
7 |  | 5 |  | 2BHK | 721.5916 |  | 0 | 1154.5466
8 |  | 6 |  | 2BHK | 721.5916 |  | 0 | 1154.5466
7th Floor For Residential
3 |  | 1 |  | 2BHK | 664.7082 |  | 0 | 1063.5331
4 |  | 2 |  | 2BHK | 664.7082 |  | 0 | 1063.5331
5 |  | 3 |  | 1BHK | 454.8 |  | 0 | 727.68
6 |  | 4 |  | 1BHK | 454.8 |  | 0 | 727.68
7 |  | 5 |  | 2BHK | 721.5916 |  | 0 | 1154.5466
8 |  | 6 |  | 2BHK | 721.5916 |  | 0 | 1154.5466
8th Floor
1 |  | 1 |  | 1BHK | 454.8 |  | 0 | 727.68
2 |  | 2 |  | 1BHK | 454.8 |  | 0 | 727.68
3 |  | 3 |  | 2BHK | 664.7082 |  | 0 | 1063.5331
4 |  | 4 |  | 2BHK | 664.7082 |  | 0 | 1063.5331
5 |  | 5 |  | 1BHK | 454.8 |  | 0 | 727.68
6 |  | 6 |  | 1BHK | 454.8 |  | 0 | 727.68
7 |  | 7 |  | 2BHK | 721.5916 |  | 0 | 1154.5466
8 |  | 8 |  | 2BHK | 721.5916 |  | 0 | 1154.5466
9th Floor
1 |  | 1 |  | 1BHK | 454.8 |  | 0 | 727.68
2 |  | 2 |  | 1BHK | 454.8 |  | 0 | 727.68
3 |  | 3 |  | 2BHK | 664.7082 |  | 0 | 1063.5331
4 |  | 4 |  | 2BHK | 664.7082 |  | 0 | 1063.5331
5 |  | 5 |  | 1BHK | 454.8 |  | 0 | 727.68
6 |  | 6 |  | 1BHK | 454.8 |  | 0 | 727.68
7 |  | 7 |  | 2BHK | 721.5916 |  | 0 | 1154.5466
8 |  | 8 |  | 2BHK | 721.5916 |  | 0 | 1154.5466
10th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 33rd, 35th to 38th, 40th & 41st Floor
1 |  | 1 |  | 1BHK | 454.8 |  | 0 | 727.68
2 |  | 2 |  | 1BHK | 454.8 |  | 0 | 727.68
3 |  | 3 |  | 2BHK | 664.7082 |  | 0 | 1063.5331
4 |  | 4 |  | 2BHK | 664.7082 |  | 0 | 1063.5331
5 |  | 5 |  | 1BHK | 454.8 |  | 0 | 727.68
6 |  | 6 |  | 1BHK | 454.8 |  | 0 | 727.68
7 |  | 7 |  | 2BHK | 721.5916 |  | 0 | 1154.5466
8 |  | 8 |  | 2BHK | 721.5916 |  | 0 | 1154.5466
14th, 19th, 24th, 29th, 34th & 39th Floor (Part Refuge Area)
1 |  | 1 |  | 1BHK | 454.8 |  | 0 | 727.68
2 |  | 2 |  | 1BHK | 454.8 |  | 0 | 727.68
3 |  | Refuge Area
4 |  | 3 |  | 2BHK | 664.7082 |  | 0 | 1063.5331
5 |  | 4 |  | 1BHK | 454.8 |  | 0 | 727.68
6 |  | 5 |  | 1BHK | 454.8 |  | 0 | 727.68
7 |  | 6 |  | 2BHK | 721.5916 |  | 0 | 1154.5466
8 |  | 7 |  | 2BHK | 721.5916 |  | 0 | 1154.5466
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Tower 4 & 5 = Construction work was in process at the time of visit. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Deck Area + Balcony + Chajja. 5. We considered Flat rate as per Market Inquires. 6. Car parking is subjected to authentic documentation. 7. Construction details are collected from Mr. Micheal - 7710024861. 8.We have updated Approved floor plan & CC of Tower No.5 on (02/05/2023). 8. RZ-5 plot consist of 7 towers but on RERA site only 6 towers are registered.
Site & Building/Tower Photographs
Name of the Project |  |  | : | The Highlands at Godrej City, Panvel (Tower 4 & 5)
Project Site Address |  |  | : | The Highlands at Godrej City situated at Village- Talegaon, Taluka- Khalapur, Dist- Raigad - 410221
Site Visit Date & Time |  |  | : | 04/07/2025 at 10:51AM
Layout Plan
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Nitesh patil | Authorized Signatory Name & Signature | :
1
2
3
4
5
6
7
Tower 4
Tower 5
Tower 5
Tower 4
Tower 4
Tower 5
Tower 6

## T1
Particulars | totaL floor | 26
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 96.2963 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 27 | 26 | 0 | Progress |  |  | 10 | 38.5185 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 28.8889 | 0 | 0 | 0 | 0 | 0
| 26 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 26 | 0 | 0
Flooring | Total Floor | completed Floor
| 26 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 26 | 0 |  | RCC | 38.5185 | 28.8889
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 26 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 48.52% | 58.89%

## T2
Particulars | totaL floor | 27
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 85.7143 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 28 | 24 | 0 | Progress |  |  | 10 | 34.2857 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 25.7143 | 0 | 0 | 0 | 0 | 0
| 27 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 27 | 0 | 0
Flooring | Total Floor | completed Floor
| 27 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 27 | 0 |  | RCC | 34.2857 | 25.7143
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 27 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 44.29% | 55.71%