## Report
APF Report Format | [8 empty] | Old Int Date
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02 | 2025-04-23 | 2025-07-22
Project Name |  |  | : | Zenith (Tower No. 14) |  | Date & Time of Site Visit |  | 04/07/2025 at 11:06AM | 70 | < 90
Name of the person met at site & Contact No. |  |  | : | NA |  | Date of Report Release |  | 05/07/2025
Data from APF Request Form | [8 empty] | Mr.Akshay 9324767870
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | Dhruva Woollen Mills Pvt Ltd. | Developer Name | : | Dhruva Woollen Mills Pvt Ltd.
Developer Office Address |  |  | : | Aryabhatt Building, C G Compound, Kanjurmarg (East)
Project Address | : | As per ARF | : | ZENITH, Survey No. 51 Hissa No 1 To 15 Survey No 52 Hissa No 1 To 3 Survey No 53 At Thane (M Corp.), Thane, Thane, 400608
| : | As per Legal Documents | : | Zenith, Old Survey No.208(Pt) to 212(Pt), S.No. 215(Pt) to 220(Pt) & New Survey No.43, H.No.2,3,4A,4B, 4C, 4D, S.No.44 H.No.1, 2A, 2B, …, S.No.56 H.No.1 to 6, Balkum Road, Balkum Pada, Balkum, Thane West, Thane, Pin Code - 400607. | [5 empty] | Old Survey No.208(Pt) to 212(Pt), S.No. 215(Pt) to 220(Pt) & New Survey No.43, H.No.2,3,4A,4B, 4C, 4D, S.No.44 H.No.1, 2A, 2B, … , S.No.56 H.No.1 to 6
| : | As per Actual at site | : | Opposite Runwal Garden City, Balkum Pada, Majiwada, Thane, Maharashtra 400608
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate, NOC
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Thane Municipal Corporation
RERA Registration No. | : | P51700046734 |  |  | RERA Registration Validity | : | 2028-09-30
Project Launch Date | : | 2022-03-07 |  |  | Construction Start Date | : | 2022-03-07
Proposed Date of Completion (As per RERA) | : | 2028-09-30 |  |  | Developer Bank Name (As per RERA) | : | ICICI BANK ICIC0000740
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 108416
FSI/FAR Permissible | : | 1.1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 80345.28
Permissible Built up Area (In Sq.Mt) | : | 74827.5 |  |  | Total Number of Units Planned | : | As per RERA Site Flats = 289
Total Number of Units Approved | : | Flats = 262 |  |  | If Mixed, No. of Commercial Units | : | Shop = NA
Latitude, Longitude | : | 19.223378, 72.988604
Location Link | : | https://goo.gl/maps/NN7Gnnd7SWETnC3t8
Extra Amenities available | : | Swimming Pool, Library, Banquet Hall, Childrens Play Area, Indoor Games, Barbeque Deck, Mini Theatre, Jogging Area, Meditation Area, Gym, SeniOR Citizen Area, CCTV.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle/Upper
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 0.100Km From Runwal Garden City Bus Stop
Distance from the nearest School (Km) | : | About 0.450KM from Vidya Prasarak's Vidyalaya Balkum & Jr College |  |  | Distance from Hospital (Km) | : | About 0.700Km from Ashtavinayak Hospital
Distance from the Main Market (Km) | : | 1. Approx 0.300KM from Balaji Super Market. 2. Approx 2.1KM from Sunup Market. |  |  | Distance from Railway Station (Km) | : | 5.9KM from Thane Railway Station 6.9KM from Kalva Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Substation | Internal Road | Green Area |  | Internal Road
As per Site / Actual |  |  | : | MSEB Substation | Internal Road | Open Area |  | Internal Road
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Building No.14 |  | Sale |  | 4B + Gr/St + 1st to 45th Floor |  |  | 4B + Gr/St + 1st to 45th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | S05/0106/16(88/425)/TMC/TD-DP/TPS/3989/22 Date: 07/03/2022
CC Details | : | S05/0106/16(88/425)/TMC/TD-DP/TPS/3989/22 Date: 07/03/2022 Valid Up to: Building No.14 = 4B + St + 1st to 45th Floor |  |  | Approved Plan Details | : | S05/0106/16(88/425)/TMC/TD-DP/TPS/3989/22 Date: 07/03/2022
Environmental Clearance Details | : | Date: |  |  | Airport Authority Clearance Details | : | Date:
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
Construction Status
Construction Status
Building No. = G + 20th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 20 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5
Excavation |  | 20 |  | 100% | 20% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 10
Plinth |  | 20 |  | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 4
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 8
Door & Window Frames |  | 0 |  | 0% |  |  |  |  | Basement 1 | 12
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 16
Ext.Plaster |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Plumb.& Electri. |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Painting |  | 0 |  | 0% |  |  |  |  | Plinth completed | 20
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | #REF!
Building No. 14 = 4B + Gr/St + 1st to 45th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Footing work is process
|  |  |  | 3 | 1 |  | 0 | 45 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 11.25
Excavation |  | 45 |  | 100% | 15% |  | Excavation work Completed. Footing work is process |  | Excavation in process | 22.5
Plinth |  | 9 |  | 20% |  |  |  |  | Excavation Completed | 45
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 9
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 18
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 27
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 36
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 45
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building No. 14 = 4B + Gr/St + 1st to 45th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 4 Floor Completed
|  |  |  | 4 | 1 |  | 0 | 45 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 11.25
Excavation |  | 45 |  | 100% | 30.34% |  | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 4 Floor Completed |  | Excavation in process | 22.5
Plinth |  | 45 |  | 100% |  |  |  |  | Excavation Completed | 45
RCC (Including podiums) |  | 9 |  | 19.57% |  |  |  |  | Footing in Process | 7.5
Brickwork |  | 4 |  | 8.889% |  |  |  |  | Footing Completed | 15
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 22.5
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 30
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 37.5
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 45 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 17500 to 18500 | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  |  | : | 600000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 2814.9387
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 10841.6945
Distress Value (Rs. Per sqft) | [5 empty] | : | 2251.9509
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Buiulding No.14 |  | Sale |  | Flats | 262 |  | 229902.7648 | 344854.1472
Total |  | - |  | - | 262 |  | 229902.7648 | 344854.1472
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
50%
Building No.14
Ground Floor For Fitness Center, Meter Room, Creche, Society Office, Drivers Room & Parking | [9 empty] | 10.764
1st Floor For Residential
1st Floor For Residential |  | 1 |  | 2 | 647.3674 |  | 0 | 971.0511 |  | 60.1419
1st Floor For Residential |  | 2 |  | 2 | 647.3674 |  | 0 | 971.0511
1st Floor For Residential |  | 3 |  | 3 | 1090.4352 |  | 0 | 1635.6528
1st Floor For Residential |  | 4 |  | 2 | 770.3407 |  | 0 | 1155.5111
1st Floor For Residential |  | 5 |  | 2 | 770.3407 |  | 0 | 1155.5111
1st Floor For Residential |  | 6 |  | 3 | 1156.9309 |  | 0 | 1735.3963 |  | 92.7575
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th to 42nd, 44th & 45th Floor
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th to 42nd, 44th & 45th Floor |  | 1 |  | 2 | 737.9788 |  | 0 | 1106.9681
|  | 2 |  | 2 | 737.9788 |  | 0 | 1106.9681
|  | 3 |  | 3 | 1113.6155 |  | 0 | 1670.4232
|  | 4 |  | 2 | 770.3407 |  | 0 | 1155.5111
|  | 5 |  | 2 | 770.3407 |  | 0 | 1155.5111
|  | 6 |  | 3 | 1156.9309 |  | 0 | 1735.3963
8th, 13th, 18th, 23rd, 28th, 33rd, 38th & 43rd Floor (Part Refuge Area)
8th, 13th, 18th, 23rd, 28th, 33rd, 38th & 43rd Floor (Part Refuge Area) |  | 1 |  | 2 | 737.9788 |  | 0 | 1106.9681
|  | 2 |  | 2 | 737.9788 |  | 0 | 1106.9681
|  | 3 |  | 3 | 1113.6155 |  | 0 | 1670.4232
|  | 4 |  | 2 | 770.3407 |  | 0 | 1155.5111
|  | 5 |  | 3 | 950.2502 |  | 0 | 1425.3753
|  | 6 |  | Refuge Area
1st Floor
1st Floor |  | 101 | [5 empty] | 0
1st Floor |  | 102 | [5 empty] | 0
1st Floor |  | 103 | [5 empty] | 0
1st Floor |  | 104 | [5 empty] | 0
1st Floor |  | 105 | [5 empty] | 0
1st Floor |  | 106 | [5 empty] | 0
1st Floor |  | 107 | [5 empty] | 0
1st Floor |  | 108 | [5 empty] | 0
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 201,..,901 | [5 empty] | 0 |  |  |  | 201,..,901 | 201 | 901
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 202,..,902 | [5 empty] | 0 |  |  |  | 202,..,902 | 202 | 902
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 203,..,903 | [5 empty] | 0 |  |  |  | 203,..,903 | 203 | 903
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 204,..,904 | [5 empty] | 0 |  |  |  | 204,..,904 | 204 | 904
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 205,..,905 | [5 empty] | 0 |  |  |  | 205,..,905 | 205 | 905
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 206,..,906 | [5 empty] | 0 |  |  |  | 206,..,906 | 206 | 906
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 207,..,907 | [5 empty] | 0 |  |  |  | 207,..,907 | 207 | 907
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 208,..,908 | [5 empty] | 0 |  |  |  | 208,..,908 | 208 | 908
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 209,..,909 | [5 empty] | 0 |  |  |  | 209,..,909 | 209 | 909
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor |  | 210,..,910 | [5 empty] | 0 |  |  |  | 210,..,910 | 210 | 910
2nd to 5th Floor
2nd to 5th Floor |  | 201 to 501 | [5 empty] | 0 |  |  |  | 201 to 501 | 201 | 501
2nd to 5th Floor |  | 202 to 502 | [5 empty] | 0 |  |  |  | 202 to 502 | 202 | 502
2nd to 5th Floor |  | 203 to 503 | [5 empty] | 0 |  |  |  | 203 to 503 | 203 | 503
2nd to 5th Floor |  | 204 to 504 | [5 empty] | 0 |  |  |  | 204 to 504 | 204 | 504
2nd to 5th Floor |  | 205 to 505 | [5 empty] | 0 |  |  |  | 205 to 505 | 205 | 505
2nd to 5th Floor |  | 206 to 506 | [5 empty] | 0 |  |  |  | 206 to 506 | 206 | 506
2nd to 5th Floor |  | 207 to 507 | [5 empty] | 0 |  |  |  | 207 to 507 | 207 | 507
2nd to 5th Floor |  | 208 to 508 | [5 empty] | 0 |  |  |  | 208 to 508 | 208 | 508
2nd to 5th Floor |  | 209 to 509 | [5 empty] | 0 |  |  |  | 209 to 509 | 209 | 509
2nd to 5th Floor |  | 210 to 510 | [5 empty] | 0 |  |  |  | 210 to 510 | 210 | 510
2nd & 5th Floor
2nd & 5th Floor |  | 201 & 501 | [5 empty] | 0 |  |  |  | 201 & 501 | 201 | 501
2nd & 5th Floor |  | 202 & 502 | [5 empty] | 0 |  |  |  | 202 & 502 | 202 | 502
2nd & 5th Floor |  | 203 & 503 | [5 empty] | 0 |  |  |  | 203 & 503 | 203 | 503
2nd & 5th Floor |  | 204 & 504 | [5 empty] | 0 |  |  |  | 204 & 504 | 204 | 504
2nd & 5th Floor |  | 205 & 505 | [5 empty] | 0 |  |  |  | 205 & 505 | 205 | 505
2nd & 5th Floor |  | 206 & 506 | [5 empty] | 0 |  |  |  | 206 & 506 | 206 | 506
2nd & 5th Floor |  | 207 & 507 | [5 empty] | 0 |  |  |  | 207 & 507 | 207 | 507
2nd & 5th Floor |  | 208 & 508 | [5 empty] | 0 |  |  |  | 208 & 508 | 208 | 508
2nd & 5th Floor |  | 209 & 509 | [5 empty] | 0 |  |  |  | 209 & 509 | 209 | 509
2nd & 5th Floor |  | 210 & 510 | [5 empty] | 0 |  |  |  | 210 & 510 | 210 | 510
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Construction work is in process at the time of Visit. Internal visit not allowed. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Balcony. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. | [6 empty] | 7. On Site, we meet Mr.Abhijit Pandey.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Zenith (Tower No. 14)
Project Site Address |  |  | : | ZENITH, Survey No. 51 Hissa No 1 To 15 Survey No 52 Hissa No 1 To 3 Survey No 53 At Thane (M Corp.), Thane, Thane, 400608
Site Visit Date & Time |  |  | : | 04/07/2025 at 11:06AM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr.Ajay Songare | Authorized Signatory Name & Signature | :
Note on H6: Rushil Sanghvi or Fahad
Note on E9: Initiation Address
Note on E10: Plan Address
Note on E11: Map Address
Note on C17: Maybe same as RERA Registration Validity or different
Note on H17: From Rera
Note on H20: From RERA
Note on A39: As per Layout
Note on H110: Ready Recknor