## report
APF Report Format
Name of Valuation Agency |  |  | : | V.S.JADON & CO VALUERS LLP |  | Date of Technical Initiation |  | 2025-07-02 | 2025-07-22 |  | 70
Project Name |  |  | : | The Highlands at Godrej City, Panvel Tower 1, 2 & 3 |  | Date of Site Visit |  | 04/07/2025 at 10:51AM | 2025-04-23 | old initiation date < 90
Name of the person met at site & Contact No. |  |  | : | NA |  | Date of Report Release |  | 07/07/2025 | Mr.Shantanu - 7262030139
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | Godrej Group | Developer Name | : | Caroa Properties LLP
Developer Office Address |  |  | : | Office at Godrej One, 5th floor, Pirojshanagar, Eastern Express Highway, Vikhroli (East), Mumbai 400 079
Project Address | : | As per ARF | : | Integrated Township Project (ITP) on land bearing S.No.38/0, 74/0, 36/1, 73/0, 30/1, 75/0, 42/4, 42/1, 42/3, 32/2, 39/0, 43/0, 44/4, 70/1, 70/2, 72/0, 76/1, 76/2, 68/0, 81/2A, 81/2B, 40/0, 47/2, 50/12, 50/13, 69/0, 41/1, 41/2, 44/3, 47/1, 71/0, 36/2, 37/1, 37/2, 78/0 of village -Khanavale, Taluka-Panvel, Dist -Raigad, And S.No.6/1, 6/5, 7/1, 6/6, 7/2, 7/3A, 7/4, 5/2B, 9/2, 4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 7/3B, 7/B/1, 7/B/2, 7B/3, 7B/4, 7B/5, 7B/6, 7B/7, 7C/1, 7C/2, 7C/3, 7C/4, 7C/5, 7C/6, 7C/7, 7C/8, 8/3A/1, 8/3A/2, 8/3A/3, 8/3A/4, 8/3A/5, 8/3A/6, 8/3A/7, 8/3A/8, 8/3A/9, 8/3A/10, 8/D/1, 8/D/2, 8/D/3, 8/D/4, 8/D/5, 8/D/6, 8/D/7, 8/D/8, 8/B/1, 8/B/2, 8/B/3, 8/B/4, 8/B/5, 8/D/6, 8/D/7, 8/D/8, 8/B/1, 8/B/2, 8/B/3, 8/B/4, 8/B/5, 8/B/6, 8/C/1, 8/C/2, 8/1A/1, 8/1A/2, 8/1A/3, 8/1A/4, 8/1A/5, 8/1A/6, 9/B/1, 9/B/2, 9/B/3, 9/B/4, 9/B/5, 9/B/6, 9/B/7, 9/B/8, 9/D/1, 9/D/2, 9/D/3, 9/D/4, 9/D/5, 9/D/6, 9/D/7, 9/D/8, 9/C/1, 9/C/2, 9/C/3, 9/C/4, 9/C/5, 9/C/5, 9/C/6, 9/C/7, 9/C/8, 9/C/9, 7/C/9, 7/C/10 of village Talegaon, Taluka-Khalapur, Dist-Raigad - 410221
| : | As per Legal Documents | : | S. Nos.4/1,4/2,4/3pt,4/4pt,4/5pt,4/6,5pt,6/6pt at Village- Talegaon, Taluka- Khalapur, Dist- Raigad - 410221
| : | As per Actual at site | : | The Highlands at Godrej City situated at Village- Talegaon, Taluka- Khalapur, Dist- Raigad - 410221
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate
General Details
Status of Holding |  |  | : | Freehold | Name of Municipal Corporation/Authority | : | MSRDC
RERA Registration No. |  |  | : | P52000026790 | RERA Registration Validity | : | 2026-09-30
Project Launch Date |  |  | : | Sept 2020. | Construction Start Date | : | Nov 2020.
Proposed Date of Completion (As per RERA) |  |  | : | 2026-09-30 | Developer Bank Name (As per RERA) | : | Axis Bank
Project Type (Mixed, Residential, Comm.) |  |  | : | Residential | Plot Area (In Sq.Mt) | : | 431675.64
Permissible Built up Area (In Sq.Mt) |  |  | : | 71208.134 | Proposed Built up Area (In Sq.Mt) | : | 66090.298
Free/ Fungible FSI |  |  | : | 0.6 | Total Number of Units Planned | : | 859
Total Number of Units Approved |  |  | : | 859 | If Mixed, No. of Commercial Units | : | -
Latitude |  |  | : | 18.9274 | Longitude | : | 73.1813
Extra Amenities available |  |  | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area |  |  | : | Developing | Class of Locality | : | Middle class
Type of Road |  |  | : | Bitumen | Width of the Road in ft. | : | -
Electrification/Electric poles observed |  |  | : | Yes | Distance from Bus stand (Km) | : | About 6.6KM from Rasayani Bus Depot
Distance from the nearest School (Km) |  |  | : | About 3.7 KM from St. Wilfred's School, Panvel | Distance from Hospital (Km) | : | About 5 km form Mangal Murti Clinic Dr Raut.
Distance from the Main Market (Km) |  |  | : | 1. Approx. 2KM from Village Market. 2. Approx. 10KM from Panvel Main Market. | Distance from nearest Railway/Metro/Airport (Km) | : | 5.4KM from Somatne Railway Station 10.5KM from Panvel Railway Station
Water Supply |  |  | : | Being Provisioned | Electricity Supply | : | Being Provisioned
Drainage Connection |  |  | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Survey No 5-2 | Survey no 5-1 | Survey no 4-3 and 4-6 |  | Survey no 5-1
As per Site / Actual |  |  | : | Open Plot | Open Plot | Open Plot |  | Open Plot
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  |  | Type (Sale/Rehab) |  | No. of Floors Planned |  | No. of Floors Approved
Tower No.1 (Type C) |  |  | Sale |  | G + 1st to 39th Floor |  | G + 1st to 39th Floor
Tower No.2 (Type C) |  |  | Sale |  | B0 + P1 + G + 1st to 39th Floor |  | B0 + P1 + G + 1st to 39th Floor
Tower No.3 (Type A) |  |  | Sale |  | B0 + P1 to P4 + G + 1st to 39th Floor |  | B0 + P1 to P4 + G + 1st to 36th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans |  |  | : | Under Construction | LOI/IOD Details | : | MSRDC/SPA/ITP-3/CC/2020/502 Dated: 06/10/2020.
CC Details |  |  | : | MSRDC/SPA/ITP-3/CC/2020/502 Dated: 06/10/2020. | Approved Plan Details | : | MSRDC/SPA/ITP-3/CC/2020/502 Dated: 06/10/2020.
Environmental Clearance Details |  |  | : | SEIAA-EC-0000002285 Date : 25/06/2020. | Airport Authority Clearance Details | : | NOC for Height Clearance NAVI/WEST/B/022820/450961 Dated : 12/03/2020. Valid upto : 10/03/2028.
Tree NOC details |  |  | : | JVK No.B/20/JMIN/970/2019-20. Date : 03/12/2019. | Other NOC Details | : | Fire NOC Dated : 29/08/2020. (By MFS)
Construction Status
Tower No.1 (Type C) = G + 1st to 39th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 39 Slab, Brickwork upto 38 Floor, Internal Plaster upto 30.4 Floor, External Plaster upto 30.4 Floor, External Plumbing, Elevation and Waterproofing upto 7 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 39 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.75
Excavation |  | 39 |  | 100% | 59.04% |  | Excavation work Completed. Plinth work completed, RCC upto 39 Slab, Brickwork upto 38 Floor, Internal Plaster upto 30.4 Floor, External Plaster upto 30.4 Floor, External Plumbing, Elevation and Waterproofing upto 7 Floor Completed |  | Excavation in process | 19.5
Plinth |  | 39 |  | 100% |  |  |  |  | Excavation Completed | 39
RCC (Including podiums) |  | 39 |  | 97.5% |  |  |  |  | Footing in Process | 9.75
Brickwork |  | 38 |  | 97.44% |  |  |  |  | Footing Completed | 19.5
Internal Plaster |  | 30.4 |  | 77.95% |  |  |  |  | Basement 1 | 0
External Plaster |  | 30.4 |  | 77.95% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 7 |  | 17.95% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 29.25
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 39 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower No.2 (Type C) = B0 + P1 (BS) + G + 1st to 39th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 39 Slab, Brickwork upto 38 Floor, Internal Plaster upto 30.4 Floor, External Plaster upto 30.4 Floor Completed
|  |  |  | 2 | 1 |  | 0 | 39 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.75
Excavation |  | 39 |  | 100% | 58.14% |  | Excavation work Completed. Plinth work completed, RCC upto 39 Slab, Brickwork upto 38 Floor, Internal Plaster upto 30.4 Floor, External Plaster upto 30.4 Floor Completed |  | Excavation in process | 19.5
Plinth |  | 39 |  | 100% |  |  |  |  | Excavation Completed | 39
RCC (Including podiums) |  | 39 |  | 97.5% |  |  |  |  | Footing in Process | 9.75
Brickwork |  | 38 |  | 97.44% |  |  |  |  | Footing Completed | 19.5
Internal Plaster |  | 30.4 |  | 77.95% |  |  |  |  | Basement 1 | 29.25
External Plaster |  | 30.4 |  | 77.95% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 39 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower No.3 (Type A) = B0 + P1 to P4 (BS)+ G + 1st to 39th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 39 Slab, Brickwork upto 38 Floor, Internal Plaster upto 36 Floor, External Plaster upto 36 Floor Completed
|  |  |  | 5 | 1 |  | 0 | 39 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.75
Excavation |  | 39 |  | 100% | 58.86% |  | Excavation work Completed. Plinth work completed, RCC upto 39 Slab, Brickwork upto 38 Floor, Internal Plaster upto 36 Floor, External Plaster upto 36 Floor Completed |  | Excavation in process | 19.5
Plinth |  | 39 |  | 100% |  |  |  |  | Excavation Completed | 39
RCC (Including podiums) |  | 39 |  | 97.5% |  |  |  |  | Footing in Process | 5.5714
Brickwork |  | 38 |  | 97.44% |  |  |  |  | Footing Completed | 11.1429
Internal Plaster |  | 36 |  | 92.31% |  |  |  |  | Basement 1 | 16.7143
External Plaster |  | 36 |  | 92.31% |  |  |  |  | Basement 2 | 22.2857
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 27.8571
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 33.4286
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 39 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Overall Project Completion % | [7 empty] | 58.68%
Market Value
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA/PlotArea) | : | CA
Rate Per Sq. Ft. (on Carpet area) |  |  | : | 12000/- to 13700/- | Floor Rise Details Per Sq. Ft. (on Carpet area) | : | 60/- from 2nd Floor |  |  | Rate matched with Tower 6 on 08/01/2025 by gaurav
Car Parking Charges |  |  | : | 500000/- | Other Charges | : | As applicable and documented.
Guideline Values & Distress Value
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 410.63
Government Guideline/ Circle rate for Flat Built up(Rs per sqft) | [5 empty] | : | 4580.08
Distress Value (Rs. Per sqft) | [5 empty] | : | 6400
Unit Details, Nomenclature and Area Details
Building/Tower & Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area (60% Loading)
RZ-5
Tower No.1
Ground Floor (Level 6.9 M)
1st Floor (Level 10.05 M) for Residential & Meter Room
1st Floor (Level 10.05 M) |  | 1 |  | 2BHK | 609.4727 |  | 0 | 975.1564 |  | 2
|  | 2 |  | 2BHK | 609.4727 |  | 0 | 975.1564
2nd Floor Floor (Level 13.2 M)
2nd Floor Floor (Level 13.2 M) |  | 1 |  | 1BHK | 399.6426 |  | 0 | 639.4281
|  | 2 |  | 1BHK | 399.6426 |  | 0 | 639.4281
|  | 3 |  | 2BHK | 609.4727 |  | 0 | 975.1564
|  | 4 |  | 2BHK | 609.4727 |  | 0 | 975.1564
|  | 5 |  | 2BHK | 609.4727 |  | 0 | 975.1564 |  | 6
|  | 6 |  | 2BHK | 609.4727 |  | 0 | 975.1564
3rd Floor (Level 16.35 M)
3rd Floor (Level 16.35 M) |  | 1 |  | 1BHK | 399.6426 |  | 0 | 639.4281
|  | 2 |  | 1BHK | 399.6426 |  | 0 | 639.4281
|  | 3 |  | 2BHK | 609.4727 |  | 0 | 975.1564
|  | 4 |  | 2BHK | 609.4727 |  | 0 | 975.1564
|  | 5 |  | 1BHK | 399.6426 |  | 0 | 639.4281
|  | 6 |  | 1BHK | 399.6426 |  | 0 | 639.4281
|  | 7 |  | 2BHK | 609.4727 |  | 0 | 975.1564 |  | 8
|  | 8 |  | 2BHK | 609.4727 |  | 0 | 975.1564
4th Floor (Level 19.675 M)
4th Floor (Level 19.675 M) |  | 1 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 2 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 3 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 4 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 5 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 6 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 7 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 8 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 8
5th Floor (Level 22.825 M)
5th Floor (Level 22.825 M) |  | 1 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 2 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 3 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 4 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 5 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 6 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 7 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 8 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 8
6th Floor (Level 25.775 M)
6th Floor (Level 25.775 M) |  | 1 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 2 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 3 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 4 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 5 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 6 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 7 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 8 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 8
7th Floor (Level 28.725 M) (Part Refuge Area)
7th Floor (Level 28.725 M) (Part Refuge Area) |  | 1 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 2 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 3 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 4 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 5 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 6 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 7 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 7
|  | 8 |  | Refuge Area
8th, 9th, 10th, 11th, 13th, 14th, 15th, 16th, 18th, 19th, 20th, 21st, 23rd, 24th, 25th, 26th, 28th, 29th, 30th, 31st, 33th, 34th, 35th, 36th, 38th & 39th Floor
8th, 9th, 10th, 11th, 13th, 14th, 15th, 16th, 18th, 19th, 20th, 21st, 23rd, 24th, 25th, 26th, 28th, 29th, 30th, 31st, 33th, 34th, 35th, 36th, 38th & 39th Floor |  | 1 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 2 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 3 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 4 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 5 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 6 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 7 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 8 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 208
12th, 17th, 22nd, 27th, 32nd & 37th Floor (Part Refuge Area)
12th, 17th, 22nd, 27th, 32nd & 37th Floor (Part Refuge Area) |  | 1 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 2 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 3 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 4 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 5 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 6 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 7 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 42
|  | 8 |  | Refuge Area
Tower No.2
Basement 0 + Parking Floor 0 (Level 0.6 M)
Basement 1 + Parking Floor 1 (Level 3.75 M)
Ground Floor (+B2) +Parking Floor 2 (Level 6.9 M)
1st Floor (+B3) +Parking Floor 3 (Level 10.5 M) for Parking & Residential
1st Floor |  | 1 |  | 1BHK | 399.6426 |  | 0 | 639.4281 |  | 1
2nd Floor Floor (Level 13.2 M) for Residential & Meter Room, Double Height Lobby
2nd Floor Floor (Level 13.2 M) |  | 1 |  | 1BHK | 399.6426 |  | 0 | 639.4281
|  | 2 |  | 2BHK | 609.4727 |  | 0 | 975.1564 |  | 2
3rd Floor + Parking Floor 5th (Level 16.35 M)
3rd Floor + Parking Floor 5th (Level 16.35 M) |  | 1 |  | 1BHK | 399.6426 |  | 0 | 639.4281
|  | 2 |  | 2BHK | 609.4727 |  | 0 | 975.1564
|  | 3 |  | 2BHK | 609.4727 |  | 0 | 975.1564
|  | 4 |  | 2BHK | 609.4727 |  | 0 | 975.1564 |  | 4
4th Floor (Level 19.675 M)
4th Floor (Level 19.675 M) |  | 1 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 2 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 3 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 4 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 5 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 6 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 7 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 7
5th Floor (Level 22.825 M)
5th Floor (Level 22.825 M) |  | 1 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 2 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 3 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 4 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 5 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 6 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 7 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 7
6th Floor (Level 25.775 M)
6th Floor (Level 25.775 M) |  | 1 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 2 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 3 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 4 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 5 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 6 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 7 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 8 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 8
7th Floor (Level 28.725 M) (Part Refuge Area)
7th Floor (Level 28.725 M) (Part Refuge Area) |  | 1 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 2 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 3 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 4 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 5 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 6 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 7 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 7
|  | 8 |  | Refuge Area | 521.3576 |  | 0 | 834.1721
8th, 9th, 10th, 11th, 13th, 14th, 15th, 16th, 18th, 19th, 20th, 21st, 23rd, 24th, 25th, 26th, 28th, 29th, 30th, 31st, 33th, 34th, 35th, 36th, 38th & 39th Floor
8th, 9th, 10th, 11th, 13th, 14th, 15th, 16th, 18th, 19th, 20th, 21st, 23rd, 24th, 25th, 26th, 28th, 29th, 30th, 31st, 33th, 34th, 35th, 36th, 38th & 39th Floor |  | 1 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 2 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 3 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 4 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 5 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 6 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 7 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 8 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 208
12th, 17th, 22nd, 27th, 32nd & 37th Floor (Part Refuge Area)
12th, 17th, 22nd, 27th, 32nd & 37th Floor (Part Refuge Area) |  | 1 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 2 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 3 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 4 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 5 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 6 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 7 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 42
|  | 8 |  | Refuge Area | 521.3576 |  | 0 | 834.1721
Tower No.3
Basement 0 + Parking Floor 0 (Level 0.6 M)
Basement 1 + Parking Floor 1 (Level 3.75 M)
Basement 2 + Parking Floor 2 (Level 6.9 M)
Basement 3 + Parking Floor 3 (Level 10.05 M)
Basement 4 + Parking Floor 4 (Level 13.2 M)
Ground Floor + Parking Floor 5 (Level 16.35 M)
1st Floor (Level 19.675M SFL & 19.875 FFl)
1st Floor (Level 19.675M SFL & 19.875 FFl) |  | 1 |  | 2BHK | 688.6527 |  | 0 | 1101.8444
|  | 2 |  | 2BHK | 688.6527 |  | 0 | 1101.8444
|  | 3 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 4 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 4
2nd Floor (Level 22.825M)
2nd Floor (Level 22.825M) |  | 1 |  | 2BHK | 688.6527 |  | 0 | 1101.8444
|  | 2 |  | 2BHK | 688.6527 |  | 0 | 1101.8444
|  | 3 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 4 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 5 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 6 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 6
3rd Floor (Level 25.775M)
3rd Floor (Level 25.775M) |  | 1 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 2 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 3 |  | 2BHK | 688.6527 |  | 0 | 1101.8444
|  | 4 |  | 2BHK | 688.6527 |  | 0 | 1101.8444
|  | 5 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 6 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 7 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 8 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 8
4th Floor (Level 28.725M)
4th Floor (Level 28.725M) |  | 1 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 2 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 3 |  | 2BHK | 688.6527 |  | 0 | 1101.8444
|  | 4 |  | 2BHK | 688.6527 |  | 0 | 1101.8444
|  | 5 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 6 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 7 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 8 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 8
5th, 6th, 7th, 8th, 10th, 11th, 12th, 13th, 15th, 16th, 17th, 18th, 20th, 21st, 22nd, 23rd, 25th, 26th, 27th, 28th, 30th, 31st, 32nd, 33rd, 35th & 36th Floor
5th, 6th, 7th, 8th, 10th, 11th, 12th, 13th, 15th, 16th, 17th, 18th, 20th, 21st, 22nd, 23rd, 25th, 26th, 27th, 28th, 30th, 31st, 32nd, 33rd, 35th & 36th Floor |  | 1 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 2 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 3 |  | 2BHK | 688.6527 |  | 0 | 1101.8444
|  | 4 |  | 2BHK | 688.6527 |  | 0 | 1101.8444
|  | 5 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 6 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 7 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 8 |  | 2BHK | 615.9634 |  | 0 | 985.5415 |  | 208
9th, 14th, 19th, 24th, 29th & 34th Floor (Part Refuge Area)
9th, 14th, 19th, 24th, 29th & 34th Floor (Part Refuge Area) |  | 1 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 2 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 3 |  | 2BHK | 688.6527 |  | 0 | 1101.8444
|  | 4 |  | 2BHK | 688.6527 |  | 0 | 1101.8444
|  | 5 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 6 |  | 1BHK | 411.4211 |  | 0 | 658.2737
|  | 7 |  | 2BHK | 615.9634 |  | 0 | 985.5415
|  | 8 |  | Refuge Area | 521.3576 |  | 0 | 834.1721 |  | 42
Project Specific Remarks & Observation | [9 empty] | 859
Remarks / Observations | : | 1. Construction work is in process at the time of Visit. (Internal visit was not allowed). 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet 5. We considered Flat rate as per Market Inquires. 6. Car parking is subjected to authentic documentation. 7. Tower 3 - We have considered construction percent as per proposed no. of floor( B0+ P1 to P4 + Gr.+ 1st to 39th Floor) because construction work goes beyond approved no. of floor(B1+P1 to P4+ Gr.+ 1st to 36th Floor). Please provide revised CC & approved plans. 7. RZ-5 plot consist of 7 towers but on RERA site only 3 towers are registered.
Site & Building/Tower Photographs
Name of the Project |  |  | : | The Highlands at Godrej City, Panvel Tower 1, 2 & 3
Project Site Address |  |  | : | The Highlands at Godrej City situated at Village- Talegaon, Taluka- Khalapur, Dist- Raigad - 410221
Site Visit Date & Time |  |  | : | 04/07/2025 at 10:51AM
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Nitesh Patil | Authorized Signatory Name & Signature | :
1
3
2
Tower 1
Tower 2
Tower 3
1
2
3
1
3
2
1
1
2
2
3
3

## T1
Particulars | totaL floor | 26
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 96.2963 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 27 | 26 | 0 | Progress |  |  | 10 | 38.5185 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 28.8889 | 0 | 0 | 0 | 0 | 0
| 26 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 26 | 0 | 0
Flooring | Total Floor | completed Floor
| 26 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 26 | 0 |  | RCC | 38.5185 | 28.8889
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 26 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 48.52% | 58.89%

## T2
Particulars | totaL floor | 27
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 85.7143 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 28 | 24 | 0 | Progress |  |  | 10 | 34.2857 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 25.7143 | 0 | 0 | 0 | 0 | 0
| 27 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 27 | 0 | 0
Flooring | Total Floor | completed Floor
| 27 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 27 | 0 |  | RCC | 34.2857 | 25.7143
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 27 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 44.29% | 55.71%