## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  |  | : | The Views |  | Date & Time of Site Visit |  | 07/07/2025 at 02:51PM |  |  | 2025-04-26 | 2025-07-07
Name of the person met at site & Contact No. |  |  | : | NA |  | Date of Report Release |  | 08/07/2025 | Mr. Mehul mindhe sales 9152942580 |  |  | 72
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | M/s.Agnel Developers | Developer Name | : | M/s.Agnel Developers
Developer Office Address |  |  | : | CTS No. 94A/9/10 & 194A/9/11, situated at Village Ghatkopar (East), Mumbai 400075, Maharashtra, India
Project Address | : | As per ARF | : | The Views, C.T.S. No. 194A/9/10 & 194A/9/11 of Village Ghatkopar, Pant nagar at Ghatkopar East, Village Ghatkopar (East), Mumbai 400075, Maharashtra, India.
| : | As per Legal Documents | : | Proposed Re-development of sale building no.01 (Re-development of 512 ESW tenants association) (Redevelopment building nos. 244 to 307) on plot bearing C.T.S. No. 194A/9/10 & 194A/9/11 of Village Ghatkopar, Pant nagar at Ghatkopar East, Mumbai.
| : | As per Actual at site | : | Adani - The Views, Road - Eastern Express Highway, Near - Yashodham Society, Village Ghatkopar (East), Mumbai 400075, Maharashtra, India
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Maharashtra Housing and Area Development Authority
RERA Registration No. | : | Tower A & B = P51900031165 Tower C & D = P51900033194 |  |  | RERA Registration Validity | : | 2025-12-31
Project Launch Date | : | 2018-12-30 |  |  | Construction Start Date | : | 2021-10-11
Proposed Date of Completion (As per RERA) | : | 2025-12-31 |  |  | Developer Bank Name (As per RERA) | : | HDFC BANK IFSC Code - HDFC0000835
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 14510.71
FSI/FAR Permissible | : | 1.2 |  |  | Proposed Built up Area (In Sq.Mt) | : | 14408.73
Permissible Built up Area (In Sq.Mt) | : | 14408.73 |  |  | Total Number of Units Planned | : | As per RERA - Flats = 565 & Shop = 4
Total Number of Units Approved | : | Flats = 572 |  |  | If Mixed, No. of Commercial Units | : | NA
Latitude | : | 19.0801 |  |  | Longitude | : | 72.9167
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Upper
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 1.2 KM from Ghatkopar Bus Depot
Distance from the nearest School (Km) | : | About 1.5 KM from P G Garodia School. |  |  | Distance from Hospital (Km) | : | About 2.1 KM form Parakh Hospital
Distance from the Main Market (Km) | : | 1. Approx. 950 M from Pantnagar Bhaji Market. 2. Approx. 1.5 KM from Home Mart. |  |  | Distance from Railway Station (Km) | : | 1.4 KM from Ghatkopar Railway Station 3 KM from Vidhyavihar Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Open Plot | Road | Road |  | Road
As per Site / Actual |  |  | : | Open Plot | Internal Road | Eastern Express Highway |  | Yashodham Society
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Tower A & D |  | Sale |  | 2B + G/St + 1st to 21st Floor |  |  | 2B + G/St + 1st to 21st Floor
Tower B & C |  | Sale |  | 2B + G/St + 1st to 21st Floor |  |  | 2B + G/St + 1st to 21st Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | MHADA-01/404/2022 Date: 10/02/2022
Approved Plan Details | : | MHADA-01/404/2022 Date: 10/02/2022
CC Details Tower - A & D | : | MH/EE/(BP)/GM/MHADA-1/404/2023/FCC/2/Amend Date: 07/08/2023 Valid Up to: 19/09/2023 Valid Up to :This Full C.C. is granted for Tower A and Tower D comprising of ground (pt) for parking + 1st for amenities + 2nd to 21st upper floor for residential users having height 67.73mt upto terrace + LMR + OHT as per approved PhaseII Plan and as per Amended plan dt. 24.06.2022.
Tower - B & C | : | MH/EE/(BP)/GM/MHADA-1/404/2023/FCC/1/Amend Date: 28/06/2023 Valid Up to : This C.C. is permitted for Phase-I having plot area 3326.16 Sq.Mt. on which building comprising of Tower B and Tower C comprising of ground (pt) for commercial user + 1st for amenities + 2nd to 21st upper floor for residential users having height 67.73mt upto terrace + LMR + OHT as per approved Phase-I Plan dtd. 27.06.2023 and as per Amended plan dt. 24.06.2022. D.A. Phase programme plan dtd. 27.06.2023.
Environmental Clearance Details | : | SEIAA-2019/CR-102/SEIAA Date: 21/05/2019 |  |  | Airport Authority Clearance Details | : | AAI/RHQ/WR/NOC/SNCR/WEST/B/110811/011/01/329 Date: 04/01/2019
Tree NOC Details | : | Dy.SG/TA/P/1120 Date: 10/06/2013 |  |  | Fire NOC Details | : | FB/HR/R VI /115 Date: 01/02/2019
Construction Status
Tower (A) = 2B + G/St + 1st to 21st Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 18 Floor, Flooring & Fitting upto 15 Floor, Wooden Work upto 15 Floor, Electrical & Sanitary fittings upto 10 Floor Completed
|  |  |  | 2 | 1 |  | 0 | 21 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.25
Excavation |  | 21 |  | 100% | 74.4% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 18 Floor, Flooring & Fitting upto 15 Floor, Wooden Work upto 15 Floor, Electrical & Sanitary fittings upto 10 Floor Completed |  | Excavation in process | 10.5
Plinth |  | 21 |  | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 22 |  | 100% |  |  |  |  | Footing in Process | 5.25
Brickwork |  | 21 |  | 100% |  |  |  |  | Footing Completed | 10.5
Internal Plaster |  | 21 |  | 100% |  |  |  |  | Basement 1 | 15.75
External Plaster |  | 21 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 18 |  | 85.71% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 15 |  | 71.43% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 15 |  | 71.43% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 10 |  | 47.62% |  |  |  |  | Plinth completed | 21 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower (B) = 2B + G/St + 1st to 21st Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 18 Floor, Flooring & Fitting upto 15 Floor, Wooden Work upto 15 Floor, Electrical & Sanitary fittings upto 10 Floor Completed
|  |  |  | 2 | 1 |  | 0 | 21 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.25
Excavation |  | 21 |  | 100% | 74.4% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 18 Floor, Flooring & Fitting upto 15 Floor, Wooden Work upto 15 Floor, Electrical & Sanitary fittings upto 10 Floor Completed |  | Excavation in process | 10.5
Plinth |  | 21 |  | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 22 |  | 100% |  |  |  |  | Footing in Process | 5.25
Brickwork |  | 21 |  | 100% |  |  |  |  | Footing Completed | 10.5
Internal Plaster |  | 21 |  | 100% |  |  |  |  | Basement 1 | 15.75
External Plaster |  | 21 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 18 |  | 85.71% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 15 |  | 71.43% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 15 |  | 71.43% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 10 |  | 47.62% |  |  |  |  | Plinth completed | 21 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower (C) = 2B + G/St + 1st to 21st Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 15 Floor, Flooring & Fitting upto 13 Floor, Wooden Work upto 13 Floor, Electrical & Sanitary fittings upto 5 Floor Completed
|  |  |  | 2 | 1 |  | 0 | 21 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.25
Excavation |  | 21 |  | 100% | 71.9% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 15 Floor, Flooring & Fitting upto 13 Floor, Wooden Work upto 13 Floor, Electrical & Sanitary fittings upto 5 Floor Completed |  | Excavation in process | 10.5
Plinth |  | 21 |  | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 22 |  | 100% |  |  |  |  | Footing in Process | 5.25
Brickwork |  | 21 |  | 100% |  |  |  |  | Footing Completed | 10.5
Internal Plaster |  | 21 |  | 100% |  |  |  |  | Basement 1 | 15.75
External Plaster |  | 21 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 15 |  | 71.43% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 13 |  | 61.9% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 13 |  | 61.9% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 5 |  | 23.81% |  |  |  |  | Plinth completed | 21 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower (D) = 2B + G/St + 1st to 21st Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 15 Floor, Flooring & Fitting upto 13 Floor, Wooden Work upto 13 Floor, Electrical & Sanitary fittings upto 5 Floor Completed
|  |  |  | 2 | 1 |  | 0 | 21 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.25
Excavation |  | 21 |  | 100% | 71.9% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 15 Floor, Flooring & Fitting upto 13 Floor, Wooden Work upto 13 Floor, Electrical & Sanitary fittings upto 5 Floor Completed |  | Excavation in process | 10.5
Plinth |  | 21 |  | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 22 |  | 100% |  |  |  |  | Footing in Process | 5.25
Brickwork |  | 21 |  | 100% |  |  |  |  | Footing Completed | 10.5
Internal Plaster |  | 21 |  | 100% |  |  |  |  | Basement 1 | 15.75
External Plaster |  | 21 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 15 |  | 71.43% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 13 |  | 61.9% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 13 |  | 61.9% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 5 |  | 23.81% |  |  |  |  | Plinth completed | 21 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 73.15%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 30500 to 31500 | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA |  |  | Rushil | 2022-12-27 | 26500 to 30500 | verbal & market
Car Parking Charges |  |  | : | 800000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 3783.9093
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 9011.5199
Distress Value (Rs. Per sqft) | [5 empty] | : | 3027.1275
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Tower A |  | Sale |  | Flats | 141 |  | 101653 | 157562.15
Tower B |  | Sale |  | Flats | 145 |  | 103580.5441 | 160549.8433
Tower C |  | Sale |  | Flats | 145 |  | 103193.3575 | 159949.7041
Tower D |  | Sale |  | Flats | 141 |  | 101397 | 157165.35
Total |  | Sale |  | Flats | 572 |  | 409823.9016 | 635227.0474
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
55%
Tower A
1st & 2nd Basement Floor for Parking
Ground Floor for Parking
1st Floor for Residential & Amenities
1st Floor for Residential & Amenities |  | 1 |  | Fitness Center
1st Floor for Residential & Amenities |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4
1st Floor for Residential & Amenities |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
1st Floor for Residential & Amenities |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
1st Floor for Residential & Amenities |  | 5 |  | 2BHK | 601 |  | 0 | 931.55
1st Floor for Residential & Amenities |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
2nd Floor for Residential & Amenities
2nd Floor for Residential & Amenities |  | 1 |  | Fitness Center |  |  |  | 0
2nd Floor for Residential & Amenities |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4
2nd Floor for Residential & Amenities |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
2nd Floor for Residential & Amenities |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
2nd Floor for Residential & Amenities |  | 5 |  | 2BHK | 582 |  | 0 | 902.1
2nd Floor for Residential & Amenities |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
3rd Floor for Residential & Service Floor
3rd Floor for Residential & Service Floor |  | 1 |  | Service Area |  |  |  | 0
3rd Floor for Residential & Service Floor |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4
3rd Floor for Residential & Service Floor |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
3rd Floor for Residential & Service Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
3rd Floor for Residential & Service Floor |  | 5 |  | 2BHK | 582 |  | 0 | 902.1
3rd Floor for Residential & Service Floor |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
4th Floor
4th Floor |  | 1 |  | 2BHK | 747 |  | 0 | 1157.85
4th Floor |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4
4th Floor |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
4th Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
4th Floor |  | 5 |  | 2BHK | 582 |  | 0 | 902.1
4th Floor |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
4th Floor |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
5th, 6th, 8th , 10th & 12th Floor
5th, 6th, 8th , 10th & 12th Floor |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
5th, 6th, 8th , 10th & 12th Floor |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4 | 26075.1057
5th, 6th, 8th , 10th & 12th Floor |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
5th, 6th, 8th , 10th & 12th Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
5th, 6th, 8th , 10th & 12th Floor |  | 5 |  | 2BHK | 582 |  | 0 | 902.1
5th, 6th, 8th , 10th & 12th Floor |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
5th, 6th, 8th , 10th & 12th Floor |  | 7 |  | 2BHK | 726 |  | 0 | 1125.3
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area)
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4 | 26075.1057
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 5 |  | 2BHK | 582 |  | 0 | 902.1
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 7 |  | 2BHK | 726 |  | 0 | 1125.3
14th Floor
14th Floor |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
14th Floor |  | 2 |  | 3BHK | 925 |  | 0 | 1433.75 | 25595.8876
14th Floor |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
14th Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
14th Floor |  | 5 |  | 2BHK | 582 |  | 0 | 902.1
14th Floor |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
14th Floor |  | 7 |  | 2BHK | 726 |  | 0 | 1125.3
16th Floor
16th Floor |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
16th Floor |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4 | 26075.1057
16th Floor |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
16th Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
16th Floor |  | 5 |  | 2BHK | 582 |  | 0 | 902.1
16th Floor |  | 6 |  | 2BHK | 733 |  | 0 | 1136.15
16th Floor |  | 7 |  | 2BHK | 726 |  | 0 | 1125.3
18th Floor
18th Floor |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
18th Floor |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4 | 26075.1057
18th Floor |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
18th Floor |  | 4 |  | 2BHK | 824 |  | 0 | 1277.2
18th Floor |  | 5 |  | 2BHK | 582 |  | 0 | 902.1
18th Floor |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
18th Floor |  | 7 |  | 2BHK | 726 |  | 0 | 1125.3
19th Floor (Part Refuge Area)
19th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
19th Floor (Part Refuge Area) |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4 | 26075.1057
19th Floor (Part Refuge Area) |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
19th Floor (Part Refuge Area) |  | 4 |  | 2BHK | 824 |  | 0 | 1277.2
19th Floor (Part Refuge Area) |  | 5 |  | 2BHK | 582 |  | 0 | 902.1
19th Floor (Part Refuge Area) |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
19th Floor (Part Refuge Area) |  | 7 |  | 2BHK | 726 |  | 0 | 1125.3
20th Floor
20th Floor |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
20th Floor |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4 | 26075.1057
20th Floor |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
20th Floor |  | 4 |  | 2BHK | 824 |  | 0 | 1277.2
20th Floor |  | 5 |  | 2BHK | 582 |  | 0 | 902.1
20th Floor |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
20th Floor |  | 7 |  | 2BHK | 726 |  | 0 | 1125.3
21st Floor
21st Floor |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
21st Floor |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4 | 26075.1057
21st Floor |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
21st Floor |  | 4 |  | 2BHK | 824 |  | 0 | 1277.2
21st Floor |  | 5 |  | 2BHK | 582 |  | 0 | 902.1
21st Floor |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
21st Floor |  | 7 |  | 2BHK | 726 |  | 0 | 1125.3
Tower B
1st & 2nd Basement Floor for Parking
Ground Floor for Parking
Ground Floor for Parking |  | 5 |  | M.P.Room | 378.8928 |  | 0 | 587.2838
Ground Floor for Parking |  | 6 |  | M.P.Room | 527.6513 |  | 0 | 817.8595
Ground Floor for Parking |  | 7 |  | M.P.Room | 400 |  | 0 | 620
Ground Floor for Parking |  | 8 |  | M.P.Room | 777 |  | 0 | 1204.35
1st Floor for Residential & Amenities
1st Floor for Residential & Amenities |  | 1 |  | Fitness Center |  |  |  | 0
1st Floor for Residential & Amenities |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2
1st Floor for Residential & Amenities |  | 3 |  | 2BHK | 601 |  | 0 | 931.55
1st Floor for Residential & Amenities |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
1st Floor for Residential & Amenities |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
1st Floor for Residential & Amenities |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
2nd Floor for Residential & Amenities
2nd Floor for Residential & Amenities |  | 1 |  | Fitness Center |  |  |  | 0
2nd Floor for Residential & Amenities |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2
2nd Floor for Residential & Amenities |  | 3 |  | 2BHK | 601 |  | 0 | 931.55
2nd Floor for Residential & Amenities |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
2nd Floor for Residential & Amenities |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
2nd Floor for Residential & Amenities |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
3rd Floor for Residential & Service Floor
3rd Floor for Residential & Service Floor |  | 1 |  | Service Area |  |  |  | 0
3rd Floor for Residential & Service Floor |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2
3rd Floor for Residential & Service Floor |  | 3 |  | 2BHK | 601 |  | 0 | 931.55
3rd Floor for Residential & Service Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
3rd Floor for Residential & Service Floor |  | 5 |  | 2BHK | 556 |  | 0 | 861.8 | 24390.9928
3rd Floor for Residential & Service Floor |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
4th Floor
4th Floor |  | 1 |  | 2BHK | 706 |  | 0 | 1094.3
4th Floor |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2
4th Floor |  | 3 |  | 2BHK | 601 |  | 0 | 931.55
4th Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
4th Floor |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
4th Floor |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
4th Floor |  | 7 |  | 2BHK | 747 |  | 0 | 1157.85
5th, 6th, 8th , 10th & 12th Floor
5th, 6th, 8th , 10th & 12th Floor |  | 1 |  | 2BHK | 695 |  | 0 | 1077.25
5th, 6th, 8th , 10th & 12th Floor |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2
5th, 6th, 8th , 10th & 12th Floor |  | 3 |  | 2BHK | 601 |  | 0 | 931.55
5th, 6th, 8th , 10th & 12th Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
5th, 6th, 8th , 10th & 12th Floor |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
5th, 6th, 8th , 10th & 12th Floor |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
5th, 6th, 8th , 10th & 12th Floor |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area)
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 695 |  | 0 | 1077.25
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 3 |  | 2BHK | 601 |  | 0 | 931.55
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
14th Floor
14th Floor |  | 1 |  | 2BHK | 695 |  | 0 | 1077.25
14th Floor |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2
14th Floor |  | 3 |  | 2BHK | 601 |  | 0 | 931.55
14th Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
14th Floor |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
14th Floor |  | 6 |  | 3BHK | 925 |  | 0 | 1433.75
14th Floor |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
16th Floor
16th Floor |  | 1 |  | 2BHK | 695 |  | 0 | 1077.25
16th Floor |  | 2 |  | 2BHK | 734 |  | 0 | 1137.7
16th Floor |  | 3 |  | 2BHK | 626 |  | 0 | 970.3
16th Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
16th Floor |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
16th Floor |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
16th Floor |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
18th Floor
18th Floor |  | 1 |  | 2BHK | 695 |  | 0 | 1077.25
18th Floor |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2
18th Floor |  | 3 |  | 2BHK | 601 |  | 0 | 931.55
18th Floor |  | 4 |  | 2BHK | 824 |  | 0 | 1277.2
18th Floor |  | 5 |  | 2BHK | 559 |  | 0 | 866.45
18th Floor |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
18th Floor |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
19th Floor (Part Refuge Area)
19th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 695 |  | 0 | 1077.25
19th Floor (Part Refuge Area) |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2 | 32701.9282
19th Floor (Part Refuge Area) |  | 3 |  | 2BHK | 601 |  | 0 | 931.55
19th Floor (Part Refuge Area) |  | 4 |  | 2BHK | 824 |  | 0 | 1277.2
19th Floor (Part Refuge Area) |  | 5 |  | 2BHK | 559 |  | 0 | 866.45
19th Floor (Part Refuge Area) |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
19th Floor (Part Refuge Area) |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
20th Floor
20th Floor |  | 1 |  | 2BHK | 695 |  | 0 | 1077.25
20th Floor |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2 | 32701.9282
20th Floor |  | 3 |  | 2BHK | 601 |  | 0 | 931.55
20th Floor |  | 4 |  | 2BHK | 824 |  | 0 | 1277.2
20th Floor |  | 5 |  | 2BHK | 559 |  | 0 | 866.45
20th Floor |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
20th Floor |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
21st Floor
21st Floor |  | 1 |  | 2BHK | 695 |  | 0 | 1077.25
21st Floor |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2 | 32701.9282
21st Floor |  | 3 |  | 2BHK | 601 |  | 0 | 931.55
21st Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
21st Floor |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
21st Floor |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
21st Floor |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
Tower C
1st & 2nd Basement Floor for Parking
Ground Floor for Parking
Ground Floor for Parking |  | 1 |  | M.P.Room | 657.3575 |  | 0 | 1018.9041
Ground Floor for Parking |  | 2 |  | M.P.Room | 400 |  | 0 | 620
Ground Floor for Parking |  | 3 |  | M.P.Room | 526 |  | 0 | 815.3
Ground Floor for Parking |  | 4 |  | M.P.Room | 371 |  | 0 | 575.05
1st Floor for Residential & Amenities
1st Floor for Residential & Amenities |  | 1 |  | Fitness Center |  |  |  | 0
1st Floor for Residential & Amenities |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4
1st Floor for Residential & Amenities |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
1st Floor for Residential & Amenities |  | 4 |  | 2BHK | 743 |  | 0 | 1151.65
1st Floor for Residential & Amenities |  | 5 |  | 1BHK | 513 |  | 0 | 795.15
1st Floor for Residential & Amenities |  | 6 |  | 2BHK | 641 |  | 0 | 993.55
2nd Floor for Residential & Amenities
2nd Floor for Residential & Amenities |  | 1 |  | Fitness Center |  |  |  | 0
2nd Floor for Residential & Amenities |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4
2nd Floor for Residential & Amenities |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
2nd Floor for Residential & Amenities |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
2nd Floor for Residential & Amenities |  | 5 |  | 2BHK | 601 |  | 0 | 931.55
2nd Floor for Residential & Amenities |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
3rd Floor for Residential & Service Floor
3rd Floor for Residential & Service Floor |  | 1 |  | Service Area |  |  |  | 0
3rd Floor for Residential & Service Floor |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4
3rd Floor for Residential & Service Floor |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
3rd Floor for Residential & Service Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
3rd Floor for Residential & Service Floor |  | 5 |  | 2BHK | 601 |  | 0 | 931.55
3rd Floor for Residential & Service Floor |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
4th Floor
4th Floor |  | 1 |  | 2BHK | 747 |  | 0 | 1157.85
4th Floor |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4
4th Floor |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
4th Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
4th Floor |  | 5 |  | 2BHK | 601 |  | 0 | 931.55
4th Floor |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
4th Floor |  | 7 |  | 2BHK | 706 |  | 0 | 1094.3
5th, 6th, 8th , 10th & 12th Floor
5th, 6th, 8th , 10th & 12th Floor |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
5th, 6th, 8th , 10th & 12th Floor |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4
5th, 6th, 8th , 10th & 12th Floor |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
5th, 6th, 8th , 10th & 12th Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
5th, 6th, 8th , 10th & 12th Floor |  | 5 |  | 2BHK | 601 |  | 0 | 931.55
5th, 6th, 8th , 10th & 12th Floor |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
5th, 6th, 8th , 10th & 12th Floor |  | 7 |  | 2BHK | 695 |  | 0 | 1077.25 |  | balcony of 66 ft is not added
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area)
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 5 |  | 2BHK | 601 |  | 0 | 931.55
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 7 |  | 2BHK | 695 |  | 0 | 1077.25
14th Floor
14th Floor |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
14th Floor |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4
14th Floor |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
14th Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
14th Floor |  | 5 |  | 2BHK | 601 |  | 0 | 931.55
14th Floor |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
14th Floor |  | 7 |  | 2BHK | 695 |  | 0 | 1077.25
16th Floor
16th Floor |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
16th Floor |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4
16th Floor |  | 3 |  | 2BHK | 556 |  | 0 | 861.8
16th Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
16th Floor |  | 5 |  | 2BHK | 605 |  | 0 | 937.75
16th Floor |  | 6 |  | 2BHK | 734 |  | 0 | 1137.7
16th Floor |  | 7 |  | 2BHK | 695 |  | 0 | 1077.25
18th Floor
18th Floor |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
18th Floor |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4
18th Floor |  | 3 |  | 2BHK | 559 |  | 0 | 866.45
18th Floor |  | 4 |  | 2BHK | 824 |  | 0 | 1277.2
18th Floor |  | 5 |  | 2BHK | 605 |  | 0 | 937.75
18th Floor |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
18th Floor |  | 7 |  | 2BHK | 695 |  | 0 | 1077.25
19th Floor (Part Refuge Area)
19th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
19th Floor (Part Refuge Area) |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4 | 26075.1057
19th Floor (Part Refuge Area) |  | 3 |  | 2BHK | 559 |  | 0 | 866.45
19th Floor (Part Refuge Area) |  | 4 |  | 2BHK | 824 |  | 0 | 1277.2
19th Floor (Part Refuge Area) |  | 5 |  | 2BHK | 605 |  | 0 | 937.75
19th Floor (Part Refuge Area) |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
19th Floor (Part Refuge Area) |  | 7 |  | 2BHK | 695 |  | 0 | 1077.25
20th Floor
20th Floor |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
20th Floor |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4 | 26075.1057
20th Floor |  | 3 |  | 2BHK | 559 |  | 0 | 866.45
20th Floor |  | 4 |  | 2BHK | 824 |  | 0 | 1277.2
20th Floor |  | 5 |  | 2BHK | 605 |  | 0 | 937.75
20th Floor |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
20th Floor |  | 7 |  | 2BHK | 695 |  | 0 | 1077.25
21st Floor
21st Floor |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
21st Floor |  | 2 |  | 3BHK | 908 |  | 0 | 1407.4 | 26075.1057
21st Floor |  | 3 |  | 2BHK | 559 |  | 0 | 866.45
21st Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
21st Floor |  | 5 |  | 2BHK | 605 |  | 0 | 937.75
21st Floor |  | 6 |  | 2BHK | 724 |  | 0 | 1122.2
21st Floor |  | 7 |  | 2BHK | 695 |  | 0 | 1077.25
Tower D
1st & 2nd Basement Floor for Parking
Ground Floor for Parking
1st Floor for Residential & Amenities
1st Floor for Residential & Amenities |  | 1 |  | Fitness Center
1st Floor for Residential & Amenities |  | 2 |  | 2BHK | 640 |  | 0 | 992
1st Floor for Residential & Amenities |  | 3 |  | 1BHK | 495 |  | 0 | 767.25
1st Floor for Residential & Amenities |  | 4 |  | 2BHK | 743 |  | 0 | 1151.65
1st Floor for Residential & Amenities |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
1st Floor for Residential & Amenities |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
2nd Floor for Residential & Amenities
2nd Floor for Residential & Amenities |  | 1 |  | Fitness Center |  |  |  | 0
2nd Floor for Residential & Amenities |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2
2nd Floor for Residential & Amenities |  | 3 |  | 2BHK | 582 |  | 0 | 902.1
2nd Floor for Residential & Amenities |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
2nd Floor for Residential & Amenities |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
2nd Floor for Residential & Amenities |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
3rd Floor for Residential & Service Floor
3rd Floor for Residential & Service Floor |  | 1 |  | Service Area |  |  |  | 0
3rd Floor for Residential & Service Floor |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2
3rd Floor for Residential & Service Floor |  | 3 |  | 2BHK | 582 |  | 0 | 902.1
3rd Floor for Residential & Service Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
3rd Floor for Residential & Service Floor |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
3rd Floor for Residential & Service Floor |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
4th Floor
4th Floor |  | 1 |  | 2BHK | 737 |  | 0 | 1142.35
4th Floor |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2
4th Floor |  | 3 |  | 2BHK | 582 |  | 0 | 902.1
4th Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
4th Floor |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
4th Floor |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
4th Floor |  | 7 |  | 2BHK | 747 |  | 0 | 1157.85
5th, 6th, 8th , 10th & 12th Floor
5th, 6th, 8th , 10th & 12th Floor |  | 1 |  | 2BHK | 726 |  | 0 | 1125.3
5th, 6th, 8th , 10th & 12th Floor |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2
5th, 6th, 8th , 10th & 12th Floor |  | 3 |  | 2BHK | 582 |  | 0 | 902.1
5th, 6th, 8th , 10th & 12th Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
5th, 6th, 8th , 10th & 12th Floor |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
5th, 6th, 8th , 10th & 12th Floor |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
5th, 6th, 8th , 10th & 12th Floor |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area)
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 726 |  | 0 | 1125.3
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 3 |  | 2BHK | 582 |  | 0 | 902.1
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
7th, 9th, 11th, 13th, 15th & 17th Floor (Part Refuge Area) |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
14th Floor
14th Floor |  | 1 |  | 2BHK | 726 |  | 0 | 1125.3
14th Floor |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2
14th Floor |  | 3 |  | 2BHK | 582 |  | 0 | 902.1
14th Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
14th Floor |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
14th Floor |  | 6 |  | 3BHK | 925 |  | 0 | 1433.75
14th Floor |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
16th Floor
16th Floor |  | 1 |  | 2BHK | 726 |  | 0 | 1125.3
16th Floor |  | 2 |  | 2BHK | 733 |  | 0 | 1136.15
16th Floor |  | 3 |  | 2BHK | 585 |  | 0 | 906.75
16th Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
16th Floor |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
16th Floor |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
16th Floor |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
18th Floor
18th Floor |  | 1 |  | 2BHK | 726 |  | 0 | 1125.3
18th Floor |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2
18th Floor |  | 3 |  | 2BHK | 585 |  | 0 | 906.75
18th Floor |  | 4 |  | 2BHK | 824 |  | 0 | 1277.2
18th Floor |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
18th Floor |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
18th Floor |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
19th Floor (Part Refuge Area)
19th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 726 |  | 0 | 1125.3
19th Floor (Part Refuge Area) |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2 | 32701.9282
19th Floor (Part Refuge Area) |  | 3 |  | 2BHK | 585 |  | 0 | 906.75
19th Floor (Part Refuge Area) |  | 4 |  | 2BHK | 824 |  | 0 | 1277.2
19th Floor (Part Refuge Area) |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
19th Floor (Part Refuge Area) |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
19th Floor (Part Refuge Area) |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
20th Floor
20th Floor |  | 1 |  | 2BHK | 726 |  | 0 | 1125.3
20th Floor |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2 | 32701.9282
20th Floor |  | 3 |  | 2BHK | 585 |  | 0 | 906.75
20th Floor |  | 4 |  | 2BHK | 824 |  | 0 | 1277.2
20th Floor |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
20th Floor |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
20th Floor |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
21st Floor
21st Floor |  | 1 |  | 2BHK | 726 |  | 0 | 1125.3
21st Floor |  | 2 |  | 2BHK | 724 |  | 0 | 1122.2 | 32701.9282
21st Floor |  | 3 |  | 2BHK | 585 |  | 0 | 906.75
21st Floor |  | 4 |  | 2BHK | 811 |  | 0 | 1257.05
21st Floor |  | 5 |  | 2BHK | 556 |  | 0 | 861.8
21st Floor |  | 6 |  | 3BHK | 908 |  | 0 | 1407.4
21st Floor |  | 7 |  | 2BHK | 737 |  | 0 | 1142.35
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Construction work is in process at the time of Visit. (Internal Visit Was Not Allowed). 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We have updated Approved Revised plans & CC (on 18/05/2022) 8. We have updated revised approved CC for Wing A to D from MHADA site on 28/03/2024. 7. On Site, we meet Ms.Rachna (CRM) - 8976763985. 10. Validity of CC is expired on 19/09/2023. Please provide latest CC.
Site & Building/Tower Photographs
Name of the Project |  |  | : | The Views
Project Site Address |  |  | : | The Views, C.T.S. No. 194A/9/10 & 194A/9/11 of Village Ghatkopar, Pant nagar at Ghatkopar East, Village Ghatkopar (East), Mumbai 400075, Maharashtra, India.
Site Visit Date & Time |  |  | : | 07/07/2025 at 02:51PM
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Nainesh Tambe | Authorized Signatory Name & Signature | :
A
B
C
D
C
D
A
A
D
B
D
C
B
C
D
B
A