## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02 |  | 70 | < 90
Project Name |  | Y Square, Building No.21 (Wing A & B) |  | Date & Time of Site Visit |  | 04/07/2025 at 11:19AM |  | 2025-04-23 | Old Int Date
Name of the person met at site & Contact No. |  | NA |  | Date of Report Release |  | 07/07/2025
Data from APF Request Form
Branch Name/ID |  | Godrej One, Vikhroli East, Mumbai |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | Shree Mallinath Enterprise LLP |  | Developer Name |  | Squarefeet group
Developer Office Address |  | 309, 310, 311, 312, Centrum, Near Satkar Hotel, Opp. Raila Devi Lake, Wagle Estate, Thane, Maharashtra 400604
Project Address | As per ARF | Y Square" Opp Tribe Restaurant, Next To Blossom School, Kolshet Rd, Dhokali, Thane(W) - 400607
| As per Legal Documents | Y Square, New Survey No.37/1, 37/2, 37/3, 37/4, 37/5, 37/6, 37/7, 37/8, 37/9, 37/10, 37/11, 37/12, 37/13 - 283 - A (Old), New Survey No. 38/1, 38/2 - 283 - B(Old), New Survey No. 36/1, 36/2A, 36/2B - 146/1, 146/2(Pt), 146/2(Pt) (Old), New Survey No. 10/2 - 147/2 (Old), New Survey No. 27/2A, 27/2B - 163/2, near Blossom English High School, Kolshet Road, Dhokali Pada, Dhokali, Thane West, Thane, Thane - 400607.
| As per Actual at site | Y Square, New Survey No.37/1, 37/2, 37/3, 37/4, 37/5, 37/6, 37/7, 37/8, 37/9, 37/10, 37/11, 37/12, 37/13 - 283 - A (Old), New Survey No. 38/1, 38/2 - 283 - B(Old), New Survey No. 36/1, 36/2A, 36/2B - 146/1, 146/2(Pt), 146/2(Pt) (Old), New Survey No. 10/2 - 147/2 (Old), New Survey No. 27/2A, 27/2B - 163/2, near Blossom English High School, Kolshet Road, Dhokali Pada, Dhokali, Thane West, Thane, Thane - 400607.
Documents Provided by GHF |  | RERA certificate
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Thane Muncipal Cooperation (TMC)
RERA Registration No. | : | P51700015652 |  | RERA Registration Validity | : | 2025-02-28
Project Launch Date | : | 2018-03-15 |  | Construction Start Date | : | 2018-03-15
Proposed Date of Completion (As per RERA) | : | 2025-02-28 |  | Developer Bank Name (As per RERA) | : | ICICI BANK LTD IFSC Code ICIC0004815
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  | Plot Area (In Sq.Mt) | : | 90607.52
FSI/FAR Permissible | : | 1.1 |  | Net Plot Area (In Sq.Mt) | : | 66133.09
Permissible Built up Area (In Sq.Mt) | : | 120785.22 |  | Proposed Built up Area (In Sq.Mt) | : | 120782.81
Total Number of Units Approved | : | Flats = 672 & Shop = 69 |  | Total Number of Units Planned | : | As per RERA Site Flats =786, Shop = 0 |  | 393+393
Latitude, Longitude | : | 19.2297274,72.9842089 |  | Landmark | : | Blossom English High School
Location Link | : | https://maps.app.goo.gl/oLiSBHMcstjcT53v7
Extra Amenities available | : | Sensory Gardens, Sports and recreation Zone, Creative Art Zone, Creche Centre, Kids Play Area, Story time Corners, Gym and Fitness Centre, Squash Court, Swimming Pool , Multipurpose Court, Outdoor recreation Areas, Indoor Games Area, Spa and Wellness Centre, Yoga and Meditation Pavilion, etc.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  | Class of Locality | : | Middle
Type of Road | : | Concrete |  | Width of the Road | : | 40 m
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 30 M from Everest World Bus Stop
Distance from the nearest School (Km) | : | About 1 KM from SBJ English School |  | Distance from Hospital (Km) | : | About 210 M form Navjeevan Hospital
Distance from the Main Market (Km) | : | 1. Approx. 550 M from Low Price Super Market. 2. Approx. 900 M from D Mart. |  | Distance from Railway Station (Km) | : | 5.2 KM from Thane Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North |  | South | East | West
East |  | Adj S.No. 145 |  |  | Blossom English High School
West |  | Other Plot |  |  | SPS House
North |  | Other Plot |  |  | Building
South |  | 40 M W Road |  |  | Kolshet Road
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Building No. 21 (Wing A) |  | Sale | G/St + 1st to 23rd Floors |  |  | G/St + 1st to 23rd Floors
Building No. 21 (Wing B) |  | Sale | G/St + 1st to 23rd Floors |  |  | G/St + 1st to 23rd Floors
Tower 3 |  | Sale
Tower 4 |  | Sale
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | S05/01505/16/TMC/TD-DP/TPS/0112/ (P/C)/2024/ Auto dCR |  |  |  | Date: | 2024-04-08
Approved Plan Details | : | S05/01505/16/TMC/TD-DP/TPS/0112/ (P/C)/2024/ Auto dCR |  |  |  | Date: | 2024-04-08
CC Details Valid Up to: |  | S05/01505/16/TMCB/TDD/0112/ (P/C)/2024/ Auto DCR |  |  |  | Date: | 2024-04-08
Building No. 21(Wing A) = G/St + 1st(Retail) Pt/ Podium Pt + 2nd Podium / Service floor + 3rd floor + 4th to 23rd floors Building No. 21(Wing B) = G/St + 1st(Retail) Pt/ Podium Pt + 2nd Podium / Service floor + 3rd floor + 4th to 7th floors
Environmental Clearance Details | : | SEIAA-EC-0000002164 New Survey No.37/1, 37/2, 37/3, 37/4, 37/5, 37/6, 37/7, 37/8, 37/9, 37/10, 37/11, 37/12, 37/13 - 283 - A (Old), New Survey No. 38/1, 38/2 - 283 - B(Old), New Survey No. 36/1, 36/2A, 36/2B - 146/1, 146/2(Pt), 146/2(Pt) (Old), New Survey No. 10/2 - 147/2 (Old), New Survey No. 27/2A, 27/2B - 163/2 |  |  |  | Date: | 2020-03-02
Change of User/Zone Certificate Details | : |  |  |  |  | Date:
Airport Authority Clearance Details | : |  |  |  |  | Date:
Other NOC Details | : |  |  |  |  | Date:
Construction Status
Building No. 21 (Wing A) = G/St + 1st to 23rd Floors. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 10 Slab, Brickwork upto 4 Floor, Internal Plaster upto 3 Floor, External Plaster upto 3 Floor Completed
|  |  | 0 | 1 |  | 0 | 23 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 36.94% |  | Excavation work Completed. Plinth work completed, RCC upto 10 Slab, Brickwork upto 4 Floor, Internal Plaster upto 3 Floor, External Plaster upto 3 Floor Completed |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 10 | 41.67% |  |  |  |  | Footing in Process | 5.75
Brickwork |  | 4 | 17.39% |  |  |  |  | Footing Completed | 11.5
Internal Plaster |  | 3 | 13.04% |  |  |  |  | Basement 1 | 0
External Plaster |  | 3 | 13.04% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Building No. 21 (Wing B) = G/St + 1st to 23rd Floors. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 4 Slab, Brickwork upto 1 Floor, Internal Plaster upto 1 Floor Completed
|  |  | 0 | 1 |  | 0 | 23 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 29.49% |  | Excavation work Completed. Plinth work completed, RCC upto 4 Slab, Brickwork upto 1 Floor, Internal Plaster upto 1 Floor Completed |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 4 | 16.67% |  |  |  |  | Footing in Process | 5.75
Brickwork |  | 1 | 4.348% |  |  |  |  | Footing Completed | 11.5
Internal Plaster |  | 1 | 4.348% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Tower 3= . |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  | 0 | 1 |  | 0 | 3 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 1.5
Plinth |  | 3 | 100% |  |  |  |  | Excavation Completed | 3
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 0.6
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 1.2
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 2.1
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 3
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 33.22%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 17000 to 18000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 500000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 4431.4381
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 10981.0479
Distress Value (Rs. Per sqft) |  |  |  |  | : | 3545.1505
Unit Details, Nomenclature and Area Details (Commercial) Building No.21
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Wing A |  | - |  | 30 |  | 7602.7951
Wing B |  | - |  | 39 |  | 12515.8432
Total |  | - |  | 69 |  | 20118.6383
Unit Details, Nomenclature and Area Details (Flats) Building No.21
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Wing A |  | - |  | 336 |  | 133304.5514 |  |  | 18
Wing B |  | - |  | 336 |  | 130889.8094
Total |  | - |  | 672 |  | 264194.3608
Grand Total |  | - |  | 741 |  | 284312.9991
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
Building No. 21 | [8 empty] | 10.764
Wing A
Ground Floor For Commercial, Meter Room, Drivers Room & Praking
G1 |  | - | Shop | 244.9241 | 0 | 0 | 244.9241
G2 |  | - | Shop | 213.321 | 0 | 0 | 213.321
G3 |  | - | Shop | 221.2217 | 0 | 0 | 221.2217
G4 |  | - | Shop | 233.863 | 0 | 0 | 233.863
G5 |  | - | Shop | 209.3706 | 0 | 0 | 209.3706
G6 |  | - | Shop | 225.1721 | 0 | 0 | 225.1721
G7 |  | - | Shop | 233.863 | 0 | 0 | 233.863
G8 |  | - | Shop | 247.1791 | 0 | 0 | 247.1791
G9 |  | - | Shop | 338.3879 | 0 | 0 | 338.3879
G10 |  | - | Shop | 325.3979 | 0 | 0 | 325.3979
G11 |  | - | Shop | 354.0678 | 0 | 0 | 354.0678
G12 |  | - | Shop | 340.7398 | 0 | 0 | 340.7398
G13 |  | - | Shop | 345.4813 | 0 | 0 | 345.4813
G14 |  | - | Shop | 290.614 | 0 | 0 | 290.614
G15 |  | - | Shop | 325.3979 | 0 | 0 | 325.3979
1st Podium Floor for Commercial, Electrical Room & Parking
F1 |  | - | Shop | 189.8662 | 0 | 0 | 189.8662
F2 |  | - | Shop | 165.3673 | 0 | 0 | 165.3673
F3 |  | - | Shop | 176.3918 | 0 | 0 | 176.3918
F4 |  | - | Shop | 182.5165 | 0 | 0 | 182.5165
F5 |  | - | Shop | 162.305 | 0 | 0 | 162.305
F6 |  | - | Shop | 176.3918 | 0 | 0 | 176.3918
F7 |  | - | Shop | 182.5165 | 0 | 0 | 182.5165
F8 |  | - | Shop | 192.9286 | 0 | 0 | 192.9286
F9 |  | - | Shop | 291.8874 | 0 | 0 | 291.8874
F10 |  | - | Shop | 278.0729 | 0 | 0 | 278.0729
F11 |  | - | Shop | 304.3424 | 0 | 0 | 304.3424
F12 |  | - | Shop | 286.8423 | 0 | 0 | 286.8423
F13 |  | - | Shop | 322.3495 | 0 | 0 | 322.3495
F14 |  | - | Shop | 247.8723 | 0 | 0 | 247.8723
F15 |  | - | Shop | 294.1435 | 0 | 0 | 294.1435
2nd Podium Floor For Service & Parking
3rd Floor For Residential, Society Office, Creche & Fitness Center
A1 |  | - | 1BHK | 319.9061 | 34.4717 | 0 | 354.3778 | 28.5495 | 3.2025
A2 |  | - | 2BHK | 471.1403 | 39.773 | 0 | 510.9133 | 40.7965 | 3.695
A3 |  | - | 1BHK | 314.2012 | 34.4717 | 0 | 348.6729
A4 |  | - | 1BHK | 314.2012 | 34.4717 | 0 | 348.6729
A5 |  | - | 1BHK | 318.2915 | 64.5571 | 0 | 382.8486
A6 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
A7 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
A8 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
A9 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 |  |  | 368
A10 |  | - | Fitness Center | [6 empty] | 736
A11 |  | -
A12 |  | -
A13 |  | - | 2BHK | 462.2062 | 39.6922 | 0 | 501.8984
A14 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
A15 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
A16 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
A17 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
A18 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
A19 |  | - | 1BHK | 319.9061 | 34.4717 | 0 | 354.3778
4th to 7th , 10th to 12th, 15th to 17th & 20th to 23rd Floor
A1 |  | - | 1BHK | 322.7047 | 64.5571 | 0 | 387.2618 | [6 empty] | 4701,..,2301 | 4701 | 2301
A2 |  | - | 2BHK | 475.0153 | 44.8321 | 0 | 519.8474 | 182745.9436 | [5 empty] | 4702,..,2302 | 4702 | 2302
A3 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4703,..,2303 | 4703 | 2303
A4 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4704,..,2304 | 4704 | 2304
A5 |  | - | 1BHK | 319.3679 | 64.5571 | 0 | 383.925 | [6 empty] | 4705,..,2305 | 4705 | 2305
A6 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4706,..,2306 | 4706 | 2306
A7 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4707,..,2307 | 4707 | 2307
A8 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4708,..,2308 | 4708 | 2308
A9 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4709,..,2309 | 4709 | 2309
A10 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4710,..,2310 | 4710 | 2310
A11 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4711,..,2311 | 4711 | 2311
A12 |  | - | 1BHK | 322.7047 | 64.5571 | 0 | 387.2618 | [6 empty] | 4712,..,2312 | 4712 | 2312
A13 |  | - | 2BHK | 469.3104 | 77.4739 | 0 | 546.7843 | 40.5295 | [5 empty] | 4713,..,2313 | 4713 | 2313
A14 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4714,..,2314 | 4714 | 2314
A15 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4715,..,2315 | 4715 | 2315
A16 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4716,..,2316 | 4716 | 2316
A17 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4717,..,2317 | 4717 | 2317
A18 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4718,..,2318 | 4718 | 2318
A19 |  | - | 1BHK | 322.7047 | 64.5571 | 0 | 387.2618 | [6 empty] | 4719,..,2319 | 4719 | 2319
9th, 14th & 19th Floor (Part Refuge Area)
A1 |  | - | 1BHK | 322.7047 | 64.5571 | 0 | 387.2618 | [6 empty] | 901,..,1901 | 901 | 1901
A2 |  | - | 2BHK | 475.0153 | 44.8321 | 0 | 519.8474 | [6 empty] | 902,..,1902 | 902 | 1902
A3 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 903,..,1903 | 903 | 1903
A4 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 904,..,1904 | 904 | 1904
A5 |  | - | 1BHK | 319.3679 | 64.5571 | 0 | 383.925 | [6 empty] | 905,..,1905 | 905 | 1905
A6 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 906,..,1906 | 906 | 1906
A7 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 907,..,1907 | 907 | 1907
A8 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 908,..,1908 | 908 | 1908
A9 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 909,..,1909 | 909 | 1909
A10 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 910,..,1910 | 910 | 1910
A11 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 911,..,1911 | 911 | 1911
A12 |  | - | 1BHK | 322.7047 | 64.5571 | 0 | 387.2618 | [6 empty] | 912,..,1912 | 912 | 1912
A13 |  | Refuge Area | [11 empty] | 913,..,1913 | 913 | 1913
A14 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 914,..,1914 | 914 | 1914
A15 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 915,..,1915 | 915 | 1915
A16 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 916,..,1916 | 916 | 1916
A17 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 917,..,1917 | 917 | 1917
A18 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 918,..,1918 | 918 | 1918
A19 |  | - | 1BHK | 322.7047 | 64.5571 | 0 | 387.2618 | [6 empty] | 919,..,1919 | 919 | 1919
Wing B
Ground Floor For Commercial, Meter Room & Praking
G16 |  | - | Shop | 207.9443 | 0 | 0 | 207.9443
G17 |  | - | Shop | 213.321 | 0 | 0 | 213.321
G18 |  | - | Shop | 233.863 | 0 | 0 | 233.863
G19 |  | - | Shop | 340.7613 | 0 | 0 | 340.7613
G20 |  | - | Shop | 292.0811 | 0 | 0 | 292.0811
G21 |  | - | Shop | 317.0644 | 0 | 0 | 317.0644
G22 |  | - | Shop | 356.6974 | 0 | 0 | 356.6974
G23 |  | - | Shop | 334.05 | 0 | 0 | 334.05
G24 |  | - | Shop | 317.0644 | 0 | 0 | 317.0644
G25 |  | - | Shop | 309.1378 | 0 | 0 | 309.1378
G26 |  | - | Shop | 349.3898 | 0 | 0 | 349.3898
G27 |  | - | Shop | 195.7347 | 0 | 0 | 195.7347
G28 |  | - | Shop | 218.1454 | 0 | 0 | 218.1454
G29 |  | - | Shop | 223.3476 | 0 | 0 | 223.3476
G30 |  | - | Shop | 408.2086 | 0 | 0 | 408.2086
G31 |  | - | Shop | 1111.6349 | 0 | 0 | 1111.6349
G32 |  | - | Shop | 277.5627 | 0 | 0 | 277.5627
G33 |  | - | Shop | 211.8678 | 0 | 0 | 211.8678
G34 |  | - | Shop | 215.2283 | 0 | 0 | 215.2283
G35 |  | - | Shop | 336.6398 | 0 | 0 | 336.6398
G36 |  | - | Shop | 375.3461 | 0 | 0 | 375.3461
G37 |  | - | Shop | 351.5146 | 0 | 0 | 351.5146
1st Podium Floor for Commercial, Electrical Room & Parking
F16 |  | - | Shop | 162.305 | 0 | 0 | 162.305
F17 |  | - | Shop | 165.3673 | 0 | 0 | 165.3673
F18 |  | - | Shop | 182.5165 | 0 | 0 | 182.5165
F19 |  | - | Shop | 278.4862 | 0 | 0 | 278.4862
F20 |  | - | Shop | 244.1275 | 0 | 0 | 244.1275
F21 |  | - | Shop | 271.8556 | 0 | 0 | 271.8556
F22 |  | - | Shop | 305.8375 | 0 | 0 | 305.8375
F23 |  | - | Shop | 289.332 | 0 | 0 | 289.332
F24 |  | - | Shop | 279.6229 | 0 | 0 | 279.6229
F25 |  | - | Shop | 265.0592 | 0 | 0 | 265.0592
F26 |  | - | Shop | 506.3698 | 0 | 0 | 506.3698
F27 |  | - | Shop | 154.6378 | 0 | 0 | 154.6378
F28 |  | - | Shop | 165.3673 | 0 | 0 | 165.3673
F29 |  | - | Shop | 164.3577 | 0 | 0 | 164.3577
F30 |  | - | Shop | 343.3824 | 0 | 0 | 343.3824
F31 |  | - | Shop | 502.076 | 0 | 0 | 502.076
F32 |  | - | Shop | 1038.5376 | 0 | 0 | 1038.5376
2nd Podium Floor For Service & Parking
3rd Floor For Residential, Society Office, Creche & Fitness Center
B1 |  | - | 1BHK | 319.9061 | 34.4717 | 0 | 354.3778
B2 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 |  | 1284574.5535
B3 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 |  | 16778116.6171
B4 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
B5 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
B6 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
B7 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
B8 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
B9 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
B10 |  | - | Fitness Center
B11 |  | -
B12 |  | -
B13 |  | - | 2BHK | 463.8208 | 64.5571 | 0 | 528.3778 | 41.6145
B14 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | 27.8565
B15 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
B16 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
B17 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
B18 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493
B19 |  | - | 1BHK | 319.9061 | 34.4717 | 0 | 354.3778
4th to 7th , 10th to 12th, 15th to 17th & 20th to 23rd Floor
B1 |  | - | 1BHK | 322.7047 | 64.5571 | 0 | 387.2618 | [6 empty] | 4701,..,2301 | 4701 | 2301
B2 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4702,..,2302 | 4702 | 2302
B3 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4703,..,2303 | 4703 | 2303
B4 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4704,..,2304 | 4704 | 2304
B5 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4705,..,2305 | 4705 | 2305
B6 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4706,..,2306 | 4706 | 2306
B7 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4707,..,2307 | 4707 | 2307
B8 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4708,..,2308 | 4708 | 2308
B9 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4709,..,2309 | 4709 | 2309
B10 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4710,..,2310 | 4710 | 2310
B11 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4711,..,2311 | 4711 | 2311
B12 |  | - | 1BHK | 322.4894 | 64.5571 | 0 | 387.0465 | [6 empty] | 4712,..,2312 | 4712 | 2312
B13 |  | - | 2BHK | 470.925 | 77.4739 | 0 | 548.3989 | [6 empty] | 4713,..,2313 | 4713 | 2313
B14 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4714,..,2314 | 4714 | 2314
B15 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4715,..,2315 | 4715 | 2315
B16 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4716,..,2316 | 4716 | 2316
B17 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4717,..,2317 | 4717 | 2317
B18 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 4718,..,2318 | 4718 | 2318
B19 |  | - | 1BHK | 322.7047 | 64.5571 | 0 | 387.2618 | [6 empty] | 4719,..,2319 | 4719 | 2319
9th, 14th & 19th Floor (Part Refuge Area)
B1 |  | - | 1BHK | 322.7047 | 64.5571 | 0 | 387.2618 | [6 empty] | 901,..,1901 | 901 | 1901
B2 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 902,..,1902 | 902 | 1902
B3 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 903,..,1903 | 903 | 1903
B4 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 904,..,1904 | 904 | 1904
B5 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 905,..,1905 | 905 | 1905
B6 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 906,..,1906 | 906 | 1906
B7 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 907,..,1907 | 907 | 1907
B8 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 908,..,1908 | 908 | 1908
B9 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 909,..,1909 | 909 | 1909
B10 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 910,..,1910 | 910 | 1910
B11 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 911,..,1911 | 911 | 1911
B12 |  | - | 1BHK | 322.4894 | 64.5571 | 0 | 387.0465 | [6 empty] | 912,..,1912 | 912 | 1912
B13 |  | Refuge Area | [11 empty] | 913,..,1913 | 913 | 1913
B14 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 914,..,1914 | 914 | 1914
B15 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 915,..,1915 | 915 | 1915
B16 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 916,..,1916 | 916 | 1916
B17 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 917,..,1917 | 917 | 1917
B18 |  | - | 1BHK | 316.8922 | 64.5571 | 0 | 381.4493 | [6 empty] | 918,..,1918 | 918 | 1918
B19 |  | - | 1BHK | 322.7047 | 64.5571 | 0 | 387.2618 | [6 empty] | 919,..,1919 | 919 | 1919
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor
201,..,901 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 201,..,901 | 201 | 901
202,..,902 | [6 empty] | 0 | [6 empty] | 202,..,902 | 202 | 902
203,..,903 | [6 empty] | 0 | [6 empty] | 203,..,903 | 203 | 903
204,..,904 | [6 empty] | 0 | [6 empty] | 204,..,904 | 204 | 904
205,..,905 | [6 empty] | 0 | [6 empty] | 205,..,905 | 205 | 905
206,..,906 | [6 empty] | 0 | [6 empty] | 206,..,906 | 206 | 906
207,..,907 | [6 empty] | 0 | [6 empty] | 207,..,907 | 207 | 907
208,..,908 | [6 empty] | 0 | [6 empty] | 208,..,908 | 208 | 908
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 201 to 501 | 201 | 501
202 to 502 | [6 empty] | 0 | [6 empty] | 202 to 502 | 202 | 502
203 to 503 | [6 empty] | 0 | [6 empty] | 203 to 503 | 203 | 503
204 to 504 | [6 empty] | 0 | [6 empty] | 204 to 504 | 204 | 504
205 to 505 | [6 empty] | 0 | [6 empty] | 205 to 505 | 205 | 505
206 to 506 | [6 empty] | 0 | [6 empty] | 206 to 506 | 206 | 506
207 to 507 | [6 empty] | 0 | [6 empty] | 207 to 507 | 207 | 507
208 to 508 | [6 empty] | 0 | [6 empty] | 208 to 508 | 208 | 508
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 201 & 501 | 201 | 501
202 & 502 | [6 empty] | 0 | [6 empty] | 202 & 502 | 202 | 502
203 & 503 | [6 empty] | 0 | [6 empty] | 203 & 503 | 203 | 503
204 & 504 | [6 empty] | 0 | [6 empty] | 204 & 504 | 204 | 504
205 & 505 | [6 empty] | 0 | [6 empty] | 205 & 505 | 205 | 505
206 & 506 | [6 empty] | 0 | [6 empty] | 206 & 506 | 206 | 506
207 & 507 | [6 empty] | 0 | [6 empty] | 207 & 507 | 207 | 507
208 & 508 | [6 empty] | 0 | [6 empty] | 208 & 508 | 208 | 508
Project Specific Remarks & Observation
* | Construction work is in process at the time of visit.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Balcony
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | We have taken approved plans & CC from Rera.
* | Please Check for Fire Noc.
* | In the approved plan, on Floors 9th, 14th, and 19th, these refuge floors are repeated in the non-refuge floor plan.
* | We have not drafted the 8th, 13th, and 18th floors as the approved floor plan is missing. Provide an approved plan for the 8th, 13th, and 18th floors.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
Site & Building/Tower Photographs
Name of the Project |  |  | Y Square, Building No.21 (Wing A & B)
Project Site Address |  |  | Y Square" Opp Tribe Restaurant, Next To Blossom School, Kolshet Rd, Dhokali, Thane(W) - 400607
Site Visit Date & Time |  |  | 04/07/2025 at 11:19AM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr.Ajay Songare |  | Authorized Signatory Name & Signature
Wing A
Wing B
Bldg No. 21
N
Wing A
Wing B
Wing B
Wing A
Wing A
Wing A
Wing A
Wing B
Wing B
Note on C9: SACHIN: As per initiation Mail
Note on C17: Maybe same as RERA Registration Validity or different
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G114: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%