## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  |  | : | Dosti West County ­ Dosti Nest ­ Phase 1 Building No 3 (A, B & C Wing) - Dosti Merlin Dosti West County Dosti Nest Phase 2 EWS Building No 1 = Dove (Part I )(A Wing) |  | Date of Site Visit |  | 04/07/2025 @11:43AM |  | 2025-04-07 | 2025-07-04 | 88
Name of the person met at site & Contact No. |  |  | : | Mr. Sandeep Jha (Sales) - 8097547099/7304459405 |  | Date of Report Release |  | 2025-07-08 | Dosti West County ­ Dosti Nest ­ Phase 1 & 2
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr.Suraj Khare
Builder Group Name |  |  | : | Dosti Enterprises | Developer Name | : | Dosti Realty LTD
Developer Office Address |  |  | : | Lawrency & Mayo House 1st Floor,276 Dr.D.N.Road, Fort Mumbai MH 400001
Project Address | : | As per ARF | : | Dosti West County, Dosti Nest phase I, Balkum. Off Old Mumbai-Agra Road, Thane-Bhiwandi-Wadpa Road, Thane (W) 400608.
| : | As per Legal Documents | : | Dosti West County ­ Dosti Nest ­ Phase I, New Survey No.21(pt), 22(pt), 25/5(pt), 25/6, 25/7(pt), 25/8, 25/9(pt), 25/10A, 25/10B, 25/11 & Others., near Dosti Cedar, Balkum Pipeline Road, Balkum, Thane West, Thane, Thane - 400608.
| : | As per Actual at site | : | Dosti West County ­ Dosti Nest ­ Phase I, near Dosti Cedar, Balkum Pipeline Road, Balkum, Thane West, Thane, Thane - 400608.
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate, Sale Plan, NOC
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Thane Municipal Corporation
RERA Registration No. | : | Dosti Merlin = P51700033640 Dove (Part I)(A Wing) = P51700033663 |  |  | RERA Registration Validity | : | 2027-06-30
Project Launch Date | : | 2027-06-30 |  |  | Construction Start Date | : | 2022-03-02
Proposed Date of Completion (As per RERA) | : | 2027-06-30 |  |  | Developer Bank Name (As per RERA) | : | Kotak Mahindra Bank IFSC Code - KKBK0000957
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  |  | Plot Area (In Sq.Mt) | : | 24500
FSI/FAR Permissible | : | 1.1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 151788.3
Permissible Built up Area (In Sq.Mt) | : | 152005.36 |  |  | Total Number of Units Planned | : | As per RERA, Flats = 1306 & Shop = NA
Total Number of Units Approved | : | Flats = 1298 |  |  | If Mixed, No. of Commercial Units | : | Shop = 24
Latitude | : | 19.229 |  |  | Longitude | : | 72.9963
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Senior Citizen's Area, Outdoor Activity Lawn, Chlorine-free infinity Pool, Kids Play Area.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 1.1 KM from Balkum Pada Number 1 Bus Stop
Distance from the nearest School (Km) | : | About 2.1 KM from Shantiniketan English School |  |  | Distance from Hospital (Km) | : | About 3.8KM form Highland Speciality Hospital
Distance from the Main Market (Km) | : | 1. Approx. 2 KM from Balaji Super Market. 2. Approx. 7.5 KM from D-Mart |  |  | Distance from Railway Station (Km) | : | 7 KM from Thane Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Open Plot | Open Plot | Road |  | Play Ground
As per Site / Actual |  |  | : | Open Plot | Open Plot | Balkum Pipeline Road |  | Open Plot
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Building No. 3-A Wing |  | Sale |  | St(pt)/Gr(Pt) + 3P + Upper Stilt + 1st to 32nd Floor |  |  | St(pt)/Gr(Pt) + 3P + Upper Stilt + 1st to 31st Floor
Building No. 3-B Wing |  | Sale |  | St(pt)/Gr(Pt) + 3P + Upper Stilt + 1st to 32nd Floor |  |  | St(pt)/Gr(Pt) + 3P + Upper Stilt + 1st to 32nd Floor
Building No. 3-C Wing |  | Sale |  | St(pt)/Gr(Pt) + 3P + Upper Stilt + 1st to 32nd Floor |  |  | St(pt)/Gr(Pt) + 3P + Upper Stilt + 1st to 32nd Floor
EWS Building No 1 = Dove (Part I )(A Wing) |  | Sale |  | St(pt)/Gr(Pt) + 3P + Upper Stilt + 1st to 27th Floor |  |  | St(pt)/Gr(Pt) + 3P + Upper Stilt + 1st to 27th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | V.P.S05/0135/17/TMC/TD-DP/TPS/3844/21 Date: 31/12/2021
Approved Plan Details | : | V.P.S05/0135/17/TMC/TD-DP/TPS/3844/21 Date: 31/12/2021
CC Details | : | S05/0135/17/TMC/TDD/4392/23 Date: 08/05/2023 Valid Up to: Building No. 3 - A Wing = St(pt)/ Gr(Pt) + 3P + Upper Stilt + 1st to 20th Floor Building No. 3 - B Wing = St(pt)/ Gr(Pt) + 3P + Upper Stilt + 1st to 20th Floor Building No. 3 - C Wing = St(pt)/ Gr(Pt) + 3P + Upper Stilt + 1st to 20th Floor EWS Building No. 1 = St(pt)/ Gr(Pt) + 3P + Upper Stilt + 1st to 12th Floor
Environmental Clearance Details | : | SIA/MH/MIS/145371/2020 Date:31/03/2020 |  |  | Airport Authority Clearance Details | : | -
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | : | -
Construction Status
Building No. 3 (A Wing) = St(pt)/Gr(Pt) + 3P + Upper Stilt + 1st to 32nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 28 Floor, Flooring & Fitting upto 25 Floor, Wooden Work upto 15 Floor, Electrical & Sanitary fittings upto 15 Floor Completed
|  |  |  | 0 | 1 |  | 4 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8
Excavation |  | 32 |  | 100% | 74.53% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 28 Floor, Flooring & Fitting upto 25 Floor, Wooden Work upto 15 Floor, Electrical & Sanitary fittings upto 15 Floor Completed |  | Excavation in process | 16
Plinth |  | 32 |  | 100% |  |  |  |  | Excavation Completed | 32
RCC (Including podiums) |  | 37 |  | 100% |  |  |  |  | Footing in Process | 6.4
Brickwork |  | 32 |  | 100% |  |  |  |  | Footing Completed | 12.8
Internal Plaster |  | 32 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 32 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 28 |  | 87.5% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 25 |  | 78.12% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 15 |  | 46.88% |  |  |  |  | Plinth in process | 22.4
Electrical & Sanitary fittings |  | 15 |  | 46.88% |  |  |  |  | Plinth completed | 32
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building No. 3 (B Wing = St(pt) + Gr(Pt) + 3P + Upper Stilt + 1st to 32nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 28 Floor, Flooring & Fitting upto 27 Floor, Wooden Work upto 16 Floor, Electrical & Sanitary fittings upto 20 Floor Completed
|  |  |  | 0 | 1 |  | 4 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8
Excavation |  | 32 |  | 100% | 75.62% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 28 Floor, Flooring & Fitting upto 27 Floor, Wooden Work upto 16 Floor, Electrical & Sanitary fittings upto 20 Floor Completed |  | Excavation in process | 16
Plinth |  | 32 |  | 100% |  |  |  |  | Excavation Completed | 32
RCC (Including podiums) |  | 37 |  | 100% |  |  |  |  | Footing in Process | 6.4
Brickwork |  | 32 |  | 100% |  |  |  |  | Footing Completed | 12.8
Internal Plaster |  | 32 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 32 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 28 |  | 87.5% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 27 |  | 84.38% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 16 |  | 50% |  |  |  |  | Plinth in process | 22.4
Electrical & Sanitary fittings |  | 20 |  | 62.5% |  |  |  |  | Plinth completed | 32
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building No. 3 (C Wing = St(pt) + Gr(Pt) + 3P + Upper Stilt + 1st to 32nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 28 Floor, Flooring & Fitting upto 27 Floor, Wooden Work upto 20 Floor, Electrical & Sanitary fittings upto 20 Floor Completed
|  |  |  | 0 | 1 |  | 4 | 32 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8
Excavation |  | 32 |  | 100% | 75.94% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 28 Floor, Flooring & Fitting upto 27 Floor, Wooden Work upto 20 Floor, Electrical & Sanitary fittings upto 20 Floor Completed |  | Excavation in process | 16
Plinth |  | 32 |  | 100% |  |  |  |  | Excavation Completed | 32
RCC (Including podiums) |  | 37 |  | 100% |  |  |  |  | Footing in Process | 6.4
Brickwork |  | 32 |  | 100% |  |  |  |  | Footing Completed | 12.8
Internal Plaster |  | 32 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 32 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 28 |  | 87.5% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 27 |  | 84.38% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 20 |  | 62.5% |  |  |  |  | Plinth in process | 22.4
Electrical & Sanitary fittings |  | 20 |  | 62.5% |  |  |  |  | Plinth completed | 32
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
EWS Building No 1 = Dove (Part I )(A Wing) = St(pt)/Gr(Pt) + 3P + Upper Stilt + 1st to 27th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 26 Floor, Flooring & Fitting upto 25 Floor, Wooden Work upto 20 Floor, Electrical & Sanitary fittings upto 20 Floor Completed
|  |  |  | 0 | 1 |  | 4 | 27 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 6.75
Excavation |  | 27 |  | 100% | 77.78% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 26 Floor, Flooring & Fitting upto 25 Floor, Wooden Work upto 20 Floor, Electrical & Sanitary fittings upto 20 Floor Completed |  | Excavation in process | 13.5
Plinth |  | 27 |  | 100% |  |  |  |  | Excavation Completed | 27
RCC (Including podiums) |  | 32 |  | 100% |  |  |  |  | Footing in Process | 5.4
Brickwork |  | 27 |  | 100% |  |  |  |  | Footing Completed | 10.8
Internal Plaster |  | 27 |  | 100% |  |  |  |  | Basement 1 | 0 | https://www.youtube.com/watch?v=jDg__1SFRYI
External Plaster |  | 27 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 26 |  | 96.3% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 25 |  | 92.59% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 20 |  | 74.07% |  |  |  |  | Plinth in process | 18.9
Electrical & Sanitary fittings |  | 20 |  | 74.07% |  |  |  |  | Plinth completed | 27
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 75.97%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 16500 to 17500 | Rate For Shop Per Sq. Ft. (on Carpet area) | : | 28000
Car Parking Charges |  |  | : | 700000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 2629.1342
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 7710.8881
Distress Value (Rs. Per sqft) | [5 empty] | : | 2103.3073
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
B Wing |  | Sale |  | Shops | 12 |  | 1666.8054 | 2666.8886
C Wing |  | Sale |  | Shops | 12 |  | 1681.0139 | 2689.6222
Total |  |  |  |  | 24 |  | 3347.8193 | 5356.5108
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Merlin - A Wing |  | Sale |  | Flats | 246 |  | 99454.8391 | 159127.7426
Merlin - B Wing |  | Sale |  | Flats | 418 |  | 170266.459 | 272426.3343
Merlin - C Wing |  | Sale |  | Flats | 254 |  | 102691.3586 | 164306.1738
Dove (Part I )(A Wing) |  | Sale |  | Flats | 380 |  | 105366.6432 | 168586.6291
Total |  |  |  |  | 1298 |  | 477779.2999 | 764446.8799
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
60%
Building No 3 - Dosti Merlin
A Wing
Ground Floor for Parking
1st to 2nd Parking Floor
Upper Stilt Floor For Residential
Upper Stilt Floor For Residential |  | 1 |  | 1BHK | 438.633 |  | 0 | 701.8128
|  | 2 |  | 1BHK | 438.633 |  | 0 | 701.8128
|  | 3 |  | 1BHK | 438.633 |  | 0 | 701.8128
|  | 4 |  | 1BHK | 438.633 |  | 0 | 701.8128
1st & 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 31st Floor
1st & 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 31st Floor |  | 1 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 12401,..,3101 | 12401 | 3101
|  | 2 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 12402,..,3102 | 12402 | 3102
|  | 3 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 12403,..,3103 | 12403 | 3103
|  | 4 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 12404,..,3104 | 12404 | 3104
|  | 5 |  | 1BHK | 376.4171 |  | 0 | 602.2673 |  |  |  |  | 12405,..,3105 | 12405 | 3105
|  | 6 |  | 1BHK | 376.4171 |  | 0 | 602.2673 |  |  |  |  | 12406,..,3106 | 12406 | 3106
|  | 7 |  | 1BHK | 364.5767 |  | 0 | 583.3227 |  |  |  |  | 12407,..,3107 | 12407 | 3107
|  | 8 |  | 1BHK | 364.5767 |  | 0 | 583.3227 |  |  |  |  | 12408,..,3108 | 12408 | 3108
3rd, 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
3rd, 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 1 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 3801,..,2801 | 3801 | 2801
|  | 2 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 3802,..,2802 | 3802 | 2802
|  | Refuge Area | [10 empty] | 3803,..,2803 | 3803 | 2803
|  | 4 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 3804,..,2804 | 3804 | 2804
|  | 5 |  | 1BHK | 376.4171 |  | 0 | 602.2673 |  |  |  |  | 3805,..,2805 | 3805 | 2805
|  | 6 |  | 1BHK | 376.4171 |  | 0 | 602.2673 |  |  |  |  | 3806,..,2806 | 3806 | 2806
|  | 7 |  | 1BHK | 364.5767 |  | 0 | 583.3227 |  |  |  |  | 3807,..,2807 | 3807 | 2807
|  | 8 |  | 1BHK | 364.5767 |  | 0 | 583.3227 |  |  |  |  | 3808,..,2808 | 3808 | 2808
B Wing
Ground Floor for Commercial & Parking
Ground Floor for Commercial & Parking |  | 1 |  | Shop | 132.6125 |  | 0 | 212.18 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 2 |  | Shop | 132.6125 |  | 0 | 212.18 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 3 |  | Shop | 147.0362 |  | 0 | 235.258 | 17491.0394 |  |  |  | #REF! | #REF! | #NUM!
|  | 4 |  | Shop | 147.0362 |  | 0 | 235.258 | 15621.9178 |  |  |  | #REF! | #REF! | #NUM!
|  | 5 |  | Shop | 132.6125 |  | 0 | 212.18 | 15626.1468 |  |  |  | #REF! | #REF! | #NUM!
|  | 6 |  | Shop | 135.5188 |  | 0 | 216.83 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 7 |  | Shop | 135.5188 |  | 0 | 216.83 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 8 |  | Shop | 132.6125 |  | 0 | 212.18 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 9 |  | Shop | 152.8488 |  | 0 | 244.5581 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 10 |  | Shop | 150.2654 |  | 0 | 240.4247 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 11 |  | Shop | 132.6125 |  | 0 | 212.18 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 12 |  | Shop | 135.5188 |  | 0 | 216.83 |  |  |  |  | #REF! | #REF! | #NUM!
1st to 2nd Parking Floor
Upper Stilt Floor For Residential (Part Stilt Area)
Upper Stilt Floor For Residential (Part Stilt Area) |  | 6 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 7 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 8 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 9 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 10 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 11 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 12 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 13 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | #REF! | #REF! | #NUM!
1st & 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 31st Floor
1st & 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 31st Floor |  | 1 |  | 1BHK | 376.4171 |  | 0 | 602.2673 |  |  |  |  | 12401,..,3101 | 12401 | 3101
|  | 2 |  | 1BHK | 376.4171 |  | 0 | 602.2673 |  |  |  |  | 12402,..,3102 | 12402 | 3102
|  | 3 |  | 1RK | 278.68 |  | 0 | 445.8879 |  |  |  |  | 12403,..,3103 | 12403 | 3103
|  | 4 |  | 1BHK | 376.4171 |  | 0 | 602.2673 |  |  |  |  | 12404,..,3104 | 12404 | 3104
|  | 5 |  | 1BHK | 376.4171 |  | 0 | 602.2673 |  |  |  |  | 12405,..,3105 | 12405 | 3105
|  | 6 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 12406,..,3106 | 12406 | 3106
|  | 7 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 12407,..,3107 | 12407 | 3107
|  | 8 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 12408,..,3108 | 12408 | 3108
|  | 9 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 12409 & 3109 | 12409 | 3109
|  | 10 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 12410 & 3110 | 12410 | 3110
|  | 11 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 12411 & 3111 | 12411 | 3111
|  | 12 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 12412 & 3112 | 12412 | 3112
|  | 13 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 12413 & 3113 | 12413 | 3113
3rd, 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
3rd, 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 1 |  | 1BHK | 376.4171 |  | 0 | 602.2673 |  |  |  |  | 3801,..,2801 | 3801 | 2801
|  | 2 |  | 1BHK | 376.4171 |  | 0 | 602.2673 |  |  |  |  | 3802,..,2802 | 3802 | 2802
|  | 3 |  | 1RK | 278.68 |  | 0 | 445.8879 |  |  |  |  | 3803,..,2803 | 3803 | 2803
|  | 4 |  | 1BHK | 376.4171 |  | 0 | 602.2673 |  |  |  |  | 3804,..,2804 | 3804 | 2804
|  | 5 |  | 1BHK | 376.4171 |  | 0 | 602.2673 |  |  |  |  | 3805,..,2805 | 3805 | 2805
|  | 6 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 3806,..,2806 | 3806 | 2806
|  | 7 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 3807,..,2807 | 3807 | 2807
|  | 8 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 3808,..,2808 | 3808 | 2808
|  | 9 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 3809 & 2809 | 3809 | 2809
|  | Refuge Area |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 3810 & 2810 | 3810 | 2810
|  | 11 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 3811 & 2811 | 3811 | 2811
|  | 12 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 3812 & 2812 | 3812 | 2812
|  | 13 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 3813 & 2813 | 3813 | 2813
C Wing
Ground Floor for Commercial & Parking
Ground Floor for Commercial & Parking |  | 13 |  | Shop | 135.5188 |  | 0 | 216.83 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 14 |  | Shop | 132.6125 |  | 0 | 212.18 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 15 |  | Shop | 152.8488 |  | 0 | 244.5581 | 17491.0394 |  |  |  | #REF! | #REF! | #NUM!
|  | 16 |  | Shop | 152.8488 |  | 0 | 244.5581 | 15621.9178 |  |  |  | #REF! | #REF! | #NUM!
|  | 17 |  | Shop | 132.6125 |  | 0 | 212.18 | 15626.1468 |  |  |  | #REF! | #REF! | #NUM!
|  | 18 |  | Shop | 135.5188 |  | 0 | 216.83 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 19 |  | Shop | 135.5188 |  | 0 | 216.83 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 20 |  | Shop | 132.6125 |  | 0 | 212.18 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 21 |  | Shop | 152.8488 |  | 0 | 244.5581 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 22 |  | Shop | 152.8488 |  | 0 | 244.5581 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 23 |  | Shop | 132.6125 |  | 0 | 212.18 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 24 |  | Shop | 132.6125 |  | 0 | 212.18 |  |  |  |  | #REF! | #REF! | #NUM!
1st to 2nd Parking Floor
Upper Stilt Floor For Residential (Part Stilt Area)
Upper Stilt Floor For Residential (Part Stilt Area) |  | 1 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 2 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 3 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | #REF! | #REF! | #NUM!
|  | 4 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | #REF! | #REF! | #NUM!
1st & 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 31st Floor
1st & 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 31st Floor |  | 1 |  | 1BHK | 364.5767 |  | 0 | 583.3227 |  |  |  |  | 12401,..,3101 | 12401 | 3101
|  | 2 |  | 1BHK | 364.5767 |  | 0 | 583.3227 |  |  |  |  | 12402,..,3102 | 12402 | 3102
|  | 3 |  | 1BHK | 376.4171 |  | 0 | 602.2673 |  |  |  |  | 12403,..,3103 | 12403 | 3103
|  | 4 |  | 1BHK | 376.4171 |  | 0 | 602.2673 |  |  |  |  | 12404,..,3104 | 12404 | 3104
|  | 5 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 12405,..,3105 | 12405 | 3105
|  | 6 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 12406,..,3106 | 12406 | 3106
|  | 7 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 12407,..,3107 | 12407 | 3107
|  | 8 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 12408,..,3108 | 12408 | 3108
3rd, 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
3rd, 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 1 |  | 1BHK | 364.5767 |  | 0 | 583.3227 |  |  |  |  | 3801,..,2801 | 3801 | 2801
|  | 2 |  | 1BHK | 364.5767 |  | 0 | 583.3227 |  |  |  |  | 3802,..,2802 | 3802 | 2802
|  | 3 |  | 1BHK | 376.4171 |  | 0 | 602.2673 |  |  |  |  | 3803,..,2803 | 3803 | 2803
|  | 4 |  | 1BHK | 376.4171 |  | 0 | 602.2673 |  |  |  |  | 3804,..,2804 | 3804 | 2804
|  | 5 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 3805,..,2805 | 3805 | 2805
|  | 6 |  | Refuge Area | [8 empty] | 3806,..,2806 | 3806 | 2806
|  | 7 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 3807,..,2807 | 3807 | 2807
|  | 8 |  | 1BHK | 438.633 |  | 0 | 701.8128 |  |  |  |  | 3808,..,2808 | 3808 | 2808
Details of Flats in Building
Flat No. (Sale Plan) |  | Flat No. (Approved Plan) |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
60%
EWS Building No 1 = Dove
Part 1 (Wing A)
Ground Floor for Parking
1st to 3rd Parking Floor
Upper Stilt Floor for Parking & Residential
5 |  | 5 |  | 1BHK | 277.2806 |  | 0 | 443.649 | 15507.7542
6 |  | 6 |  | 1BHK | 277.2806 |  | 0 | 443.649
7 |  | 7 |  | 1BHK | 277.2806 |  | 0 | 443.649
8 |  | 8 |  | 1BHK | 277.2806 |  | 0 | 443.649
9 |  | 9 |  | 1BHK | 277.2806 |  | 0 | 443.649
10 |  | 10 |  | 1BHK | 277.2806 |  | 0 | 443.649
11 |  | 11 |  | 1BHK | 277.2806 |  | 0 | 443.649
1st to 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th Floor
1 |  | 1 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 1201,..,2701 | 1201 | 2701
2 |  | 2 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 1202,..,2702 | 1202 | 2702
3 |  | 3 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 1203,..,2703 | 1203 | 2703
4 |  | 4 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 1204,..,2704 | 1204 | 2704
5 |  | 5 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 1205,..,2705 | 1205 | 2705
6 |  | 6 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 1206,..,2706 | 1206 | 2706
7 |  | 7 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 1207,..,2707 | 1207 | 2707
8 |  | 8 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 1208,..,2708 | 1208 | 2708
9 |  | 9 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 1209,..,2709 | 1209 | 2709
10 |  | 10 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 1210,..,2710 | 1210 | 2710
11 |  | 11 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 1211,..,2711 | 1211 | 2711
12 |  | 40 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 1212,..,2712 | 1212 | 2712
13 |  | 41 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 1213,..,2713 | 1213 | 2713
14 |  | 42 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 1214,..,2714 | 1214 | 2714
3rd, 8th, 13th, 18th & 23rd Floor (Part Refuge Area)
1 |  | 1 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 3801,..,2301 | 3801 | 2301
2 |  | 2 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 3802,..,2302 | 3802 | 2302
3 |  | 3 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 3803,..,2303 | 3803 | 2303
4 |  | 4 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 3804,..,2304 | 3804 | 2304
5 |  | 5 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 3805,..,2305 | 3805 | 2305
6 |  | 6 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 3806,..,2306 | 3806 | 2306
7 |  | 7 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 3807,..,2307 | 3807 | 2307
8 |  | 8 |  | Refuge Area | [8 empty] | 3808,..,2308 | 3808 | 2308
9 |  | 9 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 3809,..,2309 | 3809 | 2309
10 |  | 10 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 3810,..,2310 | 3810 | 2310
11 |  | 11 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 3811,..,2311 | 3811 | 2311
12 |  | 40 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 3812,..,2312 | 3812 | 2312
13 |  | 41 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 3813,..,2313 | 3813 | 2313
14 |  | 42 |  | 1BHK | 277.2806 |  | 0 | 443.649 |  |  |  |  | 3814,..,2314 | 3814 | 2314
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Construction work is in process at the time of Visit (Internal visit was not allowed). 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. On Site, we meet Mr. Sandeep Jha (Sales) - 8097547099/7304459405. 8. Construction Work goes beyond approved CC permission. Provide latest approved CC.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Dosti West County ­ Dosti Nest ­ Phase 1 & 2
Project Site Address |  |  | : | Dosti West County, Dosti Nest phase I, Balkum. Off Old Mumbai-Agra Road, Thane-Bhiwandi-Wadpa Road, Thane (W) 400608.
Site Visit Date & Time |  |  | : | 04/07/2025 @11:43AM
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Ajay Songare | Authorized Signatory Name & Signature | :
Building No 3 (A, B & C Wing) - Dosti Merlin
Building No 1 = Dove (Part I )(A Wing)
Wing A
Wing B Part II
Wing B Part I
Wing C
Merlin A
Dove A
Merlin B
Merlin C
Merlin A
Merlin C
Merlin B
Dove A