## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02
Project Name |  | Bella (Wing A to D) |  | Date & Time of Site Visit |  | 07/07/2025 @ 02:00PM |  |  | 2025-04-28 | 2025-07-07
Name of the person met at site & Contact No. |  | Ms Prasadi Sales 8657580976 |  | Date of Report Release |  | 08/07/2025 |  |  |  | 70
Data from APF Request Form
Branch Name/ID |  | Godrej One, Vikhroli East, Mumbai |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | Luceat Realtors Private Limited |  | Developer Name |  | Luceat Realtors Private Limited
Developer Office Address |  | 702, Natraj Building, M. V. Road Junction, Western Express Highway, Andheri East, Mumbai Suburban, Andheri – 400069.
Project Address | As per ARF | (Building name, CTS No., Plot No., Survey No., Road., Locality/Village., Near by Landmark., City., District., Taluka., Pin Code -)
| As per Legal Documents | Bella, CTS No.279, 280, 280/1, 282/A, 282/C & 281/A/1/1, near Kalpataru Crest, LBS Marg, Bhandup, Bhandup (West), Kurla, Mumbai - 400078
| As per Actual at site | Bella, CTS No.279, 280, 280/1, 282/A, 282/C & 281/A/1/1, near Kalpataru Crest, LBS Marg, , Bhandup, Bhandup (West), Kurla, Mumbai - 400078
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC, RERA certificate, NOC
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Municipal Corporation of Greater Mumbai (MCGM)
RERA Registration No. | : | Wing A & B = P51800031973 Wing C & D = P51800029526 |  | RERA Registration Validity | : | Wing A & B = 01/01/2026 Wing C & D = Completed
Project Launch Date | : |  |  | Construction Start Date | :
Proposed Date of Completion (As per RERA) | : | Wing A & B = 01/01/2026 Wing C & D = Completed |  | Developer Bank Name (As per RERA) | : | STANDARD CHARTERED BANK IFSC Code SCBL0036085
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  | Plot Area (In Sq.Mt) | :
FSI/FAR Permissible | : |  |  | Net Plot Area (In Sq.Mt) | :
Permissible Built up Area (In Sq.Mt) | : |  |  | Proposed Built up Area (In Sq.Mt) | :
Total Number of Units Approved | : | Flats = & Shop = |  | Total Number of Units Planned | : | As per RERA Site Flats = & Shop =
Latitude, Longitude | : | 19.1558544,72.9379579 |  | Landmark | : | Kalpataru Crest
Location Link | : | https://goo.gl/maps/ivcADK5Rsufi3ahXA
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developed |  | Class of Locality | : | Upper
Type of Road | : | Bitumen |  | Width of the Road | : | 9m
Distance from Train stand (Km) | : | 1.9 KM from Bhandup Railway Station |  | Distance from Bus stand (Km) | : | 270 M from Shangrila Biscuit Factory Bus Stop
Distance from the nearest School (Km) | : | About 4KM from School |  | Distance from Hospital (Km) | : | About 4K form Hospital
Distance from the Main Market (Km) | : | 1. Approx. 2KM from Village Market. 2. Approx. 10KM from Panvel Main Market. |  | Distance from Railway Station (Km) | : | 5.4KM from Somatne Railway Station 10.5KM from Panvel Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North | South | East | West
East |  | Other Plot |  |  | Building
West |  | Other Plot |  |  | Building
North |  | 12.20 M W Road |  |  | Bhandup Sonapur Road
South |  | Other Plot |  |  | Building
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Wing A & B |  | Sale | B + Gr/Stilt + 1st to 22nd Floor |  |  | B + Gr/Stilt + 1st to 22nd Floor
Wing C & D |  | Sale | B + Gr/Stilt + 1st to 22nd Floor |  |  | B + Gr/Stilt + 1st to 22nd Floor
Wing C |  | Sale | B + Gr/Stilt + 1st to 22nd Floor |  |  | B + Gr/Stilt + 1st to 22nd Floor
Wing D |  | Sale | B + Gr/Stilt + 1st to 22nd Floor |  |  | B + Gr/Stilt + 1st to 22nd Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : |  |  |  |  | Date:
Approved Plan Details | : |  |  |  |  | Date:
CC Details Valid Up to: |  | CHE/ES/1674/S/337(NEW)/FCC/3/Amend |  |  |  | Date: | 2024-05-13
|  | Full C.C. is re endorsed for wing ‘C’ & ‘D’ and further C.C. upto 18th floor is granted for wing ‘A’ & ‘B’ as per amended approved plan dated 09.05.2024 by restricting C.C. of 19th to 22nd floor for wing ‘A’ & ‘B’ subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution. |  |  |  | Valid Upto Date | 2025-05-12
CC Details Valid Up to: |  | CHE/ES/1674/S/337(NEW)/FCC/4/Amend |  |  |  | Date: | 2024-10-25
|  | Further C.C. is granted for staircase, lift core, lobby area from 19th floor to terrace floor with OHT on terrace floor of wing ‘A’ & ‘B’ only as per last approved amended plans dated 09.05.2024 subject to timely renewal of B.G. ,SWM NOC, Workmen’s compensation policy and taking precaution during construction work. |  |  |  | Valid Upto Date | 2025-05-23
CC Details Valid Up to: |  | CHE/ES/1674/S/337(NEW)/FCC/5/Amend |  |  |  | Date: | 2025-04-02
|  | Full C.C. is granted for Wing A & Wing B as per last approved amended plans dated 09.05.2024, subject to timely renewal of B.G., SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction along with precautionary measures for air pollution. |  |  |  | Valid Upto Date | 2025-05-23
Environmental Clearance Details | : |  |  |  |  | Date:
Change of User/Zone Certificate Details | : |  |  |  |  | Date:
Airport Authority Clearance Details | : |  |  |  |  | Date:
Part O.Certificate No.: Approved upto : | : | CHE/ES/1674/S/337(NEW)/OCC/1/New Part OC for Wing ‘A’ - Part Basement + Part Ground for shops + part stilt + 1st to 3rd Part Commercial floors Wing ‘C’ - Stilt & part Ground floor + 1st to 22nd upper residential floors. Wing ‘D’ - Ground for shops + part stilt + 1st to 3rd Part Commercial floors + 4th to 22nd upper floor upper residential floors. |  |  |  | Date: | 24/09/2024
Construction Status
Wing A & B = B + Gr/Stilt + 1st to 22nd Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 22 Slab, Brickwork upto 21 Floor, Internal Plaster upto 18 Floor, External Plaster upto 18 Floor, External Plumbing, Elevation and Waterproofing upto 12 Floor, Flooring & Fitting upto 12 Floor, Wooden Work upto 8 Floor, Electrical & Sanitary fittings upto 8 Floor Completed
|  |  | 1 | 1 |  | 0 | 22 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 67.78% |  | Excavation work Completed. Plinth work completed, RCC upto 22 Slab, Brickwork upto 21 Floor, Internal Plaster upto 18 Floor, External Plaster upto 18 Floor, External Plumbing, Elevation and Waterproofing upto 12 Floor, Flooring & Fitting upto 12 Floor, Wooden Work upto 8 Floor, Electrical & Sanitary fittings upto 8 Floor Completed |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 22 | 95.65% |  |  |  |  | Footing in Process | 4.4
Brickwork |  | 21 | 95.45% |  |  |  |  | Footing Completed | 8.8
Internal Plaster |  | 18 | 81.82% |  |  |  |  | Basement 1 | 0
External Plaster |  | 18 | 81.82% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 12 | 54.55% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 12 | 54.55% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 8 | 36.36% |  |  |  |  | Plinth in process | 14.3
Electrical & Sanitary fittings |  | 8 | 36.36% |  |  |  |  | Plinth completed | 22
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Wing C & D = B + Gr/Stilt + 1st to 22nd Floor. |  |  | Basement | Ground |  | Podium | Floors | All work completed. Please provide OC.
|  |  | 0 | 1 |  | 0 | 22 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 100% |  | All work Completed. OC Received. |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 4.4
Brickwork |  | 22 | 100% |  |  |  |  | Footing Completed | 8.8
Internal Plaster |  | 22 | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 22 | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 22 | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 22 | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 22 | 100% |  |  |  |  | Plinth in process | 15.4
Electrical & Sanitary fittings |  | 22 | 100% |  |  |  |  | Plinth completed | 22
Building Common Amenities |  | 22 | 100%
Possession |  | 22 | 100%
Construction Status
Wing C= B + Gr/Stilt + 1st to 22nd Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  | 0 | 1 |  | 0 | 22 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 4.4
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 8.8
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 15.4
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 83.89%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 26000 to 26500 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 700000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 5392.9766
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 13213.4894
Distress Value (Rs. Per sqft) |  |  |  |  | : | 4314.3813
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Total |  | - |  | 0 |  | 0 | 0
Unit Details, Nomenclature and Area Details (Flats)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Total |  | - |  | 0 |  | 0 | 0
Grand Total |  | - |  | 0 |  | 0
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
1st Floor
101 |  |  |  | 0 | 0 | 0 | 0
102 | [6 empty] | 0
103 | [6 empty] | 0
104 | [6 empty] | 0
105 | [6 empty] | 0
106 | [6 empty] | 0
107 | [6 empty] | 0
108 | [6 empty] | 0
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor
201,..,901 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 201,..,901 | 201 | 901
202,..,902 | [6 empty] | 0 | [5 empty] | 202,..,902 | 202 | 902
203,..,903 | [6 empty] | 0 | [5 empty] | 203,..,903 | 203 | 903
204,..,904 | [6 empty] | 0 | [5 empty] | 204,..,904 | 204 | 904
205,..,905 | [6 empty] | 0 | [5 empty] | 205,..,905 | 205 | 905
206,..,906 | [6 empty] | 0 | [5 empty] | 206,..,906 | 206 | 906
207,..,907 | [6 empty] | 0 | [5 empty] | 207,..,907 | 207 | 907
208,..,908 | [6 empty] | 0 | [5 empty] | 208,..,908 | 208 | 908
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 201 to 501 | 201 | 501
202 to 502 | [6 empty] | 0 | [5 empty] | 202 to 502 | 202 | 502
203 to 503 | [6 empty] | 0 | [5 empty] | 203 to 503 | 203 | 503
204 to 504 | [6 empty] | 0 | [5 empty] | 204 to 504 | 204 | 504
205 to 505 | [6 empty] | 0 | [5 empty] | 205 to 505 | 205 | 505
206 to 506 | [6 empty] | 0 | [5 empty] | 206 to 506 | 206 | 506
207 to 507 | [6 empty] | 0 | [5 empty] | 207 to 507 | 207 | 507
208 to 508 | [6 empty] | 0 | [5 empty] | 208 to 508 | 208 | 508
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 201 & 501 | 201 | 501
202 & 502 | [6 empty] | 0 | [5 empty] | 202 & 502 | 202 | 502
203 & 503 | [6 empty] | 0 | [5 empty] | 203 & 503 | 203 | 503
204 & 504 | [6 empty] | 0 | [5 empty] | 204 & 504 | 204 | 504
205 & 505 | [6 empty] | 0 | [5 empty] | 205 & 505 | 205 | 505
206 & 506 | [6 empty] | 0 | [5 empty] | 206 & 506 | 206 | 506
207 & 507 | [6 empty] | 0 | [5 empty] | 207 & 507 | 207 | 507
208 & 508 | [6 empty] | 0 | [5 empty] | 208 & 508 | 208 | 508
Project Specific Remarks & Observation
* | Wing A & B = Construction work is in process at the time of Visit. Internal photographs not allowed. Wing C & D = All work completed. OC Received.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | We are releasing stage updation report
* | We have updated CC from MCGM site on 06/02/2025.
* | We have updated CC & OC from MCGM site on 28/04/2025.
* | Remark for NOCs
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Validity of CC is expired on 23/05/2025. Please provide revised CC.
Site & Building/Tower Photographs
Name of the Project |  |  | Bella (Wing A to D)
Project Site Address |  |  | Bella, CTS No.279, 280, 280/1, 282/A, 282/C & 281/A/1/1, near Kalpataru Crest, LBS Marg, Bhandup, Bhandup (West), Kurla, Mumbai - 400078
Site Visit Date & Time |  |  | 07/07/2025 @ 02:00PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr.Nainesh Tambe |  | Authorized Signatory Name & Signature
Wing A & B
Wing C & D
Wing C & D
Wing A & B
Wing A & B
Wing
A & B
Wing C & D
Wing C & D
Note on C9: SACHIN: As per initiation Mail
Note on C17: Maybe same as RERA Registration Validity or different
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G118: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%