## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02 | 2025-07-22 |  | 70
Project Name |  |  | : | Sky Gardens at Godrej Vihaa |  | Date & Time of Site Visit |  | 03/07/2025 at 03:21PM | 2025-04-23 | Old Int Date |  | < 90
Name of the person met at site & Contact No. |  |  | : | NA |  | Date of Report Release |  | 05/07/2025
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | K. R. Real Estate Pvt. Ltd. | Developer Name | : | K. R. Real Estate Pvt. Ltd.
Developer Office Address |  |  | :
Project Address | : | As per ARF | : | Godrej Vihaa, S.No.1/6,12, 17C (P No.3),17 D (P No.4), S No.5A to E, S.No.5/6, S.No.5/7 A & B, S.No.5/8, S.No.5/23 PT, S.No.6/1,2,3 & 4, S.No.7 H.No.1 to 4, 8 to 10, S.No.9/5.At Next to Usha Kiran Residency, Badlapur East, Village- Joveli, Tal- Ambernath, Dist- Thane - 421503
| : | As per Legal Documents | :
| : | As per Actual at site | :
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | :
RERA Registration No. | : | P51700013329 |  |  | RERA Registration Validity | : | 2025-12-29
Project Launch Date | : |  |  |  | Construction Start Date | :
Proposed Date of Completion (As per RERA) | : | 2025-12-29
Project Type (Mixed, Residential, Comm.) | : | Residential + Comm. |  |  | Plot Area (In Sq.Mt) | :
FSI/FAR Permissible | : |  |  |  | Proposed Built up Area (In Sq.Mt) | :
Permissible Built up Area (In Sq.Mt) | : |  |  |  | Total Number of Units Planned | : | Flats = & Shop =
Total Number of Units Approved | : | Flats = |  |  | If Mixed, No. of Commercial Units | : | Shop =
Latitude | : | 19.1451 |  |  | Longitude | : | 73.2472
Location Link | : | https://goo.gl/maps/5PCHvq8Dmr9V9tKo7
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Distance from Railway Station (Km) | : | 4.1KM from Badlapur Railway Station |  |  | Distance from Bus stand (Km) | : | 4.2 KM from Badlapur Bus Depot
Distance from the nearest School (Km) | : | About 4KM from School |  |  | Distance from Hospital (Km) | : | About 4K form Hospital
Distance from the Main Market (Km) | : | 1. Approx. 2KM from Village Market. 2. Approx. 10KM from Panvel Main Market. |  |  |  | :
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | :
As per Site / Actual |  |  | : | UshaKiran Residency | Nano City | Neral - Badlapur Rd |  | Platinum Sagar Jewel
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Building No.10 |  | Sale |  | Gr/Stilt + 1st to 18th Floor |  |  | Gr/Stilt + 1st to 18th Floor
Building No.11 |  | Sale |  | Gr/Stilt + 1st to 18th Floor |  |  | Gr/Stilt + 1st to 18th Floor
Building No.12 |  | Sale |  | Gr/Stilt + 1st to 18th Floor |  |  | Gr/Stilt + 1st to 18th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | :
CC Details | : | KBNP/NRV/BP/5733/2017-18/Unique No.79 Date : 26/07/2017 Approved up to: Building No.10, 11 & 12 = Gr/Stilt + 1st to 18th Floor |  |  | Approved Plan Details | : | NA
Environmental Clearance Details | : |  |  |  | Airport Authority Clearance Details | :
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
Construction Status
Building No.10 & 11 = Gr/Stilt + 1st to 18th Floor |  |  | : | Basement | Ground |  | Podium | Floors | All work completed. Please provide OC.
|  |  |  | 0 | 1 |  | 0 | 18 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4.5
Excavation |  | 18 |  | 100% | 100% |  | All work completed. Please provide OC. |  | Excavation in process | 9
Plinth |  | 18 |  | 100% |  |  |  |  | Excavation Completed | 18
RCC (Including podiums) |  | 19 |  | 100% |  |  |  |  | Footing in Process | 4.5
Brickwork |  | 18 |  | 100% |  |  |  |  | Footing Completed | 9
Internal Plaster |  | 18 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 18 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 18 |  | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 18 |  | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 18 |  | 100% |  |  |  |  | Plinth in process | 13.5
Electrical & Sanitary fittings |  | 18 |  | 100% |  |  |  |  | Plinth completed | 18 |  | #VALUE!
Building Common Amenities |  | 18 |  | 100%
Possession |  | 18 |  | 100%
Construction Status
Building No.11 = Gr/Stilt + 1st to 18th Floor |  |  | : | Basement | Ground |  | Podium | Floors | All work completed. Please provide OC.
|  |  |  | 0 | 1 |  | 0 | 18 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4.5
Excavation |  | 18 |  | 100% | 100% |  | All work completed. Please provide OC. |  | Excavation in process | 9
Plinth |  | 18 |  | 100% |  |  |  |  | Excavation Completed | 18
RCC (Including podiums) |  | 19 |  | 100% |  |  |  |  | Footing in Process | 4.5
Brickwork |  | 18 |  | 100% |  |  |  |  | Footing Completed | 9
Internal Plaster |  | 18 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 18 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 18 |  | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 18 |  | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 18 |  | 100% |  |  |  |  | Plinth in process | 13.5
Electrical & Sanitary fittings |  | 18 |  | 100% |  |  |  |  | Plinth completed | 18 |  | #VALUE!
Building Common Amenities |  | 18 |  | 100%
Possession |  | 18 |  | 100%
Construction Status
Building No.12 = Gr/Stilt + 1st to 18th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 15 Floor, External Plaster upto 11 Floor, External Plumbing, Elevation and Waterproofing upto 8 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 18 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4.5
Excavation |  | 18 |  | 100% | 60.83% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 15 Floor, External Plaster upto 11 Floor, External Plumbing, Elevation and Waterproofing upto 8 Floor Completed |  | Excavation in process | 9
Plinth |  | 18 |  | 100% |  |  |  |  | Excavation Completed | 18
RCC (Including podiums) |  | 19 |  | 100% |  |  |  |  | Footing in Process | 4.5
Brickwork |  | 18 |  | 100% |  |  |  |  | Footing Completed | 9
Internal Plaster |  | 15 |  | 83.33% |  |  |  |  | Basement 1 | 0
External Plaster |  | 11 |  | 61.11% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 8 |  | 44.44% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 13.5
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 18 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 86.94%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 7500 | [7 empty] | 7009.3458
Car Parking Charges |  |  | : | 200000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 854.7009
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 4338.5359
Distress Value (Rs. Per sqft) | [5 empty] | : | 683.7607
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Total |  | 0 |  | 0 | 0 |  | 0 | 0
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
50%
1st Floor
101 | [7 empty] | 0
102 | [7 empty] | 0
103 | [7 empty] | 0
104 | [7 empty] | 0
105 | [7 empty] | 0
106 | [7 empty] | 0
107 | [7 empty] | 0
108 | [7 empty] | 0
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor
201,..,901 | [7 empty] | 0 |  |  |  |  | 201,..,901 | 201 | 901
202,..,902 | [7 empty] | 0 |  |  |  |  | 202,..,902 | 202 | 902
203,..,903 | [7 empty] | 0 |  |  |  |  | 203,..,903 | 203 | 903
204,..,904 | [7 empty] | 0 |  |  |  |  | 204,..,904 | 204 | 904
205,..,905 | [7 empty] | 0 |  |  |  |  | 205,..,905 | 205 | 905
206,..,906 | [7 empty] | 0 |  |  |  |  | 206,..,906 | 206 | 906
207,..,907 | [7 empty] | 0 |  |  |  |  | 207,..,907 | 207 | 907
208,..,908 | [7 empty] | 0 |  |  |  |  | 208,..,908 | 208 | 908
209,..,909 | [7 empty] | 0 |  |  |  |  | 209,..,909 | 209 | 909
210,..,910 | [7 empty] | 0 |  |  |  |  | 210,..,910 | 210 | 910
2nd to 5th Floor
201 to 501 | [7 empty] | 0 |  |  |  |  | 201 to 501 | 201 | 501
202 to 502 | [7 empty] | 0 |  |  |  |  | 202 to 502 | 202 | 502
203 to 503 | [7 empty] | 0 |  |  |  |  | 203 to 503 | 203 | 503
204 to 504 | [7 empty] | 0 |  |  |  |  | 204 to 504 | 204 | 504
205 to 505 | [7 empty] | 0 |  |  |  |  | 205 to 505 | 205 | 505
206 to 506 | [7 empty] | 0 |  |  |  |  | 206 to 506 | 206 | 506
207 to 507 | [7 empty] | 0 |  |  |  |  | 207 to 507 | 207 | 507
208 to 508 | [7 empty] | 0 |  |  |  |  | 208 to 508 | 208 | 508
209 to 509 | [7 empty] | 0 |  |  |  |  | 209 to 509 | 209 | 509
210 to 510 | [7 empty] | 0 |  |  |  |  | 210 to 510 | 210 | 510
2nd & 5th Floor
201 & 501 | [7 empty] | 0 |  |  |  |  | 201 & 501 | 201 | 501
202 & 502 | [7 empty] | 0 |  |  |  |  | 202 & 502 | 202 | 502
203 & 503 | [7 empty] | 0 |  |  |  |  | 203 & 503 | 203 | 503
204 & 504 | [7 empty] | 0 |  |  |  |  | 204 & 504 | 204 | 504
205 & 505 | [7 empty] | 0 |  |  |  |  | 205 & 505 | 205 | 505
206 & 506 | [7 empty] | 0 |  |  |  |  | 206 & 506 | 206 | 506
207 & 507 | [7 empty] | 0 |  |  |  |  | 207 & 507 | 207 | 507
208 & 508 | [7 empty] | 0 |  |  |  |  | 208 & 508 | 208 | 508
209 & 509 | [7 empty] | 0 |  |  |  |  | 209 & 509 | 209 | 509
210 & 510 | [7 empty] | 0 |  |  |  |  | 210 & 510 | 210 | 510
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Tower 10 & 11 = All work completed. Provide OC. Tower 12 = Construction work is in process at the time of Visit (labour found). Internal visit not allowed 2. We have considered rate by verifying it from market inquire. 3. Car parking is subjected to authentic documentation. 4. On Site, we meet Mr........(........). 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Sky Gardens at Godrej Vihaa
Project Site Address |  |  | : | Godrej Vihaa, S.No.1/6,12, 17C (P No.3),17 D (P No.4), S No.5A to E, S.No.5/6, S.No.5/7 A & B, S.No.5/8, S.No.5/23 PT, S.No.6/1,2,3 & 4, S.No.7 H.No.1 to 4, 8 to 10, S.No.9/5.At Next to Usha Kiran Residency, Badlapur East, Village- Joveli, Tal- Ambernath, Dist- Thane - 421503
Site Visit Date & Time |  |  | : | 03/07/2025 at 03:21PM
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr.Sudhir | Authorized Signatory Name & Signature | :
11
10
12
10
11
12
11
10
12
12
11
11