## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-02 | 2025-04-23 | 2025-07-22
Project Name |  |  | : | Ten X Habitat Raymond Realty (Tower A, B, C, D, E, F, G, H, J & K) |  | Date of Site Visit |  | 03/07/2025 at 01:29PM | 2024-11-11 | 2025-02-05 | 86
Name of the person met at site & Contact No. |  |  | : | NA |  | Date of Report Release |  | 04/07/2025
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | Raymond Limited | Developer Name | : | Raymond Realty
Developer Office Address |  |  | : | The Mill – Raymond Realty office J.K Gram, Pokharan Rd Number 1, J K Gram, Thane West, Thane, Maharashtra 400606
Project Address | : | As per ARF | : | Ten X Habitat Raymond Realty, Tower A, B, C, D, E, F, G, H, J & K, Road - Pokharan Road Number 2, Village - Panchpakhadi, Near - Smt. Sunitidevi Singhania school, Thane West, Thane, Maharashtra 400606
| : | As per Legal Documents | : | Ten X Habitat Raymond Realty ¦ Tower A, B, C, D, E, F, G, H, J & K, Survey No.122, 126B1/1, 126B/2, 126B1/2, 126B1/3, 126B1/4, 127, 128/B, 129/1, 129/3, Pokharan Road, Panchpakhadi, Thane.
| : | As per Actual at site | : | Ten X Habitat Raymond Realty, Tower A, B, C, D, E, F, G, H, J & K, Road - Pokharan Road Number 2, Village - Panchpakhadi, Near - Smt. Sunitidevi Singhania school, Thane West, Thane, Maharashtra 400606
Documents Provided by GHF |  |  | : | Layout, Approved Plans, CC
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Thane Municipal Corporation (TMC)
RERA Registration No. | : | Tower A & B - P51700019265 Tower C - P51700020256 Tower D - P51700020881 Tower E - P51700022779 Tower H - P51700027036 Tower J - P51700025355 Tower K - P51700022940 Tower F - P51700034190 Tower G - PP51700047152 |  |  | RERA Registration Validity | : | Tower A, B, C, D & E - Completed Tower H & K - Completed Tower J - Completed Tower F - 31/03/2026 Tower G - 30/06/2026 |  | Tower H & K - 30/09/2025 Tower J - 30/06/2025
Project Launch Date | : | 2019-05-08 |  |  | Construction Start Date | : | 2019-05-15
Proposed Date of Completion (As per RERA) | : | Tower A, B, C, D & E - Completed Tower H & K - Completed Tower J - Completed Tower F - 31/03/2026 Tower G - 30/06/2026 |  |  | Developer Bank Name (As per RERA) | : | HDFC Bank IFSC Code - HDFC0000060
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 62497.59
FSI/FAR Permissible | : | 1.1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 17843.77
Permissible Built up Area (In Sq.Mt) | : | 159978.69 |  |  | Total Number of Units Planned | : | As per RERA Site Tower A, B, C, D, E, F, G, H, J & K = Flats 3111 |  | 399 | 291
Total Number of Units Approved | : | Tower A, B, C, D, E, F, H, G, J & K = Flats 3103 |  |  | If Mixed, No. of Commercial Units | : | NA |  | 3111
Latitude & Longitude | : | 19.213711,72.967595 | [6 empty] | Changed On 30/04/2025
Location Link | : | https://maps.app.goo.gl/GKmuKV9xb73WWKE47
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities | [8 empty] | 23902.0619
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 2.2 KM from Khopat Bus Depot.
Distance from the nearest School (Km) | : | About 2.3 KM from New Horizon Scholars School |  |  | Distance from Hospital (Km) | : | About 2.6 KM form Jupiter Hospital.
Distance from the Main Market (Km) | : | 1. Approx. 1.1 KM from Kalwa Super Market. 2. Approx. 3.8 KM from Indira Nagar Market. |  |  | Distance from Railway Station (Km) | : | 4.5 KM from Thane Railway Station 7.4 KM from Kalva Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | :
As per Site / Actual |  |  | : | Smt. Sunitidevi Singhania school | Open Plot | Internal Road |  | Open Plot
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Tower A to E |  | Sale |  | G + 1st to 42nd Floor |  |  | G + 1st to 42nd Floor
Tower H, J & K |  | Sale |  | G + 1st to 42nd Floor |  |  | G + 1st to 42nd Floor
Tower F |  | Sale |  | G + 1st to 50th Floor |  |  | G + 1st to 50th Floor
Tower G |  | Sale |  | G + 1st to 50th Floor |  |  | G + 1st to 50th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | TMCB/TDD/0001/[P/C]/2022/AutoDCR Date: 26/12/2022
CC Details | : | VP/S04/0161/19/Revised TMC/TDD/3668/21 Dated: 14/08/2021 Tower A, B, C, D, J & K = G + 1st to 42nd Floor VP/S04/0161/19/TMC/TDD/3748/21 Dated: 13/11/2021 Tower E & H = G + 1st to 42nd floor TMCB/TDD/0001/[P/C]/2022/AutoDCR Dated: 26/12/2022 Tower F & G = G + 1st to 50th Floor |  |  | Approved Plan Details Tower A, B, C, D, J & K = G + 1st to 42nd Floor Tower E = G + 1st to 21st Floor Tower E = 22nd to 42nd Floor & Tower H = G + 1st to 42nd Floor Tower F & G = G + 1st to 50th Floor | : | TMC/TDD/3668/21 Dated: 14/08/2021 S04/0161/09TMC/TD-DP/TPS/3067/19 Date: 08/05/2019 S04/0161/19TMC/TD-DP/TPS3748/21 Date: 13/11/2021 TMCB/TDD/0001/[P/C]/2022/AutoDCR Date: 26/12/2022
Environmental Clearance Details | : |  |  |  | Airport Authority Clearance Details | :
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
O. Certificate No.: Valid Up to: | : | S04/0161/19/Revised TMC/TDD/32 Wing A, B & C = Gr + 1st to 42nd Floor |  |  |  |  | Date: | 2022-12-06
O. Certificate No.: Valid Up to: | : | S04/0161/19/OCC/2 Wing D = Gr + 1st to 42nd Floor |  |  |  |  | Date: | 2024-03-05
O. Certificate No.: Valid Up to: | : | S04/0161/19/OCC/3 Wing E = Gr + 1st to 42nd Floor |  |  |  |  | Date: | 2024-03-28
Construction Status
Tower A to C - Gr + 1st to 42nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | All work completed. Please provide OC.
|  |  |  | 0 | 1 |  | 0 | 42 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 10.5
Excavation |  | 42 |  | 100% | 100% |  | All work Completed. OC Received. |  | Excavation in process | 21
Plinth |  | 42 |  | 100% |  |  |  |  | Excavation Completed | 42
RCC (Including podiums) |  | 43 |  | 100% |  |  |  |  | Footing in Process | 10.5
Brickwork |  | 42 |  | 100% |  |  |  |  | Footing Completed | 21
Internal Plaster |  | 42 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 42 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 42 |  | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 42 |  | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 42 |  | 100% |  |  |  |  | Plinth in process | 31.5
Electrical & Sanitary fittings |  | 42 |  | 100% |  |  |  |  | Plinth completed | 42 | #VALUE!
Building Common Amenities |  | 42 |  | 100%
Possession |  | 42 |  | 100%
Construction Status
Tower D - Gr + 1st to 42nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | All work completed. Please provide OC.
|  |  |  | 0 | 1 |  | 0 | 42 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 10.5
Excavation |  | 42 |  | 100% | 100% |  | All work completed. Please provide OC. |  | Excavation in process | 21
Plinth |  | 42 |  | 100% |  |  |  |  | Excavation Completed | 42
RCC (Including podiums) |  | 43 |  | 100% |  |  |  |  | Footing in Process | 8.4
Brickwork |  | 42 |  | 100% |  |  |  |  | Footing Completed | 16.8
Internal Plaster |  | 42 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 42 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 42 |  | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 42 |  | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 42 |  | 100% |  |  |  |  | Plinth in process | 29.4
Electrical & Sanitary fittings |  | 42 |  | 100% |  |  |  |  | Plinth completed | 42
Building Common Amenities |  | 42 |  | 100%
Possession |  | 42 |  | 100%
Construction Status
Tower D & E = Gr + 1st to 42nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | All work completed. Please provide OC.
|  |  |  | 0 | 1 |  | 0 | 42 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 10.5
Excavation |  | 42 |  | 100% | 100% |  | All work Completed. OC Received. |  | Excavation in process | 21
Plinth |  | 42 |  | 100% |  |  |  |  | Excavation Completed | 42
RCC (Including podiums) |  | 43 |  | 100% |  |  |  |  | Footing in Process | 10.5
Brickwork |  | 42 |  | 100% |  |  |  |  | Footing Completed | 21
Internal Plaster |  | 42 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 42 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 42 |  | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 42 |  | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 42 |  | 100% |  |  |  |  | Plinth in process | 31.5
Electrical & Sanitary fittings |  | 42 |  | 100% |  |  |  |  | Plinth completed | 42 | #VALUE!
Building Common Amenities |  | 42 |  | 100%
Possession |  | 42 |  | 100%
Construction Status
Tower E - Gr + 1st to 42nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | All work completed. Please provide OC.
|  |  |  | 0 | 1 |  | 0 | 42 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 10.5
Excavation |  | 42 |  | 100% | 100% |  | All work completed. Please provide OC. |  | Excavation in process | 21
Plinth |  | 42 |  | 100% |  |  |  |  | Excavation Completed | 42
RCC (Including podiums) |  | 43 |  | 100% |  |  |  |  | Footing in Process | 8.4
Brickwork |  | 42 |  | 100% |  |  |  |  | Footing Completed | 16.8
Internal Plaster |  | 42 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 42 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 42 |  | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 42 |  | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 42 |  | 100% |  |  |  |  | Plinth in process | 29.4
Electrical & Sanitary fittings |  | 42 |  | 100% |  |  |  |  | Plinth completed | 42
Building Common Amenities |  | 42 |  | 100%
Possession |  | 42 |  | 100%
Construction Status
Tower E = Gr + 1st to 42nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | All work completed. Please provide OC.
|  |  |  | 0 | 1 |  | 0 | 42 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 10.5
Excavation |  | 42 |  | 100% | 100% |  | All work Completed. OC Received. |  | Excavation in process | 21
Plinth |  | 42 |  | 100% |  |  |  |  | Excavation Completed | 42
RCC (Including podiums) |  | 43 |  | 100% |  |  |  |  | Footing in Process | 10.5
Brickwork |  | 42 |  | 100% |  |  |  |  | Footing Completed | 21
Internal Plaster |  | 42 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 42 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 42 |  | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 42 |  | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 42 |  | 100% |  |  |  |  | Plinth in process | 31.5
Electrical & Sanitary fittings |  | 42 |  | 100% |  |  |  |  | Plinth completed | 42 | #VALUE!
Building Common Amenities |  | 42 |  | 100%
Possession |  | 42 |  | 100%
Construction Status
Tower H, J & K - Gr + 1st to 42nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Plinth, RCC, Brick, Plaster, Flooring, Wooden, Plumbing, Electrification, etc., work Completed. Finishing work is in process.
|  |  |  | 0 | 1 |  | 0 | 42 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 10.5
Excavation |  | 42 |  | 100% | 90.24% |  | Plinth, RCC, Brick, Plaster, Flooring, Wooden, Plumbing, Electrification, etc., work Completed. Finishing work is in process. |  | Excavation in process | 21
Plinth |  | 42 |  | 100% |  |  |  |  | Excavation Completed | 42
RCC (Including podiums) |  | 43 |  | 100% |  |  |  |  | Footing in Process | 8.4
Brickwork |  | 42 |  | 100% |  |  |  |  | Footing Completed | 16.8
Internal Plaster |  | 42 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 42 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 40 |  | 95.24% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 40 |  | 95.24% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 40 |  | 95.24% |  |  |  |  | Plinth in process | 29.4
Electrical & Sanitary fittings |  | 40 |  | 95.24% |  |  |  |  | Plinth completed | 42
Building Common Amenities |  | 25 |  | 59.52%
Possession |  | 0 |  | 0%
Construction Status
Tower H, J & K = Gr + 1st to 42nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | All work completed. Please provide OC.
|  |  |  | 0 | 1 |  | 0 | 42 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 10.5
Excavation |  | 42 |  | 100% | 100% |  | All work completed. Please provide OC. |  | Excavation in process | 21
Plinth |  | 42 |  | 100% |  |  |  |  | Excavation Completed | 42
RCC (Including podiums) |  | 43 |  | 100% |  |  |  |  | Footing in Process | 10.5
Brickwork |  | 42 |  | 100% |  |  |  |  | Footing Completed | 21
Internal Plaster |  | 42 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 42 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 42 |  | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 42 |  | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 42 |  | 100% |  |  |  |  | Plinth in process | 31.5
Electrical & Sanitary fittings |  | 42 |  | 100% |  |  |  |  | Plinth completed | 42 | #VALUE!
Building Common Amenities |  | 42 |  | 100%
Possession |  | 42 |  | 100%
Construction Status
Tower F & G - Gr + 1st to 51st Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 50 Slab, Brickwork upto 49 Floor, Internal Plaster upto 39.2 Floor, External Plaster upto 39.2 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 51 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 12.75
Excavation |  | 51 |  | 100% | 67.69% |  | Excavation work Completed. Plinth work completed, RCC upto 50 Slab, Brickwork upto 49 Floor, Internal Plaster upto 39.2 Floor, External Plaster upto 39.2 Floor Completed |  | Excavation in process | 25.5
Plinth |  | 51 |  | 100% |  |  |  |  | Excavation Completed | 51
RCC (Including podiums) |  | 50 |  | 96.15% |  |  |  |  | Footing in Process | 10.2
Brickwork |  | 49 |  | 96.08% |  |  |  |  | Footing Completed | 20.4
Internal Plaster |  | 39.2 |  | 76.86% |  |  |  |  | Basement 1 | 0
External Plaster |  | 39.2 |  | 76.86% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 35.7
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 51
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower F & G = Gr + 1st to 50th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 29 Floor, Flooring & Fitting upto 23 Floor, Wooden Work upto 8 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 50 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 12.5
Excavation |  | 50 |  | 100% | 67.9% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 29 Floor, Flooring & Fitting upto 23 Floor, Wooden Work upto 8 Floor Completed |  | Excavation in process | 25
Plinth |  | 50 |  | 100% |  |  |  |  | Excavation Completed | 50
RCC (Including podiums) |  | 51 |  | 100% |  |  |  |  | Footing in Process | 12.5
Brickwork |  | 50 |  | 100% |  |  |  |  | Footing Completed | 25
Internal Plaster |  | 50 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 50 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 29 |  | 58% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 23 |  | 46% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 8 |  | 16% |  |  |  |  | Plinth in process | 37.5
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 50 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 93.58%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 22,000/- | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  |  | : | 8,00,000/- | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 3781.1223
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 7878.1122
Distress Value (Rs. Per sqft) | [5 empty] | : | 3024.8978
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Tower A |  | Sale |  | Flats | 319 |  | 178963.3479 | 286341.3567
Tower B |  | Sale |  | Flats | 321 |  | 176283.4758 | 282053.5612
Tower C |  | Sale |  | Flats | 244 |  | 156116.7009 | 249786.7214
Tower D |  | Sale |  | Flats | 244 |  | 156116.7009 | 249786.7214
Tower E |  | Sale |  | Flats | 325 |  | 203628.308 | 325805.2928
Tower H |  | Sale |  | Flats | 328 |  | 180410.7034 | 288657.1254
Tower J |  | Sale |  | Flats | 321 |  | 124891.3132 | 199826.1011
Tower K |  | Sale |  | Flats | 319 |  | 124925.0443 | 199880.0709
Tower F |  | Sale |  | Flats | 391 |  | 250359.2183 | 400574.7493
Tower G |  | Sale |  | Flats | 291 |  | 189804.5904 | 303687.3446
Total |  | Sale |  | Flats | 3103 |  | 1551694.8126 | 2482711.7002
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
60%
Tower A
Ground Floor For Commercial & Parking
Ground Floor For Commercial & Parking |  | 49 |  | Shop | 132.9354 |  | 0 | 212.6966
Ground Floor For Commercial & Parking |  | 50 |  | Shop | 76.855 |  | 0 | 122.9679
Ground Floor For Commercial & Parking |  | 51 |  | Shop | 383.4137 |  | 0 | 613.4619
Ground Floor For Commercial & Parking |  | 52 |  | Shop | 419.9639 |  | 0 | 671.9423
Ground Floor For Commercial & Parking |  | 53 |  | Shop | 417.669 |  | 0 | 668.2705
Ground Floor For Commercial & Parking |  | 54 |  | Shop | 389.7967 |  | 0 | 623.6748
Ground Floor For Commercial & Parking |  | 55 |  | Shop | 75.1758 |  | 0 | 120.2812
Ground Floor For Commercial & Parking |  | 56 |  | Shop | 135.2766 |  | 0 | 216.4425
Tower K
Ground Floor For Commercial & Parking
Ground Floor For Commercial & Parking |  |  |  | Shop |  |  | 0 | 0
Ground Floor For Commercial & Parking |  |  |  | Shop |  |  | 0 | 0
Ground Floor For Commercial & Parking |  |  |  | Shop |  |  | 0 | 0
Ground Floor For Commercial & Parking |  |  |  | Shop |  |  | 0 | 0
Ground Floor For Commercial & Parking |  |  |  | Shop |  |  | 0 | 0
Ground Floor For Commercial & Parking |  |  |  | Shop |  |  | 0 | 0
Ground Floor For Commercial & Parking |  |  |  | Shop |  |  | 0 | 0
Ground Floor For Commercial & Parking |  |  |  | Shop |  |  | 0 | 0
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
50%
Tower A
Ground Floor For Parking & Fitness Center
1st Floor for Residential
1st Floor for Residential |  | 1 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 2 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 5 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 6 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 7 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 8 |  | 2BHK | 507.6066 |  | 0 | 812.1705
2nd to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th & 28th Floor
2nd to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th & 28th Floor |  | 1 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 2 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 3 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 4 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 5 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 6 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 7 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 8 |  | 2BHK | 507.6066 |  | 0 | 812.1705
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area)
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 2 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 3 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 4 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 5 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 6 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 7 |  | Refuge Area
8
29th to 31st, 33rd to 36th, 38th to 41th Floor
29th to 31st, 33rd to 36th, 38th to 41th Floor |  | 1 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 2 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 3 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 4 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 5 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 6 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 7 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 8 |  | 2BHK | 507.6066 |  | 0 | 812.1705
32nd & 37th Floor (Part Refuge Area)
32nd & 37th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 2 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 3 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 4 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 5 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 6 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 7 |  | Refuge Area
8
42nd Floor (Part Refuge Area)
42nd Floor (Part Refuge Area) |  | 1 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 2 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 3 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 4 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 5 |  | 2BHK | 643.9014 |  | 0 | 1030.2422
|  | 6 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 7 |  | 2BHK | 507.6066 |  | 0 | 812.1705
|  | 8 |  | Refuge Area
Tower B
Ground Floor For Parking & Fitness Center
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th & 29th Floor For Residential
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th & 29th Floor For Residential |  | 1 |  | 2BHK | 632.6455 |  | 0 | 1012.2328
|  | 2 |  | 2BHK | 519.6935 |  | 0 | 831.5095
|  | 3 |  | 2BHK | 519.6935 |  | 0 | 831.5095
|  | 4 |  | 2BHK | 632.6455 |  | 0 | 1012.2328
|  | 5 |  | 2BHK | 518.5406 |  | 0 | 829.665
|  | 6 |  | 2BHK | 518.5406 |  | 0 | 829.665
|  | 7 |  | 2BHK | 518.5406 |  | 0 | 829.665
|  | 8 |  | 2BHK | 518.5406 |  | 0 | 829.665
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area)
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 632.6455 |  | 0 | 1012.2328
|  | 2 |  | 2BHK | 519.6935 |  | 0 | 831.5095
|  | 3 |  | 2BHK | 519.6935 |  | 0 | 831.5095
|  | 4 |  | 2BHK | 632.6455 |  | 0 | 1012.2328
|  | 5 |  | 2BHK | 518.5406 |  | 0 | 829.665
|  | 6 |  | 2BHK | 518.5406 |  | 0 | 829.665
|  | 7 |  | Refuge Area
8
29th to 31st, 33rd to 36th, 38th to 41st Floor
29th to 31st, 33rd to 36th, 38th to 41st Floor |  | 1 |  | 2BHK | 632.6455 |  | 0 | 1012.2328
|  | 2 |  | 2BHK | 519.6935 |  | 0 | 831.5095
|  | 3 |  | 2BHK | 519.6935 |  | 0 | 831.5095
|  | 4 |  | 2BHK | 632.6455 |  | 0 | 1012.2328
|  | 5 |  | 2BHK | 518.5406 |  | 0 | 829.665
|  | 6 |  | 2BHK | 518.5406 |  | 0 | 829.665
|  | 7 |  | 2BHK | 518.5406 |  | 0 | 829.665
|  | 8 |  | 2BHK | 518.5406 |  | 0 | 829.665
32nd & 37th Floor (Part Refuge Area)
32nd & 37th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 630.6757 |  | 0 | 1009.0811
|  | 2 |  | 2BHK | 531.5425 |  | 0 | 850.4679
|  | 3 |  | 2BHK | 531.5425 |  | 0 | 850.4679
|  | 4 |  | 2BHK | 630.6757 |  | 0 | 1009.0811
|  | 5 |  | 2BHK | 531.5425 |  | 0 | 850.4679
|  | 6 |  | 2BHK | 531.5425 |  | 0 | 850.4679
|  | 7 |  | Refuge Area
8
42nd Floor (Part Refuge Area)
42nd Floor (Part Refuge Area) |  | 1 |  | 2BHK | 630.6757 |  | 0 | 1009.0811
|  | 2 |  | 2BHK | 531.5425 |  | 0 | 850.4679
|  | 3 |  | 2BHK | 531.5425 |  | 0 | 850.4679
|  | 4 |  | 2BHK | 630.6757 |  | 0 | 1009.0811
|  | 5 |  | 2BHK | 531.5425 |  | 0 | 850.4679
|  | 6 |  | 2BHK | 531.5425 |  | 0 | 850.4679
|  | 7 |  | 2BHK | 531.5425 |  | 0 | 850.4679
|  | 8 |  | Refuge Area
Tower C
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th & 28th Floor For Residential
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th & 28th Floor For Residential |  | 1 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 2 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 3 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 4 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 5 |  | 2BHK | 651.1531 |  | 0 | 1041.845
|  | 6 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area)
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 2 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 3 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 4 |  | Refuge Area
|  | 5 |  | 2BHK | 651.1531 |  | 0 | 1041.845
|  | 6 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
29th to 31st, 33rd to 36th & 38th to 41st Floor
29th to 31st, 33rd to 36th & 38th to 41st Floor |  | 1 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 2 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 3 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 4 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 5 |  | 2BHK | 651.1531 |  | 0 | 1041.845
|  | 6 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
32nd, 37th & 42nd Floor (Part Refuge Area)
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 1 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 2 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 3 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 4 |  | Refuge Area
|  | 5 |  | 2BHK | 651.1531 |  | 0 | 1041.845
|  | 6 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
Tower D
Ground Floor For Parking & Fitness Center
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th & 28th Floor For Residential
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th & 28th Floor For Residential |  | 1 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 2 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 3 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 4 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 5 |  | 2BHK | 651.1531 |  | 0 | 1041.845
|  | 6 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area)
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 2 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 3 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 4 |  | Refuge Area
|  | 5 |  | 2BHK | 651.1531 |  | 0 | 1041.845
|  | 6 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
29th to 31st, 33rd to 36th & 38th to 41st Floor
29th to 31st, 33rd to 36th & 38th to 41st Floor |  | 1 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 2 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 3 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 4 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 5 |  | 2BHK | 651.1531 |  | 0 | 1041.845
|  | 6 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
32nd, 37th & 42nd Floor (Part Refuge Area)
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 1 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 2 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 3 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
|  | 4 |  | Refuge Area
|  | 5 |  | 2BHK | 651.1531 |  | 0 | 1041.845
|  | 6 |  | 2BHK | 637.4667 |  | 0 | 1019.9467
Tower E
Ground Floor For Parking & Fitness Center
1st to 6th, 8th to 11th, 13th to 16th & 18th to 21st Floor For Residential
1st to 6th, 8th to 11th, 13th to 16th & 18th to 21st Floor For Residential |  | 1 |  | 2BHK | 619.62 |  | 0 | 991.392 | 637.9188
|  | 2 |  | 2BHK | 619.62 |  | 0 | 991.392
|  | 3 |  | 2BHK | 619.62 |  | 0 | 991.392
|  | 4 |  | 2BHK | 619.62 |  | 0 | 991.392
|  | 5 |  | 2BHK | 619.62 |  | 0 | 991.392
|  | 6 |  | 2BHK | 602.3459 |  | 0 | 963.7534
|  | 7 |  | 2BHK | 602.3459 |  | 0 | 963.7534
|  | 8 |  | 2BHK | 619.62 |  | 0 | 991.392
7th, 12th & 17th Floor (Part Refuge Area)
7th, 12th & 17th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 619.62 |  | 0 | 991.392
|  | 2 |  | 2BHK | 619.62 |  | 0 | 991.392
|  | 3 |  | 2BHK | 619.62 |  | 0 | 991.392
|  | 4 |  | 2BHK | 619.62 |  | 0 | 991.392
|  | 5 |  | 2BHK | 619.62 |  | 0 | 991.392
|  | 6 |  | 2BHK | 602.3459 |  | 0 | 963.7534
|  | 7 |  | Refuge Area
8
22nd & 27th Floor (Part Refuge Area)
22nd & 27th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 637.2073 |  | 0 | 1019.5316
22nd & 27th Floor (Part Refuge Area) |  | 2 |  | 2BHK | 637.2073 |  | 0 | 1019.5316
22nd & 27th Floor (Part Refuge Area) |  | 3 |  | 2BHK | 636.2557 |  | 0 | 1018.0092
22nd & 27th Floor (Part Refuge Area) |  | 4 |  | 2BHK | 636.2557 |  | 0 | 1018.0092
22nd & 27th Floor (Part Refuge Area) |  | 5 |  | 2BHK | 633.9049 |  | 0 | 1014.2478
22nd & 27th Floor (Part Refuge Area) |  | 6 |  | 2BHK | 635.6465 |  | 0 | 1017.0344
22nd & 27th Floor (Part Refuge Area) |  | 7 |  | 2BHK | 635.6465 |  | 0 | 1017.0344
23rd to 26th & 28th Floor
23rd to 26th & 28th Floor |  | 1 |  | 2BHK | 637.2073 |  | 0 | 1019.5316
23rd to 26th & 28th Floor |  | 2 |  | 2BHK | 637.2073 |  | 0 | 1019.5316
23rd to 26th & 28th Floor |  | 3 |  | 2BHK | 636.2557 |  | 0 | 1018.0092
23rd to 26th & 28th Floor |  | 4 |  | 2BHK | 636.2557 |  | 0 | 1018.0092
23rd to 26th & 28th Floor |  | 5 |  | 2BHK | 633.9049 |  | 0 | 1014.2478
23rd to 26th & 28th Floor |  | 6 |  | 2BHK | 635.6465 |  | 0 | 1017.0344
23rd to 26th & 28th Floor |  | 7 |  | 2BHK | 635.6465 |  | 0 | 1017.0344
23rd to 26th & 28th Floor |  | 8 |  | 2BHK | 633.9049 |  | 0 | 1014.2478
29th to 31st, 33rd to 36th, 38th to 41st Floor
29th to 31st, 33rd to 36th, 38th to 41st Floor |  | 1 |  | 2BHK | 638.4085 |  | 0 | 1021.4537
29th to 31st, 33rd to 36th, 38th to 41st Floor |  | 2 |  | 2BHK | 638.4085 |  | 0 | 1021.4537
29th to 31st, 33rd to 36th, 38th to 41st Floor |  | 3 |  | 2BHK | 639.3773 |  | 0 | 1023.0037
29th to 31st, 33rd to 36th, 38th to 41st Floor |  | 4 |  | 2BHK | 639.3773 |  | 0 | 1023.0037
29th to 31st, 33rd to 36th, 38th to 41st Floor |  | 5 |  | 2BHK | 637.0264 |  | 0 | 1019.2423
29th to 31st, 33rd to 36th, 38th to 41st Floor |  | 6 |  | 2BHK | 638.7681 |  | 0 | 1022.0289
29th to 31st, 33rd to 36th, 38th to 41st Floor |  | 7 |  | 2BHK | 638.7681 |  | 0 | 1022.0289
29th to 31st, 33rd to 36th, 38th to 41st Floor |  | 8 |  | 2BHK | 637.0264 |  | 0 | 1019.2423
32nd, 37th & 42nd Floor (Part Refuge Area)
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 1 |  | 2BHK | 638.4085 |  | 0 | 1021.4537
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 2 |  | 2BHK | 638.4085 |  | 0 | 1021.4537
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 3 |  | 2BHK | 639.3773 |  | 0 | 1023.0037
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 4 |  | 2BHK | 639.3773 |  | 0 | 1023.0037
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 5 |  | 2BHK | 637.0264 |  | 0 | 1019.2423
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 6 |  | 2BHK | 638.7681 |  | 0 | 1022.0289
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 7 |  | 2BHK | 638.7681 |  | 0 | 1022.0289
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 8 |  | Refuge Area
Tower H
Ground Floor For Parking & Fitness Center
1st To 6th, 8th To 11th, 13th To 16th, 18th To 21st, 23rd To 26th & 28th Floor For Residential
1st To 6th, 8th To 11th, 13th To 16th, 18th To 21st, 23rd To 26th & 28th Floor For Residential |  | 1 |  | 2BHK | 549.4871 |  | 0 | 879.1794
1st To 6th, 8th To 11th, 13th To 16th, 18th To 21st, 23rd To 26th & 28th Floor For Residential |  | 2 |  | 2BHK | 549.4871 |  | 0 | 879.1794
1st To 6th, 8th To 11th, 13th To 16th, 18th To 21st, 23rd To 26th & 28th Floor For Residential |  | 3 |  | 2BHK | 549.4871 |  | 0 | 879.1794
1st To 6th, 8th To 11th, 13th To 16th, 18th To 21st, 23rd To 26th & 28th Floor For Residential |  | 4 |  | 2BHK | 549.4871 |  | 0 | 879.1794
1st To 6th, 8th To 11th, 13th To 16th, 18th To 21st, 23rd To 26th & 28th Floor For Residential |  | 5 |  | 2BHK | 549.4871 |  | 0 | 879.1794
1st To 6th, 8th To 11th, 13th To 16th, 18th To 21st, 23rd To 26th & 28th Floor For Residential |  | 6 |  | 2BHK | 549.4871 |  | 0 | 879.1794
1st To 6th, 8th To 11th, 13th To 16th, 18th To 21st, 23rd To 26th & 28th Floor For Residential |  | 7 |  | 2BHK | 549.4871 |  | 0 | 879.1794
1st To 6th, 8th To 11th, 13th To 16th, 18th To 21st, 23rd To 26th & 28th Floor For Residential |  | 8 |  | 2BHK | 549.4871 |  | 0 | 879.1794
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area)
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area) |  | 1 |  | Refuge Area
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area) |  | 2 |  | 2BHK | 549.4871 |  | 0 | 879.1794
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area) |  | 3 |  | 2BHK | 549.4871 |  | 0 | 879.1794
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area) |  | 4 |  | 2BHK | 549.4871 |  | 0 | 879.1794
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area) |  | 5 |  | 2BHK | 549.4871 |  | 0 | 879.1794
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area) |  | 6 |  | 2BHK | 549.4871 |  | 0 | 879.1794
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area) |  | 7 |  | 2BHK | 549.4871 |  | 0 | 879.1794
7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area) |  | 8 |  | 2BHK | 549.4871 |  | 0 | 879.1794
29th To 31st, 33rd to 36th, 38th To 41st Floor
29th To 31st, 33rd to 36th, 38th To 41st Floor |  | 1 |  | 2BHK | 551.1286 |  | 0 | 881.8058
29th To 31st, 33rd to 36th, 38th To 41st Floor |  | 2 |  | 2BHK | 551.1286 |  | 0 | 881.8058
29th To 31st, 33rd to 36th, 38th To 41st Floor |  | 3 |  | 2BHK | 551.1286 |  | 0 | 881.8058
29th To 31st, 33rd to 36th, 38th To 41st Floor |  | 4 |  | 2BHK | 551.1286 |  | 0 | 881.8058
29th To 31st, 33rd to 36th, 38th To 41st Floor |  | 5 |  | 2BHK | 551.1286 |  | 0 | 881.8058
29th To 31st, 33rd to 36th, 38th To 41st Floor |  | 6 |  | 2BHK | 551.1286 |  | 0 | 881.8058
29th To 31st, 33rd to 36th, 38th To 41st Floor |  | 7 |  | 2BHK | 551.1286 |  | 0 | 881.8058
29th To 31st, 33rd to 36th, 38th To 41st Floor |  | 8 |  | 2BHK | 551.1286 |  | 0 | 881.8058
32nd, 37th & 42nd Floor (Part Refuge Area)
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 1 |  | Refuge Area
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 2 |  | 2BHK | 551.1286 |  | 0 | 881.8058
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 3 |  | 2BHK | 551.1286 |  | 0 | 881.8058
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 4 |  | 2BHK | 551.1286 |  | 0 | 881.8058
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 5 |  | 2BHK | 551.1286 |  | 0 | 881.8058
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 6 |  | 2BHK | 551.1286 |  | 0 | 881.8058
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 7 |  | 2BHK | 551.1286 |  | 0 | 881.8058
32nd, 37th & 42nd Floor (Part Refuge Area) |  | 8 |  | 2BHK | 551.1286 |  | 0 | 881.8058
Tower J
Ground Floor For Parking & Fitness Center
1st To 6th, 8th To 11th, 13th To 16th, 18th To 20th Floor For Residential
1st To 6th, 8th To 11th, 13th To 16th, 18th To 20th Floor For Residential |  | 1 |  | 1BHK | 384.7581 |  | 0 | 615.613
1st To 6th, 8th To 11th, 13th To 16th, 18th To 20th Floor For Residential |  | 2 |  | 1BHK | 384.7581 |  | 0 | 615.613
1st To 6th, 8th To 11th, 13th To 16th, 18th To 20th Floor For Residential |  | 3 |  | 1BHK | 384.7581 |  | 0 | 615.613
1st To 6th, 8th To 11th, 13th To 16th, 18th To 20th Floor For Residential |  | 4 |  | 1BHK | 389.1283 |  | 0 | 622.6053
1st To 6th, 8th To 11th, 13th To 16th, 18th To 20th Floor For Residential |  | 5 |  | 1BHK | 392.9592 |  | 0 | 628.7347
1st To 6th, 8th To 11th, 13th To 16th, 18th To 20th Floor For Residential |  | 6 |  | 1BHK | 391.2639 |  | 0 | 626.0222
1st To 6th, 8th To 11th, 13th To 16th, 18th To 20th Floor For Residential |  | 7 |  | 1BHK | 391.2639 |  | 0 | 626.0222
1st To 6th, 8th To 11th, 13th To 16th, 18th To 20th Floor For Residential |  | 8 |  | 1BHK | 392.9592 |  | 0 | 628.7347
7th, 12th & 17th Floor (Part Refuge Area)
7th, 12th & 17th Floor (Part Refuge Area) |  | 1 |  | 1BHK | 384.7581 |  | 0 | 615.613
7th, 12th & 17th Floor (Part Refuge Area) |  | 2 |  | 1BHK | 384.7581 |  | 0 | 615.613
7th, 12th & 17th Floor (Part Refuge Area) |  | 3 |  | Refuge Area
7th, 12th & 17th Floor (Part Refuge Area) |  | 4
7th, 12th & 17th Floor (Part Refuge Area) |  | 5 |  | 1BHK | 392.9592 |  | 0 | 628.7347
7th, 12th & 17th Floor (Part Refuge Area) |  | 6 |  | 1BHK | 391.2639 |  | 0 | 626.0222
7th, 12th & 17th Floor (Part Refuge Area) |  | 7 |  | 1BHK | 391.2639 |  | 0 | 626.0222
7th, 12th & 17th Floor (Part Refuge Area) |  | 8 |  | 1BHK | 392.9592 |  | 0 | 628.7347
21st, 23rd to 26th, 28th to 31st, 33rd to 36th & 38th to 41st Floor
21st, 23rd to 26th, 28th to 31st, 33rd to 36th & 38th to 41st Floor |  | 1 |  | 1BHK | 384.7581 |  | 0 | 615.613
21st, 23rd to 26th, 28th to 31st, 33rd to 36th & 38th to 41st Floor |  | 2 |  | 1BHK | 384.7581 |  | 0 | 615.613
21st, 23rd to 26th, 28th to 31st, 33rd to 36th & 38th to 41st Floor |  | 3 |  | 1BHK | 384.7581 |  | 0 | 615.613
21st, 23rd to 26th, 28th to 31st, 33rd to 36th & 38th to 41st Floor |  | 4 |  | 1BHK | 389.1283 |  | 0 | 622.6053
21st, 23rd to 26th, 28th to 31st, 33rd to 36th & 38th to 41st Floor |  | 5 |  | 1BHK | 392.9592 |  | 0 | 628.7347
21st, 23rd to 26th, 28th to 31st, 33rd to 36th & 38th to 41st Floor |  | 6 |  | 1BHK | 391.2639 |  | 0 | 626.0222
21st, 23rd to 26th, 28th to 31st, 33rd to 36th & 38th to 41st Floor |  | 7 |  | 1BHK | 391.2639 |  | 0 | 626.0222
21st, 23rd to 26th, 28th to 31st, 33rd to 36th & 38th to 41st Floor |  | 8 |  | 1BHK | 392.9592 |  | 0 | 628.7347
22nd, 27th, 32nd to 37th Floor (Part Refuge Area)
22nd, 27th, 32nd to 37th Floor (Part Refuge Area) |  | 1 |  | 1BHK | 384.7581 |  | 0 | 615.613
22nd, 27th, 32nd to 37th Floor (Part Refuge Area) |  | 2 |  | 1BHK | 384.7581 |  | 0 | 615.613
22nd, 27th, 32nd to 37th Floor (Part Refuge Area) |  | 3 |  | Refuge Area
22nd, 27th, 32nd to 37th Floor (Part Refuge Area) |  | 4
22nd, 27th, 32nd to 37th Floor (Part Refuge Area) |  | 5 |  | 1BHK | 392.9592 |  | 0 | 628.7347
22nd, 27th, 32nd to 37th Floor (Part Refuge Area) |  | 6 |  | 1BHK | 391.2639 |  | 0 | 626.0222
22nd, 27th, 32nd to 37th Floor (Part Refuge Area) |  | 7 |  | 1BHK | 391.2639 |  | 0 | 626.0222
22nd, 27th, 32nd to 37th Floor (Part Refuge Area) |  | 8 |  | 1BHK | 392.9592 |  | 0 | 628.7347
42nd Floor (Part Refuge Area)
42nd Floor (Part Refuge Area) |  | 1 |  | 1BHK | 384.7581 |  | 0 | 615.613
42nd Floor (Part Refuge Area) |  | 2 |  | 1BHK | 384.7581 |  | 0 | 615.613
42nd Floor (Part Refuge Area) |  | 3 |  | 1BHK | 384.7581 |  | 0 | 615.613
42nd Floor (Part Refuge Area) |  | 4 |  | Refuge Area
42nd Floor (Part Refuge Area) |  | 5 |  | 1BHK | 392.9592 |  | 0 | 628.7347
42nd Floor (Part Refuge Area) |  | 6 |  | 1BHK | 391.2639 |  | 0 | 626.0222
42nd Floor (Part Refuge Area) |  | 7 |  | 1BHK | 391.2639 |  | 0 | 626.0222
42nd Floor (Part Refuge Area) |  | 8 |  | 1BHK | 392.9592 |  | 0 | 628.7347
Tower K
Ground Floor For Parking & Fitness Center
1st Floor For Residential
1st Floor For Residential |  | 1 |  | 1BHK | 393.1379 |  | 0 | 629.0206
1st Floor For Residential |  | 2 |  | 1BHK | 391.4425 |  | 0 | 626.3081
1st Floor For Residential |  | 3 |  | 1BHK | 391.4425 |  | 0 | 626.3081
1st Floor For Residential |  | 4 |  | 1BHK | 391.4425 |  | 0 | 626.3081
1st Floor For Residential |  | 7 |  | 1BHK | 389.7138 |  | 0 | 623.5422
1st Floor For Residential |  | 8 |  | 1BHK | 393.1379 |  | 0 | 629.0206
2nd to 6th, 8th to 11th, 13th to 16th, 18th to 20th Floor
2nd to 6th, 8th to 11th, 13th to 16th, 18th to 20th Floor |  | 1 |  | 1BHK | 393.1379 |  | 0 | 629.0206
|  | 2 |  | 1BHK | 391.4425 |  | 0 | 626.3081
|  | 3 |  | 1BHK | 391.4425 |  | 0 | 626.3081
|  | 4 |  | 1BHK | 391.4425 |  | 0 | 626.3081
|  | 5 |  | 1BHK | 393.1379 |  | 0 | 629.0206
|  | 6 |  | 1BHK | 389.7138 |  | 0 | 623.5422
|  | 7 |  | 1BHK | 389.7138 |  | 0 | 623.5422
|  | 8 |  | 1BHK | 393.1379 |  | 0 | 629.0206
21st, 23rd to 26th, 28th to 31st, 33rd to 36th & 38th to 41st Floor
21st, 23rd to 26th, 28th to 31st, 33rd to 36th & 38th to 41st Floor |  | 1 |  | 1BHK | 393.1379 |  | 0 | 629.0206
|  | 2 |  | 1BHK | 391.4425 |  | 0 | 626.3081
|  | 3 |  | 1BHK | 391.4425 |  | 0 | 626.3081
|  | 4 |  | 1BHK | 391.4425 |  | 0 | 626.3081
|  | 5 |  | 1BHK | 393.1379 |  | 0 | 629.0206
|  | 6 |  | 1BHK | 389.7138 |  | 0 | 623.5422
|  | 7 |  | 1BHK | 389.7138 |  | 0 | 623.5422
|  | 8 |  | 1BHK | 393.1379 |  | 0 | 629.0206
7th, 12nd & 17th Floor
7th, 12nd & 17th Floor |  | 1 |  | Refuge Area
2
|  | 3 |  | 1BHK | 391.4425 |  | 0 | 626.3081
|  | 4 |  | 1BHK | 391.4425 |  | 0 | 626.3081
|  | 5 |  | 1BHK | 393.1379 |  | 0 | 629.0206
|  | 6 |  | 1BHK | 389.7138 |  | 0 | 623.5422
|  | 7 |  | 1BHK | 389.7138 |  | 0 | 623.5422
|  | 8 |  | 1BHK | 393.1379 |  | 0 | 629.0206
22nd, 27th, 32nd & 37th Floor (Part Refuge Area)
22nd, 27th, 32nd & 37th Floor (Part Refuge Area) |  | 1 |  | Refuge Area
2
|  | 3 |  | 1BHK | 391.4425 |  | 0 | 626.3081
|  | 4 |  | 1BHK | 391.4425 |  | 0 | 626.3081
|  | 5 |  | 1BHK | 393.1379 |  | 0 | 629.0206
|  | 6 |  | 1BHK | 389.7138 |  | 0 | 623.5422
|  | 7 |  | 1BHK | 389.7138 |  | 0 | 623.5422
|  | 8 |  | 1BHK | 393.1379 |  | 0 | 629.0206
42nd Floor (Part Refuge Area)
42nd Floor (Part Refuge Area) |  | 1 |  | Refuge Area
|  | 2 |  | 1BHK | 391.4425 |  | 0 | 626.3081
|  | 3 |  | 1BHK | 391.4425 |  | 0 | 626.3081
|  | 4 |  | 1BHK | 391.4425 |  | 0 | 626.3081
|  | 5 |  | 1BHK | 393.1379 |  | 0 | 629.0206
|  | 6 |  | 1BHK | 389.7138 |  | 0 | 623.5422
|  | 7 |  | 1BHK | 389.7138 |  | 0 | 623.5422
|  | 8 |  | 1BHK | 393.1379 |  | 0 | 629.0206
Tower F
Ground Floor For Parking & Library
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd to 36th, 38th to 41st, 43rd to 46th & 48th to 50th Floor For Residential
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd to 36th, 38th to 41st, 43rd to 46th & 48th to 50th Floor For Residential |  | 1 |  | 2BHK | 680.6928 |  | 0 | 1089.1084
|  | 2 |  | 2BHK | 528.4349 |  | 0 | 845.4958
|  | 3 |  | 2BHK | 528.4349 |  | 0 | 845.4958
|  | 4 |  | 2BHK | 680.6928 |  | 0 | 1089.1084
|  | 5 |  | 2BHK | 676.0955 |  | 0 | 1081.7527
|  | 6 |  | 2BHK | 679.6314 |  | 0 | 1087.4103
|  | 7 |  | 2BHK | 679.6314 |  | 0 | 1087.4103
|  | 8 |  | 2BHK | 676.0955 |  | 0 | 1081.7527
Service Floor Inbetween 26th & 27th Floor
7th, 12th, 17th, 22nd, 27th, 32nd, 37th, 42nd & 47th Floor (Part Refuge Area)
7th, 12th, 17th, 22nd, 27th, 32nd, 37th, 42nd & 47th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 680.6928 |  | 0 | 1089.1084 | 160
|  | 2 |  | 2BHK | 528.4349 |  | 0 | 845.4958
|  | 3 |  | 2BHK | 528.4349 |  | 0 | 845.4958
|  | 4 |  | Refuge Area | 680.6928 |  | 0 | 1089.1084
|  | 5 |  | 2BHK | 676.0955 |  | 0 | 1081.7527
|  | 6 |  | 2BHK | 679.6314 |  | 0 | 1087.4103
|  | 7 |  | 2BHK | 679.6314 |  | 0 | 1087.4103
|  | 8 |  | 2BHK | 676.0955 |  | 0 | 1081.7527
Tower G
Ground Floor For Parking & Library
1st Floor For Residential
1st Floor For Residential |  | 1 |  | 2BHK | 649.109 |  | 0 | 1038.5744
|  | 2 |  | 2BHK | 649.109 |  | 0 | 1038.5744
|  | 3 |  | 2BHK | 647.5299 |  | 0 | 1036.0479
|  | 4 |  | 2BHK | 654.7289 |  | 0 | 1047.5663
|  | 5 |  | 2BHK | 657.6998 |  | 0 | 1052.3196
|  | 6 |  | 2BHK | 654.7547 |  | 0 | 1047.6076
2nd to 6th, 8th to 11th, 13th to 15th Floor For Residential
2nd to 6th, 8th to 11th, 13th to 15th Floor For Residential |  | 1 |  | 2BHK | 649.109 |  | 0 | 1038.5744
|  | 2 |  | 2BHK | 649.109 |  | 0 | 1038.5744
|  | 3 |  | 2BHK | 647.5299 |  | 0 | 1036.0479
|  | 4 |  | 2BHK | 654.7289 |  | 0 | 1047.5663
|  | 5 |  | 2BHK | 657.6998 |  | 0 | 1052.3196
|  | 6 |  | 2BHK | 654.7547 |  | 0 | 1047.6076
7th & 12th Floor (Part Refuge Area)
7th & 12th Floor (Part Refuge Area) |  | 1 |  | Refuge Area
|  | 2 |  | 2BHK | 649.109 |  | 0 | 1038.5744
|  | 3 |  | 2BHK | 647.5299 |  | 0 | 1036.0479
|  | 4 |  | 2BHK | 654.7289 |  | 0 | 1047.5663
|  | 5 |  | 2BHK | 657.6998 |  | 0 | 1052.3196
|  | 6 |  | 2BHK | 654.7547 |  | 0 | 1047.6076
16th, 18th to 21st, 23rd to 26th, 28th to 30th Floor
16th, 18th to 21st, 23rd to 26th, 28th to 30th Floor |  | 1 |  | 2BHK | 649.109 |  | 0 | 1038.5744
|  | 2 |  | 2BHK | 649.109 |  | 0 | 1038.5744
|  | 3 |  | 2BHK | 647.5299 |  | 0 | 1036.0479
|  | 4 |  | 2BHK | 654.7289 |  | 0 | 1047.5663
|  | 5 |  | 2BHK | 657.6998 |  | 0 | 1052.3196
|  | 6 |  | 2BHK | 654.7547 |  | 0 | 1047.6076
17th, 22nd & 27th Floor (Part Refuge Area)
17th, 22nd & 27th Floor (Part Refuge Area) |  | 1 |  | Refuge Area
|  | 2 |  | 2BHK | 649.109 |  | 0 | 1038.5744
|  | 3 |  | 2BHK | 647.5299 |  | 0 | 1036.0479
|  | 4 |  | 2BHK | 654.7289 |  | 0 | 1047.5663
|  | 5 |  | 2BHK | 657.6998 |  | 0 | 1052.3196
|  | 6 |  | 2BHK | 654.7547 |  | 0 | 1047.6076
31st, 33rd to 36th, 38th to 41st, 43rd to 46th, 48th to 50th Floor
31st, 33rd to 36th, 38th to 41st, 43rd to 46th, 48th to 50th Floor |  | 1 |  | 2BHK | 649.109 |  | 0 | 1038.5744
|  | 2 |  | 2BHK | 649.109 |  | 0 | 1038.5744
|  | 3 |  | 2BHK | 647.5299 |  | 0 | 1036.0479
|  | 4 |  | 2BHK | 654.7289 |  | 0 | 1047.5663
|  | 5 |  | 2BHK | 657.6998 |  | 0 | 1052.3196
|  | 6 |  | 2BHK | 654.7547 |  | 0 | 1047.6076
32nd, 37th, 42nd & 47th Floor (Part Refuge Area)
32nd, 37th, 42nd & 47th Floor (Part Refuge Area) |  | 1 |  | Refuge Area
|  | 2 |  | 2BHK | 649.109 |  | 0 | 1038.5744
|  | 3 |  | 2BHK | 647.5299 |  | 0 | 1036.0479
|  | 4 |  | 2BHK | 654.7289 |  | 0 | 1047.5663
|  | 5 |  | 2BHK | 657.6998 |  | 0 | 1052.3196
|  | 6 |  | 2BHK | 654.7547 |  | 0 | 1047.6076
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd to 36th, 38th to 41st, 43rd to 46th & 48th to 50th For Residential
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd to 36th, 38th to 41st, 43rd to 46th & 48th to 50th For Residential |  | 1 |  | 2BHK | 680.6928 |  | 0 | 1089.1084
|  | 2 |  | 2BHK | 528.4349 |  | 0 | 845.4958
|  | 3 |  | 2BHK | 528.4349 |  | 0 | 845.4958
|  | 4 |  | 2BHK | 680.6928 |  | 0 | 1089.1084
|  | 5 |  | 2BHK | 676.0955 |  | 0 | 1081.7527
|  | 6 |  | 2BHK | 679.6314 |  | 0 | 1087.4103
|  | 7 |  | 2BHK | 679.6314 |  | 0 | 1087.4103
|  | 8 |  | 2BHK | 676.0955 |  | 0 | 1081.7527
Service Floor Inbetween 26th & 27th Floor
7th, 12th, 17th, 22nd, 27th, 32nd, 37th, 42nd & 47th Floor (Part Refuge Area)
7th, 12th, 17th, 22nd, 27th, 32nd, 37th, 42nd & 47th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 680.6928 |  | 0 | 1089.1084 | 160
|  | 2 |  | 2BHK | 528.4349 |  | 0 | 845.4958
|  | 3 |  | 2BHK | 528.4349 |  | 0 | 845.4958
|  | 4 |  | Refuge Area | 680.6928 |  | 0 | 1089.1084
|  | 5 |  | 2BHK | 676.0955 |  | 0 | 1081.7527
|  | 6 |  | 2BHK | 679.6314 |  | 0 | 1087.4103
|  | 7 |  | 2BHK | 679.6314 |  | 0 | 1087.4103
|  | 8 |  | 2BHK | 676.0955 |  | 0 | 1081.7527
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Tower A to C = All work Completed. OC Received. Tower D & E = All work Completed. OC Received. Tower F, G - Construction work is in process at the time of Visit. (Internal visit was not allowed.) Tower H, J & K - All work Completed. Provide OC. 2. We have considered rate by verifying it from market inquire. 3. Car parking is subjected to authentic documentation. 4. We have updated revised approved floor plan of Tower - A, B, C, D, J & K. (on. 28/04/2022). 5. We have updated revised approved floor plan & C.C of Tower F (on 25/06/2022). 6. We have updated revised approved floor plan & C.C of Tower F & G (on 28/01/2023). 7. We have updated OC for Wing D & E from RERA (on 30/09/2024). 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area. | [6 empty] | On Site, we meet Mr.Vedamani - 2268328901.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Ten X Habitat Raymond Realty (Tower A, B, C, D, E, F, G, H, J & K)
Project Site Address |  |  | : | Ten X Habitat Raymond Realty, Tower A, B, C, D, E, F, G, H, J & K, Road - Pokharan Road Number 2, Village - Panchpakhadi, Near - Smt. Sunitidevi Singhania school, Thane West, Thane, Maharashtra 400606
Site Visit Date & Time |  |  | : | 03/07/2025 at 01:29PM
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Ajay Songare | Authorized Signatory Name & Signature | :
E D C B A
F G H J K
G
F
F
K
J
H
G
A
E
C
B
D
F
G
H
J
K
A
B
C
D
E
A
B
C
E
D
F
G
H
J
K