## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 08/07/2025
Bank Name: |  |  |  |  | Axis Bank
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-07-07
Name of the builder group |  |  |  |  | M/s. Sai Krupa Developers
Name of the builder company |  |  |  |  | M/s. Sai Krupa Developers
Name of the Project (As per Builder) |  |  |  |  | Sai Krupa Valley
Name of the Project (As per RERA) |  |  |  |  | Sai Krupa Valley - Phase 1
Site Person - Contact Details ( Name & Contact No.) |  |  |  |  | Mr. kalpesh mali 7798541455 |  |  |  | Mr. Deepak (8898338043).
Name / No of the Building |  |  |  |  | Building No.1 to 4
Docouments Provided |  |  |  |  | Approved Plan, CC
RERA Name & No. |  |  |  |  | Building No.1 to 5 |  | P52000000739
Project location details : |  | Sai Krupa Valley, Survey No. 489/1 to 29, (Old Survey No. 169/2, 170/ 1&2, 171/1), Near Gopal Apartment, Internal Road, Chinch Aali, Neral, Neral West, Karjat, Raigad 410101
Survey No. |  | 489/1 to 29, (Old Survey No. 169/2, 170/ 1&2, 171/1)
Locality |  | Chinch Aali
Road |  | Internal Road |  |  | Locality/Village |  | Neral
City |  | Neral West |  |  | District: |  | Raigad
Taluka |  | Karjat |  |  | Pin Code |  | 410101
Nearby Landmark |  | Gopal Apartment |  |  | Distance from city centre: |  | 1.3Km from Neral Railway Station.
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market, etc.) |  |  |  |  | Yes, all the mentioned amenities are within the radius of 2 to 2.5 KM.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing Area
Quality of infrastructure in vicinity |  |  |  |  | Good
Restrictive Covenants in regard to Land Use |  |  |  |  | No
Boundaries |  |  | As per Layout |  |  | At site
East |  |  | 9 M Wide Road |  |  | Internal Road
West |  |  | Other Plot |  |  | Internal Road
North |  |  | 6 M Wide Road/Building No.5 |  |  | Internal Road/Building No.5
South |  |  | 12 M Wide Road |  |  | Internal Road
Does the boundaries at site match, as mentioned in the Docoumentation:
Latitude & Longitude |  |  | 19.0197591,73.3100068
Location Link |  |  | https://maps.app.goo.gl/oZ2gttRfSnrjuYJG7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 11974.729
Permissible FSI |  |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  |  | 0.40515
Total FSI availaible for the project |  |  |  |  | 1.5052
Total Approved Builtup area of the project (Sq.Mt) |  |  |  |  | 18023.795
Total number of Buildings |  |  |  |  | 4 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Collector of Raigad
Layout Approval No |  | MS/LNA-1/PK66/2021 |  |  |  | Dated | 2022-11-22
Approved Floor plan No. (Building No.1 & 2) |  | MS/LNA-1/PK136/2013 |  |  |  | Dated | 2016-01-28
Approved Floor plan No. (Building No.3 & 4) |  | MS/LNA-1/PK66/2021 |  |  |  | Dated | 2022-11-22
Commencement-CC No Valid Up to: |  | MS/LNA1(B)/PK136/2013 |  |  |  | Dated | 2016-01-28
Building No. 1, 2, 3 & 4 = Gr + 1st to 7th Floor Building No.5 = Gr + 1st to 3rd Floor
Commencement-CC No Valid Up to: |  | MS/LNA1/A1(B)/Tokan No.15671/PK66/2021 |  |  |  | Dated | 2022-11-22 |  |  | 112
Building No.3 = Gr + 1st to 14th Floor Building No.4 = 7th Floor (BUA = 113.073 Sq.M)
Power Noc No.: Valid Up to: |  | MVN/TANTRIK/535/2021 Survey No. 489/1 to 29, (Old Survey No. 169/2, 170/ 1&2, 171/1) |  |  |  | Dated | 2021-05-04
Fire Noc No.: Valid Up to: |  | MFS/51/2022/645 Building No. 4 = Gr + 1st to 7th Floor Building No.3 = Gr + 1st to 14th Floor |  |  |  | Dated | 2022-08-18 |  | Bldg No.5 = Gr + 1st to 3rd Floor (3 Flats)
O. Certificate No.: |  | MS/L.N.A.1(B)/67411/O.C/51/2018 Bldg No. 1 = Gr + 1st to 7th Floor (56 Flats) |  |  |  | Dated | 2019-05-07
O. Certificate No.: |  | MS/L.N.A.1(B)/Part.OC/10/2020 Bldg No. 2 = Gr + 1st to 7th Floor (112 Flats) |  |  |  | Dated | 12/11/2021 |  | Bldg No.5 = Gr + 1st to 3rd Floor (3 Flats)
Building wise Construction details
Approved No of units |  |  | Flat - 376
Approved Builtup Area of the Building No.1 to 4 (Sq.Mtr) |  |  | 17774.142 | [5 empty] | 7970.125
Approved no of Floors |  |  | Building No. 1, 2 & 4 = Gr + 1st to 7th Floor Building No.3 = Gr + 1st to 14th Floor | [5 empty] | Building No.5 = Gr + 1st to 3rd Floor
Proposed no of Floors |  |  | Building No. 1, 2 & 4 = Gr + 1st to 7th Floor Building No.3 = Gr + 1st to 14th Floor | [5 empty] | Building No.5 = Gr + 1st to 3rd Floor
Expected Completion |  |  | As per RERA - 01/08/2026 | [7 empty] | Date of Commencement of Construction: 28/01/2016. |  | Expected Completion: 01/08/2026
Projected life of the structure |  |  | 60 years After Completion
Quality of construction |  |  | Good | [5 empty] | https://housing.com/in/buy/projects/page/39978-sai-krupa-valley-by-sai-krupa-builders-in-neral/brochure
Proposed Amenities : |  |  | Club House With Modern Amenities, Gymnasium, Swimming Pool, Jogging Track, Party Lawn, Deck Area, Flower Garden, Lift, Parking etc.
Violations Observed if any : |  |  | NA
Material laying at Site |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction
Construction details: |  | Building No. 1 & 2 = Gr + 1st to 7th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. OC Received.
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 7 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% | [5 empty] | Plinth in process | 5.25
Possession |  | 7 | 100% | [5 empty] | Plinth completed | 7
Construction details: |  | Building No.3 = Gr + 1st to 14th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 12 Slab, Brickwork upto 9 Floor, Internal Plaster upto 7 Floor, External Plaster upto 6 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 14
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 12 Slab, Brickwork upto 9 Floor, Internal Plaster upto 7 Floor, External Plaster upto 6 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% |  | 54.86% |  | 76.86% |  | Excavation in process | 7
Plinth |  | 14 | 100% | [5 empty] | Excavation Completed | 14
RCC (Including podiums) |  | 12 | 80% | [5 empty] | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 9 | 64.29% | [5 empty] | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 7 | 50% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 42.86% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 10.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 14
Construction details: |  | Part 2 : Building No.3 = Gr + 1st to 14th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 5 Floor, Internal Plaster upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 14
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 5 Floor, Internal Plaster upto 1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% |  | 34.55% |  | 63.14% |  | Excavation in process | 7
Plinth |  | 14 | 100% | [5 empty] | Excavation Completed | 14
RCC (Including podiums) |  | 8 | 53.33% | [5 empty] | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 5 | 35.71% | [5 empty] | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 1 | 7.143% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 10.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 14
Average Progress % (Part 1 & 2) |  |  | 44.7% |  | Average Disbursement % (Part 1 & 2) |  | 70%
Construction details: |  | Building No.4 = Gr + 1st to 7th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 7 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% | [5 empty] | Plinth in process | 5.25
Possession |  | 7 | 100% | [5 empty] | Plinth completed | 7
Construction details: |  | Building No.5 = Gr + 1st to 3rd Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. OC Received.
Progress % |  | 100% |  |  | Disbursement % |  | 100% |  | Piling Work in process | 0.75
[9 empty] | Excavation in process | 1.5
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Excavation Completed | 3
Excavation |  | 3 | 100% |  | 100% |  | 100% |  | Footing in Process | 0.75
Plinth |  | 3 | 100% | [5 empty] | Footing Completed | 1.5
RCC (Including podiums) |  | 4 | 100% | [5 empty] | Basement 1 | 0
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Basement 2 | 0
Internal Plaster | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Basement 3 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% | [5 empty] | Basement 4 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 100% | [5 empty] | Plinth in process | 2.25
Painting & Wooden |  | 3 | 100% | [5 empty] | Plinth completed | 3
Building Common Amenities | Building Common Amenities | 3 | 100%
Possession |  | 3 | 100%
Recommended Rates of the Property :
Recommended rate of the flat Per Sq.Ft. on saleable | [5 empty] | 4250 |  |  | Bldg No. 03 Flat no. 1206 Loading change 50% on 10/07/2024 by smith cost sheet
Floor rise rate | [5 empty] | NA
Club Membership | [5 empty] | 80,000/- (For 1BHK), 10,000/- (For 2BHK)
Advance maintenance | [5 empty] | 21600/-
General Charges | [5 empty] | 6500/-
Development Charges | [5 empty] | 200/-
Recommended rate of Parking | [5 empty] | 100000
Distress valuation of the property | [5 empty] | 2,311/- (Per Sq.Ft.)
Residential Area Details :
Building & Wing |  |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 |  |  | 56 |  | 22487.6241 |  | 35410.4465
Building No.2 |  |  | 112 |  | 33221.579 |  | 52235.2593
Building No.3 |  |  | 124 |  | 64366.9332 |  | 90113.7064
Building No.4 |  |  | 84 |  | 33810.1815 |  | 52995.6875
Total |  |  | 376 |  | 153886.3177 |  | 230755.0998
Building Details Floor Wise
Details of Residential in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet Area | Attached Terrace Area | Saleble Area | PLC Y/N | Floor
Building No.1
Ground Floor For Parking
1st, 3rd & 5th Floor For Residential
1 |  | 1 BHK | 335.191 | 45.2088 | 514.4761 | N | 1st, 3rd & 5th Floor For Residential |  |  |  | 1.4 | 2186523.612
2 |  | 1 BHK | 335.191 | 45.2088 | 514.4761 | N |  |  |  |  | 1.4 | 2186523.612
3 |  | 1 BHK | 335.191 | 45.2088 | 514.4761 | N |  |  |  |  | 1.4 | 2186523.612
4 |  | 2 BHK | 458.7079 | 99.2979 | 741.4889 | N |  |  |  |  | 1.4 | 3151327.842
5 |  | 2 BHK | 467.4267 | 93.6468 | 748.0442 | N |  |  |  |  | 1.4 | 3179187.765
6 |  | 2 BHK | 456.286 | 45.2088 | 684.0091 | N |  |  |  |  | 1.4 | 2907038.862
7 |  | 2 BHK | 449.6123 | 79.1154 | 708.5726 | N |  |  |  |  | 1.4 | 3011433.516
8 |  | 2 BHK | 452.384 | 79.1154 | 712.453 | N |  |  |  |  | 1.4
2nd, 4th & 6th Floor | [10 empty] | #DIV/0!
1 |  | 1 BHK | 335.191 | 80.73 | 549.9973 | N | 2nd, 4th & 6th Floor |  |  |  | 1.4
2 |  | 1 BHK | 335.191 | 80.73 | 549.9973 | N |  |  |  |  | 1.4
3 |  | 1 BHK | 335.191 | 83.1519 | 552.4192 | N |  |  |  |  | 1.4
4 |  | 2 BHK | 462.7444 | 0 | 647.8421 | N |  |  |  |  | 1.4
5 |  | 2 BHK | 467.4267 | 0 | 654.3974 | N |  |  |  |  | 1.4
6 |  | 2 BHK | 459.717 | 47.9536 | 691.5574 | N |  |  | Dipak = 30/11/2019.
7 |  | 2 BHK | 449.6123 | 83.1519 | 712.6091 | N
8 |  | 2 BHK | 421.3837 | 83.1519 | 673.0891 | N
7th Floor
1 |  | 1 BHK | 335.191 | 46.0161 | 515.2834 | N | 7th Floor
2 |  | 1 BHK | 335.191 | 46.0161 | 515.2834 | N
3 |  | 1 BHK | 335.191 | 46.0161 | 515.2834 | N
4 |  | 1 BHK+T | 415.006 | 189.328 | 770.3364 | N
5 |  | 1 BHK+T | 346.4932 | 182.1269 | 667.2173 | N
6 |  | 1 BHK+T | 341.6494 | 133.6889 | 611.998 | N
7 |  | 1 BHK+T | 361.5628 | 155.9704 | 662.1582 | N
8 |  | 1 BHK+T | 348.0001 | 155.9704 | 643.1705 | N
Building No. 2
Ground Floor For Parking
1st, 3rd, 5th & 7th Floor For Residential
1 |  | 1 BHK | 305.5092 | 0 | 427.7129 | N | 1st, 3rd, 5th & 7th Floor For Residential
2 |  | 1 BHK | 324.5346 | 79.1154 | 533.4638 | N
3 |  | 1 BHK | 324.5346 | 93.001 | 547.3494 | N
4 |  | 1 BHK | 263.5027 | 52.313 | 421.2168 | N
5 |  | 1 BHK | 289.9822 | 52.313 | 458.2881 | N
6 |  | 1 BHK | 263.5027 | 52.313 | 421.2168 | N
7 |  | 1 BHK | 263.5027 | 52.313 | 421.2168 | N
8 |  | 1 BHK | 263.5027 | 52.313 | 421.2168 | N
9 |  | 1 BHK | 263.5027 | 52.313 | 421.2168 | N
10 |  | 1 BHK | 263.5027 | 52.313 | 421.2168 | N
11 |  | 1 BHK | 289.9822 | 52.313 | 458.2881 | N
12 |  | 1 BHK | 289.9822 | 52.313 | 458.2881 | N
13 |  | 1 BHK | 314.1204 | 93.001 | 532.7696 | N
14 |  | 1 BHK | 324.5346 | 93.001 | 547.3494 | N
15 |  | 1 BHK | 324.5346 | 93.001 | 547.3494 | N
16 |  | 1 BHK | 305.5092 | 0 | 427.7129 | N
2nd, 4th & 6th Floor | [10 empty] | 4250
1 |  | 1 BHK | 302.8182 | 0 | 423.9455 | N | 2nd, 4th & 6th Floor |  |  |  | 1801768.4685
2 |  | 1 BHK | 313.2324 | 52.313 | 490.8384 | N |  |  |  |  | 2086063.2
3 |  | 1 BHK | 313.2324 | 52.313 | 490.8384 | N |  |  |  |  | 2086063.2
4 |  | 1 BHK | 323.808 | 40.6879 | 494.0192 | N |  |  |  |  | 2099581.4385
5 |  | 1 BHK | 289.9822 | 0 | 405.975 | N |  |  |  |  | 1725393.852
6 |  | 1 BHK | 289.9822 | 0 | 405.975 | N |  |  |  |  | 1725393.852
7 |  | 1 BHK | 293.8572 | 93.001 | 504.401 | N |  |  |  |  | 2143704.42
8 |  | 1 BHK | 293.8572 | 93.001 | 504.401 | N |  |  |  |  | 2143704.42
9 |  | 1 BHK | 293.8572 | 93.001 | 504.401 | N |  |  |  |  | 2143704.42
10 |  | 1 BHK | 293.8572 | 93.001 | 504.401 | N |  |  |  |  | 2143704.42
11 |  | 1 BHK | 289.9822 | 0 | 405.975 | N |  |  |  |  | 1725393.852
12 |  | 1 BHK | 289.9822 | 0 | 405.975 | N |  |  |  |  | 1725393.852
13 |  | 1 BHK | 323.808 | 57.1568 | 510.4881 | N |  |  |  |  | 2169574.3485
14 |  | 1 BHK | 313.2324 | 52.313 | 490.8384 | N |  |  |  |  | 2086063.2
15 |  | 1 BHK | 313.2324 | 52.313 | 490.8384 | N |  |  |  |  | 2086063.2
16 |  | 1 BHK | 302.8182 | 0 | 423.9455 | N |  |  | 10.764 |  | 1801768.4685
Building No.3 | [10 empty] | Saleble AREA
Ground Floor For Soceity Office, Driver Room & Parking | [10 empty] | 50%
1st, 2nd, 3rd, 4th, 6th, 7th, 9th, 11th & 14th Floor For Residential
1 |  | 1 BHK | 400.2593 | 0 | 560.3631 | N | 1st, 2nd, 3rd, 4th, 6th, 7th, 9th, 11th & 14th Floor For Residential |  | 30.9825 | 5.15 | 5.055
2 |  | 1 BHK | 402.1969 | 0 | 563.0756 | N
3 |  | 1 BHK | 434.7687 | 0 | 608.6762 | N
4 |  | 1 BHK | 438.3208 | 0 | 613.6492 | N
5 |  | 2 BHK | 624.721 | 0 | 874.6094 | N |  |  | 501.5755 | 8.31
6 |  | 2 BHK | 626.6586 | 0 | 877.322 | N
7 |  | 2 BHK | 623.9353 | 0 | 873.5094 | N |  |  |  | 11.4
8 |  | 2 BHK | 566.4878 | 0 | 793.0829 | N
9 |  | 2 BHK | 564.8732 | 0 | 790.8225 | N
12th Floor
1 |  | 1 BHK | 400.2593 | 0 | 560.3631 | N | 12th Floor |  | 30.9825 | 5.15 | 5.055
2 |  | 1 BHK | 402.1969 | 0 | 563.0756 | N
3 |  | 1 BHK | 434.7687 | 0 | 608.6762 | N
4 |  | 1 BHK | 438.3208 | 0 | 613.6492 | N
5 |  | 2 BHK | 624.721 | 0 | 874.6094 | N |  |  | 501.5755 | 8.31
6 |  | 2 BHK | 626.6586 | 0 | 939.9878 | N |  |  | loading change 50%
7 |  | 2 BHK | 623.9353 | 0 | 873.5094 | N |  |  |  | 11.4
8 |  | 2 BHK | 566.4878 | 0 | 793.0829 | N
9 |  | 2 BHK | 564.8732 | 0 | 790.8225 | N
5th & 10th Floor
1 |  | 1 BHK | 400.2593 | 0 | 560.3631 | N | 5th & 10th Floor
2 |  | 1 BHK | 402.1969 | 0 | 563.0756 | N
3 |  | 1 BHK | 434.7687 | 0 | 608.6762 | N
4 |  | 1 BHK | 438.3208 | 0 | 613.6492 | N
5 |  | 2 BHK | 624.721 | 0 | 874.6094 | N
6 |  | 2 BHK | 626.6586 | 0 | 877.322 | N
7 |  | 2 BHK | 623.9353 | 0 | 873.5094 | N
8 |  | 2 BHK | 566.4878 | 0 | 793.0829 | N
9 |  | 1 BHK | 409.5164 | 0 | 573.3229 | N
8th & 13th Floor (Part Refuge Area)
1 |  | 1 BHK | 400.2593 | 0 | 560.3631 | N | 8th & 13th Floor (Part Refuge Area)
2 |  | 1 BHK | 402.1969 | 0 | 563.0756 | N
3 |  | 1 BHK | 436.3618 | 0 | 610.9065 | N
4 |  | Refuge Area
5 |  | 2 BHK | 624.721 | 0 | 874.6094 | N
6 |  | 2 BHK | 626.6586 | 0 | 877.322 | N
7 |  | 2 BHK | 623.9353 | 0 | 873.5094 | N
8 |  | 2 BHK | 566.4878 | 0 | 793.0829 | N
9 |  | 2 BHK | 564.8732 | 0 | 790.8225 | N
Building No.4
Ground Floor For Parking
1st, 3rd & 5th Floor For Residential
1 |  | 1 BHK | 347.7848 | 79.1154 | 566.0142 | N | 1st, 3rd & 5th Floor For Residential
2 |  | 1 BHK | 349.7224 | 77.5008 | 567.1121 | N
3 |  | 2 BHK | 508.5452 | 93.6468 | 805.6101 | N |  |  | 350 zoom
4 |  | 1 BHK | 349.7224 | 77.5008 | 567.1121 | N
5 |  | 1 BHK | 342.941 | 77.5008 | 557.6183 | N
6 |  | 1 BHK | 342.941 | 77.5008 | 557.6183 | N |  |  | 2369877.588
7 |  | 1 BHK | 342.941 | 77.5008 | 557.6183 | N |  |  | 84.2821
8 |  | 2 BHK | 508.5452 | 92.0322 | 803.9955 | N |  |  | 497.85
9 |  | 2 BHK | 504.8316 | 93.6468 | 800.411 | N
10 |  | 2 BHK | 496.2742 | 77.5008 | 772.2847 | N
11 |  | 2 BHK | 496.2742 | 77.5008 | 772.2847 | N |  |  | 78.4696
12 |  | 1 BHK | 354.8891 | 77.5008 | 574.3455 | N
2nd, 4th & 6th Floor
1 |  | 1 BHK | 326.3914 | 33.5837 | 490.5316 | N | 2nd, 4th & 6th Floor
2 |  | 1 BHK | 327.9253 | 43.5942 | 502.6896 | N
3 |  | 2 BHK | 485.1335 | 45.2088 | 724.3957 | N |  |  | 87.1884 | 108.1782
4 |  | 1 BHK | 327.9253 | 43.5942 | 502.6896 | N
5 |  | 1 BHK | 321.1439 | 43.5942 | 493.1957 | N |  |  | 2.87 RPLC 2.7
6 |  | 1 BHK | 321.1439 | 43.5942 | 493.1957 | N
7 |  | 1 BHK | 321.1439 | 43.5942 | 493.1957 | N
8 |  | 2 BHK | 485.1335 | 45.2088 | 724.3957 | N
9 |  | 2 BHK | 481.4199 | 45.2088 | 719.1967 | N
10 |  | 2 BHK | 472.8625 | 75.8862 | 737.8937 | N
11 |  | 2 BHK | 472.8625 | 75.8862 | 737.8937 | N
12 |  | 1 BHK | 333.092 | 43.5942 | 509.923 | N
7th Floor | [10 empty] | 250%
1 |  | 1 BHK | 347.7848 | 79.1154 | 566.0142 | N | 7th Floor
2 |  | 1 BHK | 349.7224 | 77.5008 | 567.1121 | N
3 |  | 2 BHK | 508.5452 | 93.6468 | 805.6101 | N
4 |  | 1 BHK | 349.7224 | 77.5008 | 567.1121 | N
5 |  | 1 BHK | 342.941 | 77.5008 | 557.6183 | N
6 |  | 1 BHK | 342.941 | 77.5008 | 557.6183 | N
7 |  | 1 BHK | 342.941 | 77.5008 | 557.6183 | N
8 |  | 2 BHK | 508.5452 | 92.0322 | 803.9955 | N
9 |  | 2 BHK | 504.8316 | 93.6468 | 800.411 | N
10 |  | 2 BHK | 496.2742 | 77.5008 | 772.2847 | N
11 |  | 2 BHK | 496.2742 | 77.5008 | 772.2847 | N
12 |  | 1 BHK | 354.8891 | 77.5008 | 574.3455 | N
Building No.5
Ground Floor For Parking
1st & 2nd Floor For Residential
1 |  | 2 BHK | 719.0352 | 0 | 1042.601 | N | 1st & 2nd Floor For Residential |  | 10.764
3rd Floor
1 |  | 1 BHK | 635.3182 | 85.3585 | 1006.5699 | N | 3rd Floor
Remarks : 1. Building No. 1 & 2 = All work completed. OC Received. Building No. 4 = All work completed. Please provide OC. Building No. 3 = Construction work is in process at the time of visit. 2. As per RERA site & commencement certifacate total five Numbers of buildings are consist. But provided plan only For four buildings Bldg No. 1 to 4. 3. We have considered rate by verifying it from market inquire. 4. We considered Gross carpet area = Net carpet + Enclose Balcony + W.S Area. 5. We considered saleable area as per our calculation (40% Loading). 6. As per RERA site, In the project Sai Krupa Valley-Phase 1 consists of Building No.1 to 5 7. As per site meet persons Mr. Deepak (8898338043), Building no.5 is belongs to landowner. 8.We have upadated revised approved plans & CC for Building No.3 & 4 on 02/07/2024 10. High tension lines are passing nearby project Sai Krupa Valley-Phase 1 (Building No.1, 2 & 3) . 11. Recommended Rates/Other Charges of the Property have been revised on 10/07/2024. 12. With Reference to Remark 10, Power NOC is provided by Bank Official on Mail which is attached below 7. On site, we meet Kalpesh (7798541455). | [9 empty] | 8. As per site meet persons Mr. Deepak (8898338043), Building no.5 is belongs to landowner, Therefore we have not drafted area for that building
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is arrived at by loading 37% on Gross Carpet area thereafter adding of terrace area (the terrace area more than 100 add half of terrace area).
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja.
Inspected By : |  |  | Naynesh Sunil Lovanshi |  | Report By : |  | Shruti
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Sai Krupa Valley - Phase 1
Layout :
Remark No. 12
Google Map:
Note on L233: SACHIN: Give loading of 50% for A Category
3
4
Building No.5
Building No.1
Building No.2
Building No.3
Building No.4
H.T Lines
Building No.3
Building No.4
Building No.4
Building No.3
H.T Lines
OC Received
OC Received
Building No.3
Building No.3
Building No.1
Building No.2
Building No.4

## C %
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 8 | 100 | Progress |  |  | 10 | 40 | 15 | 10 | 10 | 5 | 5
Bricks | Total Floor | completed Floor | 100 | Recommended |  |  | 30 | 30 | 15 | 10 | 5 | 5 | 5
| 7 | 7 | 100
plaster | Total Floor | completed Floor | 100
| 7 | 7 | 100
Flooring | Total Floor | completed Floor
| 7 | 7 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 7 | 7 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 7 | 7 |  | Plaster | 10 | 10
|  |  |  | Flooring | 10 | 5
|  |  |  | Wood & painting | 5 | 5
|  |  |  | Finishing | 5 | 5
|  |  |  | total | 95 | 100

## C % (2)
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 8 | 100 | Progress |  |  | 10 | 40 | 15 | 10 | 10 | 5 | 5
Bricks | Total Floor | completed Floor | 100 | Recommended |  |  | 30 | 30 | 15 | 10 | 5 | 5 | 5
| 7 | 7 | 100
plaster | Total Floor | completed Floor | 100
| 7 | 7 | 100
Flooring | Total Floor | completed Floor
| 7 | 7 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 7 | 7 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 7 | 7 |  | Plaster | 10 | 10
|  |  |  | Flooring | 10 | 5
|  |  |  | Wood & painting | 5 | 5
|  |  |  | Finishing | 5 | 5
|  |  |  | total | 95 | 100

## C % (3)
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 6.25 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 0.5 | 0 | Progress |  |  | 10 | 2.5 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 1.875 | 0 | 0 | 0 | 0 | 0
| 7 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 7 | 0 | 0
Flooring | Total Floor | completed Floor
| 7 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 7 | 0 |  | RCC | 2.5 | 1.875
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 7 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 12.5 | 31.875

## C % (4)
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 8 | 100 | Progress |  |  | 10 | 40 | 15 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 30 | 15 | 0 | 0 | 0 | 0
| 7 | 7 | 0
plaster | Total Floor | completed Floor | 0
| 7 | 0 | 0
Flooring | Total Floor | completed Floor
| 7 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 7 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 7 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 65 | 75

## Note
2020-10-27 | Pratiksha
2021-02-13 | Pratiksha

## Valuation
2020-10-27 | Pratiksha
Market Research Data
| Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
| Housing | Sai Krupa Valley | 1BHK | 353 | 511.85 | 3424.8315 | 1753000
| Housing | Sai Krupa Valley | 2BHK | 620 | 899 | 3418.2425 | 3073000
| Proptiger | Sai Krupa Valley | 1BHK | 230 | 333.5 | 5697.1514 | 1900000
| Proptiger | Sai Krupa Valley | 2BHK | 653 | 946.85 | 4029.1493 | 3815000
| Average |  |  |  |  | 4142.3437
| Valuation Adopted |  |  |  |  | 4200