## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 06/07/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-07-05
Name of the builder group |  |  |  |  | M/s.Vrudee Associates
Name of the builder company |  |  |  |  | M/s.Vrudee Associates
Name of the Project |  |  |  |  | Patels Prestige
Contect Details ( Name & Contect No.) |  |  |  |  | 9665393600/9820412604
Name / no of the Building |  |  |  |  | Type A, B & C
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC.
RERA No. |  |  |  |  | P51700017035
Project Address |  | Patels Prestige, Survey no.17 Hissa no. 2/A, C, D Plot no.3, Ambernath, Thane.
Plot No | Plot no.3 | Survey no |  | Survey no.17 Hissa no. 2/A, C, D |  |  | Locality | Khoj Khuntavali
Road | Navare Park Road |  |  |  | District | Thane
City | Ambernath |  |  |  | Pin Code | 421501
Near by Landmark |  | Father Agnel School |  |  | Distance from city centre: |  | 2.8 Km from Ambernath Railway Station.
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Main road |  | Shankar Heights |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 19.215 |  | Longitude |  | 73.1989
Location Link |  | https://goo.gl/maps/4nais2D5WcM238gS8?coh=178572&entry=tt
Approval details:
Approved usage of the Property: Residential + Commercial (Restrictive Covenants in regard to Land Use, if any) : No
Total land area of the project in Sq. Mt. |  |  |  |  | 6800 (Net area =5332.5)
Permissible FSI |  |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  |  | 0.54
Total FSI availaible for the project |  |  |  |  | 1.64
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 8769.75
Total number of Buildings |  |  |  |  | 03 Wings
Approval Detail : Plan approval
Type A
Layout Approval No |  | ANP/NRV/BP/20-21/1312/9110/58 |  |  |  | Dated | 2021-03-15
Building plan No B + Gr + 1st to 7th Floor 8th to 12th Floor |  | A.N.P/NRV/BP/19-20/379/8933/22 A.N.P/NRV/BP/20-21/1312/9110/58 |  |  |  | Dated | 09/07/2019 15/03/2021
Type B
Layout Approval No |  | ANP/NRV/BP/20-21/1312/9110/58 |  |  |  | Dated | 2021-03-15
Building plan No 1st to 7th Floor 8th Floor |  | NRV/BP/18-19/263/8844/15 A.N.P/NRV/BP/20-21/1312/9110/58 |  |  |  | Dated | 24/05/2018 15/03/2021
O. Certificate No.: |  | NA |  |  | Date of approval: | Dated | NA | Expiry date: NA
Type C
Layout Approval No |  | ANP/NRV/BP/20-21/1312/9110/58 |  |  |  | Dated | 2021-03-15
Building plan No B + Gr + 1st to 7th Floor |  | NRV/BP/18-19/263/8844/15 |  |  |  | Dated | 2018-05-24
Type A, B & C
Date of CC Valid up to: |  | ANP/NRV/B.P/20-21/1312/9110/58 Type A = B + Gr/st + 1st to 12th Floor Type B = B + Gr/st + 1st to 8th Floor Type C = B + Gr/st + 1st to 7th Floor |  |  |  | Dated | 2021-03-15
O. Certificate No.: |  | ANP/NRV/22-23/1465 Approved upto : Type C = B + Gr/st + 1st to 7th Floor |  |  | Date of approval: | Dated | 2023-03-01 | Expiry date: NA
|  | ANP/NRV/2021-22/1101 Approved upto : Type B = LG + G + 1st to 8th Floor |  |  | Date of approval: | Dated | 2021-12-17 | Expiry date: NA
|  | AMC/TPD/2024-25/1251 Approved upto : Type A = LG + Gr/st + 1st to 12th Floor |  |  | Date of approval: | Dated | 2025-01-02
Commencement date of construction |  |  | 2018-05-24 |  | Expected Completion |  | Completed
Building wise Construction details
Approved area of building Sq.Mt |  |  | 8769.75 |  | Approved no of units |  | Shops = 8 , Flats = 360
Approved no of Floors |  | Type A = LG + Gr/st + 1st to 12th Floor Type B = LG + Gr/st + 1st to 8th Floor Type C = LG + Gr/st + 1st to 7th Floor Club house = G + 1st Floor |  |  |  | No of floors at site : See Construction details
Approved no of Floors |  | Type A = LG + Gr + 1st to 12th Floor. Type B = LG + G + 1st to 8th Floor. Type C = LG + G + 1st to7th Floor. Club house = G + 1st Floor
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years
Material laying at Site: : Nothing
Construction details: A Wing = LG + Gr + 1st to 12th Floor. | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 14 Slab completed, Brickwork upto 12 Floor completed, Internal Plaster upto 12 Floor completed, External Plaster upto 12 Floor completed, Flooring upto 12 Floor completed, Painting upto 12 Floor completed, Finishing upto 12 Floor completed
Ground |  | 2 | Podium |  | 0 |  | Floors | 12 | All work Completed. Wait For OC.
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. Provide OC.
Progress % |  | 100% |  | Disbursement % |  |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 12 | 100% |  | 100% |  | 100%
Plinth |  | 12 | 100%
RCC |  | 14 | 100% | [5 empty] | Excavation in process |  | 6
Brickwork | Brickwork & Internal Plaster | 12 | 100% | [5 empty] | Excavation Completed |  | 12
Internal Plaster | Brickwork & Internal Plaster | 12 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 100% | [5 empty] | Footing in Process |  | 3
Flooring & Fitting | Flooring & Fitting | 12 | 100% | [5 empty] | Footing Completed |  | 6
Painting & Wooden |  | 12 | 100% | [5 empty] | Plinth in process |  | 9
Building Common Amenities | Building Common Amenities | 12 | 100% | [5 empty] | Plinth completed |  | 12
Possession |  | 12 | 100%
Construction details: B Wing = LG + G + 1st to 8th Floor. | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 10 Slab completed, Brickwork upto 8 Floor completed, Internal Plaster upto 8 Floor completed, External Plaster upto 8 Floor completed, Flooring upto 8 Floor completed, Painting upto 8 Floor completed, Finishing upto 8 Floor completed
Ground |  | 2 | Podium |  | 0 |  | Floors | 8 | All work Completed. Wait For OC.
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. Provide OC.
Progress % |  | 100% |  | Disbursement % |  |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 8 | 100% |  | 100% |  | 100%
Plinth |  | 8 | 100%
RCC |  | 10 | 100% | [5 empty] | Excavation in process |  | 4
Brickwork | Brickwork & Internal Plaster | 8 | 100% | [5 empty] | Excavation Completed |  | 8
Internal Plaster | Brickwork & Internal Plaster | 8 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8 | 100% | [5 empty] | Footing in Process |  | 2
Flooring & Fitting | Flooring & Fitting | 8 | 100% | [5 empty] | Footing Completed |  | 4
Painting & Wooden |  | 8 | 100% | [5 empty] | Plinth in process |  | 6
Building Common Amenities | Building Common Amenities | 8 | 100% | [5 empty] | Plinth completed |  | 8
Possession |  | 8 | 100%
Construction details: C Wing = B + G + 1st to 7th Floor. | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 7 Floor completed, Flooring upto 7 Floor completed, Painting upto 7 Floor completed, Finishing upto 7 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 7 | All work Completed. Wait For OC.
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. Provide OC.
Progress % |  | 100% |  | Disbursement % |  |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 7 | 100% |  | 100% |  | 100%
Plinth |  | 7 | 100%
RCC |  | 8 | 100% | [5 empty] | Excavation in process |  | 3.5
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Excavation Completed |  | 7
Internal Plaster | Brickwork & Internal Plaster | 7 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% | [5 empty] | Footing in Process |  | 1.75
Flooring & Fitting | Flooring & Fitting | 7 | 100% | [5 empty] | Footing Completed |  | 3.5
Painting & Wooden |  | 7 | 100% | [5 empty] | Plinth in process |  | 5.25
Building Common Amenities | Building Common Amenities | 7 | 100% | [5 empty] | Plinth completed |  | 7
Possession |  | 7 | 100%
Wheather the construction is as per approved Building plan : Yes
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the Flat Per Sq. Ft. ( on saleable area) | [5 empty] | 4400
Recommended rate of the Shop Per Sq. Ft. ( on saleable area) | [5 empty] | 6000
Floor rise rate Per Sq. Ft. | [5 empty] | 15/- from 5th Floor
Club house Charges | [5 empty] | 2,00,000/-
Any Other | [5 empty] | NA
Society formation charges | [5 empty] | NA
Recommended rate of Parking | [5 empty] | NA
Development charges | [5 empty] | 300000/-
Distressed valuation of the Property | [5 empty] | 3520
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Type A
Ground Floor For Commercial & Residential
1 |  | Shop | 187.9179 |  | 0 | 281.8769 | NA | Ground Floor For Commercial & Residential
2 |  | Shop | 263.0851 | 0 | 0 | 394.6276 | NA
3 |  | Shop | 263.0851 | 0 | 0 | 394.6276 | NA
4 |  | Shop | 187.9179 | 0 | 0 | 281.8769 | NA
5 |  | Shop | 187.9179 | 0 | 0 | 281.8769 | NA |  |  | 10.764
6 |  | Shop | 263.0851 | 0 | 0 | 394.6276 | NA
7 |  | Shop | 263.0851 | 0 | 0 | 394.6276 | NA
8 |  | Shop | 187.9179 | 0 | 0 | 281.8769 | NA
1 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA |  |  |  | 1.45
2 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA |  |  |  | 158192.6304
3 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA |  |  |  | 525
4 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
5 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
6 |  | 2 BHK | 514.6505 |  | 0 | 746.2433 | NA
11 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
12 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
13 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
14 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
1st, 3rd, 5th & 7th Floors
1 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA | 1st, 3rd, 5th & 7th Floors
2 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA
3 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA
4 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA
5 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA |  |  | 10.764
6 |  | 2 BHK | 514.6505 | 0 | 0 | 771.9758 | NA
7 |  | 2 BHK | 514.6505 | 0 | 0 | 771.9758 | NA
8 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA
9 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
10 |  | 2 BHK | 514.6505 | 0 | 0 | 746.2433 | NA
11 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
12 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
13 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
14 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
2nd, 4th & 6th Floors
1 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA | 2nd, 4th & 6th Floors
2 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA
3 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA
4 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA
5 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA |  |  | 10.764
6 |  | 2 BHK | 514.6505 | 0 | 0 | 771.9758 | NA
7 |  | 2 BHK | 514.6505 | 0 | 0 | 771.9758 | NA
8 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA
9 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
10 |  | 2 BHK | 514.6505 | 0 | 0 | 746.2433 | NA
11 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
12 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
13 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
14 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
8th Floor (Part Refuge Area)
1 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA | 8th Floor (Part Refuge Area)
2 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA
3 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA
4 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA
5 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA |  |  | 10.764
6 |  | 2 BHK | 514.6505 | 0 | 0 | 771.9758 | NA
7 |  | 2 BHK | 514.6505 | 0 | 0 | 771.9758 | NA
8 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA
9 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA |  |  |  | 38.8974 | 418.6916
10 |  | 2 BHK | 514.6505 | 0 | 0 | 746.2433 | NA |  |  |  | 38.1572 | 410.7241
11 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
12 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
13 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
14 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
9th, 10th, 11th & 12th Floor
2 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA | 9th, 10th, 11th & 12th Floor
3 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA
4 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA
5 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA |  |  | 10.764
6 |  | 2 BHK | 514.6505 | 0 | 0 | 771.9758 | NA
7 |  | 2 BHK | 514.6505 | 0 | 0 | 771.9758 | NA
8 |  | 1 BHK | 417.3095 | 0 | 0 | 625.9643 | NA | [5 empty] | 182
9 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA |  |  |  | 38.8974 | 418.6916 | 90
10 |  | 2 BHK | 514.6505 | 0 | 0 | 746.2433 | NA |  |  |  | 38.1572 | 410.7241 | 88
11 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA | [5 empty] | 360
12 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
13 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
14 |  | 1 BHK | 417.3095 | 0 | 0 | 605.0988 | NA
Type B
Ground Floor For Residential
1 |  | 1 BHK | 414.92 |  | 0 | 601.634 | NA | Ground Floor For Residential
2 |  | 1 BHK | 414.92 |  | 0 | 601.634 | NA
3 |  | 2 BHK | 511.64 |  | 0 | 741.878 | NA
4 |  | 3 BHK | 678.64 |  | 0 | 984.028 | NA
5 |  | 1 BHK | 414.92 |  | 0 | 601.634 | NA
6 |  | 1 BHK | 414.92 |  | 0 | 601.634 | NA
7 |  | 1 BHK | 405.92 |  | 0 | 588.584 | NA
8 |  | 2 BHK | 511.64 |  | 0 | 741.878 | NA
9 |  | 1 BHK | 414.92 |  | 0 | 601.634 | NA
10 |  | 2 BHK | 528.92 |  | 0 | 766.934 | NA
1st, 3rd, 5th & 7th Floors
1 |  | 1 BHK | 414.92 |  | 46.2099 | 647.8439 | NA | 1st, 3rd, 5th & 7th Floors
2 |  | 1 BHK | 414.92 |  | 46.2099 | 647.8439 | NA
3 |  | 2 BHK | 511.64 |  | 47.0817 | 788.9597 | NA
4 |  | 3 BHK | 680.64 |  | 106.1976 | 1040.0268 | NA
5 |  | 1 BHK | 414.92 |  | 46.2099 | 647.8439 | NA
6 |  | 1 BHK | 414.92 |  | 46.2099 | 647.8439 | NA
7 |  | 1 BHK | 405.92 |  | 25.2846 | 613.8686 | NA
8 |  | 2 BHK | 511.64 |  | 47.0817 | 788.9597 | NA
9 |  | 1 BHK | 414.92 |  | 47.0817 | 648.7157 | NA
10 |  | 2 BHK | 528.92 |  | 46.2099 | 813.1439 | NA
2nd, 4th & 6th Floors
1 |  | 1 BHK | 414.92 |  | 0 | 601.634 | NA | 2nd, 4th & 6th Floors
2 |  | 1 BHK | 414.92 |  | 0 | 601.634 | NA
3 |  | 2 BHK | 511.64 |  | 0 | 741.878 | NA
4 |  | 3 BHK | 678.64 |  | 0 | 984.028 | NA
5 |  | 1 BHK | 414.92 |  | 0 | 601.634 | NA
6 |  | 1 BHK | 414.92 |  | 0 | 601.634 | NA
7 |  | 1 BHK | 405.92 |  | 0 | 588.584 | NA
8 |  | 2 BHK | 511.64 |  | 0 | 741.878 | NA
9 |  | 1 BHK | 414.92 |  | 0 | 601.634 | NA
10 |  | 2 BHK | 528.92 |  | 0 | 766.934 | NA
8th Floor (Part Refuge Area)
1 |  | 1 BHK | 438.7406 |  | 0 | 636.1739 | NA | 8th Floor (Part Refuge Area) |  |  | 32.7464
2 |  | 1 BHK | 438.7406 |  | 0 | 636.1739 | NA
3 |  | 2 BHK | 528.0818 |  | 0 | 765.7187 | NA
4 |  | 3 BHK | 708.3788 |  | 0 | 1027.1493 | NA
5 |  | 1 BHK | 425.8238 |  | 0 | 617.4446 | NA |  |  |  | 10.764
6 |  | 1 BHK | 425.8238 |  | 0 | 617.4446 | NA
7 |  | 1 BHK | 426.685 |  | 0 | 618.6932 | NA
8 |  | 2 BHK | 526.5749 |  | 0 | 763.5336 | NA
9 |  | 1 BHK | 425.178 |  | 0 | 616.5081 | NA
10 |  | 1BHK | 425.178 |  | 0 | 616.5081 | NA
Type C
Ground, 2nd, 4th & 6th Floors
1 |  | 1 BHK | 414.92 |  | 0 | 601.634 | NA | Ground, 2nd, 4th & 6th Floors
2 |  | 2 BHK | 505.346 |  | 0 | 732.7517 | NA
3 |  | 2 BHK | 505.346 |  | 0 | 732.7517 | NA
4 |  | 1 BHK | 414.92 |  | 0 | 601.634 | NA
5 |  | 1 BHK | 427.98 |  | 0 | 620.571 | NA
6 |  | 1 BHK | 414.92 |  | 0 | 601.634 | NA
7 |  | 1 BHK | 414.92 |  | 0 | 601.634 | NA
8 |  | 2 BHK | 505.346 |  | 0 | 732.7517 | NA
9 |  | 2 BHK | 505.346 |  | 0 | 732.7517 | NA
10 |  | 1 BHK | 414.92 |  | 0 | 601.634 | NA
11 |  | 1 BHK | 414.92 |  | 0 | 601.634 | NA
1st, 3rd, 5th & 7th Floors
1 |  | 1 BHK | 414.92 |  | 46 | 647.634 | NA | 1st, 3rd, 5th & 7th Floors
2 |  | 2 BHK | 505.346 |  | 50 | 782.7517 | NA
3 |  | 2 BHK | 505.346 |  | 50 | 782.7517 | NA
4 |  | 1 BHK | 414.92 |  | 46 | 647.634 | NA
5 |  | 1 BHK | 427.98 |  | 46 | 666.571 | NA
6 |  | 1 BHK | 414.92 |  | 46 | 647.634 | NA
7 |  | 1 BHK | 414.92 |  | 46 | 647.634 | NA
8 |  | 2 BHK | 505.346 |  | 50 | 782.7517 | NA
9 |  | 2 BHK | 505.346 |  | 50 | 782.7517 | NA
10 |  | 1 BHK | 414.92 |  | 46 | 647.634 | NA
11 |  | 1 BHK | 414.92 |  | 46 | 647.634 | NA
Remarks: 1. Type A, B & C = All work Completed. OC Received. 2. We adopted Carpet area as per Builder area statement sheet. 3. We have given rate verify by market inquire. 4. Other charges from Builder cost sheet. 5. Construction work was in process at the time of visit. 6.We have updated Approved C.C & Floor plan of Type A (Gr + 12th Floor) & Type B (8th Floor) on (04/07/2022) 7. We have updated OC from Rera for Wing B & C (On 14/05/2023). 8. We have updated OC for Type A (On 06/07/2025). 6. On site, we meet Mr. Patel - 9665393600/ 9819242190/ 8928730617
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  |  | Patels Prestige
GOOGLE MAP :
A
B
C

## Note
16/06/2020. | Pratiksha | We considered recommended rate as per Builder cost sheet.

## Wing A
| Floor No | 1st
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
7 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.74 | 4.27 | 11.6998 | CB | 1.3 | 2.9 | 3.77 | 1.45 | 1.62 | 2.349
| kitch | 2.29 | 1.5 | 3.435 | CB | 2.54 | 1 | 2.54 |  |  | 0
| Bed1 | 2.9 | 2.27 | 6.583 | CB |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
| toilet1 | 1.91 | 1.22 | 2.3302 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.22 | 1.9 | 2.318 | DB |  |  | 0 |  |  | 0
| passage1 | 1.22 | 2.3 | 2.806 |  |  |  | 0 |  |  | 0
| passage2 | 1.22 | 0.9 | 1.098 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 325.8263 | 30.27 |  |  | 67.9208 | 6.31 |  | 25.2846 | 2.349 | 393.7471
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0

## B
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
plinth | 10 | 10 | 100%
slab | 8 | 1 | 12.5% |  | Parking |  | Rate
Bricks | 7 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
total | 15% | 33.75% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15% |  |  |  |  | 35
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%
Particulars | total floor | 7
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 5 | 0 | 0 | 0 | 0 | 0
RCC | 5 | 3.75 |  | Recommended |  | 30 | 3.75 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0

## C
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 7 | 100% |  | Palghar |  | 100000/-
plaster | 7 | 7 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
total | 75% | 85% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15% |  |  |  |  | 35
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%
Particulars | total floor | 7
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0