## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 08/07/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-07-07
Name of the builder group |  |  |  | Macrotech Developers Limited
Name of the builder company |  |  |  | Macrotech Developers Limited
Name of the Project |  |  |  | Crown Dombivli 1 Sector O (Cluster 15.05)
Provided Contact Details ( Name & Contact No.) |  |  |  | Mr. Rajendra Giri 9820248856
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Rajendra Giri 9820248856
Name / No of the Building |  |  |  | Coral A, Coral B, Coral C, Coral D
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51700048779
Project location details |  | Crown Dombivli 1 Sector O (Cluster 15.05), Survey No.53/1, 53/2, 53/3, 54/3B, 54/3C, 54/4, 54/5, 54/6 & others, near Runwal Gardens, Kalyan Shilphata Road, Mangaon, Antarli, Dombivli East, Kalyan, Thane - 421203.
Survey No |  | 53/1, 53/2, 53/3, 54/3B, 54/3C, 54/4, 54/5, 54/6 & others
Locality |  | Mangaon
Road |  | Kalyan Shilphata Road |  | Locality/Village |  | Antarli
City |  | Dombivli East |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421203
Nearby Landmark |  | Runwal Gardens |  | Distance from city centre: |  | 5.5KM from Dombivli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Kalyan Shilphata Road
North | NA | NA |  |  | Central Ave Road
South | NA | NA |  |  | Ira Global School
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.1809539,73.0954437
Location Link |  | https://goo.gl/maps/8nzWw87s2HkvY9F3A
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 134781.95
Permissible FSI |  |  |  | 1.8
Permissible TDR/Paid FSI |  |  |  | 1.8247
Total FSI availaible for the project |  |  |  | 3.6247
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 488550.28
Total number of Buildings |  |  |  | 4 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Directorate of Town Planning and Pricing Thane
Layout Approval No |  | Ekatmik Nagar Vasahat/Mouje-Antarli, Khoni, Hedutane, Kole, Gharivali, Katai & Mangaon, Ta-Kalyan & Mouje-Umbroli, Ta-Ambarnath SSTN/5059 |  |  | Dated | 2023-05-23
Approved Floor plan No. |  | Ekatmik Nagar Vasahat/Mouje-Antarli, Khoni, Hedutane, Kole, Gharivali, Katai & Mangaon, Ta-Kalyan & Mouje-Umbroli, Ta-Ambarnath SSTN/5059 |  |  | Dated | 2023-05-23
Commencement-CC No Valid Up to: |  | Ekatmik Nagar Vasahat/MJ-Antarli, Khoni & etc,/ Sector "B, D, I1, I2, O, P & R"/SSTN/5059 |  |  | Dated | 2023-05-23
Cluster 15.05 Coral Wing A, B, C & D = Gr + 1st to 14th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 25338.2
Approved no of units |  |  | Flats - 416
Approved no of Floors |  |  | Cluster 15.05 Coral A, B, C & D Wing = G + 1st to 14th Floor
Proposed no of Floors |  |  | Coral A & B Wing = G + 1st to 14th Floor
Coral C & D Wing = G + 1st to 14th Floor
Expected Completion |  |  | As per RERA - 31/12/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Children Play Area, Gymnasium, Library, Indoor Games, Senior Citizen Area, Green Lawn
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Coral A & B Wing = G + 1st to 14th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 13 Floor, Painting upto 12 Floor, Finishing upto 4 Floor Completed | , Flooring upto 13 Floor, Painting upto 12 Floor, Finishing upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 13 Floor, Painting upto 12 Floor, Finishing upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 90% |  | 94.64% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 13 | 92.86% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 12 | 85.71% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 28.57% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Sector O (Cluster 15.05) |  | Coral C Wing = G + 1st to 14th Floor | [5 empty] | Excavation, Plinth Completed, Footing work Completed, RCC upto 9 Slab, Brickwork upto 8 Floor, Internal Plaster upto 6 Floor, External Plaster upto 5.6 Floor Completed | , RCC upto 9 Slab, Brickwork upto 8 Floor, Internal Plaster upto 6 Floor, External Plaster upto 5.6 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth | , Footing work Completed
Stage of construction: |  | Excavation, Plinth Completed, Footing work Completed, RCC upto 9 Slab, Brickwork upto 8 Floor, Internal Plaster upto 6 Floor, External Plaster upto 5.6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 45.5% |  | 70% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 9 | 60% |  |  |  |  | Footing in Process | 7
Brickwork | Brickwork & Internal Plaster | 8 | 57.14% |  |  |  |  | Footing Completed | 14
Internal Plaster | Brickwork & Internal Plaster | 6 | 42.86% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5.6 | 40% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Coral D Wing = G + 1st to 14th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 1 Slab Completed | , RCC upto 1 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 1 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 12.67% |  | 47% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 1 | 6.667% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 7000 |  |  |  | 6900 to 7000 & 2.25L to 4L by sanket on 30/05/2023
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Provisional Building Common Area Maintenance (CAM) Charges for 18 months* |  |  |  |  | 90000
City management charges for 60 months* |  |  |  |  | 140000
Utility Connection & Related Expenses* |  |  |  |  | 150000
Land Under Construction (LUC) Reimbursement Charges* |  |  |  |  | 20000
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 350000
Distressed valuation of the Property |  |  |  |  | 5600
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 96 |  | 43937.7869 |  | 65906.6803
Wing B |  | 112 |  | 51140.1946 |  | 76710.2918
Wing C |  | 112 |  | 51079.9162 |  | 76619.8742
Wing D |  | 96 |  | 43937.7869 |  | 65906.6803
Total |  | 416 |  | 190095.6845 |  | 285143.5267
Grand Total |  | 416 |  | 190095.6845 |  | 285143.5267
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Cluster 10.05
Coral Wing A + B
Ground Floor For Commercial, Amenity/ Common Area & Meter Room
1 |  |  |  | 0 | 0 | Ground Floor For Commercial, Amenity/ Common Area & Meter Room
2 |  |  |  | 0 | 0
3 |  |  |  | 0 | 0
4 |  |  |  | 0 | 0
5 |  |  |  | 0 | 0
6 |  |  |  | 0 | 0
7 |  |  |  | 0 | 0
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Sector O
Cluster 15.05
Coral | [8 empty] | 10.764
Wing A | [8 empty] | 10.764
1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
1 |  | 2 | 457.6853 | 0 | 686.5279 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential |  |  | 40.8245
2 |  | 2 | 457.6853 | 0 | 686.5279
3 |  | 2 | 457.6853 | 0 | 686.5279
4 |  | 2 | 457.6853 | 0 | 686.5279
5 |  | 2 | 457.6853 | 0 | 686.5279
6 |  | 2 | 457.6853 | 0 | 686.5279
7 |  | 2 | 457.6853 | 0 | 686.5279
8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
1 |  | 2 | 457.6853 | 0 | 686.5279 | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
2 |  | 2 | 457.6853 | 0 | 686.5279
3 |  | 2 | 457.6853 | 0 | 686.5279
4 |  | 2 | 457.6853 | 0 | 686.5279
5 |  | Refuge Area
6 |  | 2 | 457.6853 | 0 | 686.5279
7 |  | 2 | 457.6853 | 0 | 686.5279
Wing B
1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
1 |  | 2 | 457.6853 | 0 | 686.5279 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
2 |  | 2 | 457.6853 | 0 | 686.5279
3 |  | 2 | 457.6853 | 0 | 686.5279
4 |  | 2 | 457.6853 | 0 | 686.5279
5 |  | 2 | 457.6853 | 0 | 686.5279
6 |  | 2 | 457.6853 | 0 | 686.5279
7 |  | 2 | 453.3797 | 0 | 680.0695
8 |  | 2 | 453.3797 | 0 | 680.0695
8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
1 |  | 2 | 457.6853 | 0 | 686.5279 | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
2 |  | 2 | 457.6853 | 0 | 686.5279
3 |  | 2 | 457.6853 | 0 | 686.5279
4 |  | 2 | 457.6853 | 0 | 686.5279
5 |  | 2 | 457.6853 | 0 | 686.5279
6 |  | 2 | 457.6853 | 0 | 686.5279
7 |  | 2 | 453.3797 | 0 | 680.0695
8 |  | 2 | 453.3797 | 0 | 680.0695
Wing C
1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
1 |  | 2 | 457.6853 | 0 | 686.5279 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
2 |  | 2 | 457.6853 | 0 | 686.5279 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
3 |  | 2 | 453.3797 | 0 | 680.0695 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
4 |  | 2 | 453.3797 | 0 | 680.0695 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
5 |  | 2 | 453.3797 | 0 | 680.0695 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
6 |  | 2 | 457.6853 | 0 | 686.5279 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
7 |  | 2 | 457.6853 | 0 | 686.5279 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
8 |  | 2 | 457.6853 | 0 | 686.5279 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
1 |  | 2 | 457.6853 | 0 | 686.5279 | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
2 |  | 2 | 457.6853 | 0 | 686.5279 | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
3 |  | 2 | 453.3797 | 0 | 680.0695 | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
4 |  | 2 | 453.3797 | 0 | 680.0695 | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
5 |  | 2 | 453.3797 | 0 | 680.0695 | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
6 |  | 2 | 457.6853 | 0 | 686.5279 | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
7 |  | 2 | 457.6853 | 0 | 686.5279 | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
8 |  | 2 | 457.6853 | 0 | 686.5279 | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
Wing D
1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
1 |  | 2 | 457.6853 | 0 | 686.5279 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
2 |  | 2 | 457.6853 | 0 | 686.5279 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
3 |  | 2 | 457.6853 | 0 | 686.5279 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
4 |  | 2 | 457.6853 | 0 | 686.5279 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
5 |  | 2 | 457.6853 | 0 | 686.5279 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
6 |  | 2 | 457.6853 | 0 | 686.5279 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
7 |  | 2 | 457.6853 | 0 | 686.5279 | 1st to 7th, 9th to 12th Floor 14th Floor (15th Floor as per Builder) For Residential
8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
1 |  | 2 | 457.6853 | 0 | 686.5279 | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
2 |  | 2 | 457.6853 | 0 | 686.5279 | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
3 |  | Refuge Area |  |  |  | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
4 |  | 2 | 457.6853 | 0 | 686.5279 | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
5 |  | 2 | 457.6853 | 0 | 686.5279 | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
6 |  | 2 | 457.6853 | 0 | 686.5279 | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
7 |  | 2 | 457.6853 | 0 | 686.5279 | 8th Floor 13th Floor (14th Floor as per Builder) (Part Refuge Area)
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
Remarks:
* | Wing A, B, C & D = Construction work is in process at the time of Visit. Internal photographs not allowed. Wing D = Work is same as last visit (06/02/2025).
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Ground Floor Plan is not drafted for Building Coral A to D.
* | The ground floor layout is on hold and in the planning segments, according to Mr. Rajendra Giri. Therefore, the ground floor modification will be performed in the next updated plans.
* | Internal visit was not allowed. Photoghraphs are taken from gate.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Krishna Kambali |  | Report By : |  | Shruti
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Crown Dombivli 1 Sector O (Cluster 15.05)
Layout :
Google Map :
Formulas:
Antarli = [Antarli, row above]
Ruby
Opal
Coral
Coral A & B Wing
Coral D Wing
Coral A & B Wing
Coral C
Coral D

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted