## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 14/07/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-07-11
Name of the builder company |  |  |  |  | M/s.Rising Infra
Name of the builder |  |  |  |  | Mr.Narendra Sopan Dahitankar
Name of the Project |  |  |  |  | Anand Park
Contact Details ( Name & Contact No.) |  |  |  |  | 2148222192
Name / No of the Building |  |  |  |  | 1 Building
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA Name & No. |  |  |  |  | P52000016934
Project location details |  | Anand Park, Survey No.51, Plot No.7, Karjat - Murbad Road, Bopele, Neral, Karjat, Raigad.
Survey No |  | 51 |  |  | Plot No |  | 7
Road |  | Karjat - Murbad Road |  |  | Locality/Village |  | Bopele
City |  | Neral |  |  | District |  | Raigad
Taluka |  | Karjat |  |  | Pin Code |  | 410101
Near by Landmark |  | Abhishek Florida Hari OM Nagar |  |  | Distance from city centre: |  | 1.2Km from Neral Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Building |  | Building |  | Road |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 19.0277 |  | Longitude |  | 73.3273
Location Link |  | https://goo.gl/maps/Rbi63AdtEaL9NE6U6
Approval details:
Approved usage of the Property: |  |  |  |  | Residential + Commercial
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 316
Permissible FSI |  |  |  |  | 1.2
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1.2
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 379.2
Total number of Buildings |  |  |  |  | 1 Building
Approval Detail : Plan approval
Layout Approval No |  | J.K.RZP/GP/NSVP/267/2016 |  |  |  | Dated | 10/06/2016.
Approved Floor plan No. |  | J.K.RZP/GP/NSVP/267/2016 |  |  |  | Dated | 10/06/2016.
Commencement Certificate No. |  | J.K.RZP/GP/NSVP/267/2016 Valid Up to: G + 1st to 3rd Floor |  |  |  | Dated | 10/06/2016. | Valid upto date: One year from date of issue
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 10/06/2016. |  | Expected Completion |  | 2024-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 379.2 |  | Approved no of units |  | Flats = 09 & shop = 04 |  |  | Give less % in Painting & Wooden to Adjust Flooring % because Flooring Was not Fully completed on visit 04/08/2021.
Approved no of Floors |  | G + 1st to 3rd Floor |  |  | No of floors at site : See Construction details
Proposed no of Floors |  |  | G + 1st to 5th Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details: |  | G + 1st to 5th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 3 Floor, External Plaster upto 3 Floor, Flooring upto 3 Floor, Painting upto 3 Floor, Finishing upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 5
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 3 Floor, External Plaster upto 3 Floor, Flooring upto 3 Floor, Painting upto 3 Floor, Finishing upto 1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% |  | 78% |  | 89% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% | [5 empty] | Excavation Completed | 5
RCC |  | 6 | 100% | [5 empty] | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 60% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 60% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 60% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 3 | 60% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 1 | 20% | [5 empty] | Plinth in process | 3.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 5
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3500 |  |  |  | 06/10/2022 - rate - 4500 to 3500 flat & 8000 to 5000 shop - market enquire - sachin sir
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 5000/-
Society registration charges | [5 empty] | 150000/-
Recommended rate of Parking | [5 empty] | 50000/-
Development charges | [5 empty] | 250000/-
Distressed valuation of the Property | [5 empty] | 2800
Commercial Area Details :
Building & Wing |  | No. of Shops | Total Carpet Area |  |  | Total Saleable Area
Shops |  | 4 | 658.1611 |  |  | 2129
Residential Area Details :
Building & Wing |  | No. of Flats | Total Carpet Area |  |  | Total Saleable Area
Flats |  | 9 | 3921.8634 |  |  | 6155
Building details Floor Wise
Details of Flats in Building
Flat No. (As per Sale Plan) | Flat No. (As per Approved Plan) | Description | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Ground Floor is For Parking & Commercial
1 |  | Shop | 181.8207 |  | 0 | 573 | N | Ground Floor |  |  | 3.1515
2 |  | Shop | 140.6047 |  | 0 | 467 | N |  |  | 4271.9486 | 3.3214 | 5353.3191
3 |  | Shop | 140.6047 |  | 0 | 467 | N |  |  |  | 3.3214
4 |  | Shop | 195.1309 |  | 0 | 622 | N |  |  |  | 3.1876
1st Floor
1 | 1 | 1BHK | 398.3756 |  | 39.9344 | 674 | N | 1st Floor |  | 3412.4629
2 | 2 | 1BHK | 440.0323 |  | 0 | 677 | N |  |  | 3397.3412 | 1.5385 | 3545.0517
3 | 3 | 1BHK | 461.7756 |  | 0 | 710 | N |  |  | 3239.4366 | 1.5375
2nd Floor | [9 empty] | #DIV/0! | #DIV/0!
4 | 1 | 1BHK | 419.6884 |  | 0 | 646 | N | 2nd Floor |  | 3560.3715 | 1.5392
5 | 2 | 1BHK | 440.0323 |  | 0 | 677 | N |  |  | 3397.3412 | 1.5385
6 | 3 | 1BHK | 461.7756 |  | 0 | 710 | N |  |  | 3239.4366 | 1.5375
3rd Floor | [10 empty] | #DIV/0!
7 | 1 | 1BHK | 398.3756 |  | 39.9344 | 674 | N | 3rd Floor
8 | 2 | 1BHK | 440.0323 |  | 0 | 677 | N
9 | 3 | 1BHK | 461.7756 |  | 0 | 710 | N
Remarks:
1. Construction work was stopped. Work is same as last visit (10/07/2024). 2. We considered Saleable area as per Builder area sheet. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area + W.S Area. 5. We have considered rate by verifying it from market inquire. 6. We have considered Other charges from cost sheet. 7. Car parking is subjected to authentic documentation. 8. We have considered construction percent as per proposed no of floor. 9. Provide revised approved floor plan & CC. 10. On site we met Mr. Ashok : 7558420264. 11. The project has received first CC on 10/06/2016, But construction work is not yet completed. 12. As per RERA, completion period of project is expired on 31/12/2024 but still project work is pending. 8. On site we meet Mr.Vishwanath 8928834324.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Naynesh |  | Report Prepared By : |  |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Anand Park
Google Map :

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing | Anand Park | 1BHK | 420 | 609 | 2553.3662 | 1555000
housing | Anand Park | 1BHK | 440 | 638 | 2553.2915 | 1629000
housing | Anand Park | 1BHK | 441 | 639.45 | 2553.7571 | 1633000
housing | Anand Park | 1BHK | 458 | 664.1 | 2549.3149 | 1693000
Average |  |  |  |  | 2552.4324
Valuation Adopted |  |  |  |  | 2500

## C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 3
Particulars | total floor | 3
plinth | 10 | 10 | 100%
slab | 4 | 4 | 100% |  | Parking |  | Rate
Bricks | 3 | 3 | 100% |  | Palghar |  | 100000/-
plaster | 3 | 3 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 3 | 3 | 100% |  | Panvel |  | 300000/-
Wood & painting | 3 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 3 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 10 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 5 | 0 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 10 | 5
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 85% | 90% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 4.7 | 12.925 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.1 | 2.5 | 5.25 | Balcony | 1 | 2.1 | 2.1 |  |  | 0
|  |  |  | 0 | WS | 2.1 | 0.4 | 0.84 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.3 | 3.25 | 7.475 | Balcony | 2.3 | 1 | 2.3 |  |  | 0
|  |  |  | 0 | CB | 3.25 | 0.45 | 1.4625 |  |  | 0
|  |  |  | 0 | Ws | 2.3 | 0.4 | 0.92 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.5 | 1.2 | 1.8 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.2 | 0.9 | 1.08 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1 | 1.2 | 1.2 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 320.0137 | 29.73 |  |  | 82.0486 | 7.6225 |  | 0 | 0
|  |  | 402.0623 | 37.3525

## Note
Date | Checked By | Description
30/06/2020. |  | Shop Rate as per Builder cost sheet is too high. So, we have given rate verify by Market Inquire (8000/-) - Conform Asmita