## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-10
Name of the builder group |  |  |  | M/s. N N Datar & Associates
Name of the builder company |  |  |  | M/s. N N Datar & Associates
Name of the Project |  |  |  | Biz Point
Contact Details ( Name & Contact No.) |  |  |  | Mr.Kulkarni - 8169353447
Name / No of the Building |  |  |  | A Wing
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans
RERA No. |  |  |  | P51800009838
Project location details |  | Biz Point, CTS No.3852 to 3855 & 3857 and Plot No.24 & 26, near The Metropole, Dhruvraj singh road, Ghatkopar karol, Ghatkopar west, Kurla, Mumbai - 400086.
CTS No |  | 3852 to 3855 & 3857 and Plot No.24 & 26
Road |  | Dhruvraj singh road |  | Locality/Village |  | Ghatkopar karol
City |  | Ghatkopar west |  | District |  | Mumbai
Taluka |  | Kurla |  | Pin Code |  | 400086
Nearby Landmark |  | The Metropole |  | Distance from city centre: |  | 0.55 KM from Ghatkopar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Dhruvraj singh road
West | NA | NA |  |  | Building
North | NA | NA |  |  | Khodadad Apartment
South | NA | NA |  |  | Laxmi narayan lane
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.0881401,72.9097933
Location Link |  | https://maps.app.goo.gl/BVvUfkJ5EbXpWw1w6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2619.4
Permissible FSI |  |  |  | 1.33
Permissible TDR/Paid FSI |  |  |  | 1.1196
Total FSI availaible for the project |  |  |  | 2.4496
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 6416.53
Total number of Buildings |  |  |  | 2 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai (MCGM)
Layout Approval No |  | CHE/ES/6407/N/W/337(NEW) |  |  | Dated | 2022-01-28
Approved Floor plan No. |  | CHE/ES/6407/N/W/337(NEW) |  |  | Dated | 2022-01-28
Commencement-CC No Valid Up to: |  | CE / 6407 / BPES / AN/FCC/5/Amend |  |  | Dated | 2022-10-19
|  | "Further C.C. i.e., Full C.C. for Wing ‘A’ and Further C.C. up to 4th floor only for Wing ‘B’ as per approved amended plan dated 28.01.2022 " |  |  | Valid Upto Date | 2023-08-19
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 6416.53
Approved no of units |  |  | Shops - 10, Offices - 127
Approved no of Floors |  |  | A Wing = 3B + G/St + 1st to 13th Floor B Wing = 3B + G/St + 1st to 8th Floor
Proposed no of Floors |  |  | A Wing = 3B + G/St + 1st to 13th Floor
B Wing = 3B + G/St + 1st to 8th Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A Wing = 3B + G/St + 1st to 13th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster upto 11 Floor Completed, Flooring upto 7 Floor Completed.
Basement | 3 | Ground | 1 | Podium | 0 | Floors | 13
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster upto 11 Floor Completed, Flooring upto 7 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.25
Excavation |  | 13 | 100% | 78.85% |  | 91.92% |  | Excavation in process | 6.5
Plinth |  | 13 | 100% |  |  |  |  | Excavation Completed | 13
RCC (Including podiums) |  | 14 | 100% |  |  |  |  | Footing in Process | 2.6
Brickwork | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Footing Completed | 5.2
Internal Plaster | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Basement 1 | 7.8
Ext. facade & Plumbing | External Plaster & Plumbing | 11 | 84.62% |  |  |  |  | Basement 2 | 10.4
Flooring & Fitting | Flooring & Fitting | 7 | 53.85% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 13
Construction details: |  | B Wing = 3B + G/St + 1st to 8th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed.
Basement | 3 | Ground | 1 | Podium | 0 | Floors | 8
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2
Excavation |  | 8 | 100% | 18.89% |  | 51.67% |  | Excavation in process | 4
Plinth |  | 8 | 100% |  |  |  |  | Excavation Completed | 8
RCC (Including podiums) |  | 2 | 22.22% |  |  |  |  | Footing in Process | 1.6
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 4.8
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 6.4
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 8
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft.
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 32000
Recommended rate of the Office/Shop (Above GF) Per Sq. Ft. |  |  |  |  | 20000
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 800000
Distressed valuation of the Property |  |  |  |  | 25600
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  | plzz check no of units count
A Wing | Shop | 9 |  | 5254.7749 |  | 8407.6398
| Office | 127 |  | 45978.0767 |  | 73564.9227
B Wing | Shop | 1 |  | 11569.483 |  | 18511.1729
Total |  | 137 |  | 62802.3346 |  | 100483.7354
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
A Wing
3rd to 1st Basement Floor for Parking | [7 empty] | Lower ground floor is mention on approved Floor plan
Ground Floor for Commercial & Parking
1 |  | Shop (Duplex with 1st Floor) | 2192.3329 | 0 | 3507.7327 | Ground Floor for Commercial & Parking
2 |  | Shop (Duplex with 1st Floor) | 669.8502 | 0 | 1071.7603 | Ground Floor for Commercial & Parking
3 |  | Shop (Duplex with 1st Floor) | 708.3853 | 0 | 1133.4165 | Ground Floor for Commercial & Parking
4 |  | Shop (Duplex with 1st Floor) | 708.3853 | 0 | 1133.4165 | Ground Floor for Commercial & Parking
5 |  | Shop | 203.5526 | 0 | 325.6842 | Ground Floor for Commercial & Parking
6 |  | Shop | 203.5526 | 0 | 325.6842 | Ground Floor for Commercial & Parking
7 |  | Shop | 120.1262 | 0 | 192.202 | Ground Floor for Commercial & Parking
1st Floor for Commercial
5 |  | Shop | 224.2948 | 0 | 358.8718 | 1st Floor for Commercial
6 |  | Shop | 224.2948 | 0 | 358.8718
2nd Floor
1 |  | Office | 304.7396 | 0 | 487.5834 | 2nd Floor
2 |  | Office | 304.7396 | 0 | 487.5834
3 |  | Office | 326.6691 | 0 | 522.6706
3A |  | Office | 182.6231 | 0 | 292.197
4 |  | Office | 209.9421 | 0 | 335.9074
5 |  | Office | 209.9421 | 0 | 335.9074
6 |  | Office | 209.9421 | 0 | 335.9074
7 |  | Office | 279.5691 | 0 | 447.3105
8 |  | Office | 358.79 | 0 | 574.0639
9 |  | Office | 358.79 | 0 | 574.0639
10 |  | Office | 358.79 | 0 | 574.0639
3rd Floor
1 |  | Office | 304.7396 | 0 | 487.5834 | 3rd Floor
2 |  | Office | 304.7396 | 0 | 487.5834
3 |  | Office | 494.9653 | 0 | 791.9445
4 |  | Office | 214.0217 | 0 | 342.4347
5 |  | Office | 214.0217 | 0 | 342.4347
6 |  | Office | 657.4404 | 0 | 1051.9046
7
8 |  | Office | 416.9048 | 0 | 667.0477
9 |  | Office | 416.9048 | 0 | 667.0477
10 |  | Office | 416.9048 | 0 | 667.0477
4th Floor
1 |  | Office | 317.7059 | 0 | 508.3295 | 4th Floor
2 |  | Office | 312.7846 | 0 | 500.4554
3 |  | Office | 499.1374 | 0 | 798.6199
4 |  | Office | 218.8171 | 0 | 350.1073
5 |  | Office | 218.8171 | 0 | 350.1073
6 |  | Office | 659.1777 | 0 | 1054.6843
7
8 |  | Office | 387.9001 | 0 | 620.6402
9 |  | Office | 386.152 | 0 | 617.8433
10 |  | Office | 387.9001 | 0 | 620.6402
11 |  | Office | 355.1463 | 0 | 568.2341
12 |  | Office | 295.3717 | 0 | 472.5947
5th Floor
1 |  | Office | 317.7059 | 0 | 508.3295 | 5th Floor
2 |  | Office | 312.7846 | 0 | 500.4554
3 |  | Office | 499.1374 | 0 | 798.6199
4 |  | Office | 218.8171 | 0 | 350.1073
5 |  | Office | 218.8171 | 0 | 350.1073
6 |  | Office | 659.1777 | 0 | 1054.6843
7
8 |  | Office | 387.9001 | 0 | 620.6402
9 |  | Office | 386.152 | 0 | 617.8433
10 |  | Office | 387.9001 | 0 | 620.6402
11 |  | Office | 355.1463 | 0 | 568.2341
12 |  | Office | 295.3717 | 0 | 472.5947
6th Floor
1 |  | Office | 317.7059 | 0 | 508.3295 | 6th Floor
2 |  | Office | 312.7846 | 0 | 500.4554
3 |  | Office | 499.1374 | 0 | 798.6199
4 |  | Office | 218.8171 | 0 | 350.1073
5 |  | Office | 218.8171 | 0 | 350.1073
6 |  | Office | 659.1777 | 0 | 1054.6843
7
8 |  | Office | 387.9001 | 0 | 620.6402
9 |  | Office | 386.152 | 0 | 617.8433
10 |  | Office | 387.9001 | 0 | 620.6402
11 |  | Office | 355.1463 | 0 | 568.2341
12 |  | Office | 295.3717 | 0 | 472.5947
7th Floor (Part Refuge Area)
1 |  | Office | 317.7059 | 0 | 508.3295 | 7th Floor (Part Refuge Area)
2 |  | Office | 312.7846 | 0 | 500.4554
3 |  | Refuge Area
4
5
6
7 |  | Office | 446.4326 | 0 | 714.2922
8 |  | Office | 387.9001 | 0 | 620.6402
9 |  | Office | 386.152 | 0 | 617.8433
10 |  | Office | 387.9001 | 0 | 620.6402
11 |  | Office | 355.1463 | 0 | 568.2341
12 |  | Office | 295.3717 | 0 | 472.5947
8th Floor
1 |  | Office | 309.5027 | 0 | 495.2043 | 8th Floor
2 |  | Office | 309.5027 | 0 | 495.2043
3 |  | Office | 494.9653 | 0 | 791.9445
3A
4 |  | Office | 214.0217 | 0 | 342.4347
5 |  | Office | 214.0217 | 0 | 342.4347
6 |  | Office | 657.4404 | 0 | 1051.9046
7
8 |  | Office | 383.1198 | 0 | 612.9917
9 |  | Office | 383.9885 | 0 | 614.3816
10 |  | Office | 383.9885 | 0 | 614.3816
11 |  | Office | 353.2303 | 0 | 565.1686
12 |  | Office | 261.562 | 0 | 418.4992
9th to 13th Floor
1 |  | Office | 320.2166 | 0 | 512.3466 | 9th to 13th Floor
2 |  | Office | 315.6102 | 0 | 504.9763
3 |  | Office | 502.6734 | 0 | 804.2775
4 |  | Office | 221.6426 | 0 | 354.6282
5 |  | Office | 221.6426 | 0 | 354.6282
6 |  | Office | 667.9772 | 0 | 1068.7636
7
8 |  | Office | 396.1184 | 0 | 633.7895
9 |  | Office | 394.1174 | 0 | 630.5878
10 |  | Office | 396.1184 | 0 | 633.7895
11 |  | Office | 357.9719 | 0 | 572.755
12 |  | Office | 298.1972 | 0 | 477.1156
B Wing
3rd to 1st Basement Floor for Parking
Ground Floor for Commercial & Parking
1 |  | Anchor Shop (Duplex with 1st Floor) | 11569.483 | 0 | 18511.1729 | Ground Floor for Commercial & Parking
2nd, 3rd & 4th Floor for theater
5th & 6th Floor for Parking
7th Floor (Part Gymnasium & Terrace Area)
8th Floor (Terrace Area)
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
Remarks:
* | A Wing - Construction work was in process at the time of visit.( Internal photographs not allowed) B Wing - Construction work is on hold.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Niche Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | A Wing is only considered for APF (As per Bank).
* | On Site, we meet Mr. Rajeev : 9833810600.
* | We have updated revised C.C (on 12/01/2023)
* | Validity of CC is expired on 19/08/2023. Please provide revised CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Akash Kadam |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Biz Point
Google Map :
Formulas:
Ghatkopar karol = [Ghatkopar karol, row above]

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted