## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 10/07/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-07-08
Name of the builder group |  |  |  |  | M/s.Pashmina Realty Private Limited
Name of the builder company |  |  |  |  | M/s.Pashmina Realty Private Limited
Name of the Project |  |  |  |  | Lake Riviera
Contact Details ( Name & Contact No.) |  |  |  |  | 2266166700
Site Person - Contact Details ( Name & Contact No.) |  |  |  |  | NA |  |  |  | 9594055381
Name / no of the Building |  |  |  |  | Building no.4 (A, B & C Wings)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC.
RERA no. |  |  |  |  | 1 Building (A & B Wing ) = P51800009353 1 Building (C Wing ) = P51800018480
Project location details |  | Lake Riviera, Building no.4 (A, B & C Wings) CTS No.-11 H/A(Pt.), 11HA/106/A 11HA/122/A to 11HA/190/A, 11B/10, 11B/11, 11B/11/28 To 11B/11/93, 11/C, Village Chandivali, Powai, Mumbai.
CTS No | CTS No.-11 H/A(Pt.), 11HA/106/A 11HA/122/A to 11HA/190/A, 11B/10, 11B/11, 11B/11/28 To 11B/11/93, 11/C |  |  |  | Plot No. | NA | Locality | Chandivali
Road | Chandivali Road |  |  |  | District | Mumbai
City | Powai |  |  |  | Pin Code | 400072
Near by Landmark |  | Woodland Heights CHS |  |  | Distance from city centre: |  | About 6.4 Km from Vikroli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Higher Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Shristi Building |  | Lake Home Bldg |  | Lake Home |  | Panchavati complex
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed structure
Latitude & Longitude |  | 19.115175623,72.902691585
Location Link |  | https://maps.app.goo.gl/Euvn6puescs7V2dDA
Approval details:
Approved usage of the Property: Residential (Restrictive Covenants in regard to Land Use, if any) : No
Total land area of the project in Sq. Mt. |  |  |  |  | 12098.01
Permissible FSI |  |  |  |  | Zonal |  | Free Sale | PTC
Permissible FSI |  |  |  |  | 1 |  | 0.75 | 0.75
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 2.5
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 30245.025
Total number of Buildings |  |  |  |  | 2 Building (3 Wings)
Approval Detail : Plan approval
Layout Approval No |  | Sale Building no.4 = SRA/ENG/L/PVT/0059/20111011/APS-4 |  |  |  | Dated | 2021-08-17
Building plan approval No |  | Sale Building no.4 = SRA/ENG/L/PVT/0059/20111011/APS-4 |  |  |  | Dated | 2021-08-17 | Expiry date:NA
Commencement Certificate No. |  | L/PVT/0059/20111011/AP/S-4 Valid Up to: This CC is re-endorsed & further extended upto 12th upper floors of wing 'A' & 'B' & upto 9th upper floor for wing 'C' as per approved amended plans dtd 11/05/2022. |  |  |  | Dated | 2022-11-22
Commencement Certificate No. |  | L/PVT/0059/20111011/AP/S4 Valid Up to: Sale Building No.4 (C Wing) = Top of 2nd level Podium |  |  |  | Dated | 31/10/2018. | Expiry date: One year from date of issue
Commencement Certificate No. |  | L/PVT/0059/20111011/AP/S4 Valid Up to: this CC is extended upto 10th Floor of Wing A of Sale Building No.4 as per approved plan dated 30/08/2018. |  |  |  | Dated | 17/09/2020. | Expiry date: One year from date of issue
Commencement Certificate No. |  | L/PVT/0059/20111011/AP/S4 Valid Up to: this CC is extended upto 10th Floor of Wing B of Sale Building No.4 as per approved plan dated 30/08/2018. |  |  |  | Dated | 17/02/2021. | Expiry date: One year from date of issue
O. Certificate No.: NA |  | NA |  |  | Date of approval: NA | Dated | NA | Expiry date: NA
Commencement date of construction |  |  | 17/02/2021. |  | Expected Completion |  | Wing A & B = 31/12/2025 Wing C = 29/06/2025
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 30245.025 |  | Approved no of units |  | Flats = 182
Approved no of Floors |  | A, B & C Wing = 2B + G + 1st E deck + 2nd to 19th Floor C Wing = B+G+ 2P+3rd to 15th Floor
Proposed no of Floors |  | A, B & C Wing = 2B + G + 1st E deck + 2nd to 19th Floor
Quality of construction: Good |  |  |  |  | Projected life : 60 Years after completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Wing A & B = 2B + G + 1st E deck + 2nd to 19th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 13 Slab, Brickwork upto 12 Floor, Internal Plaster upto 12 Floor, External Plaster upto 12 Floor, Flooring upto 12 Floor, Painting upto 12 Floor, Finishing upto 10 Floor Completed
Basement | 2 | Ground | 1 | Podium |  | 0 | Floors | 19
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 13 Slab, Brickwork upto 12 Floor, Internal Plaster upto 12 Floor, External Plaster upto 12 Floor, Flooring upto 12 Floor, Painting upto 12 Floor, Finishing upto 10 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% |  | 63.89% |  | 77.13% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% | [5 empty] | Excavation Completed | 19
RCC (Including podiums) |  | 13 | 65% | [5 empty] | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 12 | 63.16% | [5 empty] | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 12 | 63.16% | [5 empty] | Basement 1 | 14.25
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 63.16% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 63.16% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 12 | 63.16% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 10 | 52.63% | [5 empty] | Plinth in process | 0
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 19
Construction details: |  | B Wing = 2B + G + 1st E deck + 2nd to 19th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 13 Slab, Brickwork upto 12 Floor, Internal Plaster upto 12 Floor, External Plaster upto 11 Floor, Flooring upto 8 Floor, Painting upto 8 Floor Completed
Basement | 2 | Ground | 1 | Podium |  | 0 | Floors | 19
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 13 Slab, Brickwork upto 12 Floor, Internal Plaster upto 12 Floor, External Plaster upto 11 Floor, Flooring upto 8 Floor, Painting upto 8 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% |  | 57.58% |  | 75.82% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% | [5 empty] | Excavation Completed | 19
RCC (Including podiums) |  | 13 | 65% | [5 empty] | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 12 | 63.16% | [5 empty] | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 12 | 63.16% | [5 empty] | Basement 1 | 14.25
Ext. Plaster & Plumbing | External Plaster & Plumbing | 11 | 57.89% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 8 | 42.11% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 8 | 42.11% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 0
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 19
Construction details: |  | C Wing = 2B + G + 1st E deck + 2nd to 19th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 3 Floor Completed
Basement | 2 | Ground | 1 | Podium |  | 0 | Floors | 19
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 3 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% |  | 29.18% |  | 59.29% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% | [5 empty] | Excavation Completed | 19
RCC (Including podiums) |  | 9 | 45% | [5 empty] | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 3 | 15.79% | [5 empty] | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 14.25
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 0
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 19
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 20000
Floor rise rate Per Sq. Ft. | [5 empty] | NA
PLC charges | [5 empty] | NA
Electric & Water connection charges | [5 empty] | 50,000/-
Advc Maintainence for 24 months | [5 empty] | 2,80,000/-
Society formation charges | [5 empty] | 10,000/-
Recommended rate of Parking | [5 empty] | 8,00,000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Valuation as per Government reckoners rates | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 16000
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Building no.4 (Sale Building)
A Wing
1st & 2nd Basement Floor For Parking
1st floor Podium & 2nd E-Deck Floor For Parking
2nd to 6th, 8th, 10th, 12th, 16th, 18th to 19th Floor
1 |  | 2 BHK | 856.3838 |  | 0 | 1284.5758 | N | 3rd to 6th, 8th to 13th, 15th to 19th
2 |  | 3 BHK | 1097.1745 |  | 0 | 1645.7618 | N |  | 246638.5459
3 |  | 2 BHK | 810.9598 |  | 0 | 1216.4396 | N |  | 315986.2618
4 |  | 3 BHK | 1053.7956 |  | 0 | 1580.6934 | N |  | 233556.4109
9th, 11th, 13th, 15th & 19th Floor (Part Refuge Area)
1 |  | 2 BHK | 856.3838 |  | 0 | 1284.5758 | N | 9th, 11th, 13th, 15th & 19th Floor (Part Refuge Area)
2 |  | 3 BHK | 1097.1745 |  | 0 | 1645.7618 | N |  | 246638.5459
3 |  | 2 BHK | 810.9598 |  | 0 | 1216.4396 | N |  | 315986.2618
4 |  | 3 BHK | 1053.7956 |  | 0 | 1580.6934 | N |  | 233556.4109
7th Floor (Part Refuge Area) | [8 empty] | 303493.1328 | 15180.109
1 |  | 2 BHK | 856.3838 |  | 0 | 1284.5758 | N | 7th Floor (Part Refuge Area) |  | 15798.1552
2 |  | 3 BHK | 1097.1745 |  | 0 | 1645.7618 | N |  | 246638.5459 |  | 12533.3207
3 |  | 2 BHK | 810.9598 |  | 0 | 1216.4396 | N |  | 315986.2618
4 |  | 3 BHK | 1053.7956 |  | 0 | 1580.6934 | N |  | 233556.4109
14th Floor (Part Refuge Area) | [8 empty] | 303493.1328
1 |  | 2 BHK | 856.3838 |  | 0 | 1284.5758 | N | 14th Floor (Part Refuge Area)
2 |  | 3 BHK | 1097.1745 |  | 0 | 1645.7618 | N
3 |  | 2 BHK | 810.9598 |  | 0 | 1216.4396 | N
4 |  | 3 BHK | 1053.7956 |  | 0 | 1580.6934 | N
B Wing
1st & 2nd Basement Floor For Parking
2nd to 6th, 8th, 10th, 12th, 16th, 18th to 19th Floor
1 |  | 2 BHK | 685.021 |  | 0 | 1027.5314 | N | 2nd to 6th, 8th, 10th, 12th, 16th, 18th to 19th Floor | 197286.0365
2 |  | 2 BHK | 697.3996 |  | 0 | 1046.0993 | N |  | 200851.0733
3 |  | 2 BHK | 804.8243 |  | 0 | 1207.2364 | N |  | 231789.3926
4 |  | 2 BHK | 804.609 |  | 0 | 1206.9135 | N |  | 231727.392
4 |  | 2 BHK | 698.0454 |  | 0 | 1047.0681 | N |  | 201037.0752
7th Floor (Part Refuge Area)
1 |  | 2 BHK | 685.021 |  | 0 | 1027.5314 | N | 7th Floor (Part Refuge Area) | 24135.5145
2 |  | 2 BHK | 697.3996 |  | 0 | 1046.0993 | N
3 |  | 2 BHK | 804.8243 |  | 0 | 1207.2364 | N
4 |  | Refuge Area
4 |  | 2 BHK | 698.0454 |  | 0 | 1047.0681 | N
14th Floor (Part Refuge Area)
1 |  | 2 BHK | 685.021 |  | 0 | 1027.5314 | N | 14th Floor (Part Refuge Area)
2 |  | 2 BHK | 697.3996 |  | 0 | 1046.0993 | N
3 |  | 2 BHK | 804.8243 |  | 0 | 1207.2364 | N
4 |  | Refuge Area
4 |  | 2 BHK | 698.0454 |  | 0 | 1047.0681 | N
9th, 11th, 13th, 15th & 19th Floor
1 |  | 2 BHK | 685.021 |  | 0 | 1027.5314 | N | 9th, 11th, 13th, 15th & 19th Floor | 197286.0365
2 |  | 2 BHK | 697.3996 |  | 0 | 1046.0993 | N |  | 200851.0733
3 |  | 2 BHK | 804.8243 |  | 0 | 1207.2364 | N |  | 231789.3926
4 |  | 2 BHK | 804.609 |  | 0 | 1206.9135 | N |  | 231727.392
4 |  | 2 BHK | 698.0454 |  | 0 | 1047.0681 | N |  | 201037.0752
C Wing
Basement & Ground Floor For Parking
1st floor Podium & 2nd Floor E-Deck For Parking
3rd to 6th, 8th to 13th &15th Floor
1 |  | 2 BHK | 702.7816 |  | 0 | 1054.1723 | N | 3rd to 6th, 8th to 13th, 15th to 19th | 17075.0069
2 |  | 3 BHK | 941.9576 |  | 0 | 1412.9365 | N
3 |  | 2 BHK | 670.2743 |  | 0 | 1005.4114 | N
4 |  | 2 BHK | 670.2743 |  | 0 | 1005.4114 | N
7th Floor (Part Refuge Area)
1 |  | 2 BHK | 702.7816 |  | 0 | 1054.1723 | N | 7th Floor (Part Refuge Area)
2 |  | Refuge Area
3 |  | 2 BHK | 670.2743 |  | 0 | 1005.4114 | N
4 |  | 2 BHK | 670.2743 |  | 0 | 1005.4114 | N
14th Floor (Part Refuge Area)
1 |  | 2 BHK | 702.7816 |  | 0 | 1054.1723 | N | 14th Floor (Part Refuge Area) | 21343.7586
2 |  | Refuge Area
3 |  | 2 BHK | 670.2743 |  | 0 | 1005.4114 | N
4 |  | 2 BHK | 670.2743 |  | 0 | 1005.4114 | N
Remarks: 1. We considered carpet area as per approved plan. 2. Wing A & B = All work completed upto 12th Floor (Waiting for OC). Wing C = Construction work is same as last visit dtd.07/04/2025 3. Saleable area as per our calculation. 4. We considered rate as per builder cost sheet provided us on 24/04/2019. 5. We considered only building no.4 -A, B, C Wing (Sale Building) beacuse building no.4 - D Wing & Building no.2 (Composite Building) is not verified on RERA so we didn't consider it in report. 6. We update updated revised approved plans of Wing A & B & CC. ( on 01/02/2022) 8. Please provide approved revised plans of Wing C. 9. Please provide approved revised plans of Wing A & B (Ground & 1st Floor plans). 10. We have updated latest CC from Rera (On 23/03/2024). 11. As per RERA, completion period of Wing C is expired on 29/06/2025 but still project work is pending. 12. Wing A & B = All over completed upto 12th floor i.e., Construction Stage of Wing A & B can be considered completed 100 % upto 12th Floor. 13. With ref. to remark no. 12 We have received builder-sales conversation mail and part OC application on mail by Bank official which are attached below. 14. Part OC Application letter was submitted on 24/01/2024 to authority SRA. But project have not received any OC for any particular floor or Wing till yet. 15. Provide revised approved plans. 7. On Site we meet Ms. Vishal - 8879760909. | [8 empty] | 2024-04-20
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  |  | Lake Riviera
Remark No. 13 :
Google Map :
Formulas:
Locality = [Locality, row above]
C
C
C
C
A
B

## VALUTATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick | Lake Riviera | 3BHK | 1055 | 1582.5 | 15797.7883 | 25000000
Magic Brick | Lake Riviera | 2BHK | 805 | 1207.5 | 15734.9896 | 19000000
Magic Brick | Lake Riviera | 2BHK | 735 | 1102.5 | 17687.0748 | 19500000
Magic Brick | Lake Riviera | 2BHK | 705 | 1057.5 | 15602.8369 | 16500000
Magic Brick | Lake Riviera | 3BHK | 995 | 1492.5 | 17420.4355 | 26000000
99 Acres | Lake Riviera | 3BHK | 1090 | 1635 | 13455.6575 | 22000000
Average |  |  |  |  | 15949.7971
Valuation Adopted |  |  |  |  | 16000

## A
Particulars | totaL floor | 19
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 55 |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 20 | 11 | 15.7895 | Progress | 10 | 22 | 2.3684 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended | 30 | 16.5 | 2.3684 | 0 | 0 | 0 | 0
| 19 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 19 | 0 | 0
Flooring | Total Floor | completed Floor
| 19 | 0 |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 19 | 0 |  |  | RCC | 22 | 16.5
Finishing | Total Floor | completed Floor |  |  | Bricks | 2.3684 | 2.3684
| 19 | 0 |  |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 34.3684 | 48.8684

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## B
Particulars | totaL floor | 19
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 28.5714 |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 14 | 4 | 0 | Progress | 10 | 11.4286 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended | 30 | 8.5714 | 0 | 0 | 0 | 0 | 0
| 19 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 19 | 0 | 0
Flooring | Total Floor | completed Floor
| 19 | 0 |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 19 | 0 |  |  | RCC | 11.4286 | 8.5714
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 19 | 0 |  |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 21.4286 | 38.5714

## C
Particulars | totaL floor | 19
| total | completed
plinth | 10 | 3 | 30
slab | total slab | completed slab | 0 |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 20 | 0 | 0 | Progress | 3 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended | 23 | 0 | 0 | 0 | 0 | 0 | 0
| 19 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 19 | 0 | 0
Flooring | Total Floor | completed Floor
| 19 | 0 |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 3 | 23
| 19 | 0 |  |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 19 | 0 |  |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 3 | 23

## Compatibility Report
Compatibility Report for VSJCV - AXIS - APF Old - Mar 21 - 27796 - Lake Riviera.xls
Run on 12-03-2021 15:52
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences | Version
One or more objects in this workbook such as shapes, WordArt, or text boxes may allow text to overflow the object boundaries. Earlier versions of Excel do not recognize this option and will hide overflowing text. | 6
| Sheet1'!A1:J240 | Excel 97-2003