## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 16/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-08
Name of the builder group |  |  |  | M/s. Macrotech Developers Limited
Name of the builder company |  |  |  | M/s. Macrotech Developers Limited
Name of the Project |  |  |  | Liana C & D |  |  |  | Lodha Codename Premier - Liana C & D
Contact Details ( Name & Contact No.) |  |  |  | 8104395863
Name / No of the Building |  |  |  | Wing C - P.B Type (Cluster -15.03) Wing D - P.B Type (Cluster 15.03)
Docouments Provided |  |  |  | Approved Plans, CC.
RERA No. |  |  |  | Liana Wing C = P51700034770 Liana Wing D = P51700046119
Project location details |  | Liana C & D, Survey No.65/15A of Mangaon & 212/2 of Hedutane, Sector - O, near Runwal MyCity, Kalyan - Silphata Road, Mangaon - Hedutane, Dombivali east, Kalyan , Thane - 421203.
Survey No |  | 65/15A of Mangaon & 212/2 of Hedutane, Sector - O
Road |  | Kalyan - Silphata Road |  | Locality/Village |  | Mangaon - Hedutane
City |  | Dombivali east |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421203
Nearby Landmark |  | Runwal MyCity |  | Distance from city centre: |  | 4.7 KM from Dombivli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residentail
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Ekveera Aai Apartment
West | NA | NA |  |  | Kalyan - Shilphata road
North | NA | NA |  |  | Sub station
South | NA | NA |  |  | Smart buy Manpada by Lodha
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.1819563,73.0894868
Location Link : |  | https://goo.gl/maps/ufAF3SxCg7KuthqY9?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 138266.9
Permissible FSI |  |  |  | 1.8
Permissible TDR/Paid FSI |  |  |  | 0.76077
Total FSI availaible for the project |  |  |  | 2.5608
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 354070.01
Total number of Buildings |  |  |  | 2 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Town Planning, Thane
Layout Approval No |  | Antarli, Khoni, Hedutane, Kole, Gharivli, Katai, & Mangav, Taluka Kalyan, M.Umbroli, Taluka Ambernath /SSTHANE/2959 |  |  | Dated | 2022-12-15
Approved Floor plan No. |  | Antarli, Khoni, Hedutane, Kole, Gharivli, Katai, & Mangav, Taluka Kalyan, M.Umbroli, Taluka Ambernath /SSTHANE/2959 |  |  | Dated | 2022-12-15
Commencement-CC No Valid Up to: |  | Ekatmik Nagar Vasahat/M. Antarli, Khoni & Other/Sec- B.D.I.O&P/SSTHANE/1384 |  |  | Dated | 2022-12-15
Liana - Wing C & D (Cluster -15.03 ) = G/St + 1st to 23rd Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 354070.01
Approved no of units |  |  | Flats - 280
Approved no of Floors |  |  | Liana - Wing C - Type P.B(Cluster -15.03)= G/St + 1st to 23rd Floor Liana - Wing D - Type P.B(Cluster -15.03)= G/St + 1st to 23rd Floor
Proposed no of Floors |  |  | Liana - Wing C - Type P.B(Cluster -15.03)= G/St + 1st to 23rd Floor
Liana - Wing D - Type P.B(Cluster -15.03)= G/St + 1st to 23rd Floor
Expected Completion |  |  | As per RERA - Wing C = 31/03/2026 Wing D = 31/08/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Liana - Wing C - Type P.B(Cluster -15.03)= G/St + 1st to 23rd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 23 Slab Completed, Brickwork upto 22 Floor Completed, Internal Plaster upto 18.7 Floor Completed, External Plaster upto 17.6 Floor Completed, Flooring upto 6 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 23 Slab Completed, Brickwork upto 22 Floor Completed, Internal Plaster upto 18.7 Floor Completed, External Plaster upto 17.6 Floor Completed, Flooring upto 6 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 71.87% |  | 87.73% |  | Excavation in process | 11.5 | We have understand stage of building is visce versa on 16/07/2025 therfore as per dicuss with sir wing D Stage is not increased
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 23 | 95.83% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 22 | 95.65% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 18.7 | 81.3% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 17.6 | 76.52% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 6 | 26.09% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | Liana - Wing D - Type P.B(Cluster -15.03)= G/St + 1st to 23rd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster upto 20 Floor Completed, External Plaster upto 20 Floor Completed, Flooring upto 18 Floor Completed, Painting upto 10 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster upto 20 Floor Completed, External Plaster upto 20 Floor Completed, Flooring upto 18 Floor Completed, Painting upto 10 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 82.72% |  | 92.61% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 20 | 86.96% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 20 | 86.96% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 18 | 78.26% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 10 | 43.48% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 7500 |  |  | 6800 to 7500 on 60% loading & 400000 park by sanket & Ganesh Sir on 14/09/2023 recording saved
Provisional Building Common Area Maintenance (CAM) Charges for 18 months* |  |  |  |  | 70000
Provisional Federation Common Area Maintenance (CAM) Charges for 60 months* |  |  |  |  | 180000
Utility Connection &amp. Related Expenses* |  |  |  |  | 90000
Electricity Deposit Reimbursement* |  |  |  |  | 5000
Recommended rate of Parking |  |  |  |  | 400000
Distressed valuation of the Property |  |  |  |  | 6000
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Liana C - Type B (Cluster - 15.03) |  | 140 |  | 80278.3426 |  | 128445.3481
Liana D - Type P.B (Cluster - 15.03) |  | 140 |  | 80278.3426 |  | 128445.3481
Total |  | 280 |  | 160556.6851 |  | 256890.6962
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Liana C (Cluster - 15.03)
P.B - Type
Ground Floor for Residential, Entrance Lobby & Meter Room
1 |  | 2BHK | 549.0716 | 0 | 878.5146 | Ground Floor for Residential, Entrance Lobby & Meter Room |  | 45.5814 | 10.764
2 |  | 2BHK | 549.0716 | 0 | 878.5146
3 |  | 2BHK | 549.0716 | 0 | 878.5146
4 |  | 2BHK | 549.0716 | 0 | 878.5146
5 |  | 1BHK | 477.491 | 0 | 763.9857
1st & 2nd Floor
1 |  | 2BHK | 541.8598 | 0 | 866.9756 | 1st & 2nd Floor |  | 141
2 |  | 2BHK | 541.8598 | 0 | 866.9756
3 |  | 2BHK | 575.0129 | 0 | 920.0206
4 |  | 2BHK | 575.0129 | 0 | 920.0206
5 |  | 2BHK | 664.1388 | 0 | 1062.6221
6 |  | 2BHK | 575.0129 | 0 | 920.0206
3rd to 7th, 9th to 12th, 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder) Floor for Residential | [7 empty] | 5
1 |  | 2BHK | 573.3983 | 0 | 917.4372 | 3rd to 7th, 9th to 12th, 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder) Floor for Residential |  | 4
2 |  | 2BHK | 573.3983 | 0 | 917.4372 |  |  | 4
3 |  | 2BHK | 575.0129 | 0 | 920.0206 |  |  | 5 | 10.764
4 |  | 2BHK | 575.0129 | 0 | 920.0206 |  |  | 18 | 10.764
5 |  | 2BHK | 575.0129 | 0 | 920.0206
6 |  | 2BHK | 575.0129 | 0 | 920.0206
8th, 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area) | [7 empty] | 18
1 |  | 2BHK | 573.3983 | 0 | 917.4372 | 8th, 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
2 |  | 2BHK | 573.3983 | 0 | 917.4372
3 |  | 2BHK | 575.0129 | 0 | 920.0206 |  |  |  | 10.764
4 |  | Refuge Area | [6 empty] | 10.764
5 |  | 2BHK | 575.0129 | 0 | 920.0206
6 |  | 2BHK | 575.0129 | 0 | 920.0206
Liana D (Cluster - 15.03)
P.B - Type
Ground Floor for Residential, Entrance Lobby & Meter Room
1 |  | 2BHK | 549.0716 | 0 | 878.5146 | Ground Floor for Residential, Entrance Lobby & Meter Room |  | 45.5814 | 10.764
2 |  | 2BHK | 549.0716 | 0 | 878.5146
3 |  | 2BHK | 549.0716 | 0 | 878.5146
4 |  | 2BHK | 549.0716 | 0 | 878.5146
5 |  | 1BHK | 477.491 | 0 | 763.9857
1st & 2nd Floor
1 |  | 2BHK | 541.8598 | 0 | 866.9756 | 1st & 2nd Floor |  | 141
2 |  | 2BHK | 541.8598 | 0 | 866.9756
3 |  | 2BHK | 575.0129 | 0 | 920.0206
4 |  | 2BHK | 575.0129 | 0 | 920.0206
5 |  | 2BHK | 664.1388 | 0 | 1062.6221
6 |  | 2BHK | 575.0129 | 0 | 920.0206
3rd to 7th, 9th to 12th, 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder) Floor for Residential | [7 empty] | 5
1 |  | 2BHK | 573.3983 | 0 | 917.4372 | 3rd to 7th, 9th to 12th, 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder) Floor for Residential |  | 4
2 |  | 2BHK | 573.3983 | 0 | 917.4372 |  |  | 4
3 |  | 2BHK | 575.0129 | 0 | 920.0206 |  |  | 5 | 10.764
4 |  | 2BHK | 575.0129 | 0 | 920.0206 |  |  | 18 | 10.764
5 |  | 2BHK | 575.0129 | 0 | 920.0206
6 |  | 2BHK | 575.0129 | 0 | 920.0206
8th, 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area) | [7 empty] | 18
1 |  | 2BHK | 573.3983 | 0 | 917.4372 | 8th, 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
2 |  | 2BHK | 573.3983 | 0 | 917.4372
3 |  | 2BHK | 575.0129 | 0 | 920.0206 |  |  |  | 10.764
4 |  | Refuge Area | [6 empty] | 10.764
5 |  | 2BHK | 575.0129 | 0 | 920.0206
6 |  | 2BHK | 575.0129 | 0 | 920.0206
Remarks:
* | Construction work is in process at the time of Visit (Internal photo was not allowed)
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + Dry Balcony + Chajja Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated Approved Revised plans of Liana Wing C & D (on 29/04/2023)
* | On Site, we meet Mr. Rajendra Giri : 9820248856.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Krishna Kambali |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Liana C & D
Layout : | Liana C & D
Google Map :
Formulas:
Mangaon - Hedutane = [Mangaon - Hedutane, row above]
Liana A & B
Liana D & C

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted