## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 23/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder group |  |  |  | JPV Realtors Private Limited
Name of the builder company |  |  |  | JPV Realtors Private Limited
Name of the Project |  |  |  | Pratap Adinath
Provided Contact Details (Name & Contact No.) |  |  |  | 7506166126
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Abhijit Panchal 9082902154
Name / No of the Building |  |  |  | 01 Building
Name / No of the Existing Building |  |  |  | Borivali Adinath CHSL
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Airport Noc
RERA No. |  |  |  | P51800050861
Project location details |  | Pratap Adinath, CTS No..13/12, 13/13 & 13/14 & Redevelopment of Borivali Adinath CHSL, near Happy Home, Jai Punit Nagar Internal Road, Mahavir Nagar, Kandivali, Borivali (West), Borivali, Mumbai - 400092.
CTS No. |  | 13/12, 13/13 & 13/14 & Redevelopment of Borivali Adinath CHSL
Locality |  | Mahavir Nagar
Road |  | Jai Punit Nagar Internal Road |  | Locality/Village |  | Kandivali
City |  | Borivali (West) |  | District |  | Mumbai
Taluka |  | Borivali |  | Pin Code |  | 400092
Nearby Landmark |  | Happy Home |  | Distance from city centre: |  | 2.1 KM from Borivali Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Bahubali Tower |  |  | Dev Nagar Dersar Lane
West | NA | Jaya International |  |  | Internal Road
North | NA | Happy Homes CHS |  |  | Internal Road
South | NA | Nalla |  |  | Nalla
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.215948,72.847575
Location Link |  | https://goo.gl/maps/1eXN1UKyV6gqzanD8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2750.2
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 1.9484
Total FSI availaible for the project |  |  |  | 2.9484
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 8108.76
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai
Layout Approval No |  | P-12221/2022/(13/12 And Other)/R/C Ward/KANDIVALI R/C/337/2/Amend |  |  | Dated | 2024-12-13
Approved Floor plan No. |  | P-12221/2022/(13/12 And Other)/R/C Ward/KANDIVALI R/C/337/2/Amend |  |  | Dated | 2024-12-13
Commencement-CC No Valid Up to: |  | P-12221/2022/(13/12 And Other)/R/C Ward/KANDIVALI R/C/FCC/1/New |  |  | Dated | 2025-02-13
[5 empty] | Valid Upto Date | 2025-04-04
This C.C. is extended further for the entire work of the building comprising of Ground Floor (Pt.) for Shops/Bank, Multipurpose Rooms, (Pt.) stilt + 1st to 3rd Podiums parking + 4th Podium as E-Deck floor + 6th to 21st + 22nd (pt.) upper floors for Residential use as per approved amended plan dated 13.12.2024.
Airport Authority of India NOC No. Valid Up to: |  | JUHU/WEST/B/092122/699042 |  |  | Dated | 2022-11-07
|  | Site Elevation (AMSL) = 9.5 M Permissible Top Elevation (AMSL) = 109.5 M |  |  | Valid Upto Date | 2030-11-06
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 8108.76
Approved no of units |  |  | Flats - 114, MP Room - 07, Shops - 04, Bank - 01
Approved no of Floors |  |  | Gr/Stilt + 1st to 4th Podium Floor + 6th to 22nd Floor
Proposed no of Floors |  |  | Gr/Stilt + 1st to 4th Podium Floor + 6th to 22nd Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Gymnasium, Kids' Play Areas, Power Backup, Treated Water Supply, 24*7 Water Supply, Party Lawn, CCTV/Video Surveillance, Fire Fighting Systems, 24 x 7 Security, Indoor Games, Jogging / Cycle Track.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Gr/Stilt + 1st to 4th Podium Floor + 6th to 22nd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 15 Floor, External Plaster upto 12 Floor Completed | , Internal Plaster upto 15 Floor, External Plaster upto 12 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 15 Floor, External Plaster upto 12 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5 |  | stage given as per 22 floors but building will be completed on 22nd Slab (as 5th Floor is ignored)
Excavation |  | 22 | 100% | 68.07% |  | 86.14% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 15 | 68.18% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 54.55% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [6 empty] | Inspection | Online | MIS
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 21000 |  |  | 19000 to 21000 During updation by market research 23/07/2025 |  |  |  | 30000 | 23723.998 | 24000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 35000 | [7 empty] | 33355.9558
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 900000
Distressed valuation of the Property |  |  |  |  | 16800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  | 34952.5803 | 22550.0518 | 19354.8387
Shops |  | 4 |  | 1740.7541 |  | 2698.1688 |  | 35242.4088 | 22737.0379
Total |  | 4 |  | 1740.7541 |  | 2698.1688 |  | 45280.9916 | 29213.543
Residential Area Details : | [7 empty] | 35270.5728 | 22755.2083
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | 24313.9602
MP Room |  | 7 |  | 2658.1698 |  | 3987.2547
Flats |  | 114 |  | 74355.4516 |  | 111533.1773
Total |  | 121 |  | 77013.6214 |  | 115520.432
Grand Total |  | 125 |  | 78754.3754 |  | 118218.6009
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Ground Floor for Commercial, Bank & Residential
1 |  | Shop | 506.3386 | 0 | 784.8248 | Ground Floor for Commercial, Bank & Residential
2 |  | Shop | 403.3271 | 0 | 625.157
3 |  | Shop | 435.1885 | 0 | 674.5422 |  |  |  | 33355.9558
4 |  | Shop | 395.8999 | 0 | 613.6449
- |  | Bank
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Ground Floor for Commercial, Bank & Residential
1 |  | MP Room | 533.8944 | 0 | 800.8416 | Ground Floor for Commercial, Bank & Residential |  | 47.2184
2 |  | MP Room | 564.2489 | 0 | 846.3733
3 |  | MP Room | 401.6048 | 0 | 602.4073
4 |  | MP Room | 376.6324 | 0 | 564.9485
5 |  | MP Room | 366.2989 | 0 | 549.4484
6 |  | MP Room | 213.2348 | 0 | 319.8523
7 |  | MP Room | 202.2556 | 0 | 303.3833
1st to 3rd Podium Floor for Parking
4th Podium E Deck Floor for Fitness Centre, DG Set, Society Office, Meter Room & Sub Station
6th Floor for Residential | [11 empty] | 21000
1 |  | 2BHK | 642.0726 | 0 | 963.1089 | 6th Floor for Residential |  | 56.415 |  |  |  | 20225286.9
2 |  | 2BHK | 642.0726 | 0 | 963.1089 | [6 empty] | 20225286.9
3 |  | 1BHK | 451.2269 | 0 | 676.8403 |  |  |  | 23196.0176 |  |  | 14213646.72
4 |  | 2BHK | 543.1514 | 0 | 814.7272 | [6 empty] | 17109270.36
5 |  | 3BHK | 851.6477 | 0 | 1277.4715 | [6 empty] | 26826901.92
6 |  | 2BHK | 543.1514 | 0 | 814.7272 | [6 empty] | 17109270.36
7 |  | 1BHK | 469.8486 | 0 | 704.7729 | [6 empty] | 14800230.9
7th Floor
1 |  | 2BHK | 651.6526 | 0 | 977.4788 | 7th Floor
2 |  | 2BHK | 651.6526 | 0 | 977.4788
3 |  | 1BHK | 451.2269 | 0 | 676.8403
4 |  | 2BHK | 580.5025 | 0 | 870.7538
5 |  | 3BHK | 851.6477 | 0 | 1277.4715
6 |  | 2BHK | 580.5025 | 0 | 870.7538
7 |  | 1BHK | 469.8486 | 0 | 704.7729
8th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 8th Floor (Part Refuge Area)
2
3 |  | 1BHK | 451.2269 | 0 | 676.8403
4 |  | 2BHK | 580.5025 | 0 | 870.7538
5 |  | 3BHK | 945.0792 | 0 | 1417.6188
6 |  | 2BHK | 580.5025 | 0 | 870.7538
7 |  | 1BHK | 469.8486 | 0 | 704.7729
9th Floor
1 |  | 2BHK | 651.6526 | 0 | 977.4788 | 9th Floor
2 |  | 2BHK | 651.6526 | 0 | 977.4788
3 |  | 1BHK | 451.2269 | 0 | 676.8403
4 |  | 2BHK | 580.5025 | 0 | 870.7538
5 |  | 3BHK | 945.0792 | 0 | 1417.6188
6 |  | 2BHK | 580.5025 | 0 | 870.7538
7 |  | 1BHK | 469.8486 | 0 | 704.7729
10th Floor
1 |  | 2BHK | 698.0454 | 0 | 1047.0681 | 10th Floor
2 |  | 2BHK | 698.0454 | 0 | 1047.0681
3 |  | 1BHK | 451.2269 | 0 | 676.8403
4 |  | 2BHK | 589.2214 | 0 | 883.832
5 |  | 3BHK | 1010.0938 | 0 | 1515.1406 |  |  |  | 23496.1686
6 |  | 2BHK | 589.2214 | 0 | 883.832
7 |  | 1BHK | 469.8486 | 0 | 704.7729
11th Floor
1 |  | 2BHK | 716.2366 | 0 | 1074.3548 | 11th Floor |  |  | 24479.8078
2 |  | 2BHK | 716.2366 | 0 | 1074.3548
3 |  | 1BHK | 451.2269 | 0 | 676.8403
4 |  | 2BHK | 608.166 | 0 | 912.249
5 |  | 3BHK | 1010.0938 | 0 | 1515.1406
6 |  | 2BHK | 608.166 | 0 | 912.249
7 |  | 1BHK | 469.8486 | 0 | 704.7729
12th & 13th Floor
1 |  | 2BHK | 746.8063 | 0 | 1120.2095 | 12th & 13th Floor |  |  | 59.562 | 5.73 | 65.292 | 22400000 | 19996.26
2 |  | 2BHK | 746.8063 | 0 | 1120.2095
3 |  | 1BHK | 451.2269 | 0 | 676.8403
4 |  | 2BHK | 608.166 | 0 | 912.249
5 |  | 3BHK | 1010.0938 | 0 | 1515.1406
6 |  | 2BHK | 608.166 | 0 | 912.249
7 |  | 1BHK | 469.8486 | 0 | 704.7729
14th Floor
1 |  | 2BHK | 746.8063 | 0 | 1120.2095 | 14th Floor
2 |  | 2BHK | 746.8063 | 0 | 1120.2095
3 |  | 1BHK | 451.2269 | 0 | 676.8403
4 |  | 2BHK | 651.222 | 0 | 976.833 |  |  | 57.9125
5 |  | 3BHK | 1010.0938 | 0 | 1515.1406
6 |  | 2BHK | 651.222 | 0 | 976.833
7 |  | 1BHK | 469.8486 | 0 | 704.7729
15th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 15th Floor (Part Refuge Area)
2
3 |  | 1BHK | 451.2269 | 0 | 676.8403
4 |  | 2BHK | 651.222 | 0 | 976.833
5 |  | 3BHK | 1010.0938 | 0 | 1515.1406
6 |  | 2BHK | 651.222 | 0 | 976.833
7 |  | 1BHK | 469.8486 | 0 | 704.7729
16th to 18th Floor
1 |  | 2BHK | 746.8063 | 0 | 1120.2095 | 16th to 18th Floor
2 |  | 2BHK | 746.8063 | 0 | 1120.2095
3 |  | 1BHK | 451.2269 | 0 | 676.8403
4 |  | 2BHK | 651.222 | 0 | 976.833
5 |  | 3BHK | 1010.0938 | 0 | 1515.1406
6 |  | 2BHK | 651.222 | 0 | 976.833
7 |  | 1BHK | 469.8486 | 0 | 704.7729
19th to 21st Floor
1 |  | 2BHK | 746.8063 | 0 | 1120.2095 | 19th to 21st Floor
2 |  | 2BHK | 746.8063 | 0 | 1120.2095
3 |  | 1BHK | 451.2269 | 0 | 676.8403
4 |  | 2BHK | 677.2709 | 0 | 1015.9063
5 |  | 3BHK | 1010.0938 | 0 | 1515.1406
6 |  | 2BHK | 677.2709 | 0 | 1015.9063
7 |  | 1BHK | 469.8486 | 0 | 704.7729
22nd Floor (Part Terrace Area)
1 |  | 2BHK | 746.8063 | 0 | 1120.2095 | 22nd Floor (Part Terrace Area)
2 |  | 2BHK | 746.8063 | 0 | 1120.2095
3 |  | 1BHK | 451.2269 | 0 | 676.8403
4 |  | 2BHK | 677.2709 | 0 | 1015.9063
5 |  | Terrace Area
6 |  | 2BHK | 677.2709 | 0 | 1015.9063
7 |  | 1BHK | 469.8486 | 0 | 704.7729
Remarks:
1 | Construction work is in process at the time of Visit.
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We have considered Saleable area of Commercial as per our Calculation.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet.
6 | We have considered proposed No. of Floor for Stage Calculation.
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | Nalla is located on South side to the project.
11 | We refer Civil Aviation NOC from MCGM site.
12 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
13 | We have updated latest approved CC from MCGM site (on 16/01/2024 & 10/07/2025 ).
14 | Validity of CC is expired on 04/04/2025.
15 | We have updated revised approved plans (on 23/07/2025).
16 | As per the revised approved plans dtd 13/12/2024, 5th Floor is not mentioned. (Elevation and Built up Table attached below).
17 | Recommended Rates of the Property have been revised on 23/07/2025 with reference to market inquiry.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sanket Salvi |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Pratap Adinath
Remark No 16:
Layout :
Google Map :
Formulas:
Kandivali = [Kandivali, row above]
Nalla
Elevation Plan
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D58: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value |  | MIS | Max 21800
Square yard |  | 1BHK | 449 | 718.4 | 23524.4989 | 16900000
Square yard |  | 2BHK | 642 | 1027.2 | 23559.19 | 24200000 |  | Kalpataru Advay | 25000
Square yard |  | 2BHK | 746 | 1193.6 | 23542.2252 | 28100000 |  | Lodha atlus | 28000
Square yard |  | 3BHK | 812 | 1299.2 | 23552.9557 | 30600000 |  |  |  | 30066.8151
Square yard |  | 3BHK | 1009 | 1614.4 | 23538.1566 | 38000000
99 Acres |  | 1BHK | 449 | 673.5 | 20044.5434 | 13500000
99 Acres |  | 1BHK | 467 | 700.5 | 19985.7245 | 14000000
99 Acres |  | 2BHK | 675 | 1012.5 | 20049.3827 | 20300000 | 23500000 | 23209.8765
99 Acres |  | 2BHK | 746 | 1119 | 20017.8731 | 22400000 | 23500000 | 21000.8937
99 Acres |  | 3BHK | 1009 | 1513.5 | 20019.8216 | 30300000
Average |  |  |  |  | 23543.4053
Valuation Adopted