## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 10/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-08
Name of the builder group |  |  |  | M/s.THDC Parivar LLP
Name of the builder company |  |  |  | M/s.THDC Parivar LLP
Name of the Project |  |  |  | Parivar D Wing
Contact Details ( Name & Contact No.) |  |  |  | 7507603080
Name / No of the Building |  |  |  | Building No.4 (Type D)
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P99000029251
Project location details |  | Parivar D Wing, S No.7/2, 8/5, 15/2, near Rajput Mall, Internal Road, Pasthal, Boisar West, Palghar, Palghar.
S No |  | 7/2, 8/5, 15/2
Road |  | Internal Road |  | Locality/Village |  | Pasthal
City |  | Boisar West |  | District |  | Palghar
Taluka |  | Palghar |  | Pin Code |  | 401501
Nearby Landmark |  | Rajput Mall |  | Distance from city centre: |  | 3.8KM from Bosiar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Road
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.815826, 72.729113
Location Link |  | https://goo.gl/maps/kHxxNEpB5HtXVLqj9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 6484.74
Permissible FSI |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  | -9.2525e-07
Total FSI availaible for the project |  |  |  | 0.9
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 5836.26
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Layout Approval No |  | SSNR/487 J.no.Pasthal/Gram.P/PDKRN/19 |  |  | Dated | 18/03/2020. 15/01/2021.
Approved Floor plan No. |  | SSNR/487 J.no.Pasthal/Gram.P/PDKRN/19 |  |  | Dated | 18/03/2020. 15/01/2021.
Commencement Certificate No. |  | J.no.Pasthal/Gram.P/PDKRN/19 |  |  | Dated | 2021-01-15
Valid Up to: Building No.4 (Type D) - Gr. + 1st to 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 2230.39
Approved no of units |  |  | Flats - 70
Approved no of Floors |  |  | Building No.4 (Type D) - Gr. + 1st to 4th Floor
Proposed no of Floors |  |  | Building No.4 (Type D) - Gr. + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 30/06/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Building No.4 (Type D) - Gr. + 1st to 4th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 2 Floor completed, External Plaster upto 2 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 2 Floor completed, External Plaster upto 2 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 1
Excavation |  | 4 | 100% | 66.25% |  | 85% |  | Excavation in process |  | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed |  | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process |  | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed |  | 2
Internal Plaster | Brickwork & Internal Plaster | 2 | 50% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 50% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 4
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 4000
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 1,00,000/-
Distressed valuation of the Property |  |  |  |  | 3200
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 70 |  | 21299.3726 |  | 34765
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Building No.4 (Type D)
Ground Floor
1 |  | 2BHK | 481.689 | 0 | 792 | Ground Floor |  | 1.6442
2 |  | 1RK | 302.1455 | 0 | 488 | Ground Floor
3 |  | 1RK | 302.0378 | 0 | 488 | Ground Floor
4 |  | 1RK | 272.6521 | 0 | 488 | Ground Floor
5 |  | 1RK | 217.4328 | 0 | 380 | Ground Floor
6 |  | 1RK | 233.9017 | 0 | 380 | Ground Floor
7 |  | 1RK | 270.9299 | 0 | 488 | Ground Floor
8 |  | 1RK | 272.6521 | 0 | 488 | Ground Floor
9 |  | 1RK | 269.9611 | 0 | 488 | Ground Floor
10 |  | 1RK | 302.1455 | 0 | 488 | Ground Floor
11 |  | 1RK | 303.7601 | 0 | 488 | Ground Floor
12 |  | 1RK | 272.6521 | 0 | 488 | Ground Floor
13 |  | 1RK | 272.6521 | 0 | 488 | Ground Floor
14 |  | 1BHK | 318.2915 | 0 | 521 | Ground Floor
1st to 4th Floor
101 to 401 |  | 2BHK | 482.3348 | 0 | 792 | 1st to 4th Floor |  | 3168000 | 1.642 |  | 101 to 401 | 101 | 401
102 to 402 |  | 1RK | 302.899 | 0 | 488 | 1st to 4th Floor |  | 1952000 | 1.6111 |  | 102 to 402 | 102 | 402
103 to 403 |  | 1RK | 302.7913 | 0 | 488 | 1st to 4th Floor |  |  | 1.6117 |  | 103 to 403 | 103 | 403
104 to 404 |  | 1RK | 304.5136 | 0 | 488 | 1st to 4th Floor |  |  | 1.6026 |  | 104 to 404 | 104 | 404
105 to 405 |  | 1RK | 233.9017 | 0 | 380 | 1st to 4th Floor |  |  | 1.6246 |  | 105 to 405 | 105 | 405
106 to 406 |  | 1RK | 233.9017 | 0 | 380 | 1st to 4th Floor |  |  | 1.6246 |  | 106 to 406 | 106 | 406
107 to 407 |  | 1RK | 302.7913 | 0 | 488 | 1st to 4th Floor |  |  | 1.6117 |  | 107 to 407 | 107 | 407
108 to 408 |  | 1RK | 302.899 | 0 | 488 | 1st to 4th Floor |  |  | 1.6111 |  | 108 to 408 | 108 | 408
109 to 409 |  | 1RK | 301.8226 | 0 | 488 | 1st to 4th Floor |  |  | 1.6168 |  | 109 to 409 | 109 | 409
110 to 410 |  | 1RK | 302.899 | 0 | 488 | 1st to 4th Floor |  |  | 1.6111 |  | 110 to 410 | 110 | 410
111 to 411 |  | 1RK | 304.5136 | 0 | 488 | 1st to 4th Floor |  |  | 1.6026 |  | 111 to 411 | 111 | 411
112 to 412 |  | 1RK | 304.5136 | 0 | 488 | 1st to 4th Floor |  |  | 1.6026 |  | 112 to 412 | 112 | 412
113 to 413 |  | 1RK | 302.899 | 0 | 488 | 1st to 4th Floor |  |  | 1.6111 |  | 113 to 413 | 113 | 413
114 to 414 |  | 1BHK | 318.9373 | 0 | 521 | 1st to 4th Floor |  |  | 1.6335 |  | 114 to 414 | 114 | 414
Remarks:
1 | Construction work is in process at the time of visit. Labour Found (Slow Speed).
2 | We considered Saleable area as per Builder area sheet.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area.
5 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes).
6 | We have considered rate by verifying it from market inquire.
7 | Car parking is subjected to authentic documentation.
8 | On Site, we meet Mr.Ashish(8080550852).
8 | As per Sale Plan, all 1RK are converted into 1BHK with same area.
9 | We have updated CC from RERA site on 16/01/2025.
10 | Since the project has received CC on 15/01/2021, But construction work is not yet Completed.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided. | [7 empty] | As per RERA, completion period of project Parivar D Wing is expired on Date 31/03/2025 but still project is under construction
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnyesh Patil |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Parivar D Wing
Google Map :
Wing D
Wing D
Wing D

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted