## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 09/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-08
Name of the builder group |  |  |  | M/s.Shraddha Developers
Name of the builder company |  |  |  | M/s.Shraddha Developers
Name of the Project |  |  |  | Parvati Kunj
Contact Details ( Name & Contact No.) |  |  |  | 9960253099
Name / No of the Building |  |  |  | Sector III - Building No.5-A Wing(Type C4)
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P99000028259
Project location details |  | Parvati Kunj, Gut No.111, 112, 113, 115, 116 & 118, near Sai Pooja Building, Tata Housing Road, Betegaon, Boisar, Palghar, Palghar.
Gut No |  | 111, 112, 113, 115, 116 & 118
Road |  | Tata Housing Road |  | Village |  | Betegaon
City |  | Boisar |  | District |  | Palghar
Taluka |  | Palghar |  | Pin Code |  | 401501
Nearby Landmark |  | Sai Pooja Building |  | Distance from city centre: |  | 4.8Km from Boisar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | U/C Building
West | NA | NA |  |  | Tata Housing Road
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Tata Housing Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.79011,72.7835518
Location Link |  | https://goo.gl/maps/C1Yey1zfJxdm64Jd6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 14376.64
Permissible FSI |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  | 6.914e-05
Total FSI availaible for the project |  |  |  | 0.90007
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 12939.97
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Layout Approval No |  | PZP/GP/PD/405 |  |  | Dated | 26/06/2018.
Approved Floor plan No. |  | PZP/GP/PD/405 |  |  | Dated | 26/06/2018.
Commencement Certificate No. |  | PZP/GP/PD/405 |  |  | Dated | 26/06/2018.
Valid Up to: Sector III - Building No.5-A Wing(Type C4) = Gr + 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 1377.25
Approved no of units |  |  | Flats - 27, Shops - 07
Approved no of Floors |  |  | Sector III - Building No.5-A Wing(Type C4) = Gr + 1st to 4th Floor
Proposed no of Floors |  |  | Sector III - Building No.5-A Wing(Type C4) = Gr + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 30/06/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Sector III - Building No.5-A Wing(Type C4) = Gr + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 3 Floor, External Plaster upto 3 Floor, Flooring upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 3 Floor, External Plaster upto 3 Floor, Flooring upto 1 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 73.12% |  | 88.75% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4 | 2%
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1 | 4%
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2 | 8%
Internal Plaster | Brickwork & Internal Plaster | 3 | 75% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% |  |  |  |  | Basement 2 | 0 | 4%
Flooring & Fitting | Flooring & Fitting | 1 | 25% |  |  |  |  | Basement 3 | 0 | 8%
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3 | 20%
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4 | 30%
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 3150
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 5500/-
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | 85000/-
Other Charges |  |  |  |  | 100000/-
Legal Services Charges |  |  |  |  | 10000/-
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 100000/-
Distressed valuation of the Property |  |  |  |  | 2520
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop |  | 7 |  | 1076.8306 |  | 2630
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 27 |  | 10432.5764 |  | 19240
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Sector III
Building No.5 - A Wing (Type C4)
Ground Floor for Commercial
1 |  | Shop | 139.0709 | 0 | 350 | Ground Floor for Commercial
2 |  | Shop | 149.7272 | 0 | 365
3 |  | Shop | 201.2868 | 0 | 465
4 |  | Shop | 155.4322 | 0 | 380
5 |  | Shop | 121.5256 | 0 | 315
6 |  | Shop | 158.6614 | 0 | 385
7 |  | Shop | 151.1266 | 0 | 370
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Ground Floor for Residential
1 |  | 1BHK | 359.5176 | 0 | 650 | Ground Floor for Residential
2 |  | 1BHK | 359.5176 | 0 | 650
3 |  | 1BHK | 380.2921 | 0 | 695
1st Floor | [10 empty] | to |  | 1st | 1
101 |  | 2BHK | 514.9498 | 0 | 980 | 1st Floor |  |  |  |  | 101 to 101 | 1 | 101 | 101
102 |  | 1BHK | 359.5176 | 0 | 675 | [5 empty] | 102 to 102 | 2 | 102 | 102
103 |  | 1BHK | 359.5176 | 0 | 670 | [5 empty] | 103 to 103 | 3 | 103 | 103
104 |  | 1BHK | 359.5176 | 0 | 670 | [5 empty] | 104 to 104 | 4 | 104 | 104
105 |  | 1BHK | 359.5176 | 0 | 670 | [5 empty] | 105 to 105 | 5 | 105 | 105
106 |  | 1BHK | 380.2921 | 0 | 695 |  |  | 24 |  |  | 106 to 106 | 6 | 106 | 106
2nd to 4th Floor | [10 empty] | to |  | 2nd | 4
201 to 401 |  | 2BHK | 514.9498 | 0 | 920 | 2nd to 4th Floor |  |  |  |  | 201 to 401 | 1 | 201 | 401
202 to 402 |  | 1BHK | 359.5176 | 0 | 670 | [5 empty] | 202 to 402 | 2 | 202 | 402
203 to 403 |  | 1BHK | 359.5176 | 0 | 670 | [5 empty] | 203 to 403 | 3 | 203 | 403
204 to 404 |  | 1BHK | 359.5176 | 0 | 670 | [5 empty] | 204 to 404 | 4 | 204 | 404
205 to 405 |  | 1BHK | 359.5176 | 0 | 670 | [5 empty] | 205 to 405 | 5 | 205 | 405
206 to 406 |  | 1BHK | 380.2921 | 0 | 695 |  |  | 24 |  |  | 206 to 406 | 6 | 206 | 406
Remarks:
1. Construction work was stopped. work is the same as last visit (dtd.08/10/2024) 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. The project has received first CC on 26/06/2018, But construction work is not yet completed. 7. On Site, we meet Mr.Umesh Yadav (Sales) - 9960253099. | [7 empty] | but work is in process at the time of the visit. (Very Slow Speed).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Gaurav Naik |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Parvati Kunj
Google Map :

## C%
Construction details: Building No. = | [6 empty] | Plinth work completed
Ground | 1 |  | Podium | 3 | Floors | 42 | All work Completed. Wait For OC.
Stage of construction: | Plinth work completed | [5 empty] | All work Completed. Provide OC.
Type of Work | Completed Slab/Floor | Complition % | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Plinth | 10 | 100% | 10% |  | 30%
RCC Slab | 0 | 0% |  |  |  |  | Excavation in process | 1% | 2%
Brick | 0 | 0% |  |  |  |  | Excavation Completed | 2% | 4%
Plaster | 0 | 0% |  |  |  |  | Footing in Process | 4% | 8%
Flooring | 0 | 0% |  |  |  |  | Footing Completed | 5% | 15%
Painting & Wooden Work | 0 | 0% |  |  |  |  | Plinth in process | 7% | 20%
Finishing | 0 | 0% |  |  |  |  | Plinth completed | 10% | 30%
|  |  | 10% |  | 30%

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 3.6 | 9.9 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  | 2.15 | 2.05 | 4.4075 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.75 | 3.05 | 8.3875 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.2 | 1.95 | 2.34 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.95 | 1.2 | 2.34 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1.6 | 0.45 | 0.72 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 302.4146 | 28.095 |  |  | 0 | 0 |  | 0 | 0
|  |  | 302.4146 | 28.095

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted