## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 29/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-08
Name of the builder group |  |  |  | K Raheja Corp Private Limited
Name of the builder company |  |  |  | K Raheja Corp Private Limited
Name of the Project |  |  |  | Raheja Modern Vivarea |  |  |  | Raheja Modern Vivarea (North & South Tower)
Provided Contact Details ( Name & Contact No.) |  |  |  | Ms.Ritinha - 9167059638
Site Person - Contact Details ( Name & Contact No.)
Name / No of the Building |  |  |  | Tower 1 (North Tower) Tower 2 (South Tower)
Docouments Provided |  |  |  | Approved Plans & CC
RERA No. |  |  |  | Tower 1 (North Tower)- P51900034289 Tower 2 (South Tower) - P51900034288
Project location details |  | Raheja Modern Vivarea, C.S. No.7/1895, near New Shirin Talkies, Sane Guruji Marg, RTO Colony, , Byculla, Mumbai, Mumbai - 400011.
C.S. No |  | 7/1895
Locality |  | RTO Colony
Road |  | Sane Guruji Marg |  | Locality/Village |  | NA
City |  | Byculla |  | District |  | Mumbai
Taluka |  | Mumbai |  | Pin Code |  | 400011
Nearby Landmark |  | New Shirin Talkies |  | Distance from city centre: |  | 0.70 KM from Mahalaxmi Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | New Shirin Talkies
West | NA | NA |  |  | Railway track(Above 50m distance)
North | NA | NA |  |  | Mahalaxmi Heights
South | NA | NA |  |  | Aakash Horizon Co-Op Society
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 18.9790715,72.8238138
Location Link |  | https://goo.gl/maps/339g33PNmjRz2Mkz5
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 13765.31
Permissible FSI |  |  |  | 1.33
Permissible TDR/Paid FSI |  |  |  | 1.8807
Total FSI availaible for the project |  |  |  | 3.2107
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 44196.12
Total number of Buildings |  |  |  | 02 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai
Layout Approval No |  | EB/6794/E/A |  |  | Dated | 2022-01-06
Approved Floor plan No. |  | EB/6794/E/A |  |  | Dated | 2022-01-06
Commencement-CC No Valid Up to: |  | EB/6794/E/A/FCC/2/Amend |  |  | Dated | 2022-11-24
|  | This CC is endorsed and further extended for Tower-1 upto 40th habitable floors and for Tower-2 for portion marked in pink wash in accompanying plan upto 30th floor, as per amended approved plans dated 06/01/2022. |  |  | Valid Upto Date | 2023-06-21
Commencement-CC No Valid Up to: |  | EB/6794/E/A/FCC/4/Amend |  |  | Dated | 2024-10-11
|  | This CC is endorsed and extended for the entire work for Tower–1 comprising of 2 basements + Ground /stilt + 6 podiums (P1to P6) + stilt/ Yogalaya + 40 habitable floors + 2 service floors and Tower -2 comprising of 2 basements + ground /stilt+6 podiums (P1to P6) +stilt / Yogalaya + 41 habitable + 2 service floors for as per amended plan approval dated 28/08/2024. |  |  | Valid Upto Date | 2025-06-21
Airport Authority of India NOC No. |  | JUHU/WEST/B/060118/311408 Valid Upto : 216.54 AMSL |  |  | Dated Valid upto | 30/07/2018 30/07/2026 |  |  |  | Dated | 2018-07-30 | 2026-07-30
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 44196.12
Approved no of units |  |  | Flats - 224
Approved no of Floors |  |  | Tower 1 = 2B + Gr/Stilt + P1 to P6 + Amentity Floor + 1st to 40th Floor Tower 2 = 2B + Gr/Stilt + P1 to P6 + Amentity Floor + 1st to 30th Floor
Proposed no of Floors |  |  | Tower 1 = 2B + Gr/Stilt + P1 to P6 + Amentity Floor + 1st to 40th Floor
Tower 2 = 2B + Gr/Stilt + P1 to P6 + Amentity Floor + 1st to 41st Floor
Expected Completion |  |  | As per RERA - North Tower = 31/03/2028 South Tower = 30/09/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Tower 1 = 2B + Gr/Stilt + P1 to P6 + Amentity Floor + 1st to 40th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 38 Floor, External Plaster upto 33 Floor, Flooring upto 26 Floor, Painting upto 24 Floor Completed | , Internal Plaster upto 38 Floor, External Plaster upto 33 Floor, Flooring upto 26 Floor, Painting upto 24 Floor
Basement | 2 | Ground | 1 | Podium | 7 | Floors | 40 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 38 Floor, External Plaster upto 33 Floor, Flooring upto 26 Floor, Painting upto 24 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 10
Excavation |  | 40 | 100% | 82.38% |  | 92.12% |  | Excavation in process | 20
Plinth |  | 40 | 100% |  |  |  |  | Excavation Completed | 40
RCC (Including podiums) |  | 48 | 100% |  |  |  |  | Footing in Process | 10
Brickwork | Brickwork & Internal Plaster | 40 | 100% |  |  |  |  | Footing Completed | 20
Internal Plaster | Brickwork & Internal Plaster | 38 | 95% |  |  |  |  | Basement 1 | 30
Fasade & Plumbing | External Plaster & Plumbing | 33 | 82.5% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 26 | 65% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 24 | 60% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 40
Construction details: |  | Tower 2 = 2B + Gr/Stilt + P1 to P6 + Amentity Floor + 1st to 41st Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 37 Slab, Brickwork upto 29 Floor, Internal Plaster upto 23.2 Floor, External Plaster upto 20.3 Floor, Flooring upto 12 Floor Completed | , RCC upto 37 Slab, Brickwork upto 29 Floor, Internal Plaster upto 23.2 Floor, External Plaster upto 20.3 Floor, Flooring upto 12 Floor
Basement | 2 | Ground | 1 | Podium | 7 | Floors | 41 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 37 Slab, Brickwork upto 29 Floor, Internal Plaster upto 23.2 Floor, External Plaster upto 20.3 Floor, Flooring upto 12 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 10.25
Excavation |  | 41 | 100% | 57.63% |  | 77.96% |  | Excavation in process | 20.5
Plinth |  | 41 | 100% |  |  |  |  | Excavation Completed | 41
RCC (Including podiums) |  | 37 | 75.51% |  |  |  |  | Footing in Process | 10.25
Brickwork | Brickwork & Internal Plaster | 29 | 70.73% |  |  |  |  | Footing Completed | 20.5
Internal Plaster | Brickwork & Internal Plaster | 23.2 | 56.59% |  |  |  |  | Basement 1 | 30.75
Ext. Plaster & Plumbing | External Plaster & Plumbing | 20.3 | 49.51% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 29.27% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 41
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 50000 |  |  | 46K TO Rate 50000 FR 150 from 4th Floor Shailesh Index2
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate (from 4th Floor) |  |  |  |  | 150
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 1500000
Distressed valuation of the Property |  |  |  |  | 40000
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Tower 1 |  | 114 |  | 308917.7206 |  | 478822.4669
Tower 2 |  | 110 |  | 205519.3663 |  | 318555.0177
Total |  | 224 |  | 514437.0868 |  | 797377.4846
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Tower 1 (North Tower)
Basement 02 & 01 floor for Parking
Ground Floor for Parking
1st to 6th Podium Floor for Parking
Amenity Floor between 6th Podium Floor & 1st Resi. Floor
1st, 8th, 15th, 22nd, 29th & 36th Floor for Residential (Part Refuge Area)
1 |  | 4BHK | 2865.4169 | 0 | 4441.3962 | 1st, 8th, 15th, 22nd, 29th & 36th Floor for Residential (Part Refuge Area) |  |  | 10.764
2 |  | 4BHK | 3027.0491 | 0 | 4691.9261
Service Floor between 22nd & 23rd Floor
2nd to 7th, 9th to 14th, 16th to 21st, 23rd to 28th, 30th to 35th, 37th to 40th Floor
1 |  | 4BHK | 2865.4169 | 0 | 4441.3962 | 2nd to 7th, 9th to 14th, 16th to 21st, 23rd to 28th, 30th to 35th, 37th to 40th Floor |  | 47282.429
2 |  | 3.5BHK | 2153.5024 | 0 | 3337.9286 |  |  | 62913.2682
3 |  | 4BHK | 3027.0491 | 0 | 4691.9261 |  |  | 44757.7379
Service Floor between 40th & Terrace Floor
Tower 2
Basement 02 & 01 floor for Parking
Ground Floor for Parking
1st to 6th Podium Floor for Parking
Amenity Floor between 6th Podium Floor & 1st Resi. Floor
1st, 8th, 15th, 22nd, 29th Floor for Residential (Part Refuge Area)
1 |  | 5BHK | 2590.0875 | 0 | 4014.6356 | 1st, 8th, 15th, 22nd, 29th Floor for Residential (Part Refuge Area)
2 |  | 5BHK | 2590.0875 | 0 | 4014.6356
Service Floor between 22nd & 23rd Floor
2nd to 7th, 9th to 14th, 16th to 21st, 23rd to 28th & 30th Floor
1 |  | 4BHK | 2040.1924 | 0 | 3162.2982 | 2nd to 7th, 9th to 14th, 16th to 21st, 23rd to 28th & 30th Floor
2 |  | 3BHK | 1552.1774 | 0 | 2405.875 |  |  | 4987.7903
3 |  | 3BHK | 1552.1774 | 0 | 2405.875
4 |  | 4BHK | 2040.1924 | 0 | 3162.2982
Service Floor between 30th & Terrace Floor
Remarks:
* | Construction Work is in procress at the time of visit. (Internal Photo was not allowed)
* | As per site visit dtd. 09/10/2024, construction work progress of towers is given below Tower 1(North Tower) = 2B + Gr + 6P + Amenity + 39 habitable Floors completed (i.e 47th slabs completed as per architect). Tower 2(South Tower) = 2B + Gr + 6P + Amenity + 23 habitable Floors completed (i.e 31th slabs completed as per architect). | [6 empty] | change this statement during every visit on changes made by shruti dtd 25/07/2024. (Basement slabs + Gr Slab + Pod Slab + Floor Slabs)
* | We have considered Saleable area of Flats as per our Calculation. | [6 empty] | habitable
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Deck Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We refer Airport Authority of India NOC from MCGM site. | [6 empty] | Railway NOC remark is removed due to letter from builder | https://mail.google.com/mail/u/0/?tab=rm&ogbl#search/morden/FMfcgzGslbPSKGtGgcWCcNhXSrZQGCQV
* | Please provide Railway NOC.
* | We have updated revised approved CC From MCGM Site (on 22/03/2024).
* | We have updated revised approved CC From MCGM Site (on 14/01/2025).
* | Validity of CC is expired on 21/06/2025. Please provide revised CC.
* | Recommended Rates & Other Charges of the Property have been revised on 29/09/2025
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Karan Misal |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Raheja Modern Vivarea
Layout :
Google Map :
Formulas:
NA = [NA, row above]
Railway Track
Tower 1
Tower 2
Tower 1
Tower 2
1st Floor
South
South
South
North
South Tower
North Tower

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Note
Flat No | North 3 |  |  | Flat No | North 2 |  |  | Flat No | North 1 |  |  | Flat No | South 1 & 4 |  |  | Flat No | South 2 & 3 |  |  | Flat No | South Refuge
Discription | Carpet |  |  | Discription | Carpet |  |  | Discription | Carpet |  |  | Discription | Carpet |  |  | Discription | Carpet |  |  | Discription | Carpet
| L | W | A |  | L | W | A |  | L | W | A |  | L | W | A |  | L | W | A |  | L | W | A
Hall | 1.8 | 3.05 | 5.49 | Hall | 3.65 | 3.2 | 11.68 | Hall | 2.4 | 3.05 | 7.32 | Hall | 1.41 | 1.28 | 1.8048 | Hall | 2.25 | 4.01 | 9.0225 | Hall | 1.41 | 1.28 | 1.8048
| 5.11 | 2.475 | 12.6473 |  | 4.9 | 8.125 | 39.8125 |  | 5.11 | 2.475 | 12.6473 |  | 5.26 | 1.52 | 7.9952 |  | 3.97 | 8.33 | 33.0701 |  | 5.26 | 1.52 | 7.9952
| 5.18 | 10.5 | 54.39 |  | 1.45 | 3.235 | 4.6907 |  | 5.18 | 10.5 | 54.39 |  | 4.32 | 9.43 | 40.7376 |  | 1.5 | 1.82 | 2.73 |  | 4.32 | 9.43 | 40.7376
kitch | 3.66 | 4.255 | 15.5733 | kitch | 3.3 | 3.695 | 12.1935 | kitch | 3.66 | 4.255 | 15.5733 | kitch | 3.05 | 3.8 | 11.59 | kitch | 2.74 | 3.66 | 10.0284 | kitch | 3.05 | 3.8 | 11.59
| 4.11 | 1.52 | 6.2472 |  | 2.25 | 1.67 | 3.7575 |  | 4.11 | 1.52 | 6.2472 |  | 2.64 | 1.4 | 3.696 |  | 2.74 | 1.48 | 4.0552 |  | 2.64 | 1.4 | 3.696
| 1.5 | 2.7 | 4.05 |  | 2.5 | 1.825 | 4.5625 |  | 1.5 | 2.7 | 4.05 |  | 1.82 | 2.75 | 5.005 |  | 1.69 | 1.22 | 2.0618 |  | 1.82 | 2.75 | 5.005
| 1.36 | 1.225 | 1.666 |  | 1.05 | 1.225 | 1.2863 |  | 1.36 | 1.225 | 1.666 |  | 1.82 | 1.08 | 1.9656 |  | 1.69 | 1.2 | 2.028 |  | 1.82 | 1.08 | 1.9656
Bed1 | 3.66 | 5.625 | 20.5875 |  | 1.3 | 1.35 | 1.755 | Bed1 | 3.66 | 5.625 | 20.5875 | Bed1 | 1.96 | 2.8 | 5.488 |  | 2.74 | 1.4 | 3.836 | Bed1 | 4.26 | 3.55 | 15.123
| 3.66 | 5.625 | 20.5875 | Bed1 | 3.65 | 4.275 | 15.6038 |  | 1.76 | 2.425 | 4.268 |  | 3.66 | 4.56 | 16.6896 | Bed2 | 1.67 | 2.43 | 4.0581 |  | 1.83 | 2.75 | 5.0325
| 2.45 | 2.275 | 5.5738 |  | 1.85 | 2.425 | 4.4863 |  | 2.45 | 2.275 | 5.5738 |  | 1.67 | 2.65 | 4.4255 |  | 3.35 | 3.72 | 12.462 | Bed2 | 1.22 | 2.28 | 2.7816
|  |  | 0 |  | 1.225 | 2.275 | 2.7869 |  |  |  | 0 |  | 0.98 | 1.07 | 1.0486 |  | 0.9 | 2.28 | 2.052 |  | 3.66 | 4.26 | 15.5916
Bed2 | 3.95 | 5.025 | 19.8488 |  | 1.225 | 1.475 | 1.8069 | Bed2 | 1.875 | 2.425 | 4.5469 | Bed2 | 1.72 | 2.28 | 3.9216 |  | 1.22 | 1.48 | 1.8056 |  | 2.89 | 1.52 | 4.3928
| 1.875 | 2.425 | 4.5469 | Bed2 | 3.675 | 4.275 | 15.7106 |  | 3.95 | 5.025 | 19.8488 |  | 3.66 | 4.26 | 15.5916 | Bed3 | 1.07 | 2.43 | 2.6001 |  | 2.89 | 1.83 | 5.2887
| 1.2 | 2.275 | 2.73 |  | 1.875 | 2.425 | 4.5469 |  | 1.2 | 2.75 | 3.3 |  | 0.99 | 2.13 | 2.1087 |  | 3.35 | 3.72 | 12.462 | Bed2 | 1.72 | 2.28 | 3.9216
| 1.25 | 1.575 | 1.9688 |  | 1.225 | 2.275 | 2.7869 |  | 1.25 | 1.575 | 1.9688 |  | 1.43 | 1.25 | 1.7875 |  | 0.9 | 2.28 | 2.052 |  | 3.66 | 4.26 | 15.5916
Bed2 | 3.95 | 6.1 | 24.095 |  | 1.225 | 1.475 | 1.8069 | Bed2 | 3.95 | 6.1 | 24.095 | Bed2 | 1.22 | 2.28 | 2.7816 |  | 1.22 | 1.48 | 1.8056 |  | 0.99 | 2.13 | 2.1087
| 3.475 | 2.415 | 8.3921 | Bed4 | 0.45 | 1.275 | 0.57375 |  | 2.225 | 2 | 4.45 |  | 3.66 | 4.26 | 15.5916 | Bed3 | 1.66 | 2.8 | 4.648 |  | 1.25 | 1.43 | 1.7875
| 2.525 | 2.235 | 5.6434 |  | 1.2 | 2.945 | 3.534 |  | 3.475 | 1.75 | 6.0812 |  | 1.52 | 2.89 | 4.3928 |  | 3.65 | 4.56 | 16.644 | Bed4 | 1.96 | 2.8 | 5.488
| 2 | 2.645 | 5.29 | Bed4 | 3.975 | 5.18 | 20.5905 |  | 2.15 | 3.545 | 7.6217 |  | 2.89 | 1.83 | 5.2887 |  | 1.68 | 2.65 | 4.452 |  | 3.66 | 4.56 | 16.6896
Bed4 | 4.045 | 4.25 | 17.1913 |  | 2.625 | 2.795 | 7.3369 | Bed4 | 4.3 | 1.2 | 5.16 | Bed4 | 4.26 | 3.55 | 15.123 | Bed4 |  |  | 0 |  | 1.67 | 2.65 | 4.4255
| 4.3 | 1.2 | 5.16 |  | 2.7 | 3.695 | 9.9765 |  | 4.045 | 4.25 | 17.1913 |  | 1.83 | 2.75 | 5.0325 |  |  |  | 0 | Study | 2.89 | 2.8 | 8.092
| 1.8 | 2.6 | 4.68 |  |  |  | 0 |  | 2.6 | 1.8 | 4.68 |  |  |  | 0 |  |  |  | 0 |  | 3.65 | 4.56 | 16.644
| 2.2 | 2.6 | 5.72 | toilet1 | 1.75 | 1.61 | 2.8175 |  | 2.2 | 2.6 | 5.72 |  |  |  | 0 |  |  |  | 0 | Bed5 | 3.35 | 5.35 | 17.9225
toilet1 | 2.255 | 1.52 | 3.4276 | passage1 | 8.775 | 1.275 | 11.1881 | toilet1 | 2.305 | 1.52 | 3.5036 | toilet1 | 1.52 | 1.8 | 2.736 | toilet1 |  |  | 0 |  | 1.23 | 1.48 | 1.8204
toilet3 |  |  | 0 |  | 1.45 | 1.2 | 1.74 | passage1 | 4.625 | 1.2 | 5.55 | passage1 | 6.13 | 1.22 | 7.4786 | passage1 | 5.35 | 1.06 | 5.671 |  | 2.72 | 1.86 | 5.0592
|  |  | 0 | passage1 | 2.75 | 4.74 | 13.035 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 2.45 | 1.06 | 2.597
passage1 | 4.625 | 1.2 | 5.55 | DECK |  |  | 0 | passage1 |  |  | 0 | passage1 |  |  | 0 | passage1 |  |  | 0 | passage1 | 6.13 | 1.22 | 7.4786
DECK | 4.28 | 2.45 | 10.486 | DECK |  |  | 0 | DECK | 3.95 | 2.45 | 9.6775 | DECK | 4.22 | 1.72 | 7.2584 | DECK | 3.87 | 1.72 | 6.6564 | DECK | 4.22 | 1.72 | 7.2584
DECK | 3.95 | 2.45 | 9.6775 | passage4 |  |  | 0 | DECK | 4.28 | 2.45 | 10.486 | DECK |  |  | 0 | DECK |  |  | 0 | DECK |  |  | 0
passage4 |  |  | 0 |  |  |  | 0 | passage4 |  |  | 0 | passage4 |  |  | 0 | passage4 |  |  | 0 | toilet1 | 1.52 | 1.8 | 2.736
|  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  |  | 0 | Total |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Total |  | 3027.0491 | 281.2197 |  |  | 2153.5024 | 200.0652 | Total |  | 2865.4169 | 266.2037 | Total |  | 2040.1924 | 189.5385 | Total |  | 1552.1774 | 144.2008 | Total |  | 2590.0875 | 240.625
|  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF!