## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report For UDAAN ARIA
Date: |  |  |  |  | 17/07/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-07-16
Name of the builder group |  |  |  |  | M/s. Uddan Builders & Developers
Name of the builder company |  |  |  |  | M/s. Uddan Builders & Developers
Name of the Project |  |  |  |  | Udaan Aria
No. of the Project |  |  |  |  | Building No.1 - Type 1 = A Building No.2 - Type 2 = C (A & B Wing) Building No.3 - Type 3 = D Building No.4 - Type 4 = B
RERA No |  |  |  |  | P52000008827
Docouments Provided |  |  |  |  | 1. CC. 2. Approved Plan
Approved Layout Plan : MS/LNA-1/PK.150/2018 Date : 30/11/2022
Project location details: Udaan Aria, Survey No.13/1/C/1, 13/1/C/3, 13/1/D, 13/2/A/1, 13/2/A/2, 13/2/A/3, 13/2/A/4, 13/2/A/5, 13/2/A/6, 13/2/A/7, 13/2/A/8, Chinchavali, Karjat.
Survey No.13/1/C/1, 13/1/C/3, 13/1/D, 13/2/A/1, 13/2/A/2, 13/2/A/3,13/2/A/4, 13/2/A/5, 13/2/A/6, 13/2/A/7, 13/2/A/8 | [7 empty] | Locality: Chinchavali
Road : Taloja By Pass Phata |  |  |  |  | District: Riagad
City : Karjat |  |  |  |  | Pin Code : 410201
Nearby Landmark: Bhivpuri Road Railway Station |  |  |  |  | Distance from city centre: 550m from Bhivpuri Road
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market, etc.) |  |  |  |  | All the mentioned amenities are within the radius of 2 to 2.5 KM
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion : Plane
Nature of the locality : Developing
Quality of infrastructure in vicinity : Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | Not Provided
At site |  | MDR Road |  | Open Land |  | Bhivpuri Station Road |  | Kalyan Karjat Road
Does the boundaries at site match, as mentioned in the Docoumentation:
Type of Structure :RCC Framed Structure
Latitude & Longitude |  | 18.974853,73.330650 |  | 18.9757 |  | Longitude
Location Link |  | https://goo.gl/maps/4BSsC7j5JYqvFUpb9
Approval details:
Approved usage of the Property : Residential (Restrictive convenants in regards to land use , if any) : Residential
Total land area of the project |  |  |  |  | 10972
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1
Total Approved Builtup area of the project |  |  |  |  | 12310
Total number of Buildings |  |  |  |  | 04 Buildings (02 Wings)
Approval Detail :
Layout Approval No |  | MS/LNA-1/PK.150/2018 |  |  |  | Dated | 2022-11-30
Approved Floor plan No. |  | MS/LNA-1/PK.150/2018 Building No.1 = G + 2nd Floor Building No.4 = 1st & 2nd Floor |  |  |  | Dated | 22/05/2018.
Approved Floor plan No. |  | MS/LNA-1/PK/06/2016 Valid upto approved : Building no.2 & 3 = G + 1st to 2nd Floor |  |  |  | Dated | 15/03/2016.
Approved Floor plan No. |  | MS/LNA-1/PK.150/2018 Valid upto approved : Building no.1 = 3rd to 5th Floor Building no.2 & 3 = 5th Floor Building no.4 = G + 3rd to 5th Floor |  |  |  | Dated | 2022-11-30
C.certificate No. Valid Up to: |  | MSHA/L.N.A.1(B)/S.R.185/2017 Building No.1 = G + 4th Floor Building No.4 = G + 3rd Floor |  |  |  | Dated | 22/05/2018. | Valid upto date: One year from date of issue
C.certificate No. Valid Up to: |  | MS/LNA-1(B)/PK6/2016 Building no.2 & 3 = G+1st to 4th Floor |  |  |  | Dated | 15/03/2016.
C.certificate No. Valid Up to: |  | MS/LNA-1(B)/T.No.13999/PK.150/2018 Building no.1 = 3rd to 5th Floor Building no.2 & 3 = 5th Floor Building no.4 = G + 3rd to 5th Floor |  |  |  | Dated | 2022-11-30
O. Certificate No. NA |  |  |  |  | Dated | NA
Date of Commencement of Construction: 15/03/2016. |  |  |  |  | Expected Completion: 31/12/2027
Building wise Construction details
Approved area of the building : 12310.00 Sq.Mtr. |  |  |  |  | Approved no of units : Flats = 360 & Shop = 12
Approved no of Floors : |  |  | Building No.1, 2, 3, 4 = G + 1st to 5th Floor
Proposed no of Floors : G +1st to 5th Floor
Quality of construction: Good |  |  |  |  | Projected life : 60 Years after completion
Material laying at Site :Inlot, Cement, Brick.
Wheather the construction is as per approved Building plan : under construction
Violations Observed if any : No.
Proposed Amenities 1. Vitrified tiles flooring 2. Garanite marble Kitchen platform 3. Power coated sliding windows with tinted glass 4. Designer Bathroom with branded Sanitary were 5. Premium quality paints on internal walls
Recommended Rates of the Property :
Recommended rate of the flat per Sq.ft (On saleable area) (Including Development Charges) | [5 empty] | 3800 |  |  |  | 3800 to 4000 | 2023-02-24 | nikhil dani
Recommended rate of the Shop per Sq.ft (On saleable area) | [5 empty] | 6000/- |  |  |  | 3800 | 2023-02-27 | akash sir
Development Charges | [5 empty] | 85000/-
Club Charges | [5 empty] | 42,000/-
Other Amenities and Club Membership Charges | [5 empty] | 1,75,000/-
Distress valuation of the property | [5 empty] | 3040
Building details floor wise
Commercial Area Details:
Building & Wing |  | No of Units |  | Total Carpet Area |  |  | Total Saleable Area
Shops |  | 12 |  | 1738.386 |  |  | 3391.7902
Residential Area Details:
Building & Wing |  | No of Units |  | Total Carpet Area |  |  | Total Saleable Area
Building A |  | 72 |  | 24908.8648 |  |  | 36117.8539
Building C (Wing A) |  | 54 |  | 12838.9225 |  |  | 18616.4376
Building C (Wing B) |  | 60 |  | 19848.1809 |  |  | 28779.8623
Building D |  | 108 |  | 25324.0322 |  |  | 36719.8467
Building B |  | 66 |  | 22136.0045 |  |  | 32301.5073
Total |  | 360 |  | 105056.0049 |  |  | 152535.5079
Details of Flats in Building and wings.
| Sr. | Flat No. | Description | Gross Carpet area | Attached Terrace area | Saleable Area Loading : | PLC Y/N | Floor
(Building No.1 Type - 1) Building Name: 'A' | [10 empty] | 5
Ground Floor
| 1 | 001 | 1RK | 237.9382 | 0 | 345.0104 | N | Ground Floor | 25875.7814 | 51751.5629 |  | (Building No.1 Type - 1) |  |  | 24908.8648
| 2 | 002 | 1 RK | 237.9382 | 0 | 345.0104 | N |  | 25875.7814 | 51751.5629 |  | (Building No.2 Type-2) Building Name: 'C' |  |  | 12838.9225
| 3 | 003 | 1 RK | 237.9382 | 0 | 345.0104 | N |  | 25875.7814 | 51751.5629 |  |  |  |  | 19848.1809
| 4 | 004 | 1 RK | 237.9382 | 0 | 345.0104 | N |  |  | 51751.5629 |  | (Building Type-3) Building Name: 'D' |  |  | 25324.0322
| 5 | 005 | 1 BHK | 322.0051 | 0 | 466.9073 | N |  |  | 70036.1005 |  | (Building No.4 Type - 4) Building Name: 'B' |  |  | 22136.0045
| 6 | 006 | 1 BHK | 322.0051 | 0 | 466.9073 | N |  |  | 70036.1005
| 7 | 007 | 1 RK | 237.9382 | 0 | 345.0104 | N |  |  | 51751.5629
| 8 | 008 | 1 RK | 237.9382 | 0 | 345.0104 | N |  |  | 51751.5629
| 9 | 009 | 1 RK | 237.9382 | 0 | 345.0104 | N
| 10 | 010 | 1 RK | 237.9382 | 0 | 345.0104 | N
| 11 | 011 | 1 BHK | 322.0051 | 0 | 466.9073 | N
| 12 | 012 | 1 BHK | 322.0051 | 0 | 466.9073 | N |  | 12
Typical 1st & 2nd Floor Plan
| 1 | 101, 201 | 1 BHK | 362.0471 | 0 | 524.9684 | N | 1st & 2nd |  | 78745.2529
| 2 | 102, 202 | 1 BHK | 362.0471 | 0 | 524.9684 | N | 1st & 2nd | 39372.6265 | 78745.2529
| 3 | 103, 203 | 1 BHK | 362.0471 | 0 | 524.9684 | N | 1st & 2nd | 39372.6265 | 78745.2529
| 4 | 104, 204 | 1 BHK | 362.0471 | 0 | 524.9684 | N | 1st & 2nd | 39372.6265 | 78745.2529
| 5 | 105, 205 | 1 BHK | 368.0212 | 0 | 533.6307 | N | 1st & 2nd | 40022.3011 | 80044.6023
| 6 | 106, 206 | 1 BHK | 368.0212 | 0 | 533.6307 | N | 1st & 2nd | 40022.3011 | 80044.6023
| 7 | 107, 207 | 1 BHK | 359.3669 | 0 | 521.082 | N | 1st & 2nd | 39081.1508 | 78162.3016
| 8 | 108, 208 | 1 BHK | 349.1949 | 0 | 506.3326 | N | 1st & 2nd |  | 75949.896
| 9 | 109, 209 | 1 BHK | 349.1949 | 0 | 506.3326 | N | 1st & 2nd |  | 75949.896
| 10 | 110, 210 | 1 BHK | 368.0212 | 0 | 533.6307 | N | 1st & 2nd |  | 80044.6023
| 11 | 111, 211 | 1 BHK | 366.7295 | 0 | 531.7577 | N | 1st & 2nd |  | 79763.6619
| 12 | 112, 212 | 1 BHK | 366.7295 | 0 | 531.7577 | N | 1st & 2nd | 24 | 79763.6619
Typical 3rd & 4th Floor Plan
| 1 | 301, 401 | 1 BHK | 362.0471 | 0 | 524.9684 | N | 3rd & 4th
| 2 | 302, 402 | 1 BHK | 362.0471 | 0 | 524.9684 | N | 3rd & 4th
| 3 | 303, 403 | 1 BHK | 362.0471 | 0 | 524.9684 | N | 3rd & 4th
| 4 | 304, 404 | 1 BHK | 362.0471 | 0 | 524.9684 | N | 3rd & 4th
| 5 | 305, 405 | 1 BHK | 368.0212 | 0 | 533.6307 | N | 3rd & 4th
| 6 | 306, 406 | 1 BHK | 368.0212 | 0 | 533.6307 | N | 3rd & 4th
| 7 | 307, 407 | 1 BHK | 359.3669 | 0 | 521.082 | N | 3rd & 4th
| 8 | 308, 408 | 1 BHK | 349.1949 | 0 | 506.3326 | N | 3rd & 4th
| 9 | 309, 409 | 1 BHK | 349.1949 | 0 | 506.3326 | N | 3rd & 4th
| 10 | 310, 410 | 1 BHK | 368.0212 | 0 | 533.6307 | N | 3rd & 4th | 20
| 11 | 311, 411 | 1 BHK | 366.7295 | 0 | 531.7577 | N | 3rd & 4th
| 12 | 312, 412 | 1 BHK | 366.7295 | 0 | 531.7577 | N | 3rd & 4th
5th Floor
| 1 | 501 | 1 BHK | 362.0471 | 0 | 524.9684 | N | 5th Floor
| 2 | 502 | 1 BHK | 362.0471 | 0 | 524.9684 | N | 3rd & 4th
| 3 | 503 | 1 BHK | 362.0471 | 0 | 524.9684 | N | 3rd & 4th
| 4 | 504 | 1 BHK | 362.0471 | 0 | 524.9684 | N | 3rd & 4th
| 5 | 505 | 1 BHK | 368.0212 | 0 | 533.6307 | N | 3rd & 4th
| 6 | 506 | 1 BHK | 368.0212 | 0 | 533.6307 | N | 3rd & 4th
| 7 | 507 | 1 BHK | 359.3669 | 0 | 521.082 | N | 3rd & 4th
| 8 | 508 | 1 BHK | 349.1949 | 0 | 506.3326 | N | 3rd & 4th
| 9 | 509 | 1 BHK | 349.1949 | 0 | 506.3326 | N | 3rd & 4th
| 10 | 510 | 1 BHK | 368.0212 | 0 | 533.6307 | N | 3rd & 4th | 20
| 11 | 511 | 1 BHK | 366.7295 | 0 | 531.7577 | N | 3rd & 4th
| 12 | 512 | 1 BHK | 366.7295 | 0 | 531.7577 | N | 3rd & 4th
(Building No.2 Type-2) Building Name: 'C'
A-Wing
Ground Floor
| 1 | 1 | 1 RK | 239.6066 | 0 | 347.4296 | N | Ground Floor
| 2 | 2 | 1 RK | 230.7263 | 0 | 334.5532 | N
| 3 | 3 | 1 RK | 230.7263 | 0 | 334.5532 | N
| 4 | 4 | 1 RK | 229.7845 | 0 | 333.1875 | N
| 5 | 5 | 1 RK | 231.8027 | 0 | 336.114 | N
| 6 | 6 | 1 RK | 231.8027 | 0 | 336.114 | N
| 7 | 7 | 1 RK | 231.8027 | 0 | 336.114 | N
| 8 | 8 | 1 RK | 230.4572 | 0 | 334.163 | N
| 9 | 9 | 1 RK | 230.4572 | 0 | 334.163 | N |  | 9
Typical 1st To 4th Floor Plan
| 1 | 101 to 401 | 1 RK | 240.9521 | 0 | 349.3806 | N | Typical 1st To 4th Floor Plan
| 2 | 102 to 402 | 1 RK | 230.8878 | 0 | 334.7873 | N
| 3 | 103 to 403 | 1 RK | 230.8878 | 0 | 334.7873 | N
| 4 | 104 to 404 | 1 RK | 237.3193 | 0 | 344.113 | N
| 5 | 105 to 405 | 1 RK | 249.5095 | 0 | 361.7888 | N
| 6 | 106 to 406 | 1 RK | 249.5095 | 0 | 361.7888 | N
| 7 | 107 to 407 | 1 RK | 249.5095 | 0 | 361.7888 | N
| 8 | 108 to 408 | 1 RK | 230.8878 | 0 | 334.7873 | N
| 9 | 109 to 409 | 1 RK | 230.8878 | 0 | 334.7873 | N |  | 36
5th Floor | [9 empty] | 10.764
| 1 | 501 | 1 RK | 240.9521 | 0 | 349.3806 | N | 5th Floor |  |  | 19.655
| 2 | 502 | 1 RK | 230.8878 | 0 | 334.7873 | N |  |  |  | 19.95
| 3 | 503 | 1 RK | 230.8878 | 0 | 334.7873 | N
| 4 | 504 | 1 RK | 237.3193 | 0 | 344.113 | N
| 5 | 505 | 1 RK | 249.5095 | 0 | 361.7888 | N |  |  | 219.8009
| 6 | 506 | 1 RK | 249.5095 | 0 | 361.7888 | N
| 7 | 507 | 1 RK | 249.5095 | 0 | 361.7888 | N
| 8 | 508 | 1 RK | 230.8878 | 0 | 334.7873 | N
| 9 | 509 | 1 RK | 230.8878 | 0 | 334.7873 | N |  | 36
Wing-B
Ground Floor Plan
| 1 | 1 | 1 BHK | 358.4143 | 0 | 519.7007 | N | Ground Floor Plan
| 2 | 2 | 1 RK | 290.0898 | 0 | 420.6302 | N
| 3 | 3 | 1 RK | 290.0898 | 0 | 420.6302 | N
| 4 | 4 | 1 RK | 289.9283 | 0 | 420.3961 | N
| 5 | 5 | 1 RK | 290.0898 | 0 | 420.6302 | N
| 6 | 6 | 1 BHK | 333.2427 | 0 | 483.2019 | N
| 7 | 7 | 1 BHK | 331.3052 | 0 | 480.3925 | N
| 8 | 8 | 1 BHK | 331.3052 | 0 | 480.3925 | N
| 9 | 9 | 1 BHK | 333.2427 | 0 | 483.2019 | N
| 10 | 10 | 1 BHK | 358.4143 | 0 | 519.7007 | N |  | 10
Typical 1st To 4th Floor Plan
| 1 | 101 to 401 | 1 BHK | 332.0156 | 0 | 481.4226 | N | Typical 1st To 4th Floor Plan |  |  |  | 1.45 |  | 332.0156
| 2 | 102 to 402 | 1 BHK | 325.3419 | 0 | 471.7458 | N |  |  |  |  | 1.45 |  | 319.2602
| 3 | 103 to 403 | 1 BHK | 335.4601 | 0 | 486.4171 | N |  |  |  |  | 1.45 |  | 332.8229
| 4 | 104 to 404 | 1 BHK | 325.3419 | 0 | 471.7458 | N |  |  |  |  | 1.45 |  | 321.1978
| 5 | 105 to 405 | 1 BHK | 335.4601 | 0 | 486.4171 | N |  |  |  |  | 1.45 |  | 331.3697
| 6 | 106 to 406 | 1 BHK | 340.8313 | 0 | 494.2054 | N |  |  |  |  | 1.45 |  | 340.8313
| 7 | 107 to 407 | 1 BHK | 328.7218 | 0 | 476.6466 | N |  |  |  |  | 1.45 |  | 328.7218
| 8 | 108 to 408 | 1 BHK | 328.7218 | 0 | 476.6466 | N |  |  |  |  | 1.45 |  | 328.7218
| 9 | 109 to 409 | 1 BHK | 335.4601 | 0 | 486.4171 | N |  | 40 |  |  | 1.45 |  | 332.8229
| 10 | 110 to 410 | 1 BHK | 341.0573 | 0 | 494.5331 | N |  |  |  |  | 1.45 |  | 332.0156
5th Floor Plan
| 1 | 501 | 1 BHK | 332.0156 | 0 | 481.4226 | N | 5th Floor Plan |  |  | 332.0156 | 29.9
| 2 | 502 | 1 BHK | 325.3419 | 0 | 471.7458 | N |  |  |  | 319.2602 | 30.225
| 3 | 503 | 1 BHK | 335.4601 | 0 | 486.4171 | N |  |  |  | 332.8229
| 4 | 504 | 1 BHK | 325.3419 | 0 | 471.7458 | N |  |  |  | 321.1978 | 31.085
| 5 | 505 | 1 BHK | 335.4601 | 0 | 486.4171 | N |  |  |  | 331.3697 | 30.305
| 6 | 506 | 1 BHK | 340.8313 | 0 | 494.2054 | N |  |  |  | 340.8313
| 7 | 507 | 1 BHK | 328.7218 | 0 | 476.6466 | N |  |  |  | 328.7218
| 8 | 508 | 1 BHK | 328.7218 | 0 | 476.6466 | N |  |  |  | 328.7218
| 9 | 509 | 1 BHK | 335.4601 | 0 | 486.4171 | N |  | 40 |  | 332.8229
| 10 | 510 | 1 BHK | 341.0573 | 0 | 494.5331 | N |  |  |  | 332.0156
(Building Type-3) Building Name: 'D'
Ground Floor Plan
| 1 | 1 | 1 RK | 233.4712 | 0 | 338.5332 | N | Ground Floor Plan
| 2 | 2 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 3 | 3 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 4 | 4 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 5 | 5 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 6 | 6 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 7 | 7 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 8 | 8 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 9 | 9 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 10 | 10 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 11 | 11 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 12 | 12 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 13 | 13 | 1 RK | 231.3722 | 0 | 335.4897 | N
| 14 | 14 | 1 RK | 231.3722 | 0 | 335.4897 | N
| 15 | 15 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 16 | 16 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 17 | 17 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 18 | 18 | 1 RK | 233.4712 | 0 | 338.5332 | N |  | 18
Typical 1st To 4th Floor Plan
| 1 | 101 to 401 | 1 RK | 233.4712 | 0 | 338.5332 | N | Typical 1st To 4th Floor Plan
| 2 | 102 to 402 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 3 | 103 to 403 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 4 | 104 to 404 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 5 | 105 to 405 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 6 | 106 to 406 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 7 | 107 to 407 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 8 | 108 to 408 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 9 | 109 to 409 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 10 | 110 to 410 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 11 | 110 to 411 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 12 | 112 to 412 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 13 | 113 to 413 | 1 RK | 231.3722 | 0 | 335.4897 | N
| 14 | 114 to 414 | 1 RK | 231.3722 | 0 | 335.4897 | N
| 15 | 115 to 415 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 16 | 116 to 416 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 17 | 117 to 417 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 18 | 118 to 418 | 1 RK | 233.4712 | 0 | 338.5332 | N |  | 72
5th Floor Plan
| 1 | 501 | 1 RK | 233.4712 | 0 | 338.5332 | N | 5th Floor Plan
| 2 | 502 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 3 | 503 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 4 | 504 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 5 | 505 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 6 | 506 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 7 | 507 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 8 | 508 | 1 RK | 236.2698 | 0 | 342.5912 | N |  |  |  | 21.95 | 21.53 | 20.69
| 9 | 509 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 10 | 510 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 11 | 511 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 12 | 512 | 1 RK | 236.2698 | 0 | 342.5912 | N
| 13 | 513 | 1 RK | 231.3722 | 0 | 335.4897 | N
| 14 | 514 | 1 RK | 231.3722 | 0 | 335.4897 | N
| 15 | 515 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 16 | 516 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 17 | 517 | 1 RK | 233.4712 | 0 | 338.5332 | N
| 18 | 518 | 1 RK | 233.4712 | 0 | 338.5332 | N |  | 72
(Building No.4 Type - 4) Building Name: 'B'
Ground Floor is For parking & Commercial | [9 empty] | 10.764
| 1 | 1 | Shop | 87.1884 | 43.5942 | 178.7362 | N | Ground Floor
| 2 | 2 | Shop | 182.6651 | 50.8061 | 333.937 | N
| 3 | 3 | Shop | 212.4814 | 83.5286 | 412.8747 | N
| 4 | 4 | Shop | 87.1884 | 43.5942 | 178.7362 | N
| 5 | 5 | Shop | 87.1884 | 43.5942 | 178.7362 | N
| 6 | 6 | Shop | 212.4814 | 83.5286 | 412.8747 | N
| 7 | 7 | Shop | 212.4814 | 83.5286 | 412.8747 | N |  |  | 1.9431
| 8 | 8 | Shop | 87.1884 | 43.5942 | 178.7362 | N
| 9 | 9 | Shop | 87.1884 | 43.5942 | 178.7362 | N
| 10 | 10 | Shop | 212.4814 | 83.5286 | 412.8747 | N
| 11 | 11 | Shop | 182.6651 | 50.8061 | 333.937 | N
| 12 | 12 | Shop | 87.1884 | 43.5942 | 178.7362 | N
| 1 | 1 | 1BHK | 341.0573 | 0 | 494.5331 | N
| 2 | 2 | 1BHK | 321.736 | 0 | 466.5171 | N
| 3 | 3 | 1BHK | 333.8455 | 0 | 484.0759 | N
| 4 | 4 | 1BHK | 341.0573 | 0 | 494.5331 | N
| 5 | 5 | 1BHK | 341.0573 | 0 | 494.5331 | N
| 6 | 6 | 1BHK | 341.0573 | 0 | 494.5331 | N
1st Floor
| 1 | 101 | 1BHK | 321.736 | 0 | 466.5171 | N | 1st Floor
| 2 | 102 | 1BHK | 321.736 | 40.8494 | 507.3665 | N
| 3 | 103 | 1BHK | 321.736 | 40.8494 | 507.3665 | N
| 4 | 104 | 1BHK | 321.736 | 40.8494 | 507.3665 | N
| 5 | 105 | 1BHK | 328.9478 | 40.8494 | 517.8237 | N
| 6 | 106 | 1BHK | 328.9478 | 40.9032 | 517.8776 | N
| 7 | 107 | 1BHK | 328.9478 | 0 | 476.9744 | N
| 8 | 108 | 1BHK | 328.9478 | 0 | 476.9744 | N
| 9 | 109 | 1BHK | 328.9478 | 0 | 476.9744 | N
| 10 | 110 | 1BHK | 328.9478 | 0 | 476.9744 | N
| 11 | 111 | 1BHK | 328.9478 | 0 | 476.9744 | N
| 12 | 112 | 1BHK | 328.9478 | 0 | 476.9744 | N |  | 12
2nd Floor
| 1 | 201 | 1BHK | 333.8455 | 0 | 484.0759 | N | 2nd Floor
| 2 | 202 | 1BHK | 333.8455 | 0 | 484.0759 | N
| 3 | 203 | 1BHK | 333.8455 | 0 | 484.0759 | N
| 4 | 204 | 1BHK | 333.8455 | 0 | 484.0759 | N
| 5 | 205 | 1BHK | 341.0573 | 0 | 494.5331 | N
| 6 | 206 | 1BHK | 341.0573 | 0 | 494.5331 | N
| 7 | 207 | 1BHK | 341.0573 | 0 | 494.5331 | N
| 8 | 208 | 1BHK | 333.8455 | 0 | 484.0759 | N
| 9 | 209 | 1BHK | 333.8455 | 0 | 484.0759 | N
| 10 | 210 | 1BHK | 341.0573 | 0 | 494.5331 | N
| 11 | 211 | 1BHK | 341.0573 | 0 | 494.5331 | N |  | 12
| 12 | 212 | 1BHK | 341.0573 | 0 | 494.5331 | N
3rd Floor
| 1 | 301 | 1BHK | 333.8455 | 0 | 484.0759 | N | 3rd Floor
| 2 | 302 | 1BHK | 333.8455 | 0 | 484.0759 | N
| 3 | 303 | 1BHK | 333.8455 | 0 | 484.0759 | N
| 4 | 304 | 1BHK | 333.8455 | 0 | 484.0759 | N
| 5 | 305 | 1BHK | 341.0573 | 0 | 494.5331 | N
| 6 | 306 | 1BHK | 341.0573 | 0 | 494.5331 | N
| 7 | 307 | 1BHK | 341.0573 | 0 | 494.5331 | N
| 8 | 308 | 1BHK | 333.8455 | 0 | 484.0759 | N
| 9 | 309 | 1BHK | 333.8455 | 0 | 484.0759 | N
| 10 | 310 | 1BHK | 341.0573 | 0 | 494.5331 | N
| 11 | 311 | 1BHK | 341.0573 | 0 | 494.5331 | N
| 12 | 312 | 1BHK | 341.0573 | 0 | 494.5331 | N
4th & 5th Floor
| 1 | 301 | 1BHK | 333.8455 | 0 | 484.0759 | N | 4th & 5th Floor
| 2 | 302 | 1BHK | 333.8455 | 0 | 484.0759 | N
| 3 | 303 | 1BHK | 333.8455 | 0 | 484.0759 | N
| 4 | 304 | 1BHK | 333.8455 | 0 | 484.0759 | N
| 5 | 305 | 1BHK | 341.0573 | 0 | 494.5331 | N |  |  |  | 29.755
| 6 | 306 | 1BHK | 341.0573 | 0 | 494.5331 | N
| 7 | 307 | 1BHK | 341.0573 | 0 | 494.5331 | N
| 8 | 308 | 1BHK | 333.8455 | 0 | 484.0759 | N |  |  |  | 29.755 | 1.125 | 30.88 | 332.3923
| 9 | 309 | 1BHK | 333.8455 | 0 | 484.0759 | N |  |  |  | 29.74
| 10 | 310 | 1BHK | 341.0573 | 0 | 494.5331 | N
| 11 | 311 | 1BHK | 341.0573 | 0 | 494.5331 | N |  |  |  | 24.185 | 5.625 | 29.81 | 320.8748
| 12 | 312 | 1BHK | 341.0573 | 0 | 494.5331 | N
Construction details: |  | Building Type 1 = G + 1st to 5th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 5
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% |  | 100% |  | 100% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% | [5 empty] | Excavation Completed | 5
RCC |  | 6 | 100% | [5 empty] | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 5 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 5 | 100% | [5 empty] | Plinth in process | 3.75
Possession |  | 5 | 100% | [5 empty] | Plinth completed | 5
Construction details: |  | Building Type 2A = G + 1st to 5th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 5 Slab, Brickwork upto 4 Floor, Internal Plaster upto 4 Floor, External Plaster upto 4 Floor, Flooring upto 4 Floor, Painting upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 5
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 5 Slab, Brickwork upto 4 Floor, Internal Plaster upto 4 Floor, External Plaster upto 4 Floor, Flooring upto 4 Floor, Painting upto 2 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% |  | 73.33% |  | 86% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% | [5 empty] | Excavation Completed | 5
RCC |  | 5 | 83.33% | [5 empty] | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 4 | 80% | [5 empty] | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 4 | 80% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 80% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 80% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 2 | 40% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 5
Construction details: |  | Building Type 2B = G + 1st to 5th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 4.5 Floor, Internal Plaster upto 4 Floor, External Plaster upto 4 Floor, Flooring upto 4 Floor, Painting upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 5
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 4.5 Floor, Internal Plaster upto 4 Floor, External Plaster upto 4 Floor, Flooring upto 4 Floor, Painting upto 2 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% |  | 80.75% |  | 91.5% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% | [5 empty] | Excavation Completed | 5
RCC |  | 6 | 100% | [5 empty] | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 4.5 | 90% | [5 empty] | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 4 | 80% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 80% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 80% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 2 | 40% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 5
Construction details: |  | Building Type 3 = G + 1st to 5th Floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 5
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% |  | 90% |  | 95% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% | [5 empty] | Excavation Completed | 5
RCC |  | 6 | 100% | [5 empty] | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 5 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 5
Construction details: |  | Building Type 4 = G + 1st to 5th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 3 Slab, Brickwork upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 5
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab, Brickwork upto 1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% |  | 31.5% |  | 61% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% | [5 empty] | Excavation Completed | 5
RCC |  | 3 | 50% | [5 empty] | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 1 | 20% | [5 empty] | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 5
Remarks : 1. Building Type 1 - All work Complete. Please provide OC. Occupancy seems to be less( 20 30% only) in building no.1 since building is completed on dtd 07/06/2022. Building Type 2(A Wing), (B Wing) - Construction work is same Since visit dtd. 11/01/2024. Building Type 3 (D Wing) - Some Flats Occupied by tenants but Construction work is the same as last visit (dtd.05/10/2024). Building Type 4 - Construction work is same Since visit dtd. 13/04/2024. 2. We have considered Saleable area of Residential & Commercial as per our Calculation. 3. As per provided builder conformation letter we are mention the building name & building type. 4. We have considered rate by verifying it from market inquire. 5. We have considered Other charges from cost sheet. 6. As per RERA, completion period of project Udaan Aria is expired on 31/07/2024 but still project is under construction. 6. We have updated All Wings approved plans & CC on 16/12/2022 7. On site, we meet Mr. Yadav : 7064800625.
Sr.No | Building Name As per Plan |  |  |  | Building Name As per Builder
1 | Building Type 1 |  |  |  | Building A
2 | Building Type 2 |  |  |  | Building C
3 | Building Type 3 |  |  |  | Building D
4 | Building Type 4 |  |  |  | Building B
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per builder's sale plan.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  |  |  | Udaan Aria
Layout Plan :
Google Map :
Type 3 Bldg 3 (D)
Type 2 Bldg C
Type 4 Bldg 4 (B)
Type 1 Bldg 1
A
B
D
C Building (A Wing )
C Building (B Wing )
Type 1
Type 2A
Type 2B
Type 3
Type 4
Type 4
Type 1
Type 2A
Type 2B
Type 3
Type 4
Type 4
Type 1
Type 2A
Type 2B
Type 3
Type 4

## 1
Particulars | totaL floor | 5
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 6 | 6 | 100 | Progress |  |  | 10 | 40 | 15 | 10 | 10 | 4 | 1.5
Bricks | Total Floor | completed Floor | 100 | Recommended |  |  | 30 | 30 | 15 | 10 | 5 | 4 | 1.5
| 5 | 5 | 100
plaster | Total Floor | completed Floor | 80
| 5 | 5 | 30
Flooring | Total Floor | completed Floor
| 5 | 5 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 4 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 5 | 1.5 |  | Plaster | 10 | 10
|  |  |  | Flooring | 10 | 5
|  |  |  | Wood & painting | 4 | 4
|  |  |  | Finishing | 1.5 | 1.5
|  |  |  | total | 90.5 | 95.5

## 2A
Particulars | totaL floor | 5
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 83.3333 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 6 | 5 | 80 | Progress |  |  | 10 | 33.3333 | 12 | 8 | 8 | 4 | 1
Bricks | Total Floor | completed Floor | 80 | Recommended |  |  | 30 | 25 | 12 | 8 | 4 | 4 | 1
| 5 | 4 | 80
plaster | Total Floor | completed Floor | 80
| 5 | 4 | 20
Flooring | Total Floor | completed Floor
| 5 | 4 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 4 |  | RCC | 33.3333 | 25
Finishing | Total Floor | completed Floor |  | Bricks | 12 | 12
| 5 | 1 |  | Plaster | 8 | 8
|  |  |  | Flooring | 8 | 4
|  |  |  | Wood & painting | 4 | 4
|  |  |  | Finishing | 1 | 1
|  |  |  | total | 76.3333 | 84

## 2B
Particulars | totaL floor | 5
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 83.3333 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 6 | 5 | 80 | Progress |  |  | 10 | 33.3333 | 12 | 8 | 8 | 4 | 1
Bricks | Total Floor | completed Floor | 80 | Recommended |  |  | 30 | 25 | 12 | 8 | 4 | 4 | 1
| 5 | 4 | 80
plaster | Total Floor | completed Floor | 80
| 5 | 4 | 20
Flooring | Total Floor | completed Floor
| 5 | 4 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 4 |  | RCC | 33.3333 | 25
Finishing | Total Floor | completed Floor |  | Bricks | 12 | 12
| 5 | 1 |  | Plaster | 8 | 8
|  |  |  | Flooring | 8 | 4
|  |  |  | Wood & painting | 4 | 4
|  |  |  | Finishing | 1 | 1
|  |  |  | total | 76.3333 | 84

## 3
Particulars | totaL floor | 5
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 83.3333 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 6 | 5 | 80 | Progress |  |  | 10 | 33.3333 | 12 | 8 | 8 | 4 | 1
Bricks | Total Floor | completed Floor | 80 | Recommended |  |  | 30 | 25 | 12 | 8 | 4 | 4 | 1
| 5 | 4 | 80
plaster | Total Floor | completed Floor | 80
| 5 | 4 | 20
Flooring | Total Floor | completed Floor
| 5 | 4 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 4 |  | RCC | 33.3333 | 25
Finishing | Total Floor | completed Floor |  | Bricks | 12 | 12
| 5 | 1 |  | Plaster | 8 | 8
|  |  |  | Flooring | 8 | 4
|  |  |  | Wood & painting | 4 | 4
|  |  |  | Finishing | 1 | 1
|  |  |  | total | 76.3333 | 84

## 4
Particulars | totaL floor | 5
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 33.3333 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 6 | 2 | 0 | Progress |  |  | 10 | 13.3333 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 10 | 0 | 0 | 0 | 0 | 0
| 5 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 0 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 0 |  | RCC | 13.3333 | 10
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 5 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 23.3333 | 40

## Sheet3
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3.2 | 3 | 9.6 | CB | 1.2 | 1.65 | 1.98 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.7 | 1.8 | 4.86 | CB | 2.1 | 0.45 | 0.945 |  |  | 0
|  |  |  | 0 | FB | 1.5 | 3 | 4.5 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 1.5 | 2.2 | 3.3 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.2 | 1.4 | 1.68 | DB |  |  | 0 |  |  | 0
| toilet2 | 1 | 1.4 | 1.4 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 2.7 | 1 | 2.7 |  |  |  | 0 |  |  | 0
| passage2 | 1.4 | 1.5 | 2.1 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 275.989 | 25.64 |  |  | 79.9227 | 7.425 |  | 0 | 0
|  |  | 355.9117 | 33.065

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
commonfloor. | Udaan Aria | 1BHK | 0 | 542 | 3529.5203 | 1913000
commonfloor. | Udaan Aria | 1BHK | 0 | 719 | 3529.9026 | 2538000
commonfloor. | Udaan Aria | 1RK | 0 | 390 | 3528.2051 | 1376000
commonfloor. | Udaan Aria | 1RK | 0 | 453 | 3529.8013 | 1599000
Average |  |  |  |  | 3529.3573
Valuation Adopted |  |  |  |  | 3500