## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/07/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-07-11
Name of the builder group |  |  |  | Xrbia Warai Developers Private Limited
Name of the builder company |  |  |  | Xrbia Warai Developers Private Limited
Name of the Project |  |  |  | Xrbia Warai / Neral D1 to D5
Contact Details ( Name & Contact No.) |  |  |  | Atish - 9022992324
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Uday Gavli - 9737065882
Name / No of the Building |  |  |  | D1 to D5
Docouments Provided |  |  |  | Refer Data
RERA No. |  |  |  | Phase 1 - P52000002828 (D1 to D5)
Project location details |  | Xrbia Warai / Neral D1 to D5, Survey No.6/2, 6/3, 9/1, 9/2, 10/2A+2B (New S.No.10/2A/1), 10/4+5B ( New S.No.10/4A/2), 10/6, 10/9, 12/1+2+3 (New S.No.12/1A/1), 12/6+7+8 ( New S.No. 12/6A), 12/5, near Forest Escape Resort, Karjat - Murbad Road, Warai, Neral, Karjat, Raigad , 410101.
Survey No |  | 6/2, 6/3, 9/1, 9/2, 10/2A+2B (New S.No.10/2A/1), 10/4+5B ( New S.No.10/4A/2), 10/6, 10/9, 12/1+2+3 (New S.No.12/1A/1), 12/6+7+8 ( New S.No. 12/6A), 12/5
Road |  | Karjat - Murbad Road |  | Locality/Village |  | Warai
City |  | Neral |  | District |  | Raigad
Taluka |  | Karjat |  | Pin Code |  | 410101
Nearby Landmark |  | Forest Escape Resort |  | Distance from city centre: |  | 7.9 from Neral Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Poshir River
South | NA | NA |  |  | Internal Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.084895,73.346369
Location Link |  | https://goo.gl/maps/SAGTX8isKDi8ETEn9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | NA
Permissible FSI |  |  |  | NA
Permissible TDR/Paid FSI |  |  |  | NA
Total FSI availaible for the project |  |  |  | NA
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | NA
Total number of Buildings |  |  |  | 05 Building
Approval Detail : Plan approval
Layout Approval No |  | NA |  |  | Dated | NA
Approved Floor plan No. |  | NA |  |  | Dated | NA
Commencement Certificate No. |  | MS/N.L.A.1(B)/P.K.147/2015 |  |  | Dated | 2016-06-09
Valid Up to: Building D1 to D5 = G + 1st to 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | NA
Approved no of units |  |  | NA
Approved no of Floors |  |  | Building D1 to D5 = G + 1st to 4th Floor
Proposed no of Floors |  |  | Building D1 = G + 1st to 4th Floor
Building D2 & D3 = G + 1st to 4th Floor
Building D4 & D5 = G + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 29/12/2022
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building D1 = G + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster upto 3 Floor Completed, External Plaster upto 3 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster upto 3 Floor Completed, External Plaster upto 3 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 70.62% |  | 87.5% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 3 | 75% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building D2 & D3 = G + 1st to 4th Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | All work completed. Please provide OC. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 100% |  | 100% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 100% |  |  |  |  | Plinth in process | 3
Possession |  | 4 | 100% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building D4 & D5 = G + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster upto 1 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster upto 1 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 59.38% |  | 81.25% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 1 | 25% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 3800
Development Charges |  |  |  |  | 300000
Grill Charges |  |  |  |  | 40000
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 3040
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
5 |  |  |  | 0 | 0 | Ground Floor
6 |  |  |  | 0 | 0 | Ground Floor
7 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
206 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301,..,1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 301,..,1501 | 301 | 1501
302,..,1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 302,..,1502 | 302 | 1502
303,..,1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 303,..,1503 | 303 | 1503
304,..,1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 304,..,1504 | 304 | 1504
305,..,1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 305,..,1505 | 305 | 1505
306,..,1506 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | 306,..,1506 | 306 | 1506
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor |  |  |  | 201 to 501 | 201 | 501
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor |  |  |  | 202 to 502 | 202 | 502
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor |  |  |  | 203 to 503 | 203 | 503
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor |  |  |  | 204 to 504 | 204 | 504
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor |  |  |  | 205 to 505 | 205 | 505
206 to 506 |  |  |  | 0 | 0 | 2nd to 5th Floor |  |  |  | 206 to 506 | 206 | 506
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 201 & 501 | 201 | 501
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 202 & 502 | 202 | 502
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 203 & 503 | 203 | 503
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 204 & 504 | 204 | 504
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 205 & 505 | 205 | 505
206 & 506 |  |  |  | 0 | 0 | 2nd & 5th Floor |  |  |  | 206 & 506 | 206 | 506
Remarks:
1 | Building D2 & D3 - All work completed. Please provide OC. Building D1 - Construction work is same as last visit. (10/07/2023) Building D4 & D5 - Construction work is same as last visit. (13/01/2023) ( Internal visit was not allowed.) | [6 empty] | on Visit dtd 15/07/2024. Due to rain unable to take photos for all Wings/Buildings
2 | We have considered rate by verifying it from market inquire.
3 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
4 | Car parking is subjected to authentic documentation.
5 | According to our observations, the construction of Xrbia projects (Xrbia Warai, Xrbia Vangani, etc.)appears to have slowed or stopped over the past two years.
6 | As per RERA, completion period of project Phase I - Xrbia Warari (D4 & D5) is expired on Date 29/12/2022 but still project is under construction.
7 | We have considered rate by verifying it from market inquire.
8 | Car parking is subjected to authentic documentation.
9 | On Site, we meet Mr........(........).
7 | The project has received first CC on 09/06/2016, But construction work is not yet completed.
8 | Notice Attached Below.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Naynesh Sunil Lovanshi |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Xrbia Warai / Neral D1 to D5
Notice :
Google Map :
D1
D2
D3
D4
D5

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted