## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 18/07/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-07-16
Name of the builder group |  |  |  |  | M/s.Vrindavan Land Developers
Name of the builder company |  |  |  |  | M/s.Vrindavan Land Developers
Name of the Project |  |  |  |  | Madhuban
Contact Details ( Name & Contact No.) |  |  |  |  | 2225602843
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  |  | Mr.Vijay Kumar 8767834646
Name / No of the Building |  |  |  |  | Building Type A (A & B Wing) Building Type B (A Wing)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | P52000019615
Project location details |  | Madhuban, Gaonthan, Ghar No 245, Karjat - Neral Road, Umroli, Karjat, Raigad.
Gaonthan |  | Ghar No 245 |  |  |  |  | Locality | Umroli
Road | Karjat - Neral Road |  |  |  | District | Raigad
City | Karjat |  |  |  | Pin Code | 410201
Near by Landmark |  | Paresh Ghare Farm House |  |  | Distance from city centre: |  | 1.8 Km from Bhivpuri Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Road |  | Open Plot |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 18.9583873,73.3237788
Location Link |  | https://goo.gl/maps/EfmpYEkqi62RUMax9?coh=178572&entry=tt
Approval details:
Approved usage of the Property: |  |  |  |  | Residential + Commercial
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 2214.58
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 2214.58
Total number of Buildings |  |  |  |  | 02 Buildings (03 Wings)
Approval Detail : Plan approval
Layout Approval No |  | BP/M.UMROLI/T.KARJAT/285 |  |  |  | Dated | 07/02/2019.
Approved Floor plan No. |  | BP/M.UMROLI/T.KARJAT/285 |  |  |  | Dated | 07/02/2019.
Commencement Certificate No. |  | SSNR-RA/BP/M.UMROLI/T.KARJAT/285 Valid Up to: Building Type A (A & B wing) = G + 4th Floor Building Type B = G + 4th Floor |  |  |  | Dated | 07/02/2019.
O. Certificate No.: |  | NA |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 07/02/2019. |  | Expected Completion |  | 2025-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 2214.58 |  | Approved no of units |  | Flats = 78 & Office = 01
Approved no of Floors |  | Building Type A (A & B wing) = G + 4th Floor Building Type B = G + 4th Floor
Quality of construction: Average |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Type A (A wing) = G + 4th Floor | [6 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 |  | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [6 empty] | Completed
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 100% |  | 100% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 4 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 100% | [5 empty] | Plinth in process | 3
Possession |  | 4 | 100% | [5 empty] | Plinth completed | 4
Construction details: |  | Type A (B wing) = G + 4th Floor | [6 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 3.5 Floor, Flooring upto 2 Floor, Painting upto 2 Floor Completed | , External Plaster upto 3.5 Floor, Flooring upto 2 Floor, Painting upto 2 Floor
Basement | 0 | Ground | 1 |  | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 3.5 Floor, Flooring upto 2 Floor, Painting upto 2 Floor Completed | [6 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 81.25% |  | 91.88% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3.5 | 87.5% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 50% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 2 | 50% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Type B (A Wing) = G + 4th Floor | [6 empty] | Excavation, Plinth Completed, RCC upto 2 Slab Completed | , RCC upto 2 Slab
Basement | 0 | Ground | 1 |  | Podium | 0 | Floors | 4 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 2 Slab Completed | [6 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 26% |  | 57% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 2 | 40% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | : 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3100
Recommended rate of the Office Per Sq. Ft. ( on Saleable area) | [5 empty] | 4000
Other Charges | [5 empty] | 150000/-
Maintenance for 1 Year | [5 empty] | 15000/-
Recommended rate of Parking | [5 empty] | 50000/-
Distressed valuation of the Property | [5 empty] | 2480
Building & Wing |  | Total Flat | Total Carpet Area |  |  | Total Saleable Area
Building A Type A Total Area Details :
A Wing |  | 25 | 10338.822 |  |  | 14751
B Wing |  | 25 | 10025.299 |  |  | 14818
Building B Type B Total Area Details :
A Wing |  | 28 | 9708.2669 |  |  | 13694
Grand Total |  | 78 | 30072.3879 |  |  | 43263
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Building Type - A
A wing
Ground Floor is For Parking
1st To 3rd Floor is For Residential
1 |  | 1BHK | 451.0923 |  | 0 | 622 | N | 1st To 3rd Floor
2 |  | 1BHK | 470.7097 |  | 0 | 665 | N
3 |  | 1BHK | 460.5377 |  | 0 | 660 | N
4 |  | 1RK | 340.869 |  | 0 | 500 | N
5 |  | 1RK | 330.5355 |  | 0 | 415 | N
6 |  | 1BHK | 460.5377 |  | 0 | 665 | N
7 |  | 1BHK | 440.9203 |  | 0 | 622 | N
4th Floor
1 |  | Open Terrace |  |  |  |  | N | 4th Floor
2 |  | 1RK | 312.5058 |  | 0 | 564 | N
3 |  | 1BHK | 401.4972 |  | 0 | 660 | N
4 |  | Open Terrace |  |  |  |  | N
5 |  | 1RK | 275.5315 |  | 0 | 415 | N |  |  | 1.5062
6 |  | 1BHK | 483.6803 |  | 0 | 665 | N
7 |  | Open Terrace |  |  |  |  | N
B wing
Ground Floor is For Parking & Residential
1 |  | Office | 212.8043 |  | 0 | 319.2064 | N | Ground Floor
2 |  | 1RK | 264.9343 |  | 0 | 500 | N
1st To 3rd Floor is For Residential
1 |  | 1BHK | 440.9203 |  | 0 | 622 | N | 1st To 3rd Floor
2 |  | 1BHK | 460.5377 |  | 0 | 665 | N
3 |  | 1RK | 282.3128 |  | 0 | 415 | N
4 |  | 1RK | 339.7926 |  | 0 | 500 | N
5 |  | 1BHK | 450.8501 |  | 0 | 660 | N
6 |  | 1BHK | 470.7097 |  | 0 | 665 | N
7 |  | 1BHK | 451.0923 |  | 0 | 622 | N
4th Floor
1 |  | Open Terrace |  |  |  |  | N | 4th Floor
2 | [6 empty] | N
3 |  | 1RK | 312.5058 |  | 0 | 665 | N
4 |  | Open Terrace |  |  |  |  | N
5 |  | 1RK | 275.5315 |  | 0 | 660 | N
6 |  | 1BHK | 483.6803 |  | 0 | 546 | N
7 |  | Open Terrace |  |  |  |  | N
Building Type B
A wing
Ground Floor is For Parking
1st To 3rd Floor is For Residential
1 |  | 1BHK | 427.8152 |  | 0 | 560 | N | 1st To 3rd Floor
2 |  | 1BHK | 427.8152 |  | 0 | 560 | N
3 |  | 1BHK | 404.9417 |  | 0 | 561 | N
4 |  | 1RK | 246.3341 |  | 0 | 351 | N
5 |  | 1RK | 240.3601 |  | 0 | 351 | N
6 |  | 1BHK | 403.6231 |  | 0 | 564 | N
7 |  | 1BHK | 403.6231 |  | 0 | 564 | N
4th Floor
1 |  | 1RK | 287.7486 |  | 58 | 475 | N | 4th Floor
2 |  | 1RK | 287.7486 |  | 58 | 475 | N
3 |  | 1BHK | 404.9417 |  | 0 | 561 | N
4 |  | 1RK | 246.3341 |  | 0 | 351 | N
5 |  | 1RK | 240.3601 |  | 0 | 351 | N
6 |  | 1RK | 288.825 |  | 0 | 474 | N
7 |  | 1RK | 288.7712 |  | 0 | 474 | N
Remarks:
1. Building Type A (A Wing) = All work completed. Provide OC Building Type A (B Wing) = Construction work is stopped. Work is same as last visit (dtd.11/11/2024). Building Type B (A Wing) = Construction work is stopped. Work is same as last visit (dtd.02/11/2022). 2. We considered Saleable area as per Builder area sheet. 3. We considered Carpet area as per Approved Plan. 4. We have considered rate by verifying it from market inquire. 5. We have considered Other charges from cost sheet. 6. Car parking is subjected to authentic documentation. 7. Construction work of Building Type - B = (A Wing) is stopped because they want to complete first building type A. 8. In Building Type A- Wing A, there is Parking on Ground Floor in place of flat no.1, 2 as per approved plan & as per sale plan there is 1BHK, 1RK flats respectively. 9. In Building Type A- Wing B, there is Parking on Ground Floor in place of flat no.3 as per approved plan & as per sale plan there is 1BHK flat. 10. In Building Type A- Wing A & B, on there is partially residential & partially Natural Terrace on 4th Floor as per Approved Plan & as per sale plan whole floor is for residential. 11. As per RERA, completion period of project Madhuban is expired on 31/12/2024 but still project is under construction. 11. On site we met Mr. Vijay : 8767834646.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Madhuban
Google Map :
Type B (A wing)
Type A (B wing)
Bldg Type B (A Wing)
Bldg Type A (A Wing)
Bldg Type A (B Wing)
Bldg Type A (A Wing)
Bldg Type A (B Wing)
Bldg Type B (A Wing)

## C%
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 6 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 60 | Recommended |  |  | 30 | 30 | 15 | 6 | 0 | 0 | 0
| 4 | 4 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 2.4 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 4 | 0 |  | Plaster | 6 | 6
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 71 | 81

## C% (2)
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 40 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 2 | 25 | Progress |  |  | 10 | 16 | 3.75 | 1.25 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 12.5 | Recommended |  |  | 30 | 12 | 3.75 | 1.25 | 0 | 0 | 0
| 4 | 1 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 0.5 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 16 | 12
Finishing | Total Floor | completed Floor |  | Bricks | 3.75 | 3.75
| 4 | 0 |  | Plaster | 1.25 | 1.25
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 31 | 47

## C% (3)
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 0 | 0 | Progress |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 4 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 10 | 30

## Note
2020-10-23 | Pratiksha

## Valuation
23/10/2020. | Pratiksha
Market Research Data
| Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
| Housing | Madhuban | 1RK | 350 | 507.5 | 2124.1379 | 1078000
| Housing | Madhuban | 1BHK | 660 | 957 | 2124.3469 | 2033000
| Average |  |  |  |  | 2124.1379
| Valuation Adopted |  |  |  |  | 2200

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3.6 | 3.05 | 10.98 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.2 | 2.15 | 4.73 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.8 | 1.2 | 2.16 | DB |  |  | 0 |  |  | 0
| toilet2 | 1 | 1.2 | 1.2 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 0.75 | 3.05 | 2.2875 |  |  |  | 0 |  |  | 0
| passage2 | 1.5 | 2.15 | 3.225 |  |  |  | 0 |  |  | 0
| passage3 | 1 | 2.15 | 2.15 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 287.7486 | 26.7325 |  |  | 0 | 0 |  | 0 | 0
|  |  | 287.7486 | 26.7325