## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 09/07/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Sanpada | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-07-08 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | M/s. Kamdhenu Lifespaces | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | M/s. Kamdhenu Lifespaces | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Kamdhenu Grandeur | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | 9833904791
Site Person - Contact Details (Name & Contact No.) |  |  |  | NA |  |  |  | Mr. Amey 9833904791
Name / No of the Building |  |  |  | 01 Building
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans & CC | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51700055665 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Kamdhenu Grandeur, Plot No.18 & 25, Sector No. 8, near Goodwill Unity, Sanpada Road, Sanpada, Sanpada, Sanpada West, Thane, Thane - 400705. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Plot No |  | 18 & 25, Sector No. 8 | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Sanpada | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Sanpada Road |  | Locality/Village |  | Sanpada | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Sanpada West |  | District |  | Thane | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Thane |  | Pin Code |  | 400705 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Goodwill Unity |  | Distance from city centre: |  | 1.0 KM from Sanpada Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | 15.00 M. Wide Road |  |  | Chemist Bhavan Road
West | NA | 15.00 M. Wide Road |  |  | Sanpada Road
North | NA | Other Plot |  |  | Malhar 24 East
South | NA | Other Plot |  |  | Goodwill Unity
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.060341,73.009178
Location Link |  | https://maps.app.goo.gl/KxTXrLSss2xbr51u5
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 4367.61
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 3.6727
Total FSI availaible for the project |  |  |  | 4.7727
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 20845.467
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Navi Mumbai Municipal Corporation (NMMC) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | NRV/A-706 |  |  | Dated | 2024-03-12 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | NRV/A-706 |  |  | Dated | 2024-03-12 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Municipal Corporation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | NNMC/TPO/BP/706/2024 |  |  | Dated | 2024-03-12 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Proposed Builtup Area = 20845.467 Sq.M No.of Residential Unit - 210 Commercial Unit (Shop - 06 & Office - 06) EWS Unit -17 | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  | Total Proposed Builtup Area = 20845.467 Sq.M No.of Residential Unit - 210 Commercial Unit (Shop - 06 & Office - 06) EWS Unit -17 |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgaon Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 0 |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
[18 empty] | Bhiwandi Nizampur City Municipal Corporation | Nagar Rachana And Mulya Nirdharan Vibhag, Raigad -Alibag
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 20845.467
Approved no of units |  |  | Sale Flats - 210, Shops - 6, Offices - 6, EWS Flat - 17
Approved no of Floors |  |  | Gr + 1st & 2nd + P3 & P4 + 5th to 42nd Floor
Proposed no of Floors |  |  | Gr + 1st & 2nd + P3 & P4 + 5th to 42nd Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Gymnasium, Garden, Lift, Play Area, Cafeteria, Power Backup, Swimming Pool, Intercom, Fire Safety Security etc, |  |  |  |  | http://www.kamdhenugrandeur.com/
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Part I = Gr + 1st & 2nd + P3 & P4 + 5th to 42nd Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 6 Slab Completed | , RCC upto 6 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 42 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 6 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 10.5
Excavation |  | 42 | 100% | 15.58% |  | 49.19% |  | Excavation in process | 21
Plinth |  | 42 | 100% |  |  |  |  | Excavation Completed | 42
RCC (Including podiums) |  | 6 | 13.95% |  |  |  |  | Footing in Process | 10.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 21
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 31.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 42
Construction details: |  | Part II = Gr + 1st & 2nd + P3 & P4 + 5th to 42nd Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 29 Slab, Brickwork upto 24 Floor, Internal Plaster upto 18 Floor, External Plaster upto 18 Floor Completed | , RCC upto 29 Slab, Brickwork upto 24 Floor, Internal Plaster upto 18 Floor, External Plaster upto 18 Floor | [6 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 42 | Excavation, Plinth | [8 empty] | 800000 | 150000 | 100000 | 100000
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 29 Slab, Brickwork upto 24 Floor, Internal Plaster upto 18 Floor, External Plaster upto 18 Floor Completed | [5 empty] | Completed | Completed | [7 empty] | 900000 | 200000 | 150000 | 150000
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 10.5 | [7 empty] | 1000000 | 250000 | 200000 | 200000
Excavation |  | 42 | 100% | 48.76% |  | 72.38% |  | Excavation in process | 21 | [7 empty] | 1100000 | 300000 | 250000 | 250000
Plinth |  | 42 | 100% |  |  |  |  | Excavation Completed | 42 | [7 empty] | 1200000 | 350000 | 300000 | 300000
RCC (Including podiums) |  | 29 | 67.44% |  |  |  |  | Footing in Process | 10.5 | [7 empty] | 1300000 | 400000 | 350000 | 400000
Brickwork | Brickwork & Internal Plaster | 24 | 57.14% |  |  |  |  | Footing Completed | 21 | [7 empty] | 1400000 | 500000 | 400000
Internal Plaster | Brickwork & Internal Plaster | 18 | 42.86% |  |  |  |  | Basement 1 | 0 | [7 empty] | 1500000 | 600000 | 500000
Ext. Plaster & Plumbing | External Plaster & Plumbing | 18 | 42.86% |  |  |  |  | Basement 2 | 0 | [7 empty] | 1600000 | 700000 | 600000
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0 | [7 empty] | 1700000 | 800000
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0 | [7 empty] | 1800000 | 900000
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 31.5 | [8 empty] | 1000000
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 42
Average Progress % |  | 32.17% |  | Average Disbursement % |  | 60.78%
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 15000 |  |  | 14500 to 15000 & 7L |  | Bhargav | 2024-08-19 | cost sheet
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 22000 |  |  | Sale area changes 1163 to 1262 for staff case by bhargav on 19/08/2024
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 20000
Floor Rise Rate from Floor
Development Charges
Club Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 700000
Distressed valuation of the Property |  |  |  |  | 12000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop |  | 6 |  | 3884.5904 |  | 6021.1151
Office |  | 6 |  | 6828.392 |  | 10584.0077
Total |  | 12 |  | 10712.9824 |  | 16605.1227
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Sale Flat |  | 210 |  | 157330.3914 |  | 238769.9489
Total |  | 210 |  | 157330.3914 |  | 238769.9489
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
EWS Flat |  | 17 |  | 8977.0468 |  | 13465.5702
Total |  | 17 |  | 8977.0468 |  | 13465.5702
Grand Total |  | 239 |  | 177020.4206 |  | 268840.6419
Building Details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
55%
Ground Floor For Commercial, Meter Room, Fire Control Room, Driver's Room & Parking
1 |  | Shop | 763.7623 | 0 | 763.7623 | 0 | 1183.8316
2 |  | Shop | 701.9716 | 0 | 701.9716 | 0 | 1088.0559
3 |  | Shop | 476.3635 | 0 | 476.3635 | 0 | 738.3634
4 |  | Shop | 471.0111 | 0 | 471.0111 | 0 | 730.0672
5 |  | Shop | 701.9716 | 0 | 701.9716 | 0 | 1088.0559
6 |  | Shop | 769.5103 | 0 | 769.5103 | 0 | 1192.7409
1st Floor For Commercial & Parking
1 |  | Office | 1339.9267 | 0 | 1339.9267 | 0 | 2076.8863
2 |  | Office | 732.3535 | 0 | 732.3535 | 0 | 1135.1479
3 |  | Office | 1341.9159 | 0 | 1341.9159 | 0 | 2079.9696
2nd Floor
1 |  | Office | 1339.9267 | 0 | 1339.9267 | 0 | 2076.8863
2 |  | Office | 732.3535 | 0 | 732.3535 | 0 | 1135.1479
3 |  | Office | 1341.9159 | 0 | 1341.9159 | 0 | 2079.9696
Flat No. (Approved Plan) | Sale / EWS | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
3rd & 4th Podium Floor For Parking
5th Floor For Residential & Part Amenities Area
1 | EWS | 1BHK | 537.3712 | 0 | 537.3712 | 0 | 806.0568 | 47.7818
2 | EWS | 2BHK | 526.2843 | 0 | 526.2843 | 0 | 789.4264 | 46.7829
3 | EWS | 2BHK | 526.2843 | 0 | 526.2843 | 0 | 789.4264
4 | EWS | 1BHK | 537.3712 | 0 | 537.3712 | 0 | 806.0568
5 | Creche Area
6 | EWS | 1.5BHK | 455.5325 | 0 | 455.5325 | 0 | 683.2987 | 40.3535
6th & 7th Floor For Residential | [8 empty] | 50.8317
1 | EWS | 1BHK | 537.3712 | 0 | 537.3712 | 0 | 806.0568
2 | EWS | 2BHK | 526.2843 | 0 | 526.2843 | 0 | 789.4264
3 | EWS | 2BHK | 526.2843 | 0 | 526.2843 | 0 | 789.4264
4 | EWS | 1BHK | 537.3712 | 0 | 537.3712 | 0 | 806.0568
5 | EWS | 2BHK | 534.8955 | 0 | 534.8955 | 0 | 802.3432
6 | EWS | 2BHK | 534.8955 | 0 | 534.8955 | 0 | 802.3432
8th, 13th, 18th, 23rd, 28th, 33rd & 38th Floor (Part Refuge Area)
1 | Sale | 2BHK | 785.546 | 0 | 785.546 | 0 | 1178.3189 | 61.4363 | 7.4093 | 68.8456
2 | Sale | 2BHK | 775.2771 | 0 | 775.2771 | 0 | 1162.9156
3 | Sale | 2BHK | 775.2771 | 0 | 775.2771 | 0 | 1162.9156
4 | Sale | 2BHK | 785.546 | 0 | 785.546 | 0 | 1178.3189
5 | Sale | 2BHK | 686.754 | 0 | 686.754 | 0 | 1030.1309
6 | Sale | 2BHK | 686.754 | 0 | 686.754 | 0 | 1030.1309
9th Floor
1 | Sale | 2BHK | 785.546 | 0 | 785.546 | 0 | 1178.3189
2 | Sale | 2BHK | 775.2771 | 0 | 775.2771 | 0 | 1262 | Sale area changes 1163 to 1262 for staff case by bhargav on 19/08/2024
3 | Sale | 2BHK | 775.2771 | 0 | 775.2771 | 0 | 1162.9156
4 | Sale | 2BHK | 785.546 | 0 | 785.546 | 0 | 1178.3189
5 | Sale | 2BHK | 686.754 | 0 | 686.754 | 0 | 1030.1309 |  | 16308.6063
6 | Sale | 2BHK | 686.754 | 0 | 686.754 | 0 | 1030.1309
10th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th to 42nd Floor
1 | Sale | 2BHK | 785.546 | 0 | 785.546 | 0 | 1178.3189
2 | Sale | 2BHK | 775.2771 | 0 | 775.2771 | 0 | 1162.9156
3 | Sale | 2BHK | 775.2771 | 0 | 775.2771 | 0 | 1162.9156
4 | Sale | 2BHK | 785.546 | 0 | 785.546 | 0 | 1178.3189
5 | Sale | 2BHK | 686.754 | 0 | 686.754 | 0 | 1030.1309 |  | 16308.6063
6 | Sale | 2BHK | 686.754 | 0 | 686.754 | 0 | 1030.1309
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Open Balcony Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates / Other charges of the Property have been revised on 19/08/2024.
* | Please check for Environment Clearance Certificate & Fire NOC
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mayur Ranvare |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Kamdhenu Grandeur
Layout :
Google Map :
Formulas:
Sanpada = [Sanpada, row above]
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F108: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H151: SACHIN: Give loading of 50% for A Category
N
Railway Track
Part II
Part I
Part I
Part II
Part I
Part II
Part II
Part I

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
20
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate