## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 09/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-08
Name of the builder |  |  |  | Mr. Wasim shamim Khan
Name of the builder company |  |  |  | M/s. Munish Group of Company
Name of the Project |  |  |  | Munish Glorious
Contact Details ( Name & Contect No.) |  |  |  | Mr. Kalim Shaikh 8691030000
Site person Contact Details ( Name & Contect No.) |  |  |  | Mr. Kalim : 8169083290
Name / No of the Building |  |  |  | Building No. 1, 2, 4 & 5
Docouments Provided |  |  |  | Approved Plans, CC, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | Building No. 1 & 2 = P99000026565 Building No. 4 & 5 = P99000055429
Project location details |  | Munish Glorious, Survey No.11, H No. 5, 7, 8, 9, 10, 20, 21/1, 21/2, 24 and Survey No. 12, H. No.21, 22/1, 22/2, 30, Internal Road, Gokhivare, Vasai-Virar, Vasai, Palghar - 401208.
Survey No |  | 11, H No. 5, 7, 8, 9, 10, 20, 21/1, 21/2, 24 and Survey No. 12, H. No.21, 22/1, 22/2, 30
Road |  | Internal Road |  | Locality/Village |  | Gokhivare
City |  | Vasai-Virar |  | District |  | Palghar
Taluka |  | Vasai |  | Pin Code |  | 401208
Near by Landmark |  | Munish Apartmnet |  | Distance from city centre: |  | 3.10Km from Vasai Road Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Munish Smriti Apartment
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Munish Apartment
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.398369,72.846164
Location Link |  | https://maps.app.goo.gl/GpgzziPqLDcWRAHa8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3596.52
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.66
Total FSI availaible for the project |  |  |  | 1.76
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 6329.87
Total number of Buildings |  |  |  | 04 Buildings
Approval Detail : Plan approval For Building No. 1 & 2
Layout Approval No |  | VVCMC/TP/CC/VP-6194/487/2021-22 |  |  | Dated | 2021-10-06
Approved Floor plan No. |  | VVCMC/TP/CC/VP-6194/487/2021-22 |  |  | Dated | 2021-10-06
Commencement Certificate No. |  | VVCMC/TP/CC/VP-6194/487/2021-22 |  |  | Dated | 2021-10-06
Valid Up to: Building No. 1 & 2 = Gr/Stilt + 7th Floor
Full O. Certificate No. Approved upto : |  | VVCMC/TP/OC/6194/PO/2024/APL/00009 Building No. 1 & 2 = Gr/Stilt + 7th Floor (3308.52 sqmt BUA) |  | Date of approval: | Dated | 2024-02-16
Approval Detail : Plan approval For Building No. 4 & 5
Layout Approval No |  | Not provided |  |  | Dated | NA
Approved Floor plan No. |  | VVCMC/TP/CC/VP-6194/58/2023-24 |  |  | Dated | 2023-07-27
Commencement Certificate No. |  | VVCMC/TP/CC/VP-6194/58/2023-24 |  |  | Dated | 2023-07-27
Valid Up to: Building No. 4 & 5 = Gr/Stilt + 7th Floor
O. Certificate No. Approved upto : |  | NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 5112.85 |  |  |  |  | Building No. 4 & 5 Built up Area added(from CC)in previous BUA of Building No 1 & 2
Approved no of units |  |  | Flats - 174
Approved no of Floors |  |  | Building No. 1 & 2 = Gr/Stilt + 1st to 7th Floor Building No. 4 & 5 = Gr/Stilt + 1st to 7th Floor
Proposed no of Floors |  |  | Building No. 1 & 2 = Gr/Stilt + 1st to 7th Floor
Building No. 4 & 5 = Gr/Stilt + 1st to 7th Floor
Expected Completion |  |  | As per RERA - Building No. 1 & 2 = Completed Building No. 4 & 5 = 31/12/2027
Proposed Amenities : |  |  | Vitrified tiles flooring, Granite Kitchen Platform, Decorative Entrance, etc. | [5 empty] | 63
Projected life of the structure |  |  | 60 Years after completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Violations Observed if any : |  |  | NA
Wheather the construction is as per approved Building plan : |  |  | Under Construction
Construction details: |  | Building No. 1 & 2 = Gr/Stilt + 1st to 7th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 7 Floor completed, Flooring upto 7 Floor completed, Painting upto 7 Floor completed, Finishing upto 7 Floor completed
Ground |  | 1 |  | Podium | 0 | Floors | 7 | All work Completed. OC Received.
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | All work Completed. Provide OC.
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 7 | 100% | 100% |  | 100%
Plinth |  | 7 | 100%
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Excavation in process |  | 3.5
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Excavation Completed |  | 7
Internal Plaster | Brickwork & Internal Plaster | 7 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Footing in Process |  | 1.75
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Footing Completed |  | 3.5
Painting & Wooden |  | 7 | 100% |  |  |  |  | Plinth in process |  | 5.25
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth completed |  | 7
Possession |  | 7 | 100%
Construction details: |  | Building No. 4 = Gr/Stilt + 1st to 7th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 6 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed
Ground |  | 1 |  | Podium | 0 | Floors | 7 | All work Completed. OC Received.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 6 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed | [5 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 7 | 100% | 82.14% |  | 92.14%
Plinth |  | 7 | 100%
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Excavation in process |  | 3.5
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Excavation Completed |  | 7
Internal Plaster | Brickwork & Internal Plaster | 7 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 85.71% |  |  |  |  | Footing in Process |  | 1.75
Flooring & Fitting | Flooring & Fitting | 4 | 57.14% |  |  |  |  | Footing Completed |  | 3.5
Painting & Wooden |  | 4 | 57.14% |  |  |  |  | Plinth in process |  | 5.25
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth completed |  | 7
Possession |  | 0 | 0%
Construction details: |  | Building No. 5 = Gr/Stilt + 1st to 7th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 6 Floor completed, Flooring upto 2 Floor completed
Ground |  | 1 |  | Podium | 0 | Floors | 7 | All work Completed. OC Received.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 6 Floor completed, Flooring upto 2 Floor completed | [5 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 7 | 100% | 76.43% |  | 90.71%
Plinth |  | 7 | 100%
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Excavation in process |  | 3.5
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Excavation Completed |  | 7
Internal Plaster | Brickwork & Internal Plaster | 7 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 85.71% |  |  |  |  | Footing in Process |  | 1.75
Flooring & Fitting | Flooring & Fitting | 2 | 28.57% |  |  |  |  | Footing Completed |  | 3.5
Painting & Wooden |  | 0 | 0% |  |  |  |  | Plinth in process |  | 5.25
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth completed |  | 7
Possession |  | 0 | 0%
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 5000
Development Charges |  |  |  |  | 1,00,000/-
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | 1,00,000/-
Advance Maintenance Charges (2 years) |  |  |  |  | 50000/-
Recommended rate of Parking |  |  |  |  | 100000/-
Distressed valuation of the Property |  |  |  |  | 4000
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 |  | 70 |  | 19907.5067 |  | 30450
Building No.2 |  | 41 |  | 10631.8719 |  | 15895
Building No.4 |  | 35 |  | 8598.5254 |  | 13125
Building No.5 |  | 28 |  | 7244.1451 |  | 11095
Total |  | 174 |  | 46382.0491 |  | 70565
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Building no.1
Ground Floor for Parking
1st to 7th Floor
1 |  | 1RK | 202.3363 | 0 | 310 | 1st to 7th Floor |  | 5000 | 1.5321
2 |  | 1BHK | 340.7613 | 0 | 515 |  |  |  | 1.5113
3 |  | 1BHK | 340.7613 | 0 | 515 |  |  |  | 1.5113
4 |  | 1BHK | 354.5392 | 0 | 535 |  |  |  | 1.509
5 |  | 1BHK | 342.3759 | 0 | 520 |  |  |  | 1.5188
6 |  | 1RK | 239.8488 | 0 | 365 |  |  |  | 1.5218
7 |  | 1RK | 208.2565 | 0 | 335 |  |  |  | 1.6086
8 |  | 1RK | 208.2565 | 0 | 335 |  |  |  | 1.6086
9 |  | 1RK | 256.0487 | 0 | 390 |  |  |  | 1.5231
10 |  | 1BHK | 350.7449 | 0 | 530 |  |  |  | 1.5111
1st to 6th Floor
1 |  | 1BHK | 340.7613 | 0 | 530 | 1st to 6th Floor |  |  | 1.5553
2 |  | 1RK | 205.8346 | 0 | 310 |  |  |  | 1.5061
3 |  | 1BHK | 382.6064 | 0 | 545 |  |  |  | 1.4244
4 |  | 1RK | 206.3728 | 0 | 310 |  |  |  | 1.5021
5 |  | 1RK | 206.3728 | 0 | 310 |  |  |  | 1.5021
6 |  | 1RK | 206.3728 | 0 | 310 |  |  |  | 1.5021
7th Floor(Part Terrace Area)
1 |  | 1BHK | 340.7613 | 0 | 530 | 7th Floor(Part Terrace Area) |  |  | 1.5553
2 |  | 1RK | 205.8346 | 0 | 310 |  |  |  | 1.5061
3 |  | 1BHK | 382.6064 | 0 | 545 |  |  |  | 1.4244
4 |  | Terrace | [6 empty] | #DIV/0!
5 |  | 1RK | 206.3728 | 0 | 310 |  |  |  | 1.5021
6 |  | 1RK | 206.3728 | 0 | 310 |  |  |  | 1.5021
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Ground Floor
1 |  |  | 0 | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | RERA Carpet area | Chajja Area | Gross Carpet area | Attached Terrace area | Builder Saleable Area
50%
Building no.1
Ground Floor for Parking
1st to 7th Floor
1 |  | 1RK | 168.026 | 34.3102 | 202.3363 | 0 | 310 |  |  | 1.5321
2 |  | 1BHK | 280.6175 | 60.1439 | 340.7613 | 0 | 515 |  |  | 1.5113
3 |  | 1BHK | 280.6175 | 60.1439 | 340.7613 | 0 | 515 |  |  | 1.5113
4 |  | 1BHK | 294.3954 | 60.1439 | 354.5392 | 0 | 535 |  |  | 1.509
5 |  | 1BHK | 282.2321 | 60.1439 | 342.3759 | 0 | 520 |  |  | 1.5188
6 |  | 1RK | 204.4084 | 35.4405 | 239.8488 | 0 | 365 |  |  | 1.5218
7 |  | 1RK | 178.79 | 29.4665 | 208.2565 | 0 | 335 |  |  | 1.6086
8 |  | 1RK | 178.79 | 29.4665 | 208.2565 | 0 | 335 |  |  | 1.6086
9 |  | 1RK | 212.0508 | 43.9978 | 256.0486 | 0 | 390 |  |  | 1.5231
10 |  | 1BHK | 290.1974 | 60.5475 | 350.7449 | 0 | 530 |  |  | 1.5111
Building no.2 | [9 empty] | #DIV/0!
Ground Floor for Parking
1st to 6th Floor
1 |  | 1BHK | 280.6175 | 60.1439 | 340.7613 | 0 | 530 |  |  | 1.5553
2 |  | 1RK | 167.4878 | 38.3468 | 205.8346 | 0 | 310 |  |  | 1.5061
3 |  | 1BHK | 322.0589 | 60.5475 | 382.6064 | 0 | 545 |  |  | 1.4244
4 |  | 1RK | 176.099 | 30.2737 | 206.3728 | 0 | 310 |  |  | 1.5021
5 |  | 1RK | 176.099 | 30.2737 | 206.3728 | 0 | 310 |  |  | 1.5021
6 |  | 1RK | 176.099 | 30.2737 | 206.3728 | 0 | 310 |  |  | 1.5021
7th Floor(Part Terrace Area) | [9 empty] | #DIV/0!
1 |  | 1BHK | 280.6175 | 60.1439 | 340.7613 | 0 | 530
2 |  | 1RK | 167.4878 | 38.3468 | 205.8346 | 0 | 310
3 |  | 1BHK | 322.0589 | 60.5475 | 382.6064 | 0 | 545
4 |  | Terrace Area
5 |  | 1RK | 176.099 | 30.2737 | 206.3728 | 0 | 310
6 |  | 1RK | 176.099 | 30.2737 | 206.3728 | 0 | 310
Building no. 4 | [11 empty] | 10.764
Ground Floor for Entrance Lobby, Society Office, Drivers Room & Parking
1st to 7th Floor | [7 empty] | 5000
1 |  | 1RK | 180.0817 | 36.7321 | 216.8139 | 0 | 335 | 1675000 | 15.865 | 335 | 1.5451
2 |  | 1RK | 180.0817 | 36.7321 | 216.8139 | 0 | 335 | 1675000 | 1925000 | 335 | 1.5451
3 |  | 1RK | 180.0817 | 36.7321 | 216.8139 | 0 | 335 | 1675000 | 1925000 | 335 | 1.5451
4 |  | 1BHK | 299.3468 | 61.7585 | 361.1053 | 0 | 535 | 2675000 | 2925000 | 550 | 1.5231
5 |  | 1RK | 180.0817 | 36.7321 | 216.8139 | 0 | 335 | 1675000 | 1925000 | 335 | 1.5451
Building no. 5
Ground Floor for Entrance Lobby, Society Office, Drivers Room & Parking
1st to 7th Floor
1 |  | 1RK | 182.988 | 36.7321 | 219.7201 | 0 | 340 |  | 15.865 | 340 | 1.5474
2 |  | 1RK | 180.0817 | 36.7321 | 216.8139 | 0 | 335 |  |  | 335 | 1.5451
3 |  | 1RK | 180.0817 | 36.7321 | 216.8139 | 0 | 335 |  |  | 335 | 1.5451
4 |  | 1BHK | 309.6803 | 71.8497 | 381.53 | 0 | 575 |  |  | 575 | 1.5071
Remarks: | [10 empty] | #DIV/0!
1. 2. 3. 4. 5. 6. 7. 8. 9. 10. 11. 8. On Site, we meet Mr. Kalim Khan - 8691030000.
1 | Building No. 1 & 2 = All work Completed. OC Received. Building No. 4 & 5 = Construction work is in process at the time of Visit (Labour found).
2 | We considered Saleable area as per Builder area sheet.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + A. P Area.
5 | We have considered rate by verifying it from market inquire.
6 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
6 | We update latest revised approved plans for Bldg 2 & revised CC for both buidlings (on 25/3/2022).
7 | We update latest revised approved plans for Bldg 1 (on 22/5/2023).
8 | As per approved plans dtd.06/08/2021, Building No. 1 has approval of Gr. + 1st to 7th Floor and construction is done as per it.
9 | Car parking is subjected to authentic documentation.
10 | We updated OC from RERA Site (on 04/06/2024).
11 | We have updated Building No. 04 & 05 (on 04/07/2024).
12 | Please provide revised approved layout plan & Area Statement.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Navnath Bhatkar |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Munish Glorious
Google Map :
Formulas:
Gokhivare = [Gokhivare, row above]
Bldg no.02
Bldg no.02
Bldg no.01
Bldg no.02
Bldg no.04
Bldg no.04
Bldg no.05
Building 5
Building 4
Building 2
Building 1
Note on H177: SACHIN: Give loading of 50% for A Category

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.5 | 2.9 | 13.05 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.88 | 2.13 | 4.0044 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.9 | 1.07 | 2.033 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 205.4568 | 19.0874 |  |  | 0 | 0 |  | 0 | 0
|  |  | 205.4568 | 19.0874

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Housing | Vijay Paradise | 1RK |  | 0 | #DIV/0! | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted